## BID FORMAT (hidden)
General Contractor Bid Form VN Da Nang - Rental Building Hall 3 Electric
Date: |  | XX.XX.XXXX
Bidder: |  | XXXXXXX
Contact Person: |  | XXXXX XXXXX
Address: |  | XXXXXXXXXX
XXXXXXXXXX
XXXXXXXXXX
Phone: |  | XXX XXXX-XXXX
E-Mail: |  | XXXXX.XXXXX@XXXXX |  |  | #REF!
2rd submission on 26 January 2022
|  | Total Lump-sum |  |  | #REF! | Remark
Discount
#REF!
1. |  | Construction site facilities |  |  | 20176036.5818
2. |  | Production and Logistic building (Hall 3) |  |  | #REF!
3. |  | Office, Social and Technical Areas (Hall 3) |  |  | #REF!
4. |  | Machine hook-up (Hall 3) |  |  | 505516691.9131
5. |  | Scooter Garage |  |  | #REF!
6. |  | Canteen |  |  | #REF!
7. |  | Exterior Area |  |  | 268597879.1589
8. |  | Adjustments Hall 2 |  |  | #REF!
9. |  | As built documentation |  |  | 0
10. |  | Service of Architects and Engineers |  |  | #REF!
11. |  | Bond and Insurances |  |  | 0
12. |  | Alternatives | (not included in the total lump-sum) |  | 0
13. |  | Value Engineering | (not included in the total lump-sum) |  | 0
Notes
Currency: DONG (VND)
Bo = Alternative Position
psch = lump-sum |  |  |  |  | 2rd submission on 26 January 2022
SCOPE OF WORK VN Da Nang - Rental Building Hall 3 Electric | [5 empty] | Remark
Position |  | Headline | Amount | Unit | Unit Price (VND)
1. |  | Construction site facilities |  |  | 20176036.5818
1. 1. |  | Construction site facilities | 1 | psch | 0
1. 2. |  | Construction site cameras | 1 | psch | 20176036.5818
2. |  | Production and Logistic building (Hall 3) |  |  | #REF!
2.1. |  | Civil Engineering | 1 | PSCH | 0
2. 1. 10. |  | Calculations | 1 | PSCH | 0
2. 1. 20. |  | Rainwater and waste water sewer | 1 | PSCH | 0
2. 1. 30. |  | Earthworks | 1 | PSCH | 0
2. 1. 40. |  | Demolition, removal and dismantling works | 1 | PSCH | 0
2. 1. 50. |  | Foundation | 1 | PSCH | 0
2. 1. 60. |  | Building structure | 1 | PSCH | 0
2. 1. 70. |  | General concrete- / reinforced concrete works | 1 | PSCH | 0
2. 1. 80. |  | Fire protection | 1 | PSCH | 0
2. 1. 90. |  | Fire rated walls | 1 | PSCH | 0
2. 1. 100. |  | Cutting base slabs / ceilings / floors | 1 | PSCH | 0
2. 1. 110. |  | Cutting holes into existing facades, walls and roofs | 1 | PSCH | 0
2. 1. 120. |  | Exterior walls | 1 | PSCH | 0
2. 1. 130. |  | Exterior doors and windows | 1 | PSCH | 0
2. 1. 140. |  | Fire protection doors | 1 | PSCH | 0
2. 1. 150. |  | Internal doors | 1 | PSCH | 0
2. 1. 160. |  | Fire protection roller shutter door | 1 | PSCH | 0
2. 1. 170. |  | Fire protection bulkhead | 1 | PSCH | 0
2. 1. 180. |  | High speed roller shutter | 1 | PSCH | 0
2. 1. 190. |  | Fitting and metal work - general | 1 | PSCH | 0
2. 1. 200. |  | Railings and hand rails | 1 | PSCH | 0
2. 1. 210. |  | Steel stage for installations | 1 | PSCH | 0
2. 1. 220. |  | Collision protection | 1 | PSCH | 0
2. 1. 230. |  | canopies of exterior doors | 1 | PSCH | 0
2. 1. 240. |  | Concerete steps in front of the hall | 1 | PSCH | 0
2. 1. 250. |  | Painting and varnishing works | 1 | PSCH | 0
2. 1. 260. |  | Guidance systems | 1 | PSCH | 0
2. 1. 270. |  | Locking system | 1 | PSCH | 0
2. 1. 280. |  | Internal signage | 1 | PSCH | 0
2. 1. 290. |  | Adjustment ridge vent | 1 | PSCH | 0
2. 1. 300. |  | Roof reinforcment Option 1 | 1 | PSCH | 0
2. 1. 310. |  | Insert new ventilation louvers | 1 | PSCH | 0
2. 1. 320. |  | Metal louvers to cover mechanical units | 1 | PSCH | 0
2. 2. |  | Electrical Engineering | 0 | PSCH | #REF!
2. 2. 10. |  | Adjustment of existing facilities, dismantling and disposal works | 1 | PSCH | 24400000
2. 2. 20. |  | Rennovation existing grounding system and lightning protection | 1 | PSCH | 5000000
2. 2. 30. |  | Rennovation existing grounding and equipotential bonding | 1 | PSCH | 2500000
2. 2. 40. |  | Power supply | 1 | PSCH | 405876628.1459
2. 2. 50. |  | Energy measurement system | 1 | PSCH | 12524296.2357
2. 2. 60. |  | Electrical installation in the production hall | 1 | PSCH | 298880144.662
2. 2. 70. |  | Electrical installation in the logistics hall | 1 | PSCH | 45073708.1139
2. 2. 80. |  | Power supply of building utilities | 1 | PSCH | Included at 2.2. 60. item
2. 2. 90. |  | Three-arm Turnstile | 1 | PSCH | 36030743.1568
2. 2. 100. |  | Emergency lighting | 1 | PSCH | 25617198.1684
2. 2. 110. |  | Fire alarm system | 1 | PSCH | #REF!
2. 2. 120. |  | Network infrastructure | 1 | PSCH | 64282788.3235
2. 2. 130. |  | Access control preparation | 1 | PSCH | Included at 3.2. 200. item
2. 2. 140. |  | CCTV System | 1 | PSCH | 19180346.471
2. 3. |  | Mechanical Engineering |  |  | #REF!
2. 3. 10. |  | Ventilation System Production | 1 | PSCH | 189644193.2889
2. 3. 20. |  | Fire Protection Engineering | 1 | PSCH | #REF!
2. 3. 30. |  | Installation of In-Rack Sprinkler at Logistic | 1 | PSCH | #REF!
2. 3. 40. |  | Compressed Air Network Production 1 | 1 | PSCH | 147070051.5988
2. 3. 50. |  | Compressed Air Network Production 2 | 1 | PSCH | 58632929.7673
2. 3. 60. |  | Add New: Smoke Exhaust Air system | 1 | PSCH | 56117679.99
3. |  | Office, Social and Technical Areas (Hall 3) |  |  | #REF!
3. 1. |  | Civil Engineering |  |  | 0
3. 1. 10. |  | Rainwater and waste water sewer | 1 | PSCH
3. 1. 20. |  | Foundations | 1 | PSCH | 0
3. 1. 30. |  | Steel columns | 1 | PSCH | 0
3. 1. 40. |  | Building structure | 1 | PSCH | 0
3. 1. 50. |  | Concrete works | 1 | PSCH | 0
3. 1. 60. |  | Reinforced concrete slabs 1st floor | 0 | PSCH | 0
3. 1. 70. |  | Reinforced concrete stairs | 0 | PSCH | 0
3. 1. 80. |  | Screed coat | 1 | PSCH | 0
3. 1. 90. |  | Metal works | 1 | PSCH | 0
3. 1. 100. |  | Exterior walls | 1 | PSCH | 0
3. 1. 110. |  | Masonry works | 1 | PSCH | 0
3. 1. 120. |  | plastering works | 1 | PSCH | 0
3. 1. 130. |  | Drywall works | 1 | PSCH | 0
3. 1. 140. |  | Ceiling for new built-ins | 1 | PSCH | 0
3. 1. 150. |  | Fire protection | 1 | PSCH | 0
3. 1. 160. |  | Fire rated walls | 1 | PSCH | 0
3. 1. 170. |  | Cutting holes into existing facades, walls and roofs | 1 | PSCH | 0
3. 1. 180. |  | Cuts in Floor/slab/wall | 1 | PSCH | 0
3. 1. 190. |  | Exterior doors and windows | 1 | PSCH | 0
3. 1. 200. |  | Canopies for exterior doors | 1 | PSCH | 0
3. 1. 210. |  | Covering existing windows with mirroring film | 1 | PSCH | 0
3. 1. 220. |  | Internal doors | 1 | PSCH | 0
3. 1. 230. |  | Fire protection doors | 1 | PSCH | 0
3. 1. 240. |  | Suspended ceiling | 1 | PSCH | 0
3. 1. 250. |  | Floor covering works | 1 | PSCH | 0
3. 1. 260. |  | Tiles | 1 | PSCH | 0
3. 1. 270. |  | Needle Felt | 1 | PSCH | 0
3. 1. 280. |  | Raised floor | 1 | PSCH | 0
3. 1. 290. |  | Drainage of new wet rooms | 1 | PSCH | 0
3. 1. 300. |  | Railing and handrail | 1 | PSCH | 0
3. 1. 310. |  | Collision protection | 1 | PSCH | 0
3. 1. 320. |  | Vertical blinds | 1 | PSCH | 0
3. 1. 330. |  | Kitchenette | 1 | PSCH | 0
3. 1. 340. |  | Painting and varnishing works | 1 | PSCH | 0
3. 1. 350. |  | internal signage | 1 | PSCH | 0
3. 1. 360. |  | Locking system | 1 | PSCH | 0
3. 1. 370. |  | Tightness Test Gas Extinguished Rooms | 1 | PSCH | 0
3. 2. |  | Electrical engineering |  |  | #REF!
3. 2. 10. |  | Rennovation existing grounding system and lightning protection | 1 | psch | Included
3. 2. 20. |  | Rennovation existing grounding and equipotential bonding | 1 | psch | Included
3. 2. 30. |  | Main Power supply | 1 | PSCH | 197907035.9748
3. 2. 40. |  | Uninterrupted power supply (UPS) | 1 | PSCH | 15050660.8087 | Reduce the unit price
3. 2. 50. |  | Electrical Capacitor bank | 1 | PSCH | 0
3. 2. 60. |  | Power supply of building utilities | 1 | PSCH | Included
3. 2. 70. |  | Energy measurement system | 1 | PSCH | Included at 2. 2. 50. item
3. 2. 80. |  | Electrical installation in offices and meeting rooms | 1 | PSCH | 66404103.9782
3. 2. 90. |  | Electrical installation in social rooms | 1 | PSCH | 35385729.898
3. 2. 100. |  | Electrical installation in corridors and stairways | 1 | PSCH | 17389802.6953
3. 2. 110. |  | Electrical installation in technical areas | 1 | PSCH | 9713896.6252 | Reduce the unit price
3. 2. 120. |  | Electrical installation in kitchenette areas | 1 | PSCH | 16840279.0483
3. 2. 130. |  | Electrical installation for Workshop/Formbrettbau | 1 | PSCH | 12614941.0865 | Reduce the unit price
3. 2. 140. |  | Electrical installation at the reception | 1 | PSCH | 4068070.8188
3. 2. 150. |  | Electrical installation in other rooms/secondary rooms | 1 | PSCH | 31538420.0323 | Reduce the unit price
3. 2. 160. |  | Emergency lighting | 1 | PSCH | 37581630.6399
3. 2. 170. |  | Fire alarm system | 1 | PSCH | #REF!
3. 2. 180. |  | Network infrastructure | 1 | PSCH | 174994605.0134
3. 2. 190. |  | CCTV System | 1 | PSCH | 9368475.5017
3. 2. 200. |  | Access control preparation | 1 | PSCH | 19670341.0869
3. 3. |  | Mechanical Engineering |  |  | #REF!
3. 3. 10. |  | Waste Water System | 1 | PSCH | 71484007.4162
3. 3. 20. |  | Service Water System | 1 | PSCH | 59395813.3191
3. 3. 30. |  | Sanitary Furnishings | 1 | PSCH | 79558059.1592
3. 3. 40. |  | Ventilation System | 1 | PSCH | 94236583.2039
3. 3. 50. |  | Ventilation System 1st Floor Offices Ventilation Units | 1 | PSCH | 5889562.8377
3. 3. 60. |  | Ventilation System 1st Floor Offices Ducting | 1 | PSCH | 34190166.1463
3. 3. 70. |  | Air Conditioning | 1 | PSCH | 211748078.3635
3. 3. 80. |  | Fire Protection Engineering Sprinkler | 1 | PSCH | #REF!
3. 3. 90. |  | Fire Protection Engineering Temperature Controlled Storage | 1 | PSCH | #REF!
3. 3. 100. |  | Fire Protection Engineering Extinguishing Systems | 1 | PSCH | #REF!
3. 3. 110. |  | Door Fan Test for Gas Extinguishing System | 1 | PSCH | #REF!
3. 3. 120. |  | Compressed Air Connections | 1 | PSCH | Included
3. 3. 130. |  | Add New: Smoke Exhaust Air system | 1 | PSCH | 24229831.2332
4. |  | Machine hook-up (Hall 3) |  |  | 505516691.9131
4. 1. |  | Electrical engineering |  |  | 446703070.7456
4. 1. 10. |  | Machine hook-up | 1 | PSCH | 446703070.7456 | Reduce the unit price
4. 2. |  | Mechanical Engineering |  |  | 58813621.1675
4. 2. 10. |  | Machine hook-up | 1 | PSCH | 58813621.1675
5. |  | Scooter Garage |  |  | #REF!
5. 1. |  | Civil Engineering |  |  | 0
5. 1. 10. |  | Adjustments on the existing scooter garage | 1 | PSCH
5. 1. 20. |  | Expansion of Scooter Garage | 1 | PSCH
5. 2. |  | Electrical Engineering |  |  | #REF!
5. 2. 10. |  | Grounding and Lightining protection | 1 | PSCH | 0
5. 2. 20. |  | Power supply | 1 | PSCH | 6144115.6772
5. 2. 30. |  | Power supply of building utilities | 1 | PSCH
5. 2. 40. |  | Electrical installations | 1 | PSCH | 5904426.8866
5. 2. 50. |  | Emergency lighting | 1 | PSCH | 4292615.4621
5. 2. 60. |  | Fire alarms system | 1 | PSCH | #REF!
5. 2. 70. |  | CCTV System | 1 | PSCH | 17597761.4686
5. 3. |  | Mechancial Engineering |  |  | #REF!
5. 3. 10. |  | Rainwater System | 1 | PSCH | 16528783.2582
5. 3. 20. |  | Fire Protection System | 1 | PSCH | #REF!
6. |  | Canteen |  |  | #REF!
6. 1. |  | Civil Engineering |  |  | 0
6. 1. 10. |  | Demolition of existing canteen | 1 | PSCH | 0
6. 1. 20. |  | Building Structure | 1 | PSCH | 0
6. 1. 30. |  | Earthworks | 1 | PSCH | 0
6. 1. 40. |  | Rain water and waste water sewer | 1 | PSCH | 0
6. 1. 50. |  | Primary construction of reinforced concrete | 1 | PSCH | 0
6. 1. 60. |  | Foundations | 1 | PSCH | 0
6. 1. 70. |  | Concrete floor | 1 | PSCH | 0
6. 1. 80. |  | Concrete plinth | 1 | PSCH | 0
6. 1. 90. |  | Reinforced concrete columns | 1 | PSCH | 0
6. 1. 100. |  | Reinforced concrete beams | 1 | PSCH | 0
6. 1. 110. |  | Reinforced concrete 1st roof slab or structure | 1 | PSCH | 0
6. 1. 120. |  | Reinforced concrete stairs | 1 | PSCH | 0
6. 1. 130. |  | Concrete steps | 1 | PSCH | 0
6. 1. 140. |  | Screed coat | 1 | PSCH | 0
6. 1. 150. |  | Roof structure | 1 | PSCH | 0
6. 1. 160. |  | Metal facade | 1 | PSCH | 0
6. 1. 170. |  | Masonry works | 1 | PSCH | 0
6. 1. 180. |  | Exterior doors | 1 | PSCH | 0
6. 1. 190. |  | Fire protection | 1 | PSCH | 0
6. 1. 200. |  | Fire protection doors | 1 | PSCH | 0
6. 1. 210. |  | Interior doors | 1 | PSCH | 0
6. 1. 220. |  | Floor covering works | 1 | PSCH | 0
6. 1. 230. |  | Tiles | 1 | PSCH | 0
6. 1. 240. |  | Painting and finishing works | 1 | PSCH | 0
6. 1. 250. |  | Metal and railing works | 1 | PSCH | 0
6. 1. 260. |  | Elevator for goods | 1 | PSCH | 0
6. 1. 270. |  | Canpoy for the main entrance | 1 | PSCH | 0
6. 1. 280. |  | Exterior steel staircase | 1 | PSCH | 0
6. 1. 290. |  | Exterior sinks | 1 | PSCH | 0
6. 1. 300. |  | Locking system | 1 | PSCH | 0
6. 2. |  | Electrical Engineering |  |  | #REF!
Notes Calculation Basis
6. 2. 10. |  | Grounding and Lightining protection | 1 | PSCH | 0
6. 2. 20. |  | Power supply | 1 | PSCH | 12858262.8895
6. 2. 30. |  | Power supply of building utilities | 1 | PSCH | Included
6. 2. 40. |  | Electrical installations | 1 | PSCH | 25881817.2569 | Reduce the unit price
6. 2. 50. |  | Emergency lighting | 1 | PSCH | 7134770.8067
6. 2. 60. |  | Fire alarms system | 1 | PSCH | #REF!
6. 2. 70. |  | CCTV System | 1 | PSCH | 6055261.4345
6. 2. 80. |  | Network infrastructure | 1 | PSCH | 21129883.4666
6. 3. |  | Mechancial Engineering |  |  | #REF!
6. 3. 10. |  | Rainwater System | 1 | PSCH | 11954799.36
6. 3. 20. |  | Waste Water System | 1 | PSCH | 14688997.44
6. 3. 30. |  | Service Water System | 1 | PSCH | 9116560.5373
6. 3. 40. |  | Sanitary Furnishings | 1 | PSCH | 15204292.8421
6. 3. 50. |  | Air Conditioning | 1 | PSCH | 2439460.942 | Remove dehumidifier as mentioned in the 2nd interview
6. 3. 60. |  | Ventilation System Overhead Fans | 1 | PSCH | 66328606.8362
6. 3. 70. |  | Ventilation System | 1 | PSCH | 6144101.3321
6. 3. 80. |  | Fire Protection System | 1 | PSCH | #REF!
6. 3. 90. |  | Add New: Booster pump system | 1 | PSCH | 7994822.1947
7. |  | Exterior Area |  |  | 268597879.1589
7. 1. |  | Civil Engineering |  |  | 150438500
7. 1. 10. |  | Flag pole | 1 | PSCH | 0
7. 1. 20. |  | Fence | 1 | PSCH | 0
7. 1. 30. |  | Bollards and delineator panels | 1 | PSCH | 0
7. 1. 40. |  | New Septic Tanks | 1 | PSCH | 0
7. 1. 50. |  | Excavation | 1 | PSCH | 108855000
7. 1. 60. |  | Laying conduits, pipes, etc. | 1 | PSCH | 41583500
7. 1. 70. |  | Asphalt areas | 1 | PSCH | 0
7. 2. |  | Electrical Engineering |  |  | 100342530.3589
7. 2. 10. |  | Electrical Installations General | 1 | PSCH | Included
7. 2. 20. |  | Exterior Lighting | 1 | PSCH | Included
7. 2. 30. |  | Emergency Lighting | 1 | PSCH | Included
7. 2. 40. |  | Building service connections | 1 | PSCH | 94825780
7. 2. 50. |  | CCTV System | 1 | PSCH | 5516750.3589
7. 3. |  | Mechanical Engineering |  |  | 17816848.8
7. 3. 10. |  | Underground Compressed Air Connection | 1 | PSCH | 17816848.8
8. |  | Adjustments Hall 2 |  |  | #REF!
8. 1. |  | Roof Renovation |  |  | 0
8. 1. 10. |  | Roof Reinforcement Option 1 | 1 | PSCH | 0
8. 2. |  | Adjustment Ridge Vent |  |  | 0
8. 2. 10. |  | Adjustment Ridge Vent | 1 | PSCH | 0
8. 3. |  | Adjustment Overhead Fans |  |  | 0
8. 3. 10. |  | Adjustment Overhead Fans | 1 | PSCH |  | Move to Alternative at item 12.3.50
8. 4. |  | Additonal In-Rack Sprinkler Logistic |  |  | #REF!
8. 4. 10. |  | Additonal In-Rack Sprinkler Logistic | 1 | PSCH | #REF!
8. 5. |  | Additional Compressed Air Equipment |  |  | 0
8. 5. 10. |  | Additional Compressed Air Equipment | 1 | PSCH
8. 6. |  | Flag pole |  |  | 0
8. 6. 10. |  | Flag pole | 0 | PSCH | 0
9. |  | As built documentation |  |  | 0
9. 1. |  | As built documentation all trades |  |  | 0
9. 1. 10. |  | As built documentation | 1 | PSCH | 0
10. |  | Service of Architects and Engineers |  |  | #REF!
10. 1. |  | Civil engineering |  |  | 0
10. 1. 10. |  | Design works | 1 | PSCH | 0
10. 1. 20. |  | Geotechnical survey | 1 | PSCH | 0
10. 1. 30. |  | Topographical survey | 1 | PSCH | 0
10. 1. 40. |  | Fire protection report | 1 | PSCH | 0
10. 1. 50. |  | Compactation report of earthworks | 1 | PSCH | 0
10. 1. 60. |  | Structure and welding quality report | 1 | PSCH | 0
10. 1. 70. |  | Adherence and width of paint quality control reports | 1 | PSCH | 0
10. 1. 80. |  | Material quality control reports | 1 | PSCH | 0
10. 1. 90. |  | Planning service Building construction | 1 | PSCH | 0
10. 1. 100. |  | Planning service Structural design | 1 | PSCH | 0
10. 1. 110. |  | Planning service Structural revision | 1 | PSCH | 0
10. 1. 120. |  | Surveying services Inventory registration | 1 | PSCH | 0
10. 1. 130. |  | Quality control laboratory for material testing (laboratory and field testing) | 1 | PSCH | 0
10. 1. 140. |  | Revision fire department and civil protection | 1 | PSCH | 0
10. 2. |  | Electrical engineering |  |  | Included
10. 2. 10. |  | Design & approval works | 1 | psch | Included
10. 3. |  | Mechanical engineering |  |  | #REF!
10. 3. 10. |  | Design & approval works | 1 | psch | #REF!
11. |  | Bond and Insurances |  |  | 0
11. 1. |  | Bonds |  |  | 0
11. 1. 10. |  | Down Payment Bond | 1 | psch | 0
11. 1. 20. |  | P&P Bonds GC | 1 | psch | 0
11. 1. 30. |  | P&P Bonds GC Sub-Contractor | 1 | psch | 0
11. 2. |  | Insurances
|  | Insurance |  |  | 0
11. 2. 10. |  | Liability Insurance | 1 | psch | 0
11. 2. 20. |  | Contractual Obligations/Contractual Liability | 1 | psch | 0
11. 2. 30. |  | Pure financial loss | 1 | psch | 0
11. 2. 40. |  | Builder's Risk Policy | 1 | psch | 0
12. |  | Alternatives |  |  | 0
12. 1. |  | Civil Engineering |  |  | 0
12. 1. 10. | BO | Wooden fire rated doors | 1 | PSCH | 0
12. 1. 20. | BO | Shell built-ins 1st Floor on the right side | 1 | PSCH | 0
12. 1. 30. | BO | Fire rated wall between production 1 and production 2 | 1 | PSCH | 0
12. 1. 40. | BO | Roof reinforcement Option 2 Halle 2 | 1 | PSCH | 0
12. 1. 50. | BO | Roof reinforcement Option 2 Halle 3 | 1 | PSCH | 0
12. 1. 60. | BO | Exterior wall Hall 2 renovation | 1 | PSCH | 0
12. 1. 70. | BO | Exterior wall Hall 3 renovation | 1 | PSCH | 0
12. 1. 80. | BO | Metal facade renovation per m² | 1 | PSCH | 0
12. 1. 90. | BO | Keeping the existing septic tanks | 1 | PSCH | 0
12. 1. 100. | BO | Brick walls in Built-ins | 1 | PSCH | 0
12. 1. 110. | BO | Metal Facade Louvers in Canteen | 1 | PSCH | 0
12. 1. 120. | BO | Smart board slab 1 Floor Built-ins | 1 | PSCH | 0
12. 1. 130. | BO | Windows renovation per unit in Hall 3 | 1 | PSCH | 0
12. 1. 140. | BO | Change windows per unit in Halle 3 | 1 | PSCH | 0
12. 1. 150. | BO | Doors sealing in Hall 3 | 1 | PSCH | 0
12. 1. 160. | BO | Additional reinforcement of canteen roof | 1 | PSCH | 0
12. 2. |  | Electrical Engineering |  |  | 0
12. 2. 10. | BO |  | 1 | PSCH
12. 2. 20. | BO |  | 1 | PSCH
12. 2. 30. | BO |  | 1 | PSCH
12. 2. 40. | BO |  | 1 | PSCH
12. 2. 50. | BO |  | 1 | PSCH
12. 2. 60. | BO |  | 1 | PSCH
12. 2. 70. | BO |  | 1 | PSCH
12. 2. 80. | BO |  | 1 | PSCH
12. 2. 90. | BO |  | 1 | PSCH
12. 3. |  | Mechanical Engineering |  |  | 0
12. 3. 10. | BO |  | 1 | PSCH
12. 3. 20. | BO |  | 1 | PSCH
12. 3. 30. | BO |  | 1 | PSCH
12. 3. 40. | BO |  | 1 | PSCH
12. 3. 50. | BO |  | 1 | PSCH
12. 3. 60. | BO |  | 1 | PSCH
12. 3. 70. | BO |  | 1 | PSCH
12. 3. 80. | BO |  | 1 | PSCH
12. 3. 90. | BO |  | 1 | PSCH
12.3.100 | BO |  | 1 | PSCH
13. |  | Value Engineering |  |  | 0
13. 1. |  | Civil Engineering |  |  | 0
13. 1. 10. | BO |  | 1 | PSCH | 0
13. 1. 20. | BO |  | 1 | PSCH | 0
13. 1. 30. | BO |  | 1 | PSCH | 0
13. 1. 40. | BO |  | 1 | PSCH | 0
13. 1. 50. | BO |  | 1 | PSCH | 0
13. 1. 60. | BO |  | 1 | PSCH | 0
13. 1. 70. | BO |  | 1 | PSCH | 0
13. 1. 80. | BO |  | 1 | PSCH | 0
13. 1. 90. | BO |  | 1 | PSCH | 0
13. 1. 100. | BO |  | 1 | PSCH | 0
13. 2. |  | Electrical Engineering |  |  | 0
13. 2. 10. | BO |  | 1 | PSCH
13. 2. 20. | BO |  | 1 | PSCH
13. 2. 30. | BO |  | 1 | PSCH
13. 2. 40. | BO |  | 1 | PSCH
13. 2. 50. | BO |  | 1 | PSCH
13. 2. 60. | BO |  | 1 | PSCH
13. 2. 70. | BO |  | 1 | PSCH
13. 2. 80. | BO |  | 1 | PSCH
13. 2. 90. | BO |  | 1 | PSCH
13. 2. 100. | BO |  | 1 | PSCH
13. 2. 110. | BO |  | 1 | PSCH
13. 3. |  | Mechanical Engineering |  |  | 0
13. 3. 10. | BO |  | 1 | PSCH
13. 3. 20. | BO |  | 1 | PSCH
13. 3. 30. | BO |  | 1 | PSCH
13. 3. 40. | BO |  | 1 | PSCH
13. 3. 50. | BO |  | 1 | PSCH
13. 3. 60. | BO |  | 1 | PSCH
13. 3. 70. | BO |  | 1 | PSCH
13. 3. 80. | BO |  | 1 | PSCH
13. 3. 90. | BO |  | 1 | PSCH
13. 3. 100. | BO |  | 1 | PSCH
13. 3. 110. | BO |  | 1 | PSCH
13. 3. 120. | BO |  | 1 | PSCH
13. 3. 120. | BO |  | 1 | PSCH
13. 3. 120. | BO

## 1. ELEC (2) (hidden)
Project: VN-RENTAL BUILDING HALL 3 ELECTRIC
Location: Lô D1, Khu công nghiệp Tam Thăng, Huyện Tam Thăng, thành Phố Tam Kỳ, Tỉnh quản Nam, Việt Nam
Client: Draexlmaier Automotive Vietnam Company Limited
Package: Cơ - Điện
Item: Electrical System
Date: 27/02/2022
Contractor name: HMEP
Position |  | Headline | Quantity | Quantity By contractor | Unit | Material Unit | Labor Unit | Unit rate | Material Amount | Labor Amount | Amount (VND) | % Công việc hoàn thành vật tư |  |  | % Công việc hoàn thành nhân công |  |  | Giá trị thanh toán đợt 1 |  |  | Remark
[12 empty] | Đợt 1 | đợt 2 | % KL hoàn thành lũy kế | Đợt 1 | đợt 2 | % KL hoàn thành lũy kế | Vật tư | Nhân công | Tổng
1. |  | Construction site facilities | [8 empty] | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
1. 1. |  | Construction site facilities | 1 |  | psch | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
1. 2. |  | Construction site cameras | 1 |  | psch | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[17 empty] | 0% | 0 | 0 | 0
2. |  | Production and Logistic building (Hall 3) | [6 empty] | 4384819997.1499 | 819871975.3259 | 5204691972.4758 | [6 empty] | 757338468.2727 | 0 | 757338468.2727
[18 empty] | 0 | 0
2.1. |  | Civil Engineering | 1 |  | PSCH | [12 empty] | 0 | 0
2. 1. 10. |  | Calculations | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 20. |  | Rainwater and waste water sewer | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 30. |  | Earthworks | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 40. |  | Demolition, removal and dismantling works | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 50. |  | Foundation | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 60. |  | Building structure | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 70. |  | General concrete- / reinforced concrete works | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 80. |  | Fire protection | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 90. |  | Fire rated walls | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 100. |  | Cutting base slabs / ceilings / floors | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 110. |  | Cutting holes into existing facades, walls and roofs | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 120. |  | Exterior walls | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 130. |  | Exterior doors and windows | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 140. |  | Fire protection doors | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 150. |  | Internal doors | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 160. |  | Fire protection roller shutter door | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 170. |  | Fire protection bulkhead | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 180. |  | High speed roller shutter | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 190. |  | Fitting and metal work - general | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 200. |  | Railings and hand rails | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 210. |  | Steel stage for installations | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 220. |  | Collision protection | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 230. |  | canopies of exterior doors | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 240. |  | Concerete steps in front of the hall | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 250. |  | Painting and varnishing works | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 260. |  | Guidance systems | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 270. |  | Locking system | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 280. |  | Internal signage | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 290. |  | Adjustment ridge vent | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 300. |  | Roof reinforcment Option 1 | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 310. |  | Insert new ventilation louvers | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 1. 320. |  | Metal louvers to cover mechanical units | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
2. 2. |  | Electrical Engineering | 1 |  | PSCH |  |  |  | 4384819997.1499 | 819871975.3259 | 5204691972.4758 | [6 empty] | 757338468.2727 | 0 | 757338468.2727
2. 2. 10. |  | Adjustment of existing facilities, dismantling and disposal works | 1 | 1 | PSCH |  |  |  | 0 | 24400000 | 24400000 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | The cost of dismantling electrical distribution board, trunking & ladder and lighting system existing system | 1 | 1 | lot | 0 | 14000000 | 14000000 | 0 | 14000000 | 14000000 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 353 Led highbay
|  | Opening (inluded supports & waterproof) for wall through ductwork fee | 1 | 1 | lot | 0 | 10400000 | 10400000 | 0 | 10400000 | 10400000 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 26 fan
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
2. 2. 20. |  | Rennovation existing grounding system and lightning protection | 1 | 1 | PSCH | 0 | 5000000 | 5000000 | 0 | 5000000 | 5000000 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
2. 2. 30. |  | Rennovation existing grounding and equipotential bonding | 1 | 1 | PSCH | 0 | 2500000 | 2500000 | 0 | 2500000 | 2500000 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
2. 2. 40. |  | Power supply | 1 | 1 | PSCH |  |  |  | 1266144274.1142 | 405876628.1459 | 1672020902.2601 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | From DB SYN-TR1 Panel to Building 3_BMDP | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 6x(4x1Cx300mm2)+E240mm2 | 67 | 64.9 | m | 2672599.35 | 818400 | 3490999.35 | 173451697.815 | 53114160 | 226565857.815 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
| Option1 | From DB SYN-TR1 Panel to Building 3_BMDP | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 5x(4x1Cx240mm2)+E240mm2 | 67 | 67 | m | 15029239.743 | 686400 | [6 empty] | 0% |  |  | 0% | 0 | 0 | 0 | Only unite rates
|  | From Building 3_BMDP Panel to Building 3_PDP 1.0 | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 4x1Cx300mm2+E150mm2 | 15 | 14 | m | 481493.34 | 158400 | 639893.34 | 6740906.76 | 2217600 | 8958506.76 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From Building 3_BMDP Panel to Building 3_PDP 1.1 | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 2x(4x1Cx185mm2)+E185mm2 | 116 | 106 | m | 618512.88 | 176000 | 794512.88 | 65562365.28 | 18656000 | 84218365.28 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From Building 3_BMDP Panel to Building 3_PDP 2.0 | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 3x(3x1Cx240mm2)+N1Cx240mm2+E120mm2 | 182 | 203.5 | m | 909229.53 | 304700 | 1213929.53 | 185028209.355 | 62006450 | 247034659.355 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From Building 3_BMDP Panel to Building 3_PDP 1.2 | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 3x(3x1Cx240mm2)+N2x1Cx240mm2+E185mm2 | 135 | 143 | m | 1018095.6 | 304700 | 1322795.6 | 145587670.8 | 43572100 | 189159770.8 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From Building 3_BMDP Panel to Building 3_PDP 2.1 | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 3x(3x1Cx240mm2)+N2x1Cx240mm2+E185mm2 | 136 | 137 | m | 1018095.6 | 304700 | 1322795.6 | 139479097.2 | 41743900 | 181222997.2 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From Building 3_BMDP Panel to Building 3_BDP 1.0 | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 4x1Cx150mm2+E70mm2 | 70 | 16.5 | m | 247104.54 | 116765.3025 | 363869.8425 | 4077224.91 | 1926627.4913 | 6003852.4013 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From Building 3_BMDP Panel to Building 3_BDP 1.1 | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 2x(4x1Cx150mm2)+E150mm2 | 15 | 99 | m | 497079.9 | 138600 | 635679.9 | 49210910.1 | 13721400 | 62932310.1 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From Building 3_BMDP Panel to Building 3_BDP 2.0 | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 3x(3x1Cx240mm2)+N2x1Cx185mm2+E185mm2 | 116 | 191.1 | m | 1018095.6 | 304700 | 1322795.6 | 194558069.16 | 58228170 | 252786239.16 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From Building 3_BMDP Panel to Scooter garage BDP 1.0 | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 4x1Cx35mm2+E16mm2 | 131 | 86 | m | 70862.76 | 46119.15 | 116981.91 | 6094197.36 | 3966246.9 | 10060444.26 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From Building 3_BMDP Panel to Canteen BDP 1.0 | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 3x1Cx120mm2+N1Cx25mm2+E16mm2 | 174 | 181 | m | 165603.51 | 101462.13 | 267065.64 | 29974235.31 | 18364645.53 | 48338880.84 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From Building 3_BDP 1.1 Panel to Building 3_UPS1-100 kVA | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 4x1Cx70mm2+E35mm2 | 106 | 121 | m | 128659.23 | 83182.176 | 211841.406 | 15567766.83 | 10065043.296 | 25632810.126 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From Building 3 UPS1-MDP Panel to Building 3_UPS 1 DP 1.3 35kVA | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 4x1Cx70mm2+E35mm2 | 20 | 18.7 | m | 128659.23 | 83182.176 | 211841.406 | 2405927.601 | 1555506.6912 | 3961434.2922 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From Building 3_BDP 2.0 Panel to Building 3_UPS2-100 kVA | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 4x1Cx70mm2+E35mm2 | 18 | 27.5 | m | 128659.23 | 83182.176 | 211841.406 | 3538128.825 | 2287509.84 | 5825638.665 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From Building 3 UPS1-MDP Panel to Building 3_UPS 2 DP 1.3 35kVA | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 4x1Cx70mm2+E35mm2 | 25 | 27.5 | m | 128659.23 | 83182.176 | 211841.406 | 3538128.825 | 2287509.84 | 5825638.665 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From Building 3 UPS1-MDP Panel to Building 3 UPS 2-DP1.2 | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 3Cx10mm2 | 185 | 184.8 | m | 102150.27 | 17818.7625 | 119969.0325 | 18877369.896 | 3292907.31 | 22170277.206 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From Building 3 UPS1-MDP Panel to Building 3 UPS 2-DP1.3 | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 3Cx6mm2 | 115 | 105 | m | 65470.44 | 17189.865 | 82660.305 | 6874396.2 | 1804935.825 | 8679332.025 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From Building 3 UPS1-MDP Panel to Building 3_UPS 1 DP 1.3 35kVA | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 4x1Cx50mm2+E10mm2 | 115 | 90 | m | 166514.94 | 52580 | 219094.94 | 14986344.6 | 4732200 | 19718544.6 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From Building 3 UPS1-MDP Panel to PDU | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 590 | 480 | m | 32518.74 | 7485.665 | 40004.405 | 15608995.2 | 3593119.2 | 19202114.4 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | From Building 3_BDP 2.0 Panel to Building 3_UPS2-100 kVA | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 4x1Cx35mm2+E16mm2 | 18 | 27.5 | m | 448964.76 | 46119.15 | 495083.91 | 12346530.9 | 1268276.625 | 13614807.525 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From Building 3 UPS2-MDP Panel to Building 3 UPS 2-DP1.2 | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 3Cx4mm2 | 25 | 20 | m | 46999.53 | 9969.2395 | 56968.7695 | 939990.6 | 199384.79 | 1139375.39 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From Building 3 UPS1-MDP Panel to Building 3 UPS 2-DP1.2 | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 3Cx10mm2 | 180 | 193.6 | m | 102150.27 | 17818.7625 | 119969.0325 | 19776292.272 | 3449712.42 | 23226004.692 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From Building 3 UPS1-MDP Panel to Building 3 UPS 2-DP1.2 | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 3Cx6mm2 | 115 | 187 | m | 65470.44 | 14173.4395 | 79643.8795 | 12242972.28 | 2650433.1865 | 14893405.4665 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From Building 3 UPS1-MDP Panel to Building 3_UPS 2 DP 1.3 35kVA | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 4x1Cx50mm2+E10mm2 | 115 | 117.7 | m | 166514.94 | 52580 | 219094.94 | 19598808.438 | 6188666 | 25787474.438 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From Building 3 UPS2-MDP Panel to PDU | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 590 | 480 | m | 32518.74 | 7485.665 | 40004.405 | 15608995.2 | 3593119.2 | 19202114.4 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From DB PDP 1.2 Panel to Cetral feeding unit 1 | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 4x1Cx150mm2+E70mm2 | 24 | 26.4 | m | 247104.54 | 116765.3025 | 363869.8425 | 6523559.856 | 3082603.986 | 9606163.842 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From DB PDP 1.2 Panel to Cetral feeding unit 2 | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 4x1Cx150mm2+E70mm2 | 16 | 17.6 | m | 247104.54 | 116765.3025 | 363869.8425 | 4349039.904 | 2055069.324 | 6404109.228 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From DB PDP 1.2 Panel to Cetral feeding unit 3 | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 4x1Cx150mm2+E70mm2 | 57 | 68.2 | m | 247104.54 | 116765.3025 | 363869.8425 | 16852529.628 | 7963393.6305 | 24815923.2585 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From DB PDP 2.1 Panel to Cetral feeding unit 1 | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 4x1Cx150mm2+E70mm2 | 24 | 26.4 | m | 247104.54 | 116765.3025 | 363869.8425 | 6523559.856 | 3082603.986 | 9606163.842 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From DB PDP 2.1 Panel to Cetral feeding unit 2 | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 4x1Cx150mm2+E70mm2 | 16 | 17.6 | m | 247104.54 | 116765.3025 | 363869.8425 | 4349039.904 | 2055069.324 | 6404109.228 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From DB PDP 2.1 Panel to Cetral feeding unit 3 | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 4x1Cx150mm2+E70mm2 | 57 | 68.2 | m | 247104.54 | 116765.3025 | 363869.8425 | 16852529.628 | 7963393.6305 | 24815923.2585 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | Accessories | 1 | 1 | lot | 49018783.6212 | 15188870.1199 | 64207653.7411 | 49018783.6212 | 15188870.1199 | 64207653.7411 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
2. 2. 50. |  | Energy measurement system | 1 | 1 | PSCH |  |  |  | 315804122.0768 | 12524296.2357 | 328328418.3125 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | SOFTWARE PRODUCTS | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Pre-parameterization per device | 11 | 11 | pcs | 343200 | 0 | 343200 | 3775200 | 0 | 3775200 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 100170, KBR
|  | visual energy ZP5 | 3 | 3 | pcs | 6063200 | 0 | 6063200 | 18189600 | 0 | 18189600 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 14326, KBR
|  | Hourly rate for remote services, Costs per hour / co-worker | 11 | 11 | pcs | 3832400 | 0 | 3832400 | 42156400 | 0 | 42156400 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 100182, KBR
|  | Freight charges | 1 | 1 | lot | 5291000 | 0 | 5291000 | 5291000 | 0 | 5291000 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 3344406 | 1003321.8 | 4347727.8 | 3344406 | 1003321.8 | 4347727.8 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | MULTI METERS | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Multimess F144 | 11 | 11 | pcs | 21251230 | 275000 | 21526230 | 233763530 | 3025000 | 236788530 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Type: 2-LED-ESMSET-2RO1DO-US1, KBR
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | ELV cable | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable Cat6A | 330 | 330 | m | 21639.3443 | 3360 | 24999.3443 | 7140983.6066 | 1108800 | 8249783.6066 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 884024508/10, Commscope/ China
|  | PVC conduit D20 | 150 | 150 | m | 8773.9726 | 14594.0164 | 23367.989 | 1316095.8904 | 2189102.4618 | 3505198.3522 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Nano/ VN
|  | Accessories | 1 | 1 | lot | 826906.5798 | 248071.974 | 1074978.5538 | 826906.5798 | 248071.974 | 1074978.5538 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | ENGINEERING SERVICES | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Labour cost for support DRX test funtion of Access control system | 1 | 1 | lot | 0 | 4950000 | 4950000 | 0 | 4950000 | 4950000 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
2. 2. 60. |  | Electrical installation in the production hall | 1 | 1 | PSCH |  |  |  | 2359220157.2575 | 298880144.662 | 2658100301.9195 |  |  | 0% |  |  | 0% | 652018010.5216 | 0 | 652018010.5216
|  | Cable trays_Hot dip-Galvanized Steel | [11 empty] | 0% |  |  | 0%
|  | Production hall 01 | [6 empty] | 1059238180 | 131854511.8676 | 1191092691.8676 |  |  | 0% |  |  | 0% | 529619090 | 0 | 529619090
|  | Cable tray 500x100x2.0mm | 0 | 0 | m | 1443780 | 81001.3848 | 1524781.3848 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 0
|  | Cable tray 300x100x2.0mm | 0 | 129.8 | m | 1009710 | 61078.452 | 1070788.452 | 131060358 | 7927983.0721 | 138988341.0721 | 50% |  | 50% |  |  | 0% | 65530179 | 0 | 65530179 | 0
|  | Cable tray 200x100x2.0mm | 13 | 129.8 | m | 776880 | 51045.8655 | 827925.8655 | 100839024 | 6625753.3383 | 107464777.3383 | 50% |  | 50% |  |  | 0% | 50419512 | 0 | 50419512 | TGE/ VN
|  | Cable tray 500x100 with separating bar, c/w cover | 185 | 215.6 | m | 1525680 | 81001.3848 | 1606681.3848 | 328936608 | 17463898.5532 | 346400506.5532 | 50% |  | 50% |  |  | 0% | 164468304 | 0 | 164468304 | TGE/ VN
|  | Cable tray 400x100 with separating bar, c/w cover | 232 | 269.5 | m | 826020 | 68320 | 894340 | 222612390 | 18412240 | 241024630 | 50% |  | 50% |  |  | 0% | 111306195 | 0 | 111306195 | TGE/ VN
|  | Cable tray 300x100 with separating bar, c/w cover | 112 | 0 | m | 1091610 | 61078.452 | 1152688.452 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
|  | Cable tray 200x100 with separating bar, c/w cover | 112 | 0 | m | 858780 | 51045.8655 | 909825.8655 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
|  | Cable tray 200x50 with separating bar, c/w cover | 187 | 0 | m | 669240 | 51045.8655 | 720285.8655 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
|  | Cable ladder 600x100x2.0mm, c/w cover | 9 | 0 | m | 1199250 | 91952 | 1291202 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
|  | Cable ladder 500x100x2.0mm, c/w cover | 0 | 0 | m | 1067040 | 81001.3848 | 1148041.3848 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
|  | Cable ladder 400x100x2.0mm, c/w cover | 5 | 5 | m | 933660 | 68320 | 1001980 | 4668300 | 341600 | 5009900 | 50% |  | 50% |  |  | 0% | 2334150 | 0 | 2334150 | TGE/ VN
|  | Cable ladder 300x100x1.5mm, c/w cover | 2 | 2 | m | 625950 | 61078.452 | 687028.452 | 1251900 | 122156.904 | 1374056.904 | 50% |  | 50% |  |  | 0% | 625950 | 0 | 625950 | TGE/ VN
|  | Fitting and accessories | 1 | 1 | lot | 269869600 | 80960880 | 350830480 | 269869600 | 80960880 | 350830480 | 50% |  | 50% |  |  | 0% | 134934800 | 0 | 134934800
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Production hall 02 | [6 empty] | 205951658 | 26469471.7777 | 232421129.7777 |  |  | 0% |  |  | 0% | 102975829 | 0 | 102975829
|  | Cable tray 500x100x2.0mm | 0 |  | m | 1443780 | 81001.3848 | 1524781.3848 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 0
|  | Cable tray 300x100x2.0mm | 0 |  | m | 1009710 | 61078.452 | 1070788.452 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 0
|  | Cable tray 200x100x2.0mm | 10 |  | m | 776880 | 51045.8655 | 827925.8655 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
|  | Cable tray 500x100 with separating bar, c/w cover | 0 |  | m | 1525680 | 81001.3848 | 1606681.3848 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
|  | Cable tray 400x100 with separating bar, c/w cover | 64 | 73.7 | m | 826020 | 68320 | 894340 | 60877674 | 5035184 | 65912858 | 50% |  | 50% |  |  | 0% | 30438837 | 0 | 30438837 | TGE/ VN
|  | Cable tray 300x100 with separating bar, c/w cover | 0 | 0 | m | 1091610 | 61078.452 | 1152688.452 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
|  | Cable tray 200x100 with separating bar, c/w cover | 82 | 94.6 | m | 858780 | 51045.8655 | 909825.8655 | 81240588 | 4828938.8737 | 86069526.8737 | 50% |  | 50% |  |  | 0% | 40620294 | 0 | 40620294 | TGE/ VN
|  | Cable tray 200x50 with separating bar, c/w cover | 66 | 0 | m | 669240 | 51045.8655 | 720285.8655 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
|  | Cable ladder 600x100x2.0mm, c/w cover | 0 | 0 | m | 1199250 | 91952 | 1291202 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
|  | Cable ladder 500x100x2.0mm, c/w cover | 0 | 0 | m | 1067040 | 81001.3848 | 1148041.3848 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
|  | Cable ladder 400x100x2.0mm, c/w cover | 11 | 11 | m | 933660 | 68320 | 1001980 | 10270260 | 751520 | 11021780 | 50% |  | 50% |  |  | 0% | 5135130 | 0 | 5135130 | TGE/ VN
|  | Cable ladder 300x100x1.5mm, c/w cover | 0 | 0 | m | 625950 | 61078.452 | 687028.452 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
|  | Cable ladder 200x100x1.5mm, c/w cover | 2 | 2.2 | m | 496080 | 51045.8655 | 547125.8655 | 1091376 | 112300.904 | 1203676.904 | 50% |  | 50% |  |  | 0% | 545688 | 0 | 545688 | TGE/ VN
|  | Fitting and accessories | 1 | 1 | lot | 52471760 | 15741528 | 68213288 | 52471760 | 15741528 | 68213288 | 50% |  | 50% |  |  | 0% | 26235880 | 0 | 26235880
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Electrical installation | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Production hall 01 | [6 empty] | 4068960 | 2081884 | 6150844 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | 1-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB31_1_WE_G19/ Schneider/ VN
|  | 2-Way switch, 1 gang for lighting control panel | 0 | 0 | pcs | 0 | 54500 | 54500 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB31_WE/ Schneider/ VN
|  | Single Socket NEMA5 | 10 | 10 | pcs | 124560 | 54500 | 179060 | 1245600 | 545000 | 1790600 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Double Socket NEMA5 | 0 | 0 | pcs | 249120 | 54500 | 303620 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Single Socket 16A/230V, Lighting outlet general (wall) + Plug | 18 | 18 | pcs | 124560 | 54500 | 179060 | 2242080 | 981000 | 3223080 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Socket combination type 1 | 1 | 1 | pcs | 0 | 381500 | 381500 | 0 | 381500 | 381500 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Only Install Labor
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Only Install Labor
|  | Accessories | 1 | 1 | lot | 581280 | 174384 | 755664 | 581280 | 174384 | 755664 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Production hall 02 | [6 empty] | 1017240 | 425096 | 1442336 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | 1-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB31_1_WE_G19/ Schneider/ VN
|  | 2-Way switch, 1 gang for lighting control panel | 0 | 0 | pcs | 0 | 54500 | 54500 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB31_WE/ Schneider/ VN
|  | Single Socket NEMA5 | 2 | 2 | pcs | 124560 | 54500 | 179060 | 249120 | 109000 | 358120 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Double Socket NEMA5 | 0 | 0 | pcs | 249120 | 54500 | 303620 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Single Socket 16A/230V, Lighting outlet general (wall) + Plug | 5 | 5 | pcs | 124560 | 54500 | 179060 | 622800 | 272500 | 895300 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Only Install Labor
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Only Install Labor
|  | Accessories | 1 | 1 | lot | 145320 | 43596 | 188916 | 145320 | 43596 | 188916 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Lighting | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Production hall 01 | [6 empty] | 891792936.3239 | 117504814.1732 | 1009297750.4972 |  |  | 0% |  |  | 0% | 15782760.9596 | 0 | 15782760.9596
|  | Led Highbay light 115W, Type CI | 154 | 154 | pcs | 4081000 | 196000 | 4277000 | 628474000 | 30184000 | 658658000 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | BY518P LED160/NW PSU NB GM, Philips/ China
|  | LED Frame Lamp 1x46W, Type BII | 2 | 2 | pcs | 1607100 | 63504 | 1670604 | 3214200 | 127008 | 3341208 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WT158C LED56S/840 PSU L1500 GM, Philips/ China
|  | Wall mounted Light 1x15W, Type E | 18 | 18 | pcs | 585200 | 63504 | 648704 | 10533600 | 1143072 | 11676672 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WL008C LED10/NW round W, Philips/ China
|  | Accessories | 1 | 1 | lot | 19140000 | 3828000 | 22968000 | 19140000 | 3828000 | 22968000 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable for lighting system (Hall 01) | [6 empty] | 230431136.3239 | 82222734.1732 | 312653870.4972 |  |  | 0% |  |  | 0% | 15782760.9596 | 0 | 15782760.9596
|  | Cable Cu/XLPE//PVC 3Cx4.0mm2 | 565 | 800 | m | 46999.53 | 8250 | 55249.53 | 37599624 | 6600000 | 44199624 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 2404 | 2550 | m | 32518.74 | 7485.665 | 40004.405 | 82922787 | 19088445.75 | 102011232.75 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | Cable Cu/XLPE//PVC 3Cx1.5mm2 | 359 | 889 | m | 22980.09 | 5743.9305 | 28724.0205 | 20429300.01 | 5106354.2145 | 25535654.2245 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 1061 | 1850 | m | 8773.9726 | 14594.0164 | 23367.989 | 16231849.3151 | 26998930.3618 | 43230779.6768 | 50% |  | 50% |  |  | 0% | 8115924.6575 | 0 | 8115924.6575 | FPC20, Nano/ VN
|  | PVC conduit D32(cho PA đổi cáp 3x6mm group A) |  | 749 | m | 19428.0822 | 20044.0164 | 39472.0986 | 14551633.5616 | 15012968.2924 | 29564601.8541 | 50% |  | 50% |  |  | 0% | 7275816.7808 | 0 | 7275816.7808 | FPC32, Nano/ VN
|  | PVC flexible conduct D20 | 220 | 220 | m | 3554.7229 | 5289.7059 | 8844.4288 | 782039.0424 | 1163735.2941 | 1945774.3365 | 50% |  | 50% |  |  | 0% | 391019.5212 | 0 | 391019.5212 | Nano/ VN
|  | Accessories | 1 | 1 | lot | 5485667.5348 | 1645700.2604 | 7131367.7953 | 5485667.5348 | 1645700.2604 | 7131367.7953 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
|  | Cable Cu/XLPE//PVC 3Cx6.0mm2 |  | 800.8 | m | 65469.825 | 8250 | 73719.825 | 52428235.86 | 6606600 | 59034835.86 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | Production hall 02 | [6 empty] | 171116000 | 9147520 | 180263520 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | Led Highbay light 115W, Type CI | 40 | 40 | pcs | 4081000 | 196000 | 4277000 | 163240000 | 7840000 | 171080000 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | BY518P LED160/NW PSU NB GM, Philips/ China
|  | LED Frame Lamp 1x46W, Type BII | 0 | 0 | pcs | 1607100 | 63504 | 1670604 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WT158C LED56S/840 PSU L1500 GM, Philips/ China
|  | Wall mounted Light 1x15W, Type E | 5 | 5 | pcs | 585200 | 63504 | 648704 | 2926000 | 317520 | 3243520 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WL008C LED10/NW round W, Philips/ China
|  | Accessories | 1 | 1 | lot | 4950000 | 990000 | 5940000 | 4950000 | 990000 | 5940000 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable for lighting system (Hall 02) | [6 empty] | 26035182.9336 | 11396846.8435 | 37432029.777 |  |  | 0% |  |  | 0% | 3640330.5621 | 0 | 3640330.5621
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 536 | 560 | m | 32518.74 | 7485.665 | 40004.405 | 18210494.4 | 4191972.4 | 22402466.8 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | Cable Cu/XLPE//PVC 3Cx1.5mm2 | 96 | 120 | m | 22980.09 | 5743.9305 | 28724.0205 | 2757610.8 | 689271.66 | 3446882.46 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 277 | 398.2 | m | 8773.9726 | 14594.0164 | 23367.989 | 3493795.8904 | 5811337.3352 | 9305133.2256 | 80% |  | 80% |  |  | 0% | 2795036.7123 | 0 | 2795036.7123 | FPC20, Nano/ VN
|  | PVC conduit D20 | 88 | 0 | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | FPC20, Nano/ VN
|  | PVC flexible conduct D20 | 57 | 55 | m | 3554.7229 | 5289.7059 | 8844.4288 | 195509.7606 | 290933.8235 | 486443.5841 | 80% |  | 80% |  |  | 0% | 156407.8085 | 0 | 156407.8085 | Nano/ VN
|  | Accessories | 1 | 1 | lot | 1377772.0826 | 413331.6248 | 1791103.7073 | 1377772.0826 | 413331.6248 | 1791103.7073 | 50% |  | 50% |  |  | 0% | 688886.0413 | 0 | 688886.0413
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
2. 2. 70. |  | Electrical installation in the logistics hall | 1 | 1 | PSCH |  |  |  | 365728225.5911 | 45073708.1139 | 410801933.705 |  |  | 0% |  |  | 0% | 98194033.2073 | 0 | 98194033.2073
|  | Cable trays_Hot dip-Galvanized Steel | [6 empty] | 184238087 | 23645406.8737 | 207883493.8737 |  |  | 0% |  |  | 0% | 92119043.5 | 0 | 92119043.5
|  | Cable tray 500x100x2.0mm | 0 | 0 | m | 1443780 | 81001.3848 | 1524781.3848 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 0
|  | Cable tray 300x100x2.0mm | 0 | 0 | m | 1009710 | 61078.452 | 1070788.452 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 0
|  | Cable tray 200x100x2.0mm | 10 |  | m | 776880 | 51045.8655 | 827925.8655 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
|  | Cable tray 500x100 with separating bar | 9 |  | m | 1525680 | 81001.3848 | 1606681.3848 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
|  | Cable tray 400x100 with separating bar | 56 | 66 | m | 826020 | 68320 | 894340 | 54517320 | 4509120 | 59026440 | 50% |  | 50% |  |  | 0% | 27258660 | 0 | 27258660 | TGE/ VN
|  | Cable tray 300x100 with separating bar | 0 | 0 | m | 1091610 | 61078.452 | 1152688.452 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
|  | Cable tray 200x100 with separating bar | 83 | 94.6 | m | 858780 | 51045.8655 | 909825.8655 | 81240588 | 4828938.8737 | 86069526.8737 | 50% |  | 50% |  |  | 0% | 40620294 | 0 | 40620294 | TGE/ VN
|  | Cable tray 200x50 with separating bar | 66 | 0 | m | 669240 | 51045.8655 | 720285.8655 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
|  | Cable ladder 600x100x2.0mm | 0 | 0 | m | 1199250 | 91952 | 1291202 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
|  | Cable ladder 500x100x2.0mm | 0 | 0 | m | 1067040 | 81001.3848 | 1148041.3848 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
|  | Cable ladder 400x100x2.0mm | 3 | 3.3 | m | 466830 | 68320 | 535150 | 1540539 | 225456 | 1765995 | 50% |  | 50% |  |  | 0% | 770269.5 | 0 | 770269.5 | TGE/ VN
|  | Cable ladder 300x100x1.5mm | 0 | 0 | m | 625950 | 61078.452 | 687028.452 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
|  | Cable ladder 200x100x1.5mm | 0 | 0 | m | 496080 | 51045.8655 | 547125.8655 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
|  | Fitting and accessories | 1 | 1 | lot | 46939640 | 14081892 | 61021532 | 46939640 | 14081892 | 61021532 | 50% |  | 50% |  |  | 0% | 23469820 | 0 | 23469820
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Electrical installation | [6 empty] | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | 1-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB31_1_WE_G19/ Schneider/ VN
|  | 2-Way switch, 1 gang for lighting control panel | 0 | 0 | pcs | 0 | 54500 | 54500 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB31_WE/ Schneider/ VN
|  | Single Socket NEMA5 | 0 | 0 | pcs | 124560 | 54500 | 179060 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Double Socket NEMA5 | 0 | 0 | pcs | 249120 | 54500 | 303620 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Only Install Labor
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Only Install Labor
|  | Accessories | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 | 50% |  | 50% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Lighting | [6 empty] | 147378000 | 7630000 | 155008000 |  |  | 0% |  |  | 0% | 1925000 | 0 | 1925000
|  | Led Highbay light 115W, Type CII | 35 | 35 | pcs | 4100800 | 196000 | 4296800 | 143528000 | 6860000 | 150388000 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | BY518P LED160/NW PSU WB GM, Philips/ China
|  | LED Frame Lamp 1x46W, Type BII | 0 | 0 | pcs | 1607100 | 63504 | 1670604 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WT158C LED56S/840 PSU L1500 GM, Philips/ China
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 63504 | 648704 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WL008C LED10/NW round W, Philips/ China
|  | Accessories | 1 | 1 | lot | 3850000 | 770000 | 4620000 | 3850000 | 770000 | 4620000 | 50% |  | 50% |  |  | 0% | 1925000 | 0 | 1925000
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable for lighting system | [6 empty] | 34112138.5911 | 13798301.2403 | 47910439.8314 |  |  | 0% |  |  | 0% | 4149989.7073 | 0 | 4149989.7073
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 693 | 805 | m | 32518.74 | 7485.665 | 40004.405 | 26177585.7 | 6025960.325 | 32203546.025 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | Cable Cu/XLPE//PVC 3Cx1.5mm2 | 96 | 90 | m | 22980.09 | 5743.9305 | 28724.0205 | 2068208.1 | 516953.745 | 2585161.845 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 277 | 440 | m | 8773.9726 | 14594.0164 | 23367.989 | 3860547.9452 | 6421367.2212 | 10281915.1664 | 80% |  | 80% |  |  | 0% | 3088438.3562 | 0 | 3088438.3562 | FPC20, Nano/ VN
|  | PVC conduit D20 | 88 | 0 | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | FPC20, Nano/ VN
|  | PVC flexible conduct D20 | 33 | 55 | m | 3554.7229 | 5289.7059 | 8844.4288 | 195509.7606 | 290933.8235 | 486443.5841 | 80% |  | 80% |  |  | 0% | 156407.8085 | 0 | 156407.8085 | Nano/ VN
|  | Accessories | 1 | 1 | lot | 1810287.0853 | 543086.1256 | 2353373.2109 | 1810287.0853 | 543086.1256 | 2353373.2109 | 50% |  | 50% |  |  | 0% | 905143.5426 | 0 | 905143.5426
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
2. 2. 80. |  | Power supply of building utilities | 1 | 1 | PSCH |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
2. 2. 90. |  | Three-arm Turnstile | 1 | 1 | PSCH |  |  |  | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
2. 2. 100. |  | Emergency lighting | 1 | 1 | PSCH |  |  |  | 77923218.1103 | 25617198.1684 | 103540416.2786 |  |  | 0% |  |  | 0% | 7126424.5438 | 0 | 7126424.5438
|  | Production hall 01 | [6 empty] | 18834457.2 | 3323337.16 | 22157794.36 |  |  | 0% |  |  | 0% | 425388.6 | 0 | 425388.6
|  | Emergency light | 13 | 13 | pcs | 516120 | 63504 | 579624 | 6709560 | 825552 | 7535112 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | LSM/ Duhal/ VN
|  | Exit light | 13 | 13 | pcs | 566280 | 63504 | 629784 | 7361640 | 825552 | 8187192 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | SNC302L/ Duhal/ VN
|  | Single Socket 16A/230V | 26 | 26 | pcs | 150480 | 54500 | 204980 | 3912480 | 1417000 | 5329480 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S / Schneider/ VN, Plastic type
|  | Accessories | 1 | 1 | pcs | 850777.2 | 255233.16 | 1106010.36 | 850777.2 | 255233.16 | 1106010.36 | 50% |  | 50% |  |  | 0% | 425388.6 | 0 | 425388.6 | Vietnam
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable power supply | [6 empty] | 22294958.4377 | 8918664.6672 | 31213623.1048 |  |  | 0% |  |  | 0% | 2678403.3567 | 0 | 2678403.3567
|  | Cable Cu/XLPE//PVC 3Cx2.5mm2 | 619 | 569 | m | 32518.74 | 7485.665 | 40004.405 | 18503163.06 | 4259343.385 | 22762506.445 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 371 | 275 | m | 8773.9726 | 14594.0164 | 23367.989 | 2412842.4658 | 4013354.5132 | 6426196.979 | 80% |  | 80% |  |  | 0% | 1930273.9726 | 0 | 1930273.9726 | FPC20, Nano/ VN
|  | PVC flexible conduct D20 | 74 | 55 | m | 3554.7229 | 5289.7059 | 8844.4288 | 195509.7606 | 290933.8235 | 486443.5841 | 80% |  | 80% |  |  | 0% | 156407.8085 | 0 | 156407.8085 | Nano/ VN
|  | Accessories | 1 | 1 | lot | 1183443.1513 | 355032.9454 | 1538476.0967 | 1183443.1513 | 355032.9454 | 1538476.0967 | 50% |  | 50% |  |  | 0% | 591721.5757 | 0 | 591721.5757
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Production hall 02 | [6 empty] | 8540160 | 1464048 | 10004208 |  |  | 0% |  |  | 0% | 120000 | 0 | 120000
|  | Emergency light | 6 | 6 | pcs | 516120 | 63504 | 579624 | 3096720 | 381024 | 3477744 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | LSM/ Duhal/ VN
|  | Exit light | 6 | 6 | pcs | 566280 | 63504 | 629784 | 3397680 | 381024 | 3778704 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | SNC302L/ Duhal/ VN
|  | Single Socket 16A/230V | 12 | 12 | pcs | 150480 | 54500 | 204980 | 1805760 | 654000 | 2459760 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S / Schneider/ VN, Plastic type
|  | Accessories | 1 | 1 | pcs | 240000 | 48000 | 288000 | 240000 | 48000 | 288000 | 50% |  | 50% |  |  | 0% | 120000 | 0 | 120000 | Vietnam
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable power supply | [6 empty] | 10420834.2021 | 4757933.0991 | 15178767.3011 |  |  | 0% |  |  | 0% | 1589761.063 | 0 | 1589761.063
|  | Cable Cu/XLPE//PVC 3Cx2.5mm2 | 286 | 253 | m | 32518.74 | 7485.665 | 40004.405 | 8227241.22 | 1893873.245 | 10121114.465 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 171 | 165 | m | 8773.9726 | 14594.0164 | 23367.989 | 1447705.4795 | 2408012.7079 | 3855718.1874 | 80% |  | 80% |  |  | 0% | 1158164.3836 | 0 | 1158164.3836 | FPC20, Nano/ VN
|  | PVC flexible conduct D20 | 34 | 55 | m | 3554.7229 | 5289.7059 | 8844.4288 | 195509.7606 | 290933.8235 | 486443.5841 | 80% |  | 80% |  |  | 0% | 156407.8085 | 0 | 156407.8085 | Nano/ VN
|  | Accessories | 1 | 1 | lot | 550377.742 | 165113.3226 | 715491.0646 | 550377.742 | 165113.3226 | 715491.0646 | 50% |  | 50% |  |  | 0% | 275188.871 | 0 | 275188.871 | Vietnam
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Logistics area | [6 empty] | 7116800 | 1220040 | 8336840 |  |  | 0% |  |  | 0% | 100000 | 0 | 100000
|  | Emergency light | 5 | 5 | pcs | 516120 | 63504 | 579624 | 2580600 | 317520 | 2898120 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | LSM/ Duhal/ VN
|  | Exit light | 5 | 5 | pcs | 566280 | 63504 | 629784 | 2831400 | 317520 | 3148920 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | SNC302L/ Duhal/ VN
|  | Single Socket 16A/230V | 10 | 10 | pcs | 150480 | 54500 | 204980 | 1504800 | 545000 | 2049800 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S / Schneider/ VN, Plastic type
|  | Accessories | 1 | 1 | pcs | 200000 | 40000 | 240000 | 200000 | 40000 | 240000 | 50% |  | 50% |  |  | 0% | 100000 | 0 | 100000 | Vietnam
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable power supply | [6 empty] | 10716008.2705 | 5933175.2421 | 16649183.5127 |  |  | 0% |  |  | 0% | 2212871.524 | 0 | 2212871.524
|  | Cable Cu/XLPE//PVC 3Cx2.5mm2 | 238 | 238 | m | 32518.74 | 7485.665 | 40004.405 | 7739460.12 | 1781588.27 | 9521048.39 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 143 | 253 | m | 8773.9726 | 14594.0164 | 23367.989 | 2219815.0685 | 3692286.1522 | 5912101.2207 | 80% |  | 80% |  |  | 0% | 1775852.0548 | 0 | 1775852.0548 | FPC20, Nano/ VN
|  | PVC flexible conduct D20 | 29 | 55 | m | 3554.7229 | 5289.7059 | 8844.4288 | 195509.7606 | 290933.8235 | 486443.5841 | 80% |  | 80% |  |  | 0% | 156407.8085 | 0 | 156407.8085 | Nano/ VN
|  | Accessories | 1 | 1 | lot | 561223.3215 | 168366.9964 | 729590.3179 | 561223.3215 | 168366.9964 | 729590.3179 | 50% |  | 50% |  |  | 0% | 280611.6607 | 0 | 280611.6607 | Vietnam
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
2. 2. 110. |  | Fire alarm system | 1 | 1 | PSCH |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 2. 120. |  | Network infrastructure | 1 | 1 | PSCH |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 2. 130. |  | Access control preparation | 1 | 1 | PSCH |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 2. 140. |  | CCTV System | 1 | 1 | PSCH |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
3. |  | Office, Social and Technical Areas (Hall 3) | [6 empty] | 8556494945.4536 | 444494571.6059 | 9000989517.0595 |  |  | 0% |  |  | 0% | 516253334.9279 | 0 | 516253334.9279
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
3. 2. |  | Electrical engineering | 1 | 1 | PSCH |  |  |  | 8556494945.4536 | 444494571.6059 | 9000989517.0595 |  |  | 0% |  |  | 0% | 516253334.9279 | 0 | 516253334.9279
3. 2. 10. |  | Rennovation existing grounding system and lightning protection | 1 | 1 | psch | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Included
3. 2. 20. |  | Rennovation existing grounding and equipotential bonding | 1 | 1 | psch | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Included
3. 2. 30. |  | Main Power supply | 1 | 1 | PSCH |  |  |  | 4272504384.025 | 197907035.9748 | 4470411419.9998 |  |  | 0% |  |  | 0% | 481157978.5 | 0 | 481157978.5
|  | Electrical panel | [6 empty] | 2486429270 | 40937031 | 2527366301 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | Modify SYN - TR1, Add ACB 4P 2250A, 85ka, fixed type | 1 | 1 | pcs | 243347500 | 1400000 | 244747500 | 243347500 | 1400000 | 244747500 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Circuit breaker: Schneider/ Asia, Included labour
|  | Building3_BMDP min 1500kVA | 1 | 1 | pcs | 581849400 | 3920000 | 585769400 | 581849400 | 3920000 | 585769400 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Encloser: TGE/ Vietnam Circuit breaker: Schneider/ Asia
|  | Building 3_PDP 1.0 | 1 | 1 | pcs | 137478000 | 1400000 | 138878000 | 137478000 | 1400000 | 138878000 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Encloser: TGE/ Vietnam Circuit breaker: Schneider/ Asia
|  | Building 3_PDP 1.1 | 1 | 1 | pcs | 124835700 | 1400000 | 126235700 | 124835700 | 1400000 | 126235700 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Encloser: TGE/ Vietnam Circuit breaker: Schneider/ Asia
|  | Building 3_PDP 2.0 | 1 | 1 | pcs | 137478000 | 1400000 | 138878000 | 137478000 | 1400000 | 138878000 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Encloser: TGE/ Vietnam Circuit breaker: Schneider/ Asia
|  | Building 3_PDP 1.2 | 1 | 1 | pcs | 160848600 | 1400000 | 162248600 | 160848600 | 1400000 | 162248600 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Encloser: TGE/ Vietnam Circuit breaker: Schneider/ Asia
|  | Building 3_PDP 2.1 | 1 | 1 | pcs | 162050900 | 1400000 | 163450900 | 162050900 | 1400000 | 163450900 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Encloser: TGE/ Vietnam Circuit breaker: Schneider/ Asia
|  | Building 3_BDP 1.0 | 1 | 1 | pcs | 113520000 | 1400000 | 114920000 | 113520000 | 1400000 | 114920000 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Encloser: TGE/ Vietnam Circuit breaker: Schneider/ Asia
|  | Building 3_BDP 1.1 | 1 | 1 | pcs | 232601600 | 1400000 | 234001600 | 232601600 | 1400000 | 234001600 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Encloser: TGE/ Vietnam Circuit breaker: Schneider/ Asia
|  | Building 3_BDP 2.0 | 1 | 1 | pcs | 246041400 | 1400000 | 247441400 | 246041400 | 1400000 | 247441400 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Encloser: TGE/ Vietnam Circuit breaker: Schneider/ Asia
|  | Scooter garage__BDP 1.0 | 1 | 1 | pcs | 15643100 | 840000 | 16483100 | 15643100 | 840000 | 16483100 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Encloser: TGE/ Vietnam Circuit breaker: Schneider/ Asia
|  | Canteen__BDP 1.0 | 1 | 1 | pcs | 47347300 | 1400000 | 48747300 | 47347300 | 1400000 | 48747300 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Encloser: TGE/ Vietnam Circuit breaker: Schneider/ Asia
|  | Building 3_DB SEF 1 | 1 | 1 | pcs | 28968500 | 840000 | 29808500 | 28968500 | 840000 | 29808500 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Encloser: TGE/ Vietnam Circuit breaker: Schneider/ Asia
|  | Building 3_DB SEF 2 | 1 | 1 | pcs | 24835800 | 840000 | 25675800 | 24835800 | 840000 | 25675800 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Encloser: TGE/ Vietnam Circuit breaker: Schneider/ Asia
|  | Building 3_UPS1-MDP | 1 | 1 | pcs | 91081100 | 1400000 | 92481100 | 91081100 | 1400000 | 92481100 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Encloser: TGE/ Vietnam Circuit breaker: Schneider/ Asia
|  | Building UPS1-DP1.2 | 1 | 1 | pcs | 79290200 | 1400000 | 80690200 | 79290200 | 1400000 | 80690200 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Encloser: TGE/ Vietnam Circuit breaker: Schneider/ Asia
|  | Building 3_UPS 1-DP 1.2 | 1 | 1 | pcs | 10457700 | 840000 | 11297700 | 10457700 | 840000 | 11297700 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Encloser: TGE/ Vietnam Circuit breaker: Schneider/ Asia
|  | Building 3_UPS 1 DP 1.3 | 1 | 1 | pcs | 8309400 | 840000 | 9149400 | 8309400 | 840000 | 9149400 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Encloser: TGE/ Vietnam Circuit breaker: Schneider/ Asia
|  | Building 3_UPS 1 DP 1.3 35kVA | 1 | 1 | pcs | 70643100 | 1400000 | 72043100 | 70643100 | 1400000 | 72043100 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Encloser: TGE/ Vietnam Circuit breaker: Schneider/ Asia
|  | Building 3 UPS2-MD | 1 | 1 | pcs | 79290200 | 1400000 | 80690200 | 79290200 | 1400000 | 80690200 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Encloser: TGE/ Vietnam Circuit breaker: Schneider/ Asia
|  | Building UPS2-DP1.2 | 1 | 1 | pcs | 10457700 | 840000 | 11297700 | 10457700 | 840000 | 11297700 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Encloser: TGE/ Vietnam Circuit breaker: Schneider/ Asia
|  | Building 3_UPS 2-DP1.2 | 1 | 1 | pcs | 8309400 | 840000 | 9149400 | 8309400 | 840000 | 9149400 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Encloser: TGE/ Vietnam Circuit breaker: Schneider/ Asia
|  | Building 3_UPS 2 DP 1.3 | 1 | 1 | pcs | 8309400 | 840000 | 9149400 | 8309400 | 840000 | 9149400 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Encloser: TGE/ Vietnam Circuit breaker: Schneider/ Asia
|  | Building 3_UPS 2 DP 1.3 35kVA | 1 | 1 | pcs | 71126000 | 1400000 | 72526000 | 71126000 | 1400000 | 72526000 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Encloser: TGE/ Vietnam Circuit breaker: Schneider/ Asia
|  | Building 3_DP PUMP 1 | 1 |  | pcs | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Encloser: TGE/ Vietnam Circuit breaker: Schneider/ Asia
|  | Building 3_DP PUMP 2 | 1 |  | pcs | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Encloser: TGE/ Vietnam Circuit breaker: Schneider/ Asia
|  | Fitting and accessories | 1 | 1 | lot | 35656770 | 10697031 | 46353801 | 35656770 | 10697031 | 46353801 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable trays_Hot dip-Galvanized Steel | [6 empty] | 982315957 | 122770928.7283 | 1105086885.7283 |  |  | 0% |  |  | 0% | 481157978.5 | 0 | 481157978.5
|  | Cable tray 500x100x2.0mm | 0 | 0 | m | 1443780 | 81001.3848 | 1524781.3848 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 0
|  | Cable tray 300x100x2.0mm | 0 | 0 | m | 1009710 | 61078.452 | 1070788.452 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 0
|  | Cable tray 200x100x2.0mm | 0 | 0 | m | 776880 | 51045.8655 | 827925.8655 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
|  | Cable tray 500x100 with separating bar, c/w cover | 0 | 93 | m | 1525680 | 81001.3848 | 1606681.3848 | 141888240 | 7533128.7822 | 149421368.7822 | 50% |  | 50% |  |  | 0% | 70944120 | 0 | 70944120 | TGE/ VN
|  | Cable tray 400x100 with separating bar, c/w cover | 0 | 0 | m | 826020 | 68320 | 894340 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
|  | Cable tray 300x100 with separating bar, c/w cover | 0 | 0 | m | 1091610 | 61078.452 | 1152688.452 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
|  | Cable tray 200x100 with separating bar, c/w cover | 0 | 0 | m | 858780 | 51045.8655 | 909825.8655 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
|  | Cable tray 600x50 with separating bar, c/w cover | 26 | 28.6 | m | 1568970 | 87472 | 1656442 | 44872542 | 2501699.2 | 47374241.2 | 50% |  | 50% |  |  | 0% | 22436271 | 0 | 22436271 | TGE/ VN
|  | Cable tray 500x50 with separating bar, c/w cover | 6 | 6.6 | m | 1334970 | 81001.3848 | 1415971.3848 | 8810802 | 534609.1394 | 9345411.1394 | 50% |  | 50% |  |  | 0% | 4405401 | 0 | 4405401 | TGE/ VN
|  | Cable tray 400x50 with separating bar, c/w cover | 165 | 183.7 | m | 1136070 | 68320 | 1204390 | 208696059 | 12550384 | 221246443 | 50% |  | 50% |  |  | 0% | 104348029.5 | 0 | 104348029.5 | TGE/ VN
|  | Cable tray 200x50 with separating bar, c/w cover | 303 | 453.2 | m | 669240 | 51045.8655 | 720285.8655 | 303299568 | 23133986.2319 | 326433554.2319 | 50% |  | 50% |  |  | 0% | 151649784 | 0 | 151649784 | TGE/ VN
|  | Cable tray 100x50 with separating bar, c/w cover | 14 | 15.4 | m | 469170 | 51045.8655 | 520215.8655 | 7225218 | 786106.3283 | 8011324.3283 | 50% |  | 50% |  |  | 0% | 3612609 | 0 | 3612609 | TGE/ VN
|  | Cable ladder 600x100x2.0mm, c/w cover | 0 | 0 | m | 1199250 | 91952 | 1291202 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
|  | Cable ladder 500x100x2.0mm, c/w cover | 2 | 2.2 | m | 1067040 | 81001.3848 | 1148041.3848 | 2347488 | 178203.0465 | 2525691.0465 | 50% |  | 50% |  |  | 0% | 1173744 | 0 | 1173744 | TGE/ VN
|  | Cable ladder 400x100x2.0mm, c/w cover | 0 | 0 | m | 933660 | 68320 | 1001980 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
|  | Cable ladder 300x100x1.5mm, c/w cover | 0 | 0 | m | 625950 | 61078.452 | 687028.452 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
|  | Cable ladder 200x100x1.5mm, c/w cover | 0 | 0 | m | 496080 | 51045.8655 | 547125.8655 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
|  | Fitting and accessories | 1 | 1 | lot | 245176040 | 73552812 | 318728852 | 245176040 | 73552812 | 318728852 | 50% |  | 50% |  |  | 0% | 122588020 | 0 | 122588020
|  | Fire stop | 1 | 1 | set | 20000000 | 2000000 | 22000000 | 20000000 | 2000000 | 22000000 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Lighting control panel | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | BDP 1.0 | [6 empty] | 97882510.475 | 7025037.0385 | 104907547.5135 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | 8P smart key, white plastic surface material | 1 | 1 | pcs | 17060781.92 | 137500 | 17198281.92 | 17060781.92 | 137500 | 17198281.92 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | LS5094TSM/ Jung/ Germany
|  | 4P smart key, white plastic surface material | 2 | 2 | pcs | 13652800 | 137500 | 13790300 | 27305600 | 275000 | 27580600 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | LS5092TSM/ Jung/ Germany
|  | Smart light control device for 8 independent load groups - 16A/ K | 1 | 1 | pcs | 19992667.52 | 49500 | 20042167.52 | 19992667.52 | 49500 | 20042167.52 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | RM 8T KNX/ Theben/ Germany
|  | Smart light control device for 4 independent load groups - 16A/ K | 1 | 1 | pcs | 14090720 | 49500 | 14140220 | 14090720 | 49500 | 14140220 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | RM 4I KNX/ Theben/ Germany
|  | Power supply for control signals, 24VDC | 2 | 2 | pcs | 8376816 | 49500 | 8426316 | 16753632 | 99000 | 16852632 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Power supply 320 mA T KNX/ Theben/ Germany
|  | Base for smart keys | 3 | 3 | pcs | 41884.08 | 49500 | 91384.08 | 125652.24 | 148500 | 274152.24 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Keiser/ Germany
|  | Accessories | 1 | 1 | lot | 2553456.795 | 766037.0385 | 3319493.8335 | 2553456.795 | 766037.0385 | 3319493.8335 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | T&C | 1 | 1 | lot | 0 | 5500000 | 5500000 | 0 | 5500000 | 5500000 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | BDP 1.1 | [6 empty] | 162133437.125 | 10750870.3775 | 172884307.5025 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | 8P smart key, white plastic surface material | 3 | 3 | pcs | 17060781.92 | 137500 | 17198281.92 | 51182345.76 | 412500 | 51594845.76 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | LS5094TSM/ Jung/ Germany
|  | 4P smart key, white plastic surface material | 2 | 2 | pcs | 13652800 | 137500 | 13790300 | 27305600 | 275000 | 27580600 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | LS5092TSM/ Jung/ Germany
|  | Smart light control device for 8 independent load groups - 16A/ K | 2 | 2 | pcs | 19992667.52 | 49500 | 20042167.52 | 39985335.04 | 99000 | 40084335.04 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | RM 8T KNX/ Theben/ Germany
|  | Smart light control device for 4 independent load groups - 16A/ K | 1 | 1 | pcs | 14090720 | 49500 | 14140220 | 14090720 | 49500 | 14140220 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | RM 4I KNX/ Theben/ Germany
|  | Power supply for control signals, 24VDC | 3 | 3 | pcs | 8376816 | 49500 | 8426316 | 25130448 | 148500 | 25278948 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Power supply 320 mA T KNX/ Theben/ Germany
|  | Base for smart keys | 5 | 5 | pcs | 41884.08 | 49500 | 91384.08 | 209420.4 | 247500 | 456920.4 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Keiser/ Germany
|  | Accessories | 1 | 1 | lot | 4229567.925 | 1268870.3775 | 5498438.3025 | 4229567.925 | 1268870.3775 | 5498438.3025 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | T&C | 1 | 1 | lot | 0 | 8250000 | 8250000 | 0 | 8250000 | 8250000 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | BDP 2.0 | [6 empty] | 290635290.425 | 12702537.0555 | 303337827.4805 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | 8P smart key, white plastic surface material | 7 | 7 | pcs | 17060781.92 | 137500 | 17198281.92 | 119425473.44 | 962500 | 120387973.44 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | LS5094TSM/ Jung/ Germany
|  | 4P smart key, white plastic surface material | 2 | 2 | pcs | 13652800 | 137500 | 13790300 | 27305600 | 275000 | 27580600 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | LS5092TSM/ Jung/ Germany
|  | Smart light control device for 8 independent load groups - 16A/ K | 4 | 4 | pcs | 19992667.52 | 49500 | 20042167.52 | 79970670.08 | 198000 | 80168670.08 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | RM 8T KNX/ Theben/ Germany
|  | Smart light control device for 4 independent load groups - 16A/ K | 1 | 1 | pcs | 14090720 | 49500 | 14140220 | 14090720 | 49500 | 14140220 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | RM 4I KNX/ Theben/ Germany
|  | Power supply for control signals, 24VDC | 5 | 5 | pcs | 8376816 | 49500 | 8426316 | 41884080 | 247500 | 42131580 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Power supply 320 mA T KNX/ Theben/ Germany
|  | Base for smart keys | 9 | 9 | pcs | 41884.08 | 49500 | 91384.08 | 376956.72 | 445500 | 822456.72 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Keiser/ Germany
|  | Accessories | 1 | 1 | lot | 7581790.185 | 2274537.0555 | 9856327.2405 | 7581790.185 | 2274537.0555 | 9856327.2405 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | T&C | 1 | 1 | lot | 0 | 8250000 | 8250000 | 0 | 8250000 | 8250000 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable power supply | [6 empty] | 9760419 | 2320631.775 | 12081050.775 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | From Building 3_BDP 1.1 Panel to DB-PUMP1 | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 4x1Cx4mm2+E4mm2 | 71 | 64 | m | 72299.4 | 17189.865 | 89489.265 | 4627161.6 | 1100151.36 | 5727312.96 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From Building 3_BDP 2.0 Panel to DB-PUMP2 | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 4x1Cx4mm2+E4mm2 | 71 | 71 | m | 72299.4 | 17189.865 | 89489.265 | 5133257.4 | 1220480.415 | 6353737.815 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
3. 2. 40. |  | Uninterrupted power supply (UPS) | 1 | 1 | PSCH |  |  |  | 2008718012.8938 | 15050660.8087 | 2023768673.7025 |  |  | 0% |  |  | 0% | 245671.2329 | 0 | 245671.2329
|  | UPS 93PR 60kW*100%load, backup 15 Minutes, frame 125kw | 2 | 2 | set | 967016600 | 3300000 | 970316600 | 1934033200 | 6600000 | 1940633200 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Included labour
|  | 93PR 125kW Frame to contain up to max. 6 Power Modules, Back-Feed, MBS & 1 x internal PDU | 0 | 0 |  | 310491720 | 0 | 310491720 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 9106-42252, EATON/ China
|  | 93PR Power Module of 25KW capacity (Rev B) | 0 | 0 |  | 101372040 | 0 | 101372040 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 733-82069, EATON/ China
|  | Industrial Gateway Card | 0 | 0 |  | 9882180 | 0 | 9882180 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 744-07774, EATON/ China
|  | Eaton battery backup 15 mins @ 75kW | 0 | 0 |  | 6021400 | 0 | 6021400 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | ETNHF12-390WP-X, EATON/ China
|  | Battery cabinet, MCB, cable to connect Battery to UPS and accesoriess. | 0 | 0 |  | 99429000 | 0 | 99429000 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Accessories, EATON included T&C and 2nd year warranty
|  | Accessories | 1 | 1 | lot | 10000000 | 2000000 | 12000000 | 10000000 | 2000000 | 12000000 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | water leak warning system | 2 | 2 | lot |  |  |  | 64684812.8938 | 6450660.8087 | 71135473.7025 |  |  | 0% |  |  | 0% | 245671.2329 | 0 | 245671.2329 | Price included for 4 rooms
|  | Water leak detector | 4 | 4 | pcs | 1587000 | 49500 | 1636500 | 6348000 | 198000 | 6546000 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | AT/LD100/ Asia
|  | Cabinet for Water leak detector | 4 | 4 | pcs | 1725000 | 220000 | 1945000 | 6900000 | 880000 | 7780000 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
|  | Power supply | 4 | 4 | pcs | 862500 | 165000 | 1027500 | 3450000 | 660000 | 4110000 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
|  | water leak cable | 140 | 120 | m | 317400 | 22000 | 339400 | 38088000 | 2640000 | 40728000 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | A-LC1B/ Vietnam
|  | Connection conductor A-LLW58; wire holder permanent | 4 | 4 | pcs | 1269600 | 49500 | 1319100 | 5078400 | 198000 | 5276400 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | A-LLW58/ Vietnam
|  | Single Socket 1P-16A-250V | 4 | 4 | pcs | 124560 | 54500 | 179060 | 498240 | 218000 | 716240 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | 3C-1.5mm2 Cu/XLPE/PVC | 60 | 51 | m | 22980.09 | 5743.9305 | 28724.0205 | 1171984.59 | 292940.4555 | 1464925.0455 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 58 | 35 | m | 8773.9726 | 14594.0164 | 23367.989 | 307089.0411 | 510790.5744 | 817879.6155 | 80% |  | 80% |  |  | 0% | 245671.2329 | 0 | 245671.2329 | FPC20, Nano/ VN
|  | Accessories | 1 | 1 | lot | 2843099.2627 | 852929.7788 | 3696029.0415 | 2843099.2627 | 852929.7788 | 3696029.0415 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
3. 2. 50. |  | Electrical Capacitor bank | 1 | 1 | PSCH |  |  |  | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | Electrical Capacitor bank Building3_BMDP min 1500kVA | 1 |  | pcs | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Encloser: TGE/ Vietnam Capcitor Bank (25kVAR-3P-440VAC): Sunny/Equivalent Power Factor controller - VarPlus Logic - VPL 12/ Schneider
|  | Accessories | 1 | 1 | lot | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
3. 2. 60. |  | Power supply of building utilities | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0% | 0 | 0 | 0 | Included
3. 2. 70. |  | Energy measurement system | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0% | 0 | 0 | 0 | Included
3. 2. 80. |  | Electrical installation in offices and meeting rooms | 1 | 1 | PSCH |  |  |  | 1229075412.0457 | 66404103.9782 | 1295479516.0239 |  |  | 0% |  |  | 0% | 11781333.7092 | 0 | 11781333.7092
|  | Switch & Socket | [6 empty] | 221333361.2618 | 14243567.4985 | 235576928.7604 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | 1-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB31_1_WE_G19/ Schneider/ VN
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB31_WE/ Schneider/ VN
|  | Push-button - (switch) | 37 | 37 | pcs | 223200 | 54500 | 277700 | 8258400 | 2016500 | 10274900 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | E8331PRL1_WE_G19/ Schneider/ VN
|  | Single Socket NEMA5 | 15 | 15 | pcs | 124560 | 54500 | 179060 | 1868400 | 817500 | 2685900 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Double Socket NEMA5 | 15 | 15 | pcs | 249120 | 54500 | 303620 | 3736800 | 817500 | 4554300 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Dimmer Switch | 6 | 6 | pcs | 254400 | 54500 | 308900 | 1526400 | 327000 | 1853400 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Only Install Labor
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Only Install Labor
|  | Cord outlet socket with 2m cable reserve with connection terminals, E1 | 6 | 6 | pcs | 507247.2 | 54500 | 561747.2 | 3043483.2 | 327000 | 3370483.2 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 57232+075690, Legrand / France
|  | Cord outlet socket with 4m cable reserve with connection terminals, E2 | 0 | 0 | pcs | 507247.2 | 54500 | 561747.2 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 57232+075690, Legrand / France
|  | Cord outlet socket with 6m cable reserve with connection terminals, E3 | 33 | 33 | pcs | 507247.2 | 54500 | 561747.2 | 16739157.6 | 1798500 | 18537657.6 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 57232+075690, Legrand / France
|  | Floor box, recessed (3xDouble Socket NEMA5, 2xIT - Double socket) | 3 | 3 | pcs | 8885676 | 272500 | 9158176 | 26657028 | 817500 | 27474528 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 088070+088073, Legrand/ France+KB426UES2_WE_G19 / Schneider/ VN, Plastic type+272368-2, Commscope + NSP-USMB+1375191-1, Commscope
|  | Floor box, recessed (4xDouble Socket NEMA5, 2xIT - Double socket) | 1 | 1 | pcs | 9467332.8 | 272500 | 9739832.8 | 9467332.8 | 272500 | 9739832.8 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 088070+088073, Legrand/ France+KB426UES2_WE_G19 / Schneider/ VN, Plastic type+272368-2, Commscope + NSP-USMB+1375191-1, Commscope
|  | Floor box, recessed (1xDouble Socket NEMA5, 1xIT - Double socket,1x HDMI connection to the projector) | 3 | 3 | pcs | 9216914.4 | 272500 | 9489414.4 | 27650743.2 | 817500 | 28468243.2 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 088070+088073, Legrand/ France+KB426UES2_WE_G19 / Schneider/ VN, Plastic type+272368-2, Commscope + NSP-USMB+1375191-1, Commscope + + HDMI socket + HDMI cable
|  | Floor box, recessed (2xDouble Socket NEMA5, 2xIT - Double socket, 1x HDMI connection to the projector) | 1 | 1 | pcs | 10490947.2 | 272500 | 10763447.2 | 10490947.2 | 272500 | 10763447.2 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 088070+088073, Legrand/ France+KB426UES2_WE_G19 / Schneider/ VN, Plastic type+272368-2, Commscope + NSP-USMB+1375191-1, Commscope + HDMI socket + HDMI cable
|  | Floor box, recessed (3xDouble Socket NEMA5, 2xIT - Double socket, 1x HDMI connection to the projector) | 0 | 0 | pcs | 11072604 | 272500 | 11345104 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 088070+088073, Legrand/ France+KB426UES2_WE_G19 / Schneider/ VN, Plastic type+272368-2, Commscope + NSP-USMB+1375191-1, Commscope + HDMI socket + HDMI cable
|  | Floor box, recessed (4xDouble Socket NEMA5, 2xIT - Double socket, 1x HDMI connection to the projector) | 2 | 2 | pcs | 11654260.8 | 272500 | 11926760.8 | 23308521.6 | 545000 | 23853521.6 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 088070+088073, Legrand/ France+KB426UES2_WE_G19 / Schneider/ VN, Plastic type+272368-2, Commscope + NSP-USMB+1375191-1, Commscope + HDMI socket + HDMI cable
|  | Projector + Accessories | 3 | 3 | pcs | 18650000 | 381500 | 19031500 | 55950000 | 1144500 | 57094500 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | PT-LB412, Panasonic/ VN
|  | Motion sensor | 19 | 19 | pcs | 1150224 | 54500 | 1204724 | 21854256 | 1035500 | 22889756 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | SAE_UE_MS_CSAWE/ Schneider/ VN
|  | Accessories | 1 | 1 | lot | 10781891.6618 | 3234567.4985 | 14016459.1604 | 10781891.6618 | 3234567.4985 | 14016459.1604 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  |  | 0 | 0 | [9 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Lighting | 0 | 0 |  |  |  |  | 643593600 | 11842000 | 655435600 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | LED Panel 36W, Type AI | 168 | 168 | pcs | 3339600 | 56000 | 3395600 | 561052800 | 9408000 | 570460800 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | RC160V LED40S 840 W60L60 PSU, Philips/ China
|  | LED Panel 36W, Type AI - Dali Dim | 23 | 23 | pcs | 3339600 | 56000 | 3395600 | 76810800 | 1288000 | 78098800 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | RC160V LED40S 840 W60L60 PSD, Philips/ China
|  | LED Frame Lamp 1x46W, Type BII | 0 | 0 | pcs | 1607100 | 56000 | 1663100 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WT158C LED56S/840 PSU L1500 GM, Philips/ China
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 56000 | 641200 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WL008C LED10/NW round W, Philips/ China
|  | Accessories | 1 | 1 | lot | 5730000 | 1146000 | 6876000 | 5730000 | 1146000 | 6876000 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable power | [6 empty] | 364148450.7839 | 40318536.4797 | 404466987.2635 |  |  | 0% |  |  | 0% | 11781333.7092 | 0 | 11781333.7092
|  | 3C-1.5mm2 Cu/XLPE/PVC | 1142 | 1002 | m | 22980.09 | 5743.9305 | 28724.0205 | 23026050.18 | 5755418.361 | 28781468.541 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 3C-2.5mm2 Cu/XLPE/PVC | 630 | 570 | m | 32518.74 | 7485.665 | 40004.405 | 18535681.8 | 4266829.05 | 22802510.85 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 3C-2.5mm2 Cu/XLPE/PVC for E1, E2, E3 | 303 | 303 | m | 32518.74 | 7485.665 | 40004.405 | 9853178.22 | 2268156.495 | 12121334.715 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 0 | 0 | m | 72299.4 | 17189.865 | 89489.265 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 0 | 0 | m | 102372.9 | 18573.4395 | 120946.3395 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | Dado duct 50x130mm | 296 | 296 | m | 985945.6609 | 53025 | 1038970.6609 | 291839915.6313 | 15695400 | 307535315.6313 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 075603/ Legrand
|  | PVC conduit D20 | 507 | 507 | m | 8773.9726 | 14594.0164 | 23367.989 | 4448404.1096 | 7399166.3208 | 11847570.4304 | 80% |  | 80% |  |  | 0% | 3558723.2877 | 0 | 3558723.2877 | FPC20, Nano/ VN
|  | Accessories | 1 | 1 | lot | 16445220.843 | 4933566.2529 | 21378787.0959 | 16445220.843 | 4933566.2529 | 21378787.0959 | 50% |  | 50% |  |  | 0% | 8222610.4215 | 0 | 8222610.4215
|  |  | 0 | 0 | [9 empty] | 0% |  |  | 0% | 0 | 0 | 0
3. 2. 90. |  | Electrical installation in social rooms | 1 | 1 | PSCH |  |  |  | 258752977.5651 | 35385729.898 | 294138707.4631 |  |  | 0% |  |  | 0% | 7644217.1601 | 0 | 7644217.1601
|  | Switch & Socket | [6 empty] | 10372584.6 | 3183623.38 | 13556207.98 |  |  | 0% |  |  | 0% | 219372.3 | 0 | 219372.3
|  | 1-Way switch, 1 gang | 2 | 2 | pcs | 46800 | 54500 | 101300 | 93600 | 109000 | 202600 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB31_1_WE_G19/ Schneider/ VN
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB31_WE/ Schneider/ VN
|  | Single Socket NEMA5 | 29 | 29 | pcs | 124560 | 54500 | 179060 | 3612240 | 1580500 | 5192740 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Double Socket NEMA5 | 25 | 25 | pcs | 249120 | 54500 | 303620 | 6228000 | 1362500 | 7590500 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Power outlet general, 3p/4W, grounded | 0 | 0 | pcs | 150480 | 54500 | 204980 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Only Install Labor
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Only Install Labor
|  | Accessories | 1 | 1 | lot | 438744.6 | 131623.38 | 570367.98 | 438744.6 | 131623.38 | 570367.98 | 50% |  | 50% |  |  | 0% | 219372.3 | 0 | 219372.3
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Lighting | [6 empty] | 180626800 | 8680000 | 189306800 |  |  | 0% |  |  | 0% | 2100000 | 0 | 2100000
|  | LED Panel 36W, Type AI | 0 | 0 | pcs | 3339600 | 56000 | 3395600 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | RC160V LED40S 840 W60L60 PSU, Philips/ China
|  | LED Frame Lamp 1x30W, Type BI | 56 | 56 | pcs | 1346400 | 56000 | 1402400 | 75398400 | 3136000 | 78534400 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WT158C LED36S/840 PSU L1200 GM, Philips/ China
|  | LED Frame Lamp 1x46W, Type BII | 4 | 4 | pcs | 1607100 | 56000 | 1663100 | 6428400 | 224000 | 6652400 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WT158C LED56S/840 PSU L1500 GM, Philips/ China
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 56000 | 641200 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WL008C LED10/NW round W, Philips/ China
|  | LED Ceiling mounted Light 1x19W, Type D | 80 | 80 | pcs | 1182500 | 56000 | 1238500 | 94600000 | 4480000 | 99080000 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | DN393B LED22/840 PSU D200 ALU GM, Philips/ China
|  | Accessories | 1 | 1 | lot | 4200000 | 840000 | 5040000 | 4200000 | 840000 | 5040000 | 50% |  | 50% |  |  | 0% | 2100000 | 0 | 2100000
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable power | [6 empty] | 67753592.9651 | 23522106.518 | 91275699.4831 |  |  | 0% |  |  | 0% | 5324844.8601 | 0 | 5324844.8601
|  | 3C-1.5mm2 Cu/XLPE/PVC | 1187 | 1492.7 | m | 22980.09 | 5743.9305 | 28724.0205 | 34302380.343 | 8573965.0574 | 42876345.4004 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 3C-2.5mm2 Cu/XLPE/PVC | 690 | 792 | m | 32518.74 | 7485.665 | 40004.405 | 25754842.08 | 5928646.68 | 31683488.76 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 0 | 0 | m | 72299.4 | 17189.865 | 89489.265 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 0 | 0 | m | 102372.9 | 18573.4395 | 120946.3395 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | Dado duct 50x130mm | 0 | 0 | m | 985945.6609 | 53025 | 1038970.6609 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 075603/ Legrand
|  | PVC conduit D20 | 703 | 561 | m | 8773.9726 | 14594.0164 | 23367.989 | 4922198.6301 | 8187243.207 | 13109441.8371 | 80% |  | 80% |  |  | 0% | 3937758.9041 | 0 | 3937758.9041 | FPC20, Nano/ VN
|  | Accessories | 1 | 1 | lot | 2774171.912 | 832251.5736 | 3606423.4856 | 2774171.912 | 832251.5736 | 3606423.4856 | 50% |  | 50% |  |  | 0% | 1387085.956 | 0 | 1387085.956
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
3. 2. 100. |  | Electrical installation in corridors and stairways | 1 | 1 | PSCH |  |  |  | 74974338.2247 | 17389802.6953 | 92364140.92 |  |  | 0% |  |  | 0% | 4219152.3979 | 0 | 4219152.3979
|  | Switch & Socket | [6 empty] | 13582018.8 | 4641349.64 | 18223368.44 |  |  | 0% |  |  | 0% | 287249.4 | 0 | 287249.4
|  | 1-Way switch, 1 gang | 6 | 6 | pcs | 46800 | 54500 | 101300 | 280800 | 327000 | 607800 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB31_1_WE_G19/ Schneider/ VN
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB31_WE/ Schneider/ VN
|  | Push-button switch | 32 | 32 | pcs | 223200 | 54500 | 277700 | 7142400 | 1744000 | 8886400 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | E8331PRL1_WE_G19/ Schneider/ VN
|  | Single Socket NEMA5 | 12 | 12 | pcs | 124560 | 54500 | 179060 | 1494720 | 654000 | 2148720 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Double Socket NEMA5 | 0 | 0 | pcs | 249120 | 54500 | 303620 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Power outlet general, 1p/2W, grounded | 4 | 4 | pcs | 150480 | 54500 | 204980 | 601920 | 218000 | 819920 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Power outlet general, 3p/4W, grounded | 0 | 0 | pcs | 150480 | 54500 | 204980 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Single Socket 16A/230V, Lighting outlet general (wall) + Plug | 28 | 28 | pcs | 124560 | 54500 | 179060 | 3487680 | 1526000 | 5013680 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Only Install Labor
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Only Install Labor
|  | Accessories | 1 | 1 | lot | 574498.8 | 172349.64 | 746848.44 | 574498.8 | 172349.64 | 746848.44 | 50% |  | 50% |  |  | 0% | 287249.4 | 0 | 287249.4
|  |  | 0 | 0 | [9 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Lighting | 0 | 0 |  |  |  |  | 40385700 | 2790000 | 43175700 |  |  | 0% |  |  | 0% | 675000 | 0 | 675000
|  | LED Panel 36W, Type AI | 0 | 0 | pcs | 3339600 | 56000 | 3395600 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | RC160V LED40S 840 W60L60 PSU, Philips/ China
|  | LED Frame Lamp 1x30W, Type BI | 0 | 0 | pcs | 1346400 | 56000 | 1402400 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WT158C LED36S/840 PSU L1200 GM, Philips/ China
|  | LED Frame Lamp 1x46W, Type BII for Canopy | 6 | 6 | pcs | 1607100 | 56000 | 1663100 | 9642600 | 336000 | 9978600 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WT158C LED56S/840 PSU L1500 GM, Philips/ China
|  | Wall mounted Light 1x15W, Type E | 28 | 28 | pcs | 585200 | 56000 | 641200 | 16385600 | 1568000 | 17953600 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WL008C LED10/NW round W, Philips/ China
|  | LED Ceiling mounted Light 1x19W, Type D | 16 | 11 | pcs | 1182500 | 56000 | 1238500 | 13007500 | 616000 | 13623500 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | DN393B LED22/840 PSU D200 ALU GM, Philips/ China
|  | Accessories | 0 | 1 | lot | 1350000 | 270000 | 1620000 | 1350000 | 270000 | 1620000 | 50% |  | 50% |  |  | 0% | 675000 | 0 | 675000
|  |  | 0 | 0 | [9 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable power | 0 | 0 |  |  |  |  | 21006619.4247 | 9958453.0553 | 30965072.48 |  |  | 0% |  |  | 0% | 3256902.9979 | 0 | 3256902.9979
|  | 3C-1.5mm2 Cu/XLPE/PVC | 478 | 450 | m | 22980.09 | 5743.9305 | 28724.0205 | 10341040.5 | 2584768.725 | 12925809.225 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 3C-2.5mm2 Cu/XLPE/PVC | 217 | 190 | m | 32518.74 | 7485.665 | 40004.405 | 6178560.6 | 1422276.35 | 7600836.95 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 0 | 0 | m | 72299.4 | 17189.865 | 89489.265 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 0 | 0 | m | 102372.9 | 18573.4395 | 120946.3395 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | Dado duct 50x130mm | 0 | 0 | m | 985945.6609 | 53025 | 1038970.6609 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 075603/ Legrand
|  | PVC conduit D20 | 384 | 385 | m | 8773.9726 | 14594.0164 | 23367.989 | 3377979.4521 | 5618696.3185 | 8996675.7706 | 80% |  | 80% |  |  | 0% | 2702383.5616 | 0 | 2702383.5616 | FPC20, Nano/ VN
|  | Accessories | 1 | 1 | lot | 1109038.8726 | 332711.6618 | 1441750.5344 | 1109038.8726 | 332711.6618 | 1441750.5344 | 50% |  | 50% |  |  | 0% | 554519.4363 | 0 | 554519.4363
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
3. 2. 110. |  | Electrical installation in technical areas | 1 | 1 | PSCH |  |  |  | 86058509.2699 | 9713896.6252 | 95772405.895 |  |  | 0% |  |  | 0% | 969661.6395 | 0 | 969661.6395
|  | Switch & Socket | [6 empty] | 2553112.8 | 2375897.84 | 4929010.64 |  |  | 0% |  |  | 0% | 53996.4 | 0 | 53996.4
|  | 1-Way switch, 1 gang | 7 | 7 | pcs | 46800 | 54500 | 101300 | 327600 | 381500 | 709100 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB31_1_WE_G19/ Schneider/ VN
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB31_WE/ Schneider/ VN
|  | Single Socket NEMA5 | 13 | 13 | pcs | 124560 | 54500 | 179060 | 1619280 | 708500 | 2327780 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Double Socket NEMA5 | 2 | 2 | pcs | 249120 | 54500 | 303620 | 498240 | 109000 | 607240 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Power outlet general, 3p/4W, grounded | 0 | 0 | pcs | 150480 | 54500 | 204980 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Single Socket 16A/230V, Lighting outlet general (wall) + Plug | 0 | 0 | pcs | 124560 | 54500 | 179060 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Socket combination type 1 | 3 | 3 | pcs | 0 | 381500 | 381500 | 0 | 1144500 | 1144500 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Only Install Labor
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Only Install Labor
|  | Accessories | 1 | 1 | lot | 107992.8 | 32397.84 | 140390.64 | 107992.8 | 32397.84 | 140390.64 | 50% |  | 50% |  |  | 0% | 53996.4 | 0 | 53996.4
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Lighting | [6 empty] | 68830900 | 2170000 | 71000900 |  |  | 0% |  |  | 0% | 525000 | 0 | 525000
|  | LED Panel 36W, Type AI | 0 | 0 | pcs | 3339600 | 56000 | 3395600 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | RC160V LED40S 840 W60L60 PSU, Philips/ China
|  | LED Frame Lamp 1x30W, Type BI | 0 | 0 | pcs | 1346400 | 56000 | 1402400 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WT158C LED36S/840 PSU L1200 GM, Philips/ China
|  | LED Frame Lamp 1x46W, Type BII | 28 | 28 | pcs | 1607100 | 56000 | 1663100 | 44998800 | 1568000 | 46566800 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WT158C LED56S/840 PSU L1500 GM, Philips/ China
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 56000 | 641200 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WL008C LED10/NW round W, Philips/ China
|  | LED Ceiling mounted Light 1x19W, Type D | 0 | 0 | pcs | 1182500 | 56000 | 1238500 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | DN393B LED22/840 PSU D200 ALU GM, Philips/ China
|  | Battery-operated hand lamp | 7 | 7 | pcs | 3254585.7143 | 56000 | 3310585.7143 | 22782100 | 392000 | 23174100 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | LED Arbietsleuchte PL-850 3W
|  | Accessories | 1 | 1 | lot | 1050000 | 210000 | 1260000 | 1050000 | 210000 | 1260000 | 50% |  | 50% |  |  | 0% | 525000 | 0 | 525000
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable power | [6 empty] | 14674496.4699 | 5167998.7852 | 19842495.255 |  |  | 0% |  |  | 0% | 390665.2395 | 0 | 390665.2395
|  | 3C-1.5mm2 Cu/XLPE/PVC | 167 | 150 | m | 22980.09 | 5743.9305 | 28724.0205 | 3447013.5 | 861589.575 | 4308603.075 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 3C-2.5mm2 Cu/XLPE/PVC | 100 | 110 | m | 32518.74 | 7485.665 | 40004.405 | 3577061.4 | 823423.15 | 4400484.55 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 0 | 0 | m | 72299.4 | 17189.865 | 89489.265 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 43 | 53.9 | m | 102372.9 | 18573.4395 | 120946.3395 | 5517899.31 | 1001108.3891 | 6519007.6991 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | Dado duct 50x130mm | 0 | 0 | m | 985945.6609 | 53025 | 1038970.6609 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 075603/ Legrand
|  | PVC conduit D20 | 150 | 154 | m | 8773.9726 | 14594.0164 | 23367.989 | 1351191.7808 | 2247478.5274 | 3598670.3082 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | FPC20, Nano/ VN
|  | Accessories | 1 | 1 | lot | 781330.479 | 234399.1437 | 1015729.6228 | 781330.479 | 234399.1437 | 1015729.6228 | 50% |  | 50% |  |  | 0% | 390665.2395 | 0 | 390665.2395
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
3. 2. 120. |  | Electrical installation in kitchenette areas | 1 | 1 | PSCH |  |  |  | 92827708.5941 | 16840279.0483 | 109667987.6424 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | Switch & Socket | [6 empty] | 9916993.8 | 3613842.14 | 13530835.94 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | 1-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB31_1_WE_G19/ Schneider/ VN
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB31_WE/ Schneider/ VN
|  | Single Socket NEMA5 | 47 | 47 | pcs | 124560 | 54500 | 179060 | 5854320 | 2561500 | 8415820 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Double Socket NEMA5 | 11 | 11 | pcs | 249120 | 54500 | 303620 | 2740320 | 599500 | 3339820 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Power outlet general, 3p/4W, grounded | 6 | 6 | pcs | 150480 | 54500 | 204980 | 902880 | 327000 | 1229880 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Only Install Labor
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Only Install Labor
|  | Accessories | 1 | 1 | lot | 419473.8 | 125842.14 | 545315.94 | 419473.8 | 125842.14 | 545315.94 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  |  | 0 | 0 | [9 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Lighting | 0 | 0 |  |  |  |  | 40075200 | 672000 | 40747200 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | LED Panel 36W, Type AI | 12 | 12 | pcs | 3339600 | 56000 | 3395600 | 40075200 | 672000 | 40747200 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | RC160V LED40S 840 W60L60 PSU, Philips/ China
|  | LED Frame Lamp 1x46W, Type BII | 0 | 0 | pcs | 1607100 | 56000 | 1663100 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WT158C LED56S/840 PSU L1500 GM, Philips/ China
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 56000 | 641200 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WL008C LED10/NW round W, Philips/ China
|  | Accessories | 0 | 0 | lot | 240000 | 48000 | 288000 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  |  | 0 | 0 | [9 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable power | 0 | 0 |  |  |  |  | 42835514.7941 | 12554436.9083 | 55389951.7024 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | 3C-1.5mm2 Cu/XLPE/PVC | 196 | 210 | m | 22980.09 | 5743.9305 | 28724.0205 | 4825818.9 | 1206225.405 | 6032044.305 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 501 | 480 | m | 72299.4 | 17189.865 | 89489.265 | 34703712 | 8251135.2 | 42954847.2 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | Dado duct 50x130mm | 0 | 0 | m | 985945.6609 | 53025 | 1038970.6609 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 075603/ Legrand
|  | PVC conduit D20 | 120 | 176 | m | 8773.9726 | 14594.0164 | 23367.989 | 1544219.1781 | 2568546.8885 | 4112766.0666 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | FPC20, Nano/ VN
|  | Accessories | 1 | 1 | lot | 1761764.716 | 528529.4148 | 2290294.1308 | 1761764.716 | 528529.4148 | 2290294.1308 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
3. 2. 130. |  | Electrical installation for Workshop/Formbrettbau | 1 | 1 | PSCH |  |  |  | 90067954.1041 | 12614941.0865 | 102682895.1906 |  |  | 0% |  |  | 0% | 1696207.6371 | 0 | 1696207.6371
|  | Switch & Socket | [6 empty] | 596177.4 | 1315565.22 | 1911742.62 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | 1-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB31_1_WE_G19/ Schneider/ VN
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB31_WE/ Schneider/ VN
|  | Push-button switch | 2 | 2 | pcs | 223200 | 54500 | 277700 | 446400 | 109000 | 555400 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | E8331PRL1_WE_G19/ Schneider/ VN
|  | Single Socket NEMA5 | 1 | 1 | pcs | 124560 | 54500 | 179060 | 124560 | 54500 | 179060 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Double Socket NEMA5 | 0 | 0 | pcs | 249120 | 54500 | 303620 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Power outlet general, 3p/4W, grounded | 0 | 0 | pcs | 150480 | 54500 | 204980 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Only Install Labor
|  | Socket combination type 2 | 3 | 3 | pcs | 0 | 381500 | 381500 | 0 | 1144500 | 1144500 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Only Install Labor
|  | Accessories | 1 | 1 | lot | 25217.4 | 7565.22 | 32782.62 | 25217.4 | 7565.22 | 32782.62 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Lighting | [6 empty] | 52067200 | 1920000 | 53987200 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | LED Panel 36W, Type AI | 0 | 0 | pcs | 3339600 | 56000 | 3395600 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | RC160V LED40S 840 W60L60 PSU, Philips/ China
|  | LED Frame Lamp 1x46W, Type BII | 32 | 32 | pcs | 1607100 | 56000 | 1663100 | 51427200 | 1792000 | 53219200 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WT158C LED56S/840 PSU L1500 GM, Philips/ China
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 56000 | 641200 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WL008C LED10/NW round W, Philips/ China
|  | Accessories | 1 | 1 | lot | 640000 | 128000 | 768000 | 640000 | 128000 | 768000 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable power | [6 empty] | 37404576.7041 | 9379375.8665 | 46783952.5706 |  |  | 0% |  |  | 0% | 1696207.6371 | 0 | 1696207.6371
|  | 3C-1.5mm2 Cu/XLPE/PVC | 222 | 234 | m | 22980.09 | 5743.9305 | 28724.0205 | 5377341.06 | 1344079.737 | 6721420.797 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 94 | 80 | m | 72299.4 | 17189.865 | 89489.265 | 5783952 | 1375189.2 | 7159141.2 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 248 | 230 | m | 102372.9 | 18573.4395 | 120946.3395 | 23545767 | 4271891.085 | 27817658.085 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | Dado duct 50x130mm | 0 | 0 | m | 985945.6609 | 53025 | 1038970.6609 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 075603/ Legrand
|  | PVC conduit D20 | 115 | 132 | m | 8773.9726 | 14594.0164 | 23367.989 | 1158164.3836 | 1926410.1664 | 3084574.5499 | 80% |  | 80% |  |  | 0% | 926531.5068 | 0 | 926531.5068 | FPC20, Nano/ VN
|  | Accessories | 1 | 1 | lot | 1539352.2605 | 461805.6782 | 2001157.9387 | 1539352.2605 | 461805.6782 | 2001157.9387 | 50% |  | 50% |  |  | 0% | 769676.1303 | 0 | 769676.1303
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
3. 2. 140. |  | Electrical installation at the reception | 1 | 1 | PSCH |  |  |  | 41960735.3385 | 4068070.8188 | 46028806.1573 |  |  | 0% |  |  | 0% | 1007107.3252 | 0 | 1007107.3252
|  | Switch & Socket | [6 empty] | 1915601.436 | 405808.1108 | 2321409.5468 |  |  | 0% |  |  | 0% | 40513.518 | 0 | 40513.518
|  | 1-Way switch, 1 gang | 1 | 1 | pcs | 46800 | 54500 | 101300 | 46800 | 54500 | 101300 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB31_1_WE_G19/ Schneider/ VN
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB31_WE/ Schneider/ VN
|  | Single Socket NEMA5 | 1 | 1 | pcs | 124560 | 54500 | 179060 | 124560 | 54500 | 179060 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Double Socket NEMA5 | 2 | 2 | pcs | 249120 | 54500 | 303620 | 498240 | 109000 | 607240 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Power outlet general, 1p/2W, grounded | 1 | 1 | pcs | 150480 | 54500 | 204980 | 150480 | 54500 | 204980 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Power outlet general, 3p/4W, grounded | 0 | 0 | pcs | 150480 | 54500 | 204980 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Only Install Labor
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Only Install Labor
|  | Cord outlet socket with 2m cable reserve with connection terminals, E1 | 2 | 2 | pcs | 507247.2 | 54500 | 561747.2 | 1014494.4 | 109000 | 1123494.4 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 57232+075690, Legrand / France
|  | Cord outlet socket with 4m cable reserve with connection terminals, E2 | 0 | 0 | pcs | 507247.2 | 54500 | 561747.2 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 57232+075690, Legrand / France
|  | Cord outlet socket with 6m cable reserve with connection terminals, E3 | 0 | 0 | pcs | 507247.2 | 54500 | 561747.2 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 57232+075690, Legrand / France
|  | Accessories | 1 | 1 | lot | 81027.036 | 24308.1108 | 105335.1468 | 81027.036 | 24308.1108 | 105335.1468 | 50% |  | 50% |  |  | 0% | 40513.518 | 0 | 40513.518
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Lighting | [6 empty] | 13438400 | 240000 | 13678400 |  |  | 0% |  |  | 0% | 40000 | 0 | 40000
|  | LED Panel 36W, Type AI | 4 | 4 | pcs | 3339600 | 56000 | 3395600 | 13358400 | 224000 | 13582400 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | RC160V LED40S 840 W60L60 PSU, Philips/ China
|  | LED Frame Lamp 1x46W, Type BII | 0 | 0 | pcs | 1607100 | 56000 | 1663100 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WT158C LED56S/840 PSU L1500 GM, Philips/ China
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 56000 | 641200 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WL008C LED10/NW round W, Philips/ China
|  | Accessories | 1 | 1 | lot | 80000 | 16000 | 96000 | 80000 | 16000 | 96000 | 50% |  | 50% |  |  | 0% | 40000 | 0 | 40000
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable power | [6 empty] | 26606733.9025 | 3422262.708 | 30028996.6105 |  |  | 0% |  |  | 0% | 926593.8072 | 0 | 926593.8072
|  | 3C-1.5mm2 Cu/XLPE/PVC | 60 | 55 | m | 22980.09 | 5743.9305 | 28724.0205 | 1263904.95 | 315916.1775 | 1579821.1275 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 80 | 74.8 | m | 72299.4 | 17189.865 | 89489.265 | 5407995.12 | 1285801.902 | 6693797.022 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 3 | 4.4 | m | 102372.9 | 18573.4395 | 120946.3395 | 450440.76 | 81723.1338 | 532163.8938 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | Dado duct 50x130mm | 18 | 18 | m | 985945.6609 | 53025 | 1038970.6609 | 17747021.8965 | 954450 | 18701471.8965 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 075603/ Legrand
|  | PVC conduit D20 | 26 | 22 | m | 8773.9726 | 14594.0164 | 23367.989 | 193027.3973 | 321068.3611 | 514095.7583 | 80% |  | 80% |  |  | 0% | 154421.9178 | 0 | 154421.9178 | FPC20, Nano/ VN
|  | Accessories | 1 | 1 | lot | 1544343.7787 | 463303.1336 | 2007646.9124 | 1544343.7787 | 463303.1336 | 2007646.9124 | 50% |  | 50% |  |  | 0% | 772171.8894 | 0 | 772171.8894
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
3. 2. 150. |  | Electrical installation in other rooms/secondary rooms | 1 | 1 | PSCH |  |  |  | 275591719.5806 | 31538420.0323 | 307130139.6129 |  |  | 0% |  |  | 0% | 5417776.8942 | 0 | 5417776.8942
|  | Switch & Socket | [6 empty] | 15705304.986 | 4668293.1758 | 20373598.1618 |  |  | 0% |  |  | 0% | 332155.293 | 0 | 332155.293
|  | 1-Way switch, 1 gang | 7 | 7 | pcs | 46800 | 54500 | 101300 | 327600 | 381500 | 709100 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB31_1_WE_G19/ Schneider/ VN
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB31_WE/ Schneider/ VN
|  | Push-button switch | 9 | 9 | pcs | 223200 | 54500 | 277700 | 2008800 | 490500 | 2499300 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | E8331PRL1_WE_G19/ Schneider/ VN
|  | Single Socket NEMA5 | 10 | 10 | pcs | 124560 | 54500 | 179060 | 1245600 | 545000 | 1790600 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Double Socket NEMA5 | 9 | 9 | pcs | 249120 | 54500 | 303620 | 2242080 | 490500 | 2732580 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Power outlet general, 1p/2W, grounded | 0 | 0 | pcs | 150480 | 54500 | 204980 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Power outlet general, 3p/4W, grounded | 0 | 0 | pcs | 150480 | 54500 | 204980 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Socket combination type 1 | 4 | 4 | pcs | 0 | 381500 | 381500 | 0 | 1526000 | 1526000 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Only Install Labor
|  | Socket combination type 2 | 2 | 2 | pcs | 0 | 381500 | 381500 | 0 | 763000 | 763000 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Only Install Labor
|  | Cord outlet socket with 2m cable reserve with connection terminals, E1 | 0 | 0 | pcs | 507247.2 | 54500 | 561747.2 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 57232+075690, Legrand / France
|  | Cord outlet socket with 4m cable reserve with connection terminals, E2 | 0 | 0 | pcs | 507247.2 | 54500 | 561747.2 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 57232+075690, Legrand / France
|  | Cord outlet socket with 6m cable reserve with connection terminals, E3 | 0 | 0 | pcs | 507247.2 | 54500 | 561747.2 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 57232+075690, Legrand / France
|  | Floor box, recessed (1xDouble Socket NEMA5, 1xIT - Double socket,1x HDMI connection to the projector) | 1 | 1 | pcs | 9216914.4 | 272500 | 9489414.4 | 9216914.4 | 272500 | 9489414.4 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 088070+088073, Legrand/ France+KB426UES2_WE_G19 / Schneider/ VN, Plastic type+272368-2, Commscope + NSP-USMB+1375191-1, Commscope + + HDMI socket + HDMI cable
|  | Accessories | 1 | 1 | lot | 664310.586 | 199293.1758 | 863603.7618 | 664310.586 | 199293.1758 | 863603.7618 | 50% |  | 50% |  |  | 0% | 332155.293 | 0 | 332155.293
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Lighting | [6 empty] | 135827400 | 4650000 | 140477400 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | LED Panel 36W, Type AI | 9 | 9 | pcs | 3339600 | 56000 | 3395600 | 30056400 | 504000 | 30560400 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | RC160V LED40S 840 W60L60 PSU, Philips/ China
|  | LED Frame Lamp 1x46W, Type BII | 58 | 60 | pcs | 1607100 | 56000 | 1663100 | 96426000 | 3360000 | 99786000 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WT158C LED56S/840 PSU L1500 GM, Philips/ China
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 56000 | 641200 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WL008C LED10/NW round W, Philips/ China
|  | LED Ceiling mounted Light 1x19W, Type D | 6 | 6 | pcs | 1182500 | 56000 | 1238500 | 7095000 | 336000 | 7431000 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | DN393B LED22/840 PSU D200 ALU GM, Philips/ China
|  | Accessories | 1 | 1 | lot | 2250000 | 450000 | 2700000 | 2250000 | 450000 | 2700000 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable power | [6 empty] | 124059014.5946 | 22220126.8565 | 146279141.4511 |  |  | 0% |  |  | 0% | 5085621.6012 | 0 | 5085621.6012
|  | 3C-1.5mm2 Cu/XLPE/PVC | 693 | 684.5455 | m | 22980.09 | 5743.9305 | 28724.0205 | 15730916.1545 | 3931981.515 | 19662897.6695 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 3C-2.5mm2 Cu/XLPE/PVC | 442 | 464 | m | 32518.74 | 7485.665 | 40004.405 | 15088695.36 | 3473348.56 | 18562043.92 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 0 | 0 | m | 72299.4 | 17189.865 | 89489.265 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 317 | 280 | m | 102372.9 | 18573.4395 | 120946.3395 | 28664412 | 5200563.06 | 33864975.06 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | Dado duct 50x130mm | 57 | 57 | m | 985945.6609 | 53025 | 1038970.6609 | 56198902.6722 | 3022425 | 59221327.6722 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 075603/ Legrand
|  | PVC conduit D20 | 278 | 341 | m | 8773.9726 | 14594.0164 | 23367.989 | 2991924.6575 | 4976559.5964 | 7968484.2539 | 80% |  | 80% |  |  | 0% | 2393539.726 | 0 | 2393539.726 | FPC20, Nano/ VN
|  | Accessories | 1 | 1 | lot | 5384163.7503 | 1615249.1251 | 6999412.8754 | 5384163.7503 | 1615249.1251 | 6999412.8754 | 50% |  | 50% |  |  | 0% | 2692081.8751 | 0 | 2692081.8751
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
3. 2. 160. |  | Emergency lighting | 1 | 1 | PSCH |  |  |  | 125963193.8122 | 37581630.6399 | 163544824.4521 |  |  | 0% |  |  | 0% | 2114228.4318 | 0 | 2114228.4318
|  | Switch & Socket | [6 empty] | 73296840 | 12022500 | 85319340 |  |  | 0% |  |  | 0% | 1050000 | 0 | 1050000
|  | Emergency light | 81 | 81 | pcs | 516120 | 56000 | 572120 | 41805720 | 4536000 | 46341720 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | LSM/ Duhal/ VN
|  | Exit light | 24 | 24 | pcs | 566280 | 56000 | 622280 | 13590720 | 1344000 | 14934720 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | SNC302L/ Duhal/ VN
|  | Single Socket 16A/230V | 105 | 105 | pcs | 150480 | 54500 | 204980 | 15800400 | 5722500 | 21522900 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S / Schneider/ VN, Plastic type
|  | Accessories | 1 | 1 | pcs | 2100000 | 420000 | 2520000 | 2100000 | 420000 | 2520000 | 50% |  | 50% |  |  | 0% | 1050000 | 0 | 1050000
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable power supply | [6 empty] | 52666353.8122 | 25559130.6399 | 78225484.4521 |  |  | 0% |  |  | 0% | 1064228.4318 | 0 | 1064228.4318
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 1575 | 1265 | m | 32518.74 | 7485.665 | 40004.405 | 41136206.1 | 9469366.225 | 50605572.325 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 882 | 950 | m | 8773.9726 | 14594.0164 | 23367.989 | 8335273.9726 | 13864315.5912 | 22199589.5638 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | FPC20, Nano/ VN
|  | PVC flexible conduct D20 | 315 | 300 | m | 3554.7229 | 5289.7059 | 8844.4288 | 1066416.876 | 1586911.7647 | 2653328.6407 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Nano/ VN
|  | Accessories | 1 | 1 | lot | 2128456.8636 | 638537.0591 | 2766993.9226 | 2128456.8636 | 638537.0591 | 2766993.9226 | 50% |  | 50% |  |  | 0% | 1064228.4318 | 0 | 1064228.4318
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
4. |  | Machine hook-up (Hall 3) | [6 empty] | 3164184545.4338 | 446703070.7456 | 3610887616.1794 |  |  | 0% |  |  | 0% | 276767591.0237 | 0 | 276767591.0237
[14 empty] | 0% |  |  | 0% |  | 0
4. 1. |  | Electrical engineering | 1 | 1 | PSCH |  |  |  | 3164184545.4338 | 446703070.7456 | 3610887616.1794 |  |  | 0% |  |  | 0% | 276767591.0237 | 0 | 276767591.0237
4. 1. 10. |  | Machine hook-up | 1 | 1 | PSCH |  |  |  | 3164184545.4338 | 446703070.7456 | 3610887616.1794 |  |  | 0% |  |  | 0% | 276767591.0237 | 0 | 276767591.0237
|  | Cable trays_Hot dip-Galvanized Steel | [6 empty] | 538685840 | 65789758.3358 | 604475598.3358 |  |  | 0% |  |  | 0% | 269342920 | 0 | 269342920
|  | Cable tray 400x100x2.0mm | 122 | 122 | m | 776880 | 68320 | 845200 | 94779360 | 8335040 | 103114400 | 50% |  | 50% |  |  | 0% | 47389680 | 0 | 47389680 | TGE/ VN
|  | Cable tray 500x100 with separating bar | 195 | 201 | m | 1525680 | 81001.3848 | 1606681.3848 | 306661680 | 16281278.3358 | 322942958.3358 | 50% |  | 50% |  |  | 0% | 153330840 | 0 | 153330840 | TGE/ VN
|  | Fitting and accessories | 1 | 1 | lot | 137244800 | 41173440 | 178418240 | 137244800 | 41173440 | 178418240 | 50% |  | 50% |  |  | 0% | 68622400 | 0 | 68622400
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Busway Canalis KSA 250A 3L+N+PE 10kA/s, IP54 | [6 empty] | 2002937565.0909 | 225436964.9679 | 2228374530.0588 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | 250A Feeder,3L+N+PE | 190 | 194 | m | 7268140 | 553706.5149 | 7821846.5149 | 1410019160 | 107419063.8906 | 1517438223.8906 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KSA25PG, Schneider/ Asia
|  | 250A Cable Tap Box - End | 6 | 6 | pcs | 5043610 | 497400.75 | 5541010.75 | 30261660 | 2984404.5 | 33246064.5 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KSA25ETB, Schneider/ Asia
|  | 100-250A End Cover | 6 | 6 | pcs | 551650 | 27500 | 579150 | 3309900 | 165000 | 3474900 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KSB25FA3, Schneider/ Asia
|  | Joint Cover | 70 | 70 | pcs | 813560 | 27500 | 841060 | 56949200 | 1925000 | 58874200 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KSE25YA3, Schneider/ Asia
|  | PIO Cover | 282 | 651 | pcs | 90090 | 27500 | 117590 | 58648590 | 17902500 | 76551090 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KSE80YB2, Schneider/ Asia
|  | Fixing Bracket | 70 | 70 | pcs | 109450 | 220200.75 | 329650.75 | 7661500 | 15414052.5 | 23075552.5 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KSA25EZ1, Schneider/ Asia
|  | Screw-on plate for blanking of unused openings | 138 | 138 | pcs | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 12127, Schneider/ Asia
|  | Tap-off Unit included: - 1x Busbar tap-off unit with 16A/230V 3pin Industrial Socket CEE - 1x MCB 2P 16A | 82 | 69 | pcs | 2882070 | 497400.75 | 3379470.75 | 198862830 | 34320651.75 | 233183481.75 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KSB32CP + PKF16F723 + A9F74216, Schneider
|  | Tap-off Unit included: - 1x Busbar tap-off unit with 16A/400V 5pin Industrial Socket CEE - 1x MCB 3P 16A | 56 | 56 | pcs | 3041460 | 497400.75 | 3538860.75 | 170321760 | 27854442 | 198176202 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KSB32CP + PKF16F735 + A9F74316, Schneider
|  | Industrial plug 16A-230V for Industrial socket 16A-230V | 82 | 69 | pcs | 226176 | 54500 | 280676 | 15606144 | 3760500 | 19366644 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | PKF16W423/ Schneider
|  | Industrial plug 16A-400V for Industrial socket 16A-400V | 56 | 56 | pcs | 282720 | 54500 | 337220 | 15832320 | 3052000 | 18884320 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | PKF16W734/Schneider
|  | Accessories | 1 | 1 | lot | 35464501.0909 | 10639350.3273 | 46103851.4182 | 35464501.0909 | 10639350.3273 | 46103851.4182 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Electrical installation Production | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Schuko-socket 16A/230V | 0 | 0 | pcs | 0 | 54500 | 54500 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 572118/ Schuko/ Germeny
|  | 16A/230V 3pin Industrial Socket CEE | 41 | 41 | pcs | 381600 | 54500 | 436100 | 15645600 | 2234500 | 17880100 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 1341+13502/ Mennekes/ Germany
|  | Socket combination type 1 | 21 | 21 | pcs | 0 | 381500 | 381500 | 0 | 8011500 | 8011500 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Only Install Labor
|  | Socket combination type 2 | 10 | 10 | pcs | 0 | 381500 | 381500 | 0 | 3815000 | 3815000 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Only Install Labor
|  | Accessories | 1 | 1 | lot | 691014 | 207304.2 | 898318.2 | 691014 | 207304.2 | 898318.2 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable power | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | From Building 3_UPS 1 DP 1.3 35kVA Panel to16A/230V Socket (19 set) | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | 3C-2.5mm2 Cu/XLPE/PVC | 892 | 737 | m | 32518.74 | 7485.665 | 40004.405 | 23966311.38 | 5516935.105 | 29483246.485 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From Building 3_UPS 2 DP 1.3 35kVA Panel to16A/230V Socket (22 set) | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | 3C-2.5mm2 Cu/XLPE/PVC | 1107 | 1033 | m | 32518.74 | 7485.665 | 40004.405 | 33591858.42 | 7732691.945 | 41324550.365 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From PDP 1.0 Panel to Combine socket (9 set) | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 587 | 519 | m | 72299.4 | 17189.865 | 89489.265 | 37523388.6 | 8921539.935 | 46444928.535 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From PDP 1.1 Panel to Combine socket (3 set) | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 197 | 110 | m | 72299.4 | 17189.865 | 89489.265 | 7952934 | 1890885.15 | 9843819.15 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From PDP 1.2 Panel to Combine socket (4 set) | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 182 | 205 | m | 72299.4 | 17189.865 | 89489.265 | 14821377 | 3523922.325 | 18345299.325 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From PDP 2.0 Panel to Combine socket (9 set) | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 830 | 811 | m | 72299.4 | 17189.865 | 89489.265 | 58634813.4 | 13940980.515 | 72575793.915 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | From PDP 2.1 Panel to Combine socket (6 set) | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 440 | 445 | m | 72299.4 | 17189.865 | 89489.265 | 32173233 | 7649489.925 | 39822722.925 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 246 | 250 | m | 8773.9726 | 14594.0164 | 23367.989 | 2193493.1507 | 3648504.1029 | 5841997.2536 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | FPC20, Nano/ VN
|  | Accessories | 1 | 1 | lot | 9074248.7636 | 2722274.6291 | 11796523.3926 | 9074248.7636 | 2722274.6291 | 11796523.3926 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Tel-Data system | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Double data outlet RJ45 | 179 | 191 | pcs | 480000 | 81750 | 561750 | 91680000 | 15614250 | 107294250 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 760245679+2153449-1, Commscope/ China
|  | Cable Cat6A | 12618 | 12970 | m | 21639.3443 | 3360 | 24999.3443 | 280662295.082 | 43579200 | 324241495.082 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 884024508/10, Commscope/ China
|  | PVC conduit D20 | 160 | 170.7263 | m | 8773.9726 | 14594.0164 | 23367.989 | 1497947.5013 | 2491581.7963 | 3989529.2977 | 80% |  | 80% |  |  | 0% | 1198358.0011 | 0 | 1198358.0011 | FPC20, Nano/ VN
|  | Network cable test cost - FO cable |  |  | nos | 0 | 50600 | 50600 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | VN
|  | Network cable test cost - Cat6A cable | 376 | 400 | nos | 0 | 50600 | 50600 | 0 | 20240000 | 20240000 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | VN
|  | Accessories | 1 | 1 | lot | 12452626.0453 | 3735787.8136 | 16188413.8589 | 12452626.0453 | 3735787.8136 | 16188413.8589 | 50% |  | 50% |  |  | 0% | 6226313.0227 | 0 | 6226313.0227 | Vietnam
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
5. |  | Scooter Garage | [6 empty] | 108075385.8789 | 16341158.0259 | 124416543.9048 |  |  | 0% |  |  | 0% | 26388109.3386 | 0 | 26388109.3386
[14 empty] | 0% |  |  | 0% |  | 0
5. 2. |  | Electrical Engineering | 1 | 1 | PSCH |  |  |  | 108075385.8789 | 16341158.0259 | 124416543.9048 |  |  | 0% |  |  | 0% | 26388109.3386 | 0 | 26388109.3386
5. 2. 10. |  | Grounding and Lightining protection | 1 |  | PSCH |  |  |  | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | Classic lightning rod Ø16, l = 1,000mm | 9 |  | m | 312500 | 120872.0782 | 433372.0783 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | VN
|  | Claded copper - steel grounding rod Ø 16, L = 2.4m | 9 |  | m | 210227.2727 | 120872.0782 | 331099.351 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | VN
|  | Exothermic welding connection | 19 |  | m | 119318.1818 | 56925 | 176243.1818 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | VN
|  | Grounding Test Link box | 1 |  | m | 562500 | 56925 | 619425 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | VN
|  | Cable Bare Copper wire 50sqmm | 322 |  | m | 135322.14 | 22106.7 | 157428.84 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 54 |  | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | FPC20, Nano/ VN
|  | Accessories | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | T&C | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
5. 2. 20. |  | Power supply | 1 | 1 | PSCH |  |  |  | 48996560 | 6144115.6772 | 55140675.6772 |  |  | 0% |  |  | 0% | 24498280 | 0 | 24498280
|  | Cable trays | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable tray 200x100x2.0mm, c/w cover | 47 | 47 | m | 776880 | 51045.8655 | 827925.8655 | 36513360 | 2399155.6772 | 38912515.6772 | 50% |  | 50% |  |  | 0% | 18256680 | 0 | 18256680 | TGE/ VN
|  | Fitting and accessories | 1 | 1 | lot | 12483200 | 3744960 | 16228160 | 12483200 | 3744960 | 16228160 | 50% |  | 50% |  |  | 0% | 6241600 | 0 | 6241600
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
5. 2. 30. |  | Power supply of building utilities | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
5. 2. 40. |  | Electrical installations | 1 | 1 | PSCH |  |  |  | 44249283.3619 | 5904426.8866 | 50153710.2486 |  |  | 0% |  |  | 0% | 680887.8717 | 0 | 680887.8717
|  | Switch & Socket | [6 empty] | 11703872.04 | 857016.812 | 12560888.852 |  |  | 0% |  |  | 0% | 247528.02 | 0 | 247528.02
|  | 1-Way switch, 1 gang | 2 | 2 | pcs | 46800 | 54500 | 101300 | 93600 | 109000 | 202600 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB31_1_WE_G19/ Schneider/ VN
|  | 16A/230V 3pin Industrial Socket CEE | 2 | 2 | pcs | 381600 | 54500 | 436100 | 763200 | 109000 | 872200 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 1341+13502/ Mennekes/ Germany
|  | Motion sensor | 9 | 9 | pcs | 1150224 | 54500 | 1204724 | 10352016 | 490500 | 10842516 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | SAE_UE_MS_CSAWE/ Schneider/ VN
|  | Accessories | 1 | 1 | lot | 495056.04 | 148516.812 | 643572.852 | 495056.04 | 148516.812 | 643572.852 | 50% |  | 50% |  |  | 0% | 247528.02 | 0 | 247528.02
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Lighting | [6 empty] | 25171700 | 992000 | 26163700 |  |  | 0% |  |  | 0% | 240000 | 0 | 240000
|  | LED Frame Lamp 1x46W, Type BII | 15 | 15 | pcs | 1607100 | 56000 | 1663100 | 24106500 | 840000 | 24946500 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WT158C LED56S/840 PSU L1500 GM, Philips/ China
|  | Wall mounted Light 1x15W, Type E | 1 | 1 | pcs | 585200 | 56000 | 641200 | 585200 | 56000 | 641200 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WL008C LED10/NW round W, Philips/ China
|  | Accessories | 1 | 1 | lot | 480000 | 96000 | 576000 | 480000 | 96000 | 576000 | 50% |  | 50% |  |  | 0% | 240000 | 0 | 240000
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable power | [6 empty] | 7373711.3219 | 4055410.0746 | 11429121.3966 |  |  | 0% |  |  | 0% | 193359.8517 | 0 | 193359.8517
|  | 3C-1.5mm2 Cu/XLPE/PVC | 164 | 149 | m | 22980.09 | 5743.9305 | 28724.0205 | 3424033.41 | 855845.6445 | 4279879.0545 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 3C-2.5mm2 Cu/XLPE/PVC | 68 | 61 | m | 32518.74 | 7485.665 | 40004.405 | 1983643.14 | 456625.565 | 2440268.705 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 12 | 180 | m | 8773.9726 | 14594.0164 | 23367.989 | 1579315.0685 | 2626922.9541 | 4206238.0226 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | FPC20, Nano/ VN
|  | Accessories | 1 | 1 | lot | 386719.7034 | 116015.911 | 502735.6145 | 386719.7034 | 116015.911 | 502735.6145 | 50% |  | 50% |  |  | 0% | 193359.8517 | 0 | 193359.8517
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
5. 2. 50. |  | Emergency lighting | 1 | 1 | PSCH |  |  |  | 14829542.5169 | 4292615.4621 | 19122157.979 |  |  | 0% |  |  | 0% | 1208941.4669 | 0 | 1208941.4669
|  | Emergency light | 6 | 12 | pcs | 516120 | 56000 | 572120 | 6193440 | 672000 | 6865440 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | LSM/ Duhal/ VN
|  | Exit light | 1 | 2 | pcs | 566280 | 56000 | 622280 | 1132560 | 112000 | 1244560 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | SNC302L/ Duhal/ VN
|  | Single Socket 16A/230V | 8 | 8 | pcs | 124560 | 54500 | 179060 | 996480 | 436000 | 1432480 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S / Schneider/ VN, Plastic type
|  | Accessories | 1 | 1 | pcs | 440000 | 88000 | 528000 | 440000 | 88000 | 528000 | 50% |  | 50% |  |  | 0% | 220000 | 0 | 220000
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable power supply | [6 empty] | 6067062.5169 | 2984615.4621 | 9051677.979 |  |  | 0% |  |  | 0% | 988941.4669 | 0 | 988941.4669
|  | Cable Cu/XLPE/PVC 3Cx1.5mm2 | 120 | 205 | m | 22980.09 | 5743.9305 | 28724.0205 | 4710918.45 | 1177505.7525 | 5888424.2025 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 68 | 110 | m | 8773.9726 | 14594.0164 | 23367.989 | 965136.9863 | 1605341.8053 | 2570478.7916 | 80% |  | 80% |  |  | 0% | 772109.589 | 0 | 772109.589 | FPC20, Nano/ VN
|  | PVC flexible conduct D20 | 24 | 20 | m | 3554.7229 | 5289.7059 | 8844.4288 | 71094.4584 | 105794.1176 | 176888.576 | 80% |  | 80% |  |  | 0% | 56875.5667 | 0 | 56875.5667 | Nano/ VN
|  | Accessories | 1 | 1 | lot | 319912.6222 | 95973.7867 | 415886.4089 | 319912.6222 | 95973.7867 | 415886.4089 | 50% |  | 50% |  |  | 0% | 159956.3111 | 0 | 159956.3111
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
6. |  | Canteen | [6 empty] | 350267145.0631 | 45874850.9531 | 396141996.0162 |  |  | 0% |  |  | 0% | 58494282.9119 | 0 | 58494282.9119
[14 empty] | 0% |  |  | 0% |  | 0
6. 2. |  | Electrical Engineering | 1 | 1 | PSCH |  |  |  | 350267145.0631 | 45874850.9531 | 396141996.0162 |  |  | 0% |  |  | 0% | 58494282.9119 | 0 | 58494282.9119
|  | Notes Calculation Basis | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
6. 2. 10. |  | Grounding and Lightining protection | 1 | 1 | PSCH |  |  |  | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | VN, 50mm2 bare cable
|  | Classic lightning rod Ø16, l = 1,000mm | 6 |  | m | 312500 | 120872.0782 | 433372.0783 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | VN
|  | Claded copper - steel grounding rod Ø 16, L = 2.4m | 6 |  | m | 210227.2727 | 120872.0782 | 331099.351 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | VN
|  | Exothermic welding connection | 21 |  | m | 119318.1818 | 56925 | 176243.1818 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | VN
|  | Grounding Test Link box | 2 |  | m | 562500 | 56925 | 619425 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | VN
|  | Cable Bare Copper wire 50sqmm | 259 |  | m | 135322.14 | 22106.7 | 157428.84 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 36 |  | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | FPC20, Nano/ VN
|  | Accessories | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | T&C | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
6. 2. 20. |  | Power supply | 1 | 1 | PSCH |  |  |  | 106191661.9795 | 12858262.8895 | 119049924.8689 |  |  | 0% |  |  | 0% | 53661752.2226 | 0 | 53661752.2226
|  | Cable trays_Hot dip-Galvanized Steel | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable tray 200x50 with separating bar | 149 | 149 | m | 669240 | 56000 | 725240 | 99716760 | 8344000 | 108060760 | 50% |  | 50% |  |  | 0% | 49858380 | 0 | 49858380 | TGE/ VN
|  | PVC conduit D20 | 215 | 215 | m | 8773.9726 | 14594.0164 | 23367.989 | 1886404.1096 | 3137713.5285 | 5024117.6381 | 80% |  | 80% |  |  | 0% | 1509123.2877 | 0 | 1509123.2877 | FPC20, Nano/ VN
|  | Fitting and accessories | 1 | 1 | lot | 4588497.8699 | 1376549.361 | 5965047.2308 | 4588497.8699 | 1376549.361 | 5965047.2308 | 50% |  | 50% |  |  | 0% | 2294248.9349 | 0 | 2294248.9349
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
6. 2. 30. |  | Power supply of building utilities | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
6. 2. 40. |  | Electrical installations | 1 | 1 | PSCH |  |  |  | 220631937.3221 | 25881817.2569 | 246513754.579 |  |  | 0% |  |  | 0% | 4422440.8561 | 0 | 4422440.8561
|  | Switch & Socket | [6 empty] | 27779110.24 | 5475504.272 | 33254614.512 |  |  | 0% |  |  | 0% | 587507.12 | 0 | 587507.12
|  | 1-Way switch, 1 gang | 5 | 5 | pcs | 46800 | 54500 | 101300 | 234000 | 272500 | 506500 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB31_1_WE_G19/ Schneider/ VN
|  | Single Socket NEMA5 | 24 | 24 | pcs | 124560 | 54500 | 179060 | 2989440 | 1308000 | 4297440 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | 16A/230V 3pin Industrial Socket CEE | 4 | 4 | pcs | 381600 | 54500 | 436100 | 1526400 | 218000 | 1744400 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 1341+13502/ Mennekes/ Germany
|  | Socket combination type 1 | 6 | 6 | pcs | 0 | 381500 | 381500 | 0 | 2289000 | 2289000 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Only Install Labor
|  | Motion sensor | 19 | 19 | pcs | 1150224 | 54500 | 1204724 | 21854256 | 1035500 | 22889756 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | SAE_UE_MS_CSAWE/ Schneider/ VN
|  | Accessories | 1 | 1 | lot | 1175014.24 | 352504.272 | 1527518.512 | 1175014.24 | 352504.272 | 1527518.512 | 50% |  | 50% |  |  | 0% | 587507.12 | 0 | 587507.12
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Lighting | [6 empty] | 141953700 | 6649872 | 148603572 |  |  | 0% |  |  | 0% | 1860000 | 0 | 1860000
|  | LED Frame Lamp 1x46W, Type BII | 5 | 5 | pcs | 1607100 | 63504 | 1670604 | 8035500 | 317520 | 8353020 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WT158C LED56S/840 PSU L1500 GM, Philips/ China
|  | LED Frame Lamp 1x46W, Type J | 70 | 70 | pcs | 1607100 | 63504 | 1670604 | 112497000 | 4445280 | 116942280 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WT158C LED56S/840 PSU L1500 GM, Philips/ China
|  | Wall mounted Light 1x15W, Type E | 6 | 6 | pcs | 585200 | 63504 | 648704 | 3511200 | 381024 | 3892224 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | WL008C LED10/NW round W, Philips/ China
|  | LED Ceiling mounted Light 1x19W, Type D | 12 | 12 | pcs | 1182500 | 63504 | 1246004 | 14190000 | 762048 | 14952048 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | DN393B LED22/840 PSU D200 ALU GM, Philips/ China
|  | Accessories | 1 | 1 | lot | 3720000 | 744000 | 4464000 | 3720000 | 744000 | 4464000 | 50% |  | 50% |  |  | 0% | 1860000 | 0 | 1860000
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable power | [6 empty] | 50899127.0821 | 13756440.9849 | 64655568.067 |  |  | 0% |  |  | 0% | 1974933.7361 | 0 | 1974933.7361
|  | 3C-1.5mm2 Cu/XLPE/PVC | 697 | 572 | m | 22980.09 | 5743.9305 | 28724.0205 | 13144611.48 | 3285528.246 | 16430139.726 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 3C-2.5mm2 Cu/XLPE/PVC | 496 | 464 | m | 32518.74 | 7485.665 | 40004.405 | 15088695.36 | 3473348.56 | 18562043.92 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 242 | 226 | m | 72299.4 | 17189.865 | 89489.265 | 16339664.4 | 3884909.49 | 20224573.89 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 30 | 30 | m | 102372.9 | 18573.4395 | 120946.3395 | 3071187 | 557203.185 | 3628390.185 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 117 | 132 | m | 8773.9726 | 14594.0164 | 23367.989 | 1158164.3836 | 1926410.1664 | 3084574.5499 | 80% |  | 80% |  |  | 0% | 926531.5068 | 0 | 926531.5068 | FPC20, Nano/ VN
|  | Accessories | 1 | 1 | lot | 2096804.4585 | 629041.3376 | 2725845.7961 | 2096804.4585 | 629041.3376 | 2725845.7961 | 50% |  | 50% |  |  | 0% | 1048402.2293 | 0 | 1048402.2293
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
6. 2. 50. |  | Emergency lighting | 1 | 1 | PSCH |  |  |  | 23443545.7616 | 7134770.8067 | 30578316.5683 |  |  | 0% |  |  | 0% | 410089.8332 | 0 | 410089.8332
|  | Emergency light | 14 | 15 | pcs | 516120 | 63504 | 579624 | 7741800 | 952560 | 8694360 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | LSM/ Duhal/ VN
|  | Exit light | 7 | 7 | pcs | 566280 | 63504 | 629784 | 3963960 | 444528 | 4408488 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | SNC302L/ Duhal/ VN
|  | Single Socket 16A/230V | 9 | 15 | pcs | 124560 | 54500 | 179060 | 1868400 | 817500 | 2685900 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | KB413S / Schneider/ VN, Plastic type
|  | Accessories | 1 | 1 | pcs | 440000 | 88000 | 528000 | 440000 | 88000 | 528000 | 50% |  | 50% |  |  | 0% | 220000 | 0 | 220000
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable power supply | [6 empty] | 9429385.7616 | 4832182.8067 | 14261568.5683 |  |  | 0% |  |  | 0% | 190089.8332 | 0 | 190089.8332
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 315 | 221 | m | 32518.74 | 7485.665 | 40004.405 | 7186641.54 | 1654331.965 | 8840973.505 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 177 | 190 | m | 8773.9726 | 14594.0164 | 23367.989 | 1667054.7945 | 2772863.1182 | 4439917.9128 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | FPC20, Nano/ VN
|  | PVC flexible conduct D20 | 63 | 55 | m | 3554.7229 | 5289.7059 | 8844.4288 | 195509.7606 | 290933.8235 | 486443.5841 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Nano/ VN
|  | Accessories | 1 | 1 | lot | 380179.6664 | 114053.8999 | 494233.5664 | 380179.6664 | 114053.8999 | 494233.5664 | 50% |  | 50% |  |  | 0% | 190089.8332 | 0 | 190089.8332
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | TOTAL AMOUNT (Not included VAT) | [6 empty] | 16563842018.9792 | 1773285626.6565 | 18337127645.6357 | [6 empty] | 1635241786.4748 | 0 | 1635241786.4748
1. |  | Construction site facilities | [6 empty] | 124241733.1691 | 20176036.5818 | 144417769.7509 | [6 empty] | 111817559.8522 | 18158432.9237 | 129975992.7758
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
1. 1. |  | Construction site facilities | 1 | 1 | psch | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
1. 2. |  | Construction site cameras | 1 | 1 | psch |  |  |  | 124241733.1691 | 20176036.5818 | 144417769.7509 | 90% |  | 90% | 90% |  | 0.9 | 111817559.8522 | 18158432.9237 | 129975992.7758
|  | Rack for NVR+Swtich | 1 | 1 | pcs | 1848000 | 165000 | 2013000 | 1848000 | 165000 | 2013000 | 90% |  | 90% | 90% |  | 0.9 | 1663200 | 148500 | 1811700 | VN
|  | Camera bullet 360' + base, Resolution: 4K | 3 | 3 | pcs | 9067520 | 198000 | 9265520 | 27202560 | 594000 | 27796560 | 90% |  | 90% | 90% |  | 0.9 | 24482304 | 534600 | 25016904 | DS-2DE5225IW-AE, HIK Vision
|  | NVR 8 chanel | 1 | 1 | pcs | 9431520 | 165000 | 9596520 | 9431520 | 165000 | 9596520 | 90% |  | 90% | 90% |  | 0.9 | 8488368 | 148500 | 8636868 | HIK Vision
|  | 1KVA UPS | 1 | 1 | pcs | 2529000 | 137500 | 2666500 | 2529000 | 137500 | 2666500 | 90% |  | 90% | 90% |  | 0.9 | 2276100 | 123750 | 2399850 | Santank
|  | Switch PoE 4P | 1 | 1 | pcs | 1155000 | 81750 | 1236750 | 1155000 | 81750 | 1236750 | 90% |  | 90% | 90% |  | 0.9 | 1039500 | 73575 | 1113075 | VN
|  | LCD 32" | 1 | 1 | pcs | 8360000 | 163500 | 8523500 | 8360000 | 163500 | 8523500 | 90% |  | 90% | 90% |  | 0.9 | 7524000 | 147150 | 7671150 | Saumsung or equivlation
|  | Double Socket 16A/230V | 3 | 3 | pcs | 150480 | 54500 | 204980 | 451440 | 163500 | 614940 | 90% |  | 90% | 90% |  | 0.9 | 406296 | 147150 | 553446 | KB426UES2_WE_G19/ Schneider/ VN, Plastic type
|  | PVC box for socket, conver at camera | 3 | 3 | pcs | 36000 | 16350 | 52350 | 108000 | 49050 | 157050 | 90% |  | 90% | 90% |  | 0.9 | 97200 | 44145 | 141345 | Vietnam
|  | surge protection | 2 | 2 | pcs | 4494000 | 49050 | 4543050 | 8988000 | 98100 | 9086100 | 90% |  | 90% | 90% |  | 0.9 | 8089200 | 88290 | 8177490 | Schneider
|  | Cable Cat6 | 10 | 10 | m | 10032.7869 | 3360 | 13392.7869 | 100327.8689 | 33600 | 133927.8689 | 90% |  | 90% | 90% |  | 0.9 | 90295.082 | 30240 | 120535.082 | Commposcope / China, or Alantek
|  | converter quang đồng | 6 | 6 | pcs | 770000 | 49050 | 819050 | 4620000 | 294300 | 4914300 | 90% |  | 90% | 90% |  | 0.9 | 4158000 | 264870 | 4422870 | VN
|  | Fiber optical 2FO | 373 | 373 | m | 14400 | 3360 | 17760 | 5371200 | 1253280 | 6624480 | 90% |  | 90% | 90% |  | 0.9 | 4834080 | 1127952 | 5962032 | Sacom or Alantek
|  | Cable Cu/XLPE/PVC 3Cx1.5mm2 | 397 | 397 | m | 22980.09 | 5743.9305 | 28724.0205 | 9123095.73 | 2280340.4085 | 11403436.1385 | 90% |  | 90% | 90% |  | 0.9 | 8210786.157 | 2052306.3677 | 10263092.5247 | Cadivi/ Vietnam
|  | PVC conduit D20 | 81 | 81 | m | 8773.9726 | 14594.0164 | 23367.989 | 710691.7808 | 1182115.3294 | 1892807.1102 | 90% |  | 90% | 90% |  | 0.9 | 639622.6027 | 1063903.7964 | 1703526.3992 | FPC20, Nano/ VN
|  | HDPE pipe D25/32 | 397 | 397 | m | 10550.2392 | 11445 | 21995.2392 | 4188444.9761 | 4543665 | 8732109.9761 | 90% |  | 90% | 90% |  | 0.9 | 3769600.4785 | 4089298.5 | 7858898.9785 | Cadivi/ Vietnam
|  | Camera Pole 15m | 3 | 3 | pcs | 10000000 | 450000 | 10450000 | 30000000 | 1350000 | 31350000 | 90% |  | 90% | 90% |  | 0.9 | 27000000 | 1215000 | 28215000 | Vietnam
|  | Reforce cable for camera pole | 3 | 3 | lot | 550000 | 250000 | 800000 | 1650000 | 750000 | 2400000 | 90% |  | 90% | 90% |  | 0.9 | 1485000 | 675000 | 2160000 | Vietnam
|  | Concrete plinth | 3 | 3 | lot | 1000000 | 500000 | 1500000 | 3000000 | 1500000 | 4500000 | 90% |  | 90% | 90% |  | 0.9 | 2700000 | 1350000 | 4050000 | Vietnam
|  | Remove Pole + Camera | 3 | 3 | time | 0 | 1250000 | 1250000 | 0 | 3750000 | 3750000 | 90% |  | 90% | 90% |  | 0.9 | 0 | 3375000 | 3375000 | Vietnam (re-use the pole and concrete plinth)
|  | Accessories | 1 | 1 | lot | 5404452.8133 | 1621335.844 | 7025788.6573 | 5404452.8133 | 1621335.844 | 7025788.6573 | 90% |  | 90% | 90% |  | 0.9 | 4864007.532 | 1459202.2596 | 6323209.7916
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. |  | Production and Logistic building (Hall 3) | [6 empty] | 803801420.8294 | 119493877.9513 | 923295298.7807 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
2.1. |  | Civil Engineering | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 10. |  | Calculations | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 20. |  | Rainwater and waste water sewer | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 30. |  | Earthworks | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 40. |  | Demolition, removal and dismantling works | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 50. |  | Foundation | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 60. |  | Building structure | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 70. |  | General concrete- / reinforced concrete works | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 80. |  | Fire protection | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 90. |  | Fire rated walls | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 100. |  | Cutting base slabs / ceilings / floors | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 110. |  | Cutting holes into existing facades, walls and roofs | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 120. |  | Exterior walls | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 130. |  | Exterior doors and windows | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 140. |  | Fire protection doors | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 150. |  | Internal doors | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 160. |  | Fire protection roller shutter door | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 170. |  | Fire protection bulkhead | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 180. |  | High speed roller shutter | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 190. |  | Fitting and metal work - general | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 200. |  | Railings and hand rails | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 210. |  | Steel stage for installations | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 220. |  | Collision protection | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 230. |  | canopies of exterior doors | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 240. |  | Concerete steps in front of the hall | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 250. |  | Painting and varnishing works | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 260. |  | Guidance systems | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 270. |  | Locking system | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 280. |  | Internal signage | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 290. |  | Adjustment ridge vent | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 300. |  | Roof reinforcment Option 1 | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 310. |  | Insert new ventilation louvers | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 320. |  | Metal louvers to cover mechanical units | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 2. |  | Electrical Engineering | 1 | 1 | PSCH |  |  |  | 120237495.4217 | 36030743.1568 | 156268238.5785 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 2. 10. |  | Adjustment of existing facilities, dismantling and disposal works | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 2. 20. |  | Rennovation existing grounding system and lightning protection | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 2. 30. |  | Rennovation existing grounding and equipotential bonding | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 2. 40. |  | Power supply | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 2. 50. |  | Energy measurement system | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 2. 60. |  | Electrical installation in the production hall | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 2. 70. |  | Electrical installation in the logistics hall | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 2. 80. |  | Power supply of building utilities | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 2. 90. |  | Three-arm Turnstile | 1 | 1 | PSCH |  |  |  | 120237495.4217 | 36030743.1568 | 156268238.5785 |  |  | 0% |  |  | 0 | 0 | 0 | 0
|  | INTUS ACM40e-NT as access control manager | [11 empty] | 0% |  |  | 0 | 0 | 0 | 0 | Provide PCS, Only Labor Install
|  | INTUS ACM40e-NT (S3840-380) Intelligent access control manager (Supplier by Client) | 4 | 4 | set | 0 | 616000 | 616000 | 0 | 2464000 | 2464000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Only installation
|  | INTUS ACM40e 2-4 reader-ext (V3841-202) Firmware extension from 2 to 4 access readers (Supplier by Client) | 4 | 4 | set | 0 | 616000 | 616000 | 0 | 2464000 | 2464000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Only installation
|  | Network configuration setup fee (3000-243) Set up of one IPv4 terminal basis configuration by PCS. Precondition: Excel- or CSV-file with following details: IPaddress and net mask terminal, IP-address gateway, TCPport. Host name. This information must be submitted with the order. (by Client) | 4 | 4 | set | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | (by Client)
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
|  | INTUS 6xx/7xx as RFID reader for access control | [11 empty] | 0% |  |  | 0 | 0 | 0 | 0 | Provide PCS, Only Labor Install
|  | NTUS 615/La ( S3850-670) INTUS 615 Legic advant r/w access reader for flush mounting. Reads/writes Legic prime and Legic advant cards/tags. PCS universal coding: VNA00- 000 (Supplier by Client) | 8 | 8 | set | 0 | 616000 | 616000 | 0 | 4928000 | 4928000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Only installation
|  | INTUS 600/500/400 reader configuration fee (V3000-231) INTUS reader configuration price for customer specific car coding deviating from PCS standard coding. Also required for standalone parametrization. (by Client) | 8 | 8 | set | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | (by Client)
|  | NTUS 600 spacer frame (S3850-607) INTUS 315ro/615/620 spacer frame, mandatory for mounting on metal wall or for surface mounting cable introduction (Supplier by Client) | 8 | 8 | set | 0 | 616000 | 616000 | 0 | 4928000 | 4928000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Only installation
|  | NTUS 700-Panel/La (S3853-610) SM4200-M Legic advant r/w access reader for mounting in metal panels. Reads/writes Legic prime and Legic advant cards/tags. PCS universal coding: VNA00-000 (Supplier by Client) | 8 | 8 | set | 0 | 616000 | 616000 | 0 | 4928000 | 4928000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Only installation
|  | INTUS 700 reader configuration fee (V3000-249) INTUS 700 reader configuration price for card coding, deviating from PCS standard coding. (by Client) | 8 | 8 | set | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | (by Client)
|  | 5A, 12VDC Power supply adapter | 1 | 1 | set | 2220000 | 95200 | 2315200 | 2220000 | 95200 | 2315200 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | YLI
|  | Push button for releasing entrance & exit lock at reception area | 1 | 4 | pcs | 528000 | 61600 | 589600 | 2112000 | 246400 | 2358400 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | EL-EB3/ Elock/ Malaysia
|  | Emergency at the reception area | 1 | 4 | pcs | 528000 | 61600 | 589600 | 2112000 | 246400 | 2358400 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | EB-PB/ Elock/ Malaysia
|  | Cabinet box for controller located at reception | 1 | 1 | set | 3000000 | 280000 | 3280000 | 3000000 | 280000 | 3280000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Backup battery, 12VDC 7Ah | 4 | 4 | set | 540000 | 72800 | 612800 | 2160000 | 291200 | 2451200 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Phoenix
|  | Tripod turnstile | 4 | 4 | set | 21600000 | 369600 | 21969600 | 86400000 | 1478400 | 87878400 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | TS2000 Pro, ZKTECO
|  | Double Socket 16A/230V | 4 | 4 | pcs | 150480 | 54500 | 204980 | 601920 | 218000 | 819920 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
|  | Signal cable, AWG18 - 1Pair | 153 | 153 | m | 15000 | 3360 | 18360 | 2295000 | 514080 | 2809080 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 2MKABLO/ Turkey
|  | Cable Cat6A | 327 | 301 | m | 21639.3443 | 3360 | 24999.3443 | 6513442.623 | 1011360 | 7524802.623 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Commscope
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 50 | 150 | m | 32518.74 | 7485.665 | 40004.405 | 4877811 | 1122849.75 | 6000660.75 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Cadivi / VN
|  | PVC conduit D20 | 369 | 360 | m | 8773.9726 | 14594.0164 | 23367.989 | 3158630.137 | 5253845.9082 | 8412476.0452 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | Cutting concrete background and backfill | 5 | 5 | m | 0 | 125000 | 125000 | 0 | 625000 | 625000 |  |  | 0% |  |  | 0 | 0 | 0 | 0
|  | Labour cost for support DRX test funtion of Turnstile system | 1 | 1 | lot | 0 | 3500000 | 3500000 | 0 | 3500000 | 3500000 |  |  | 0% |  |  | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 4786691.6618 | 1436007.4985 | 6222699.1603 | 4786691.6618 | 1436007.4985 | 6222699.1603 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 2. 100. |  | Emergency lighting | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 2. 120. |  | Network infrastructure | 1 | 1 | PSCH |  |  | 0 | 307745509.2338 | 64282788.3235 | 372028297.5573 |  |  | 0% |  |  | 0 | 0 | 0 | 0
|  | Single Mode OS2 48 fibers SC- Duplex | 207 | 230 | m | 144000 | 28000 | 172000 | 33120000 | 6440000 | 39560000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Commscope
|  | 20 x 0,8 pair copper phone wire | 0 | 0 | m | 117360 | 13798.4 | 131158.4 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 1499418-1, Commscope/ China
|  | IDF7 42U (0.8x1.0x2.0), Included PDU, 10 patch panel, Cable routing channel 1U | 1 | 1 | pcs | 68750000 | 1308000 | 70058000 | 68750000 | 1308000 | 70058000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Rack: Rittal/ VN Patch panel: 760237046+2153449-2, Commscope/ China
|  | Patch panel 24 Port CAT6A | 8 |  | pcs | 5060000 | 654000 | 5714000 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760237046+2153449-2, Commscope/ China
|  | Patch panel 24 Port cat 5e | 2 | 2 | pcs | 2195600 | 654000 | 2849600 | 4391200 | 1308000 | 5699200 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760237040+9-1375191-2, Commscope/ China
|  | Cat 6A Patch Cord, 3m | 77 | 77 | pcs | 600000 | 13440 | 613440 | 46200000 | 1034880 | 47234880 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
|  | Cat 6A Patch Cord, 3m | 0 | 0 | pcs | 600000 | 13440 | 613440 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
|  | ODF F.O Singlemode, 48F | 2 | 2 | pcs | 6490000 | 490500 | 6980500 | 12980000 | 981000 | 13961000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 4-1671002-4+760241378, Commscope/ China
|  | Socket strip (PDU) with 7 sockets | 2 | 2 | pcs | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Included
|  | 16A Turnlock socket | 2 | 2 | pcs | 150480 | 54500 | 204980 | 300960 | 109000 | 409960 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
|  | Patch panel 24 Port | 0 | 0 | pcs | 5060000 | 654000 | 5714000 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760237046+2153449-2+VRMH01-1F, Commscope/ China
|  | Double data outlet RJ45 | 26 | 26 | pcs | 480000 | 81750 | 561750 | 12480000 | 2125500 | 14605500 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760245679+2153449-1, Commscope/ China
|  | Wifi module (Wifi supply by Client) | 25 | 25 | pcs | 0 | 136250 | 136250 | 0 | 3406250 | 3406250 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Only labor
|  | FO Patch Cord, SC-SC Duplex, LSOH, SM,3m | 20 | 20 | pcs | 550000 | 10900 | 560900 | 11000000 | 218000 | 11218000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FFWSCSC42-JXM003,Commscope/ China
|  | FO Pigtail LC, SM, 1m for welding to optical fibre | 20 | 96 | pcs | 132000 | 65400 | 197400 | 12672000 | 6278400 | 18950400 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | EH0108-001, Commscope/ China
|  | Cat 6A Patch Cord, 3m from Data outlet to Wifi | 25 | 25 | pcs | 198000 | 10900 | 208900 | 4950000 | 272500 | 5222500 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
|  | Cable Cat6A | 3219 | 3245 | m | 21639.3443 | 3360 | 24999.3443 | 70219672.1311 | 10903200 | 81122872.1311 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Commscope
|  | PVC conduit D20 | 1610 | 1510 | m | 8773.9726 | 14594.0164 | 23367.989 | 13248698.6301 | 22036964.7818 | 35285663.4119 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
|  | Network cable test cost - Cat6A cable | 52 | 52 | nos | 0 | 50600 | 50600 | 0 | 2631200 | 2631200 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
|  | Accessories | 1 | 1 | lot | 17432978.4725 | 5229893.5417 | 22662872.0142 | 17432978.4725 | 5229893.5417 | 22662872.0142 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Vietnam
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 2. 130. |  | Access control preparation | 1 | 1 | PSCH |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | N/A
2. 2. 140. |  | CCTV System | 1 | 1 | PSCH |  |  | 0 | 375818416.1739 | 19180346.471 | 394998762.6449 |  |  | 0% |  |  | 0 | 0 | 0 | 0
|  | Outside Camera CE-1-->12 | 12 | 12 | pcs | 19242720 | 198000 | 19440720 | 230912640 | 2376000 | 233288640 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Axis - P1447-LE
|  | Symphony Standard Edition - VMS Device License | 12 | 12 | pcs | 2704800 | 330000 | 3034800 | 32457600 | 3960000 | 36417600 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Sentar/ Canada
|  | Telescopic parapet mount (T91D62) | 12 | 12 | pcs | 1803200 | 49500 | 1852700 | 21638400 | 594000 | 22232400 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | T91D62, Axis
|  | Overvoltage protection | 12 | 12 | pcs | 4494000 | 49050 | 4543050 | 53928000 | 588600 | 54516600 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | PNET1GB, Schneider
|  | Double data outlet RJ45 | 12 | 12 | pcs | 480000 | 81750 | 561750 | 5760000 | 981000 | 6741000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760245679+2153449-1, Commscope/ China
|  | Cat 6A Patch Cord, 3m | 36 | 24 | pcs | 198000 | 10900 | 208900 | 4752000 | 261600 | 5013600 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
|  | Cable Cat6A | 686 | 658.24 | m | 21639.3443 | 3360 | 24999.3443 | 14243881.9672 | 2211686.4 | 16455568.3672 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Commscope
|  | PVC conduit D20 | 274 | 280.5 | m | 8773.9726 | 14594.0164 | 23367.989 | 2461099.3151 | 4093621.6035 | 6554720.9186 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
|  | Network cable test cost - Cat6A cable | 12 | 24 | nos | 0 | 50600 | 50600 | 0 | 1214400 | 1214400 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
|  | Accessories | 1 | 1 | lot | 9664794.8916 | 2899438.4675 | 12564233.3591 | 9664794.8916 | 2899438.4675 | 12564233.3591 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 3. |  | Mechanical Engineering | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 3. 10. |  | Ventilation System Production | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 3. 20. |  | Fire Protection Engineering | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 3. 30. |  | Installation of In-Rack Sprinkler at Logistic | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 3. 40. |  | Compressed Air Network Production 1 | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 3. 50. |  | Compressed Air Network Production 2 | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. |  | Office, Social and Technical Areas (Hall 3) | [6 empty] | 1095015293.254 | 204033421.602 | 1299048714.856 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 1. |  | Civil Engineering | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 10. |  | Rainwater and waste water sewer | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 20. |  | Foundations | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 30. |  | Steel columns | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 40. |  | Building structure | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 50. |  | Concrete works | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 60. |  | Reinforced concrete slabs 1st floor | 0 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 70. |  | Reinforced concrete stairs | 0 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 80. |  | Screed coat | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 90. |  | Metal works | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 100. |  | Exterior walls | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 110. |  | Masonry works | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 120. |  | plastering works | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 130. |  | Drywall works | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 140. |  | Ceiling for new built-ins | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 150. |  | Fire protection | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 160. |  | Fire rated walls | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 170. |  | Cutting holes into existing facades, walls and roofs | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 180. |  | Cuts in Floor/slab/wall | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 190. |  | Exterior doors and windows | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 200. |  | Canopies for exterior doors | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 210. |  | Covering existing windows with mirroring film | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 220. |  | Internal doors | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 230. |  | Fire protection doors | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 240. |  | Suspended ceiling | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 250. |  | Floor covering works | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 260. |  | Tiles | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 270. |  | Needle Felt | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 280. |  | Raised floor | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 290. |  | Drainage of new wet rooms | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 300. |  | Railing and handrail | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 310. |  | Collision protection | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 320. |  | Vertical blinds | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 330. |  | Kitchenette | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 340. |  | Painting and varnishing works | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 350. |  | internal signage | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 360. |  | Locking system | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 370. |  | Tightness Test Gas Extinguished Rooms | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. |  | Electrical engineering | 1 | 1 | PSCH |  |  |  | 1095015293.254 | 204033421.602 | 1299048714.856 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 10. |  | Rennovation existing grounding system and lightning protection | 1 | 1 | psch | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Included
3. 2. 20. |  | Rennovation existing grounding and equipotential bonding | 1 | 1 | psch | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Included
3. 2. 30. |  | Main Power supply | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 40. |  | Uninterrupted power supply (UPS) | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 50. |  | Electrical Capacitor bank | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 60. |  | Power supply of building utilities | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 70. |  | Energy measurement system | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 80. |  | Electrical installation in offices and meeting rooms | 1 |  | PSCH |  |  |  | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 90. |  | Electrical installation in social rooms | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 100. |  | Electrical installation in corridors and stairways | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 110. |  | Electrical installation in technical areas | 1 |  | PSCH |  |  |  | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 120. |  | Electrical installation in kitchenette areas | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 130. |  | Electrical installation for Workshop/Formbrettbau | 1 |  | PSCH |  |  |  | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 140. |  | Electrical installation at the reception | 1 |  | PSCH |  |  |  | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 150. |  | Electrical installation in other rooms/secondary rooms | 1 |  | PSCH |  |  |  | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 160. |  | Emergency lighting | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 170. |  | Fire alarm system | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 180. |  | Network infrastructure | 1 | 1 | PSCH |  |  |  | 947613765.2926 | 174994605.0134 | 1122608370.3061 |  |  | 0% |  |  | 0 | 0 | 0 | 0
|  | IDF4 42U (0.8x1.0x2.0), Included PDU, 10 patch panel, Cable routing channel 1U | 1 | 1 | pcs | 68750000 | 1308000 | 70058000 | 68750000 | 1308000 | 70058000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Rack: Rittal/ VN Patch panel: 760237046+2153449-2, Commscope/ China
|  | IDF5 42U (0.8x1.0x2.0), Included PDU, 10 patch panel, Cable routing channel 1U | 1 | 1 | pcs | 68750000 | 1308000 | 70058000 | 68750000 | 1308000 | 70058000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Rack: Rittal/ VN Patch panel: 760237046+2153449-2, Commscope/ China
|  | IDF6 42U (0.8x1.0x2.0), Included PDU, 10 patch panel, Cable routing channel 1U | 1 | 1 | pcs | 68750000 | 1308000 | 70058000 | 68750000 | 1308000 | 70058000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Rack: Rittal/ VN Patch panel: 760237046+2153449-2, Commscope/ China
|  | Patch panel 24 Port CAT6A | 24 |  | pcs | 5060000 | 654000 | 5714000 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760237046+2153449-2, Commscope/ China
|  | Patch panel 24 Port cat 5e | 6 | 6 | pcs | 2195600 | 654000 | 2849600 | 13173600 | 3924000 | 17097600 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760237040+9-1375191-2, Commscope/ China
|  | Cat 6A Patch Cord, 3m | 423 | 452 | pcs | 198000 | 10900 | 208900 | 89496000 | 4926800 | 94422800 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
|  | Cat 6A Patch Cord, 3m | 0 | 0 | pcs | 198000 | 10900 | 208900 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
|  | ODF F.O Singlemode, 48F | 6 | 6 | pcs | 6490000 | 490500 | 6980500 | 38940000 | 2943000 | 41883000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 4-1671002-4+760241378, Commscope/ China
|  | Socket strip (PDU) with 7 sockets | 6 | 6 | pcs |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Included
|  | 16A Turnlock socket | 6 | 6 | pcs | 150480 | 54500 | 204980 | 902880 | 327000 | 1229880 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
|  | Double data outlet RJ45 | 197 | 226 | pcs | 480000 | 81750 | 561750 | 108480000 | 18475500 | 126955500 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760245679+2153449-1, Commscope/ China
|  | Wifi module (Wifi supply by Client) | 29 | 29 | pcs | 0 | 136250 | 136250 | 0 | 3951250 | 3951250 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Only labor
|  | FO Patch Cord, SC-SC Duplex, LSOH, SM,3m | 60 | 60 | pcs | 550000 | 10900 | 560900 | 33000000 | 654000 | 33654000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FFWSCSC42-JXM003,Commscope/ China
|  | FO Pigtail LC, SM, 1m for welding to optical fibre | 60 | 144 | pcs | 132000 | 65400 | 197400 | 19008000 | 9417600 | 28425600 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | EH0108-001, Commscope/ China
|  | Cat 6A Patch Cord, 3m from Data outlet to Wifi | 29 | 29 | pcs | 198000 | 10900 | 208900 | 5742000 | 316100 | 6058100 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
|  | Cable Cat6A | 14691 | 14487.8 | m | 21639.3443 | 3360 | 24999.3443 | 313506491.8033 | 48679008 | 362185499.8033 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Commscope
|  | PVC conduit D20 | 138 | 2800 | m | 8773.9726 | 14594.0164 | 23367.989 | 24567123.2877 | 40863245.9529 | 65430369.2406 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | Network cable test cost - FO cable | 24 | 96 | nos | 0 | 50600 | 50600 | 0 | 4857600 | 4857600 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
|  | Network cable test cost - Cat6A cable | 197 | 452 | nos | 0 | 50600 | 50600 | 0 | 22871200 | 22871200 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
|  | Accessories | 1 | 1 | lot | 29547670.2017 | 8864301.0605 | 38411971.2622 | 29547670.2017 | 8864301.0605 | 38411971.2622 |  |  | 0% |  |  | 0 | 0 | 0 | 0
|  | Updated for data socket outlet on Dadoduct | 1 | 1 | lot | 65000000 |  | 65000000 | 65000000 | 0 | 65000000 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 190. |  | CCTV System for custom fence | 1 | 1 | PSCH |  |  |  | 93265409.772 | 9368475.5017 | 102633885.2737 |  |  | 0% |  |  | 0 | 0 | 0 | 0
|  | Camera fence CF-5,6 | 2 | 2 | pcs | 1264480 | 137500 | 1401980 | 2528960 | 275000 | 2803960 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | DS-2CD2021G1-I, Hikvision/ China
|  | Camera Inside CI-1, Dome | 1 | 1 | pcs | 20015520 | 198000 | 20213520 | 20015520 | 198000 | 20213520 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Axis - P3247-LV
|  | Symphony Standard Edition - VMS Device License | 1 | 1 | pcs | 2704800 | 330000 | 3034800 | 2704800 | 330000 | 3034800 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Sentar/ Canada
|  | LCD 43" for CE, CI | 2 | 2 | pcs | 11990000 | 163500 | 12153500 | 23980000 | 327000 | 24307000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Samsung UA43T6500AK
|  | LCD 32" for CF | 2 | 2 | pcs | 11990000 | 163500 | 12153500 | 23980000 | 327000 | 24307000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Samsung UA43T6500AK
|  | HDMI cable c/w socket, 15m | 2 | 3 | pcs | 979000 | 59950 | 1038950 | 2937000 | 179850 | 3116850 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Unitek
|  | Single data outlet RJ45 | 3 | 3 | pcs | 276000 | 81750 | 357750 | 828000 | 245250 | 1073250 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760245680-1+2153449-1, Commscope/ China
|  | Double Socket 16A/230V | 2 | 2 | pcs | 150480 | 54500 | 204980 | 300960 | 109000 | 409960 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | KB426UES2_WE_G19/ Schneider/ VN, Plastic type
|  | Cat 6A Patch Cord, 3m from Data outlet to camera | 3 | 3 | pcs | 198000 | 10900 | 208900 | 594000 | 32700 | 626700 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
|  | Cable Cat6 | 400 | 403 | m | 10032.7869 | 3360 | 13392.7869 | 4043213.1148 | 1354080 | 5397293.1148 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Commscope
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 124 | 124 | m | 32518.74 | 7485.665 | 40004.405 | 4032323.76 | 928222.46 | 4960546.22 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 210 | 210 | m | 8773.9726 | 14594.0164 | 23367.989 | 1842534.2466 | 3064743.4465 | 4907277.693 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
|  | Network cable test cost - Cat6A cable | 3 | 7 | nos | 0 | 50600 | 50600 | 0 | 354200 | 354200 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
|  | Accessories | 1 | 1 | lot | 5478098.6507 | 1643429.5952 | 7121528.2459 | 5478098.6507 | 1643429.5952 | 7121528.2459 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 200. |  | Access control preparation | 1 | 1 | PSCH |  |  |  | 54136118.1893 | 19670341.0869 | 73806459.2762 |  |  | 0% |  |  | 0 | 0 | 0 | 0
|  | Exit Button | 5 | 5 | pcs | 528000 | 61600 | 589600 | 2640000 | 308000 | 2948000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | EL-EB3/ Elock/ Malaysia
|  | Emergency Button | 5 | 5 | pcs | 528000 | 61600 | 589600 | 2640000 | 308000 | 2948000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | EB4R/ Elock/ Malaysia
|  | Door sensor | 55 | 5 | pcs | 2116800 | 95200 | 2212000 | 10584000 | 476000 | 11060000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | EL-810P/ Elock/ Malaysia/ China
|  | Access control card reader | 8 | 5 | set | 0 | 95200 | 95200 | 0 | 476000 | 476000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | by PCS, only labor install
|  | Single Socket 16A/230V | 5 | 5 | pcs | 150480 | 54500 | 204980 | 752400 | 272500 | 1024900 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | KB413S / Schneider/ VN, Plastic type
|  | Data outlet RJ45 | 5 | 5 | pcs | 480000 | 81750 | 561750 | 2400000 | 408750 | 2808750 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760245679+2153449-1, Commscope/ China
|  | AC/DC converter | 5 | 5 | pcs | 2220000 | 95200 | 2315200 | 11100000 | 476000 | 11576000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Meanwell/ China
|  | Conection box, SS304 | 5 | 5 | pcs | 180000 | 50400 | 230400 | 900000 | 252000 | 1152000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
|  | Cable cat6A | 357 | 225 | m | 21639.3443 | 3360 | 24999.3443 | 4868852.459 | 756000 | 5624852.459 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Commscope
|  | Cable telephone cat5e | 357 | 225 | m | 7475.4098 | 3360 | 10835.4098 | 1681967.2131 | 756000 | 2437967.2131 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 6-219590-2, Commscope/ China
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 286 | 286 | m | 32518.74 | 7485.665 | 40004.405 | 9300359.64 | 2140900.19 | 11441259.83 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 643 | 586 | m | 8773.9726 | 14594.0164 | 23367.989 | 5141547.9452 | 8552093.6173 | 13693641.5625 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | Labour cost for support DRX test funtion of Access control system | 1 | 1 | lot | 0 | 3850000 | 3850000 | 0 | 3850000 | 3850000 |  |  | 0% |  |  | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 2126990.932 | 638097.2796 | 2765088.2116 | 2126990.932 | 638097.2796 | 2765088.2116 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 3. |  | Mechanical Engineering | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 3. 10. |  | Waste Water System | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 3. 20. |  | Service Water System | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 3. 40. |  | Ventilation System | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 3. 50. |  | Ventilation System 1st Floor Offices Ventilation Units | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 3. 60. |  | Ventilation System 1st Floor Offices Ducting | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 3. 70. |  | Air Conditioning | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 3. 80. |  | Fire Protection Engineering Sprinkler | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 3. 90. |  | Fire Protection Engineering Temperature Controlled Storage | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 3. 100. |  | Fire Protection Engineering Extinguishing Systems | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 3. 110. |  | Door Fan Test for Gas Extinguishing System | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 3. 120. |  | Compressed Air Connections | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
4. |  | Machine hook-up (Hall 3) | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
4. 1. |  | Electrical engineering | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
4. 1. 10. |  | Power cables and lines | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
4. 2. |  | Mechanical Engineering | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
4. 2. 10. |  | Machine hook-up | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
|  | Supply & Installation pipe & fittings: Drop Piping (D25), Considering all drop piping & fittings | 1 |  | lot | 0 | 0 | [6 empty] | 0% |  |  | 0 | 0 | 0 | 0
|  | Hanger support & accessories | 1 |  | lot | 0 | 0 | [6 empty] | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
5. |  | Scooter Garage | [8 empty] | 162238150.0078 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
5. 1. |  | Civil Engineering | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
5. 1. 10. |  | Adjustments on the existing scooter garage | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
5. 1. 20. |  | Expansion of Scooter Garage | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
5. 2. |  | Electrical Engineering | 1 | 1 | PSCH |  |  |  | 144640388.5392 | 17597761.4686 | 162238150.0078 |  |  | 0% |  |  | 0 | 0 | 0 | 0
5. 2. 10. |  | Grounding and Lightining protection | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
5. 2. 20. |  | Power supply | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
5. 2. 30. |  | Power supply of building utilities | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
5. 2. 40. |  | Electrical installations | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
5. 2. 50. |  | Emergency lighting | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
5. 2. 60. |  | Fire alarms system | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
5. 2. 70. |  | CCTV System | 1 | 1 | PSCH |  |  |  | 144640388.5392 | 17597761.4686 | 162238150.0078 |  |  | 0% |  |  | 0 | 0 | 0 | 0
|  | POWER surveillance cabinet | 2 | 2 | pcs | 1650000 | 136250 | 1786250 | 3300000 | 272500 | 3572500 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | DATA surveillance cabinet | 2 | 2 | pcs | 1650000 | 136250 | 1786250 | 3300000 | 272500 | 3572500 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Terminal 4mm2 | 2 | 2 | pcs | 27500 | 10900 | 38400 | 55000 | 21800 | 76800 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | MCB 1P-16A-230V | 2 | 2 | pcs | 90000 | 49050 | 139050 | 180000 | 98100 | 278100 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Schneider
|  | Power adapter (Mean Well SDR-240-48) | 2 | 2 | pcs | 2833600 | 114450 | 2948050 | 5667200 | 228900 | 5896100 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Mean Well SDR-240-48
|  | PoE Switch Planet IGS-10020HPT | 2 | 2 | pcs | 15180000 | 272500 | 15452500 | 30360000 | 545000 | 30905000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Planet IGS-10020HPT
|  | Outside Camera CF-7-->14 | 8 | 8 | pcs | 1264480 | 137500 | 1401980 | 10115840 | 1100000 | 11215840 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | DS-2CD2021G1-I/ HIKVISION
|  | Telescopic parapet mount (T91D62) | 8 | 8 | pcs | 1803200 | 49500 | 1852700 | 14425600 | 396000 | 14821600 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | DS-2CD2021G1-I/ HIKVISION
|  | Overvoltage protection | 8 | 8 | pcs | 4494000 | 49050 | 4543050 | 35952000 | 392400 | 36344400 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | PNET1GB, Schneider
|  | Single data outlet RJ45 | 8 | 8 | pcs | 276000 | 81750 | 357750 | 2208000 | 654000 | 2862000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760245680-1+2153449-1, Commscope/ China
|  | Cat 6A Patch Cord, 3m from Data outlet to camera | 8 | 8 | pcs | 198000 | 10900 | 208900 | 1584000 | 87200 | 1671200 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
|  | Cable Cat6 | 343 | 264 | m | 10032.7869 | 3360 | 13392.7869 | 2648655.7377 | 887040 | 3535695.7377 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Commposcope / China, or Alantek
|  | Gigabit Ethernet LX Mini-GBIC SFP Transceiver | 2 | 2 | pcs | 4032000 | 272500 | 4304500 | 8064000 | 545000 | 8609000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | MGBLX1/ Cisco
|  | converter quang đồng (Connect from optic cable to Patch panel) | 2 | 2 | pcs | 935000 | 49050 | 984050 | 1870000 | 98100 | 1968100 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
|  | Cat 6A Patch Cord, 3m from Converter to patch panel | 4 | 4 | pcs | 198000 | 10900 | 208900 | 792000 | 43600 | 835600 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
|  | FO Patch Cord, SC-SC Duplex, LSOH, SM,3m | 2 | 2 | pcs | 550000 | 10900 | 560900 | 1100000 | 21800 | 1121800 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FFWSCSC42-JXM003,Commscope/ China
|  | Fiber optical 8FO (SM-OS2 G9/125) | 190 | 190 | m | 54000 | 3360 | 57360 | 10260000 | 638400 | 10898400 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | X-1427452-4, Commscope/ China
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 100 | 100 | m | 32518.74 | 7485.665 | 40004.405 | 3251874 | 748566.5 | 4000440.5 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 144 | 200 | m | 8773.9726 | 14594.0164 | 23367.989 | 1754794.5205 | 2918803.2824 | 4673597.8029 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | HDPE pipe D40/50 | 100 | 100 | m | 17049.1866 | 15805 | 32854.1866 | 1704918.6603 | 1580500 | 3285418.6603 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | The cost of cutting and refinishing the concrete path for the undergruond pipe | 8 | 8 | m | 0 | 175000 | 175000 | 0 | 1400000 | 1400000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Run with at Electrical existing Manhole
|  | Network cable test cost - FO cable | 2 | 48 | nos | 0 | 50600 | 50600 | 0 | 2428800 | 2428800 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
|  | Network cable test cost - Cat6A cable | 8 | 8 | nos | 0 | 50600 | 50600 | 0 | 404800 | 404800 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
|  | Accessories | 1 | 1 | lot | 6046505.6207 | 1813951.6862 | 7860457.3069 | 6046505.6207 | 1813951.6862 | 7860457.3069 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
5. 3. |  | Mechancial Engineering | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
5. 3. 10. |  | Rainwater System | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
5. 3. 20. |  | Fire Protection System | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. |  | Canteen | [8 empty] | 274132627.4702 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 1. |  | Civil Engineering | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 10. |  | Demolition of existing canteen | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 20. |  | Building Structure | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 30. |  | Earthworks | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 40. |  | Rain water and waste water sewer | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 50. |  | Primary construction of reinforced concrete | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 60. |  | Foundations | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 70. |  | Concrete floor | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 80. |  | Concrete plinth | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 90. |  | Reinforced concrete columns | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 100. |  | Reinforced concrete beams | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 110. |  | Reinforced concrete 1st roof slab or structure | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 120. |  | Reinforced concrete stairs | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 130. |  | Concrete steps | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 140. |  | Screed coat | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 150. |  | Roof structure | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 160. |  | Metal facade | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 170. |  | Masonry works | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 180. |  | Exterior doors | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 190. |  | Fire protection | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 200. |  | Fire protection doors | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 210. |  | Interior doors | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 220. |  | Floor covering works | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 230. |  | Tiles | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 240. |  | Painting and finishing works | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 250. |  | Metal and railing works | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 260. |  | Elevator for goods | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 270. |  | Canpoy for the main entrance | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 280. |  | Exterior steel staircase | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 290. |  | Exterior sinks | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 300. |  | Locking system | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 2. |  | Electrical Engineering | [6 empty] | 246947482.5691 | 27185144.9011 | 274132627.4702 |  |  | 0% |  |  | 0 | 0 | 0 | 0
|  | Notes Calculation Basis | [11 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 2. 10. |  | Grounding and Lightining protection | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 2. 20. |  | Power supply | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 2. 30. |  | Power supply of building utilities | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 2. 40. |  | Electrical installations | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 2. 50. |  | Emergency lighting | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 2. 60. |  | Fire alarms system | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 2. 70. |  | CCTV System For Custom fence | 1 | 1 | PSCH |  |  |  | 117565498.5134 | 6055261.4345 | 123620759.9479 |  |  | 0% |  |  | 0 | 0 | 0 | 0
|  | LCD 43" for CE, CI | 8 | 8 | pcs | 11990000 | 163500 | 12153500 | 95920000 | 1308000 | 97228000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Samsung UA43T6500AK
|  | HDMI cable c/w socket, 15m | 8 | 8 | pcs | 979000 | 59950 | 1038950 | 7832000 | 479600 | 8311600 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Unitek
|  | Outside Camera CF-16-->18 | 4 | 4 | pcs | 1264480 | 137500 | 1401980 | 5057920 | 550000 | 5607920 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | DS-2CD2021G1-I/ HIKVISION
|  | Single data outlet RJ45 | 4 | 4 | pcs | 276000 | 81750 | 357750 | 1104000 | 327000 | 1431000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760245680-1+2153449-1, Commscope/ China
|  | Cat 6A Patch Cord, 3m from Data outlet to camera | 4 | 4 | pcs | 198000 | 10900 | 208900 | 792000 | 43600 | 835600 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
|  | Cable Cat6 | 229 | 200 | m | 10032.7869 | 3360 | 13392.7869 | 2006557.377 | 672000 | 2678557.377 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Commposcope / China, or Alantek
|  | PVC conduit D20 | 91 | 85 | m | 8773.9726 | 14594.0164 | 23367.989 | 745787.6712 | 1240491.395 | 1986279.0662 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
|  | Network cable test cost - Cat6A cable | 4 | 4 | nos | 0 | 50600 | 50600 | 0 | 202400 | 202400 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
|  | Accessories | 1 | 1 | lot | 4107233.4651 | 1232170.0395 | 5339403.5046 | 4107233.4651 | 1232170.0395 | 5339403.5046 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 2. 80. |  | Network infrastructure | 1 | 1 | PSCH |  |  |  | 129381984.0557 | 21129883.4666 | 150511867.5223 |  |  | 0% |  |  | 0 | 0 | 0 | 0
|  | IDF8 12U (0.8x1.0x2.0), Included PDU, 10 patch panel, Cable routing channel 1U | 1 | 1 | pcs | 68750000 | 1308000 | 70058000 | 68750000 | 1308000 | 70058000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Rack: Rittal/ VN Patch panel: 760237046+2153449-2, Commscope/ China
|  | Patch panel 24 Port CAT6A | 2 |  | pcs | 5060000 | 654000 | 5714000 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760237046+2153449-2, Commscope/ China
|  | Cat 6A Patch Cord, 3m | 28 | 16 | pcs | 198000 | 10900 | 208900 | 3168000 | 174400 | 3342400 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
|  | Cat 6A Patch Cord, 3m | 0 | 0 | pcs | 198000 | 10900 | 208900 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
|  | ODF F.O Singlemode, 48F | 1 | 1 | pcs | 6490000 | 490500 | 6980500 | 6490000 | 490500 | 6980500 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 4-1671002-4+760241378, Commscope/ China
|  | Socket strip (PDU) with 7 sockets | 2 | 2 | pcs |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Included
|  | 16A Turnlock socket | 2 | 2 | pcs | 150480 | 54500 | 204980 | 300960 | 109000 | 409960 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
|  | Double data outlet RJ45 | 12 | 12 | pcs | 480000 | 81750 | 561750 | 5760000 | 981000 | 6741000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760245679+2153449-1, Commscope/ China
|  | Wifi module (Wifi supply by Client) | 4 | 4 | pcs | 0 | 136250 | 136250 | 0 | 545000 | 545000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Only labor
|  | FO Patch Cord, SC-SC Duplex, LSOH, SM,3m | 2 | 2 | pcs | 550000 | 10900 | 560900 | 1100000 | 21800 | 1121800 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FFWSCSC42-JXM003,Commscope/ China
|  | FO Pigtail LC, SM, 1m for welding to optical fibre | 2 | 48 | pcs | 132000 | 65400 | 197400 | 6336000 | 3139200 | 9475200 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | EH0108-001, Commscope/ China
|  | Cat 6A Patch Cord, 3m from Data outlet to wifi | 4 | 4 | pcs | 198000 | 10900 | 208900 | 792000 | 43600 | 835600 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
|  | Cable Cat6A | 1257 | 1240 | m | 21639.3443 | 3360 | 24999.3443 | 26832786.8852 | 4166400 | 30999186.8852 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Commscope
|  | PVC conduit D20 | 503 | 500 | m | 8773.9726 | 14594.0164 | 23367.989 | 4386986.3014 | 7297008.2059 | 11683994.5073 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
|  | Network cable test cost - Cat6A cable | 12 | 24 | nos | 0 | 50600 | 50600 | 0 | 1214400 | 1214400 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
|  | Accessories | 1 | 1 | lot | 5465250.8691 | 1639575.2607 | 7104826.1298 | 5465250.8691 | 1639575.2607 | 7104826.1298 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Vietnam
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 3. |  | Mechancial Engineering | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 3. 10. |  | Rainwater System | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 3. 20. |  | Waste Water System | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 3. 30. |  | Service Water System | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 3. 40. |  | Sanitary Furnishings | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 3. 50. |  | Air Conditioning | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 3. 60. |  | Ventilation System Overhead Fans | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 3. 70. |  | Ventilation System | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 3. 80. |  | Fire Protection System | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
7. |  | Exterior Area | [6 empty] | 509452988.9423 | 100342530.3589 | 609795519.3012 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
7. 1. |  | Civil Engineering | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
7. 1. 10. |  | Flag pole | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
7. 1. 20. |  | Fence | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
7. 1. 30. |  | Bollards and delineator panels | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
7. 1. 40. |  | New Septic Tanks | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
7. 1. 50. |  | Excavation | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
7. 1. 60. |  | Laying conduits, pipes, etc. | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
7. 1. 70. |  | Asphalt areas | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
7. 2. |  | Electrical Engineering | [6 empty] | 509452988.9423 | 100342530.3589 | 609795519.3012 |  |  | 0% |  |  | 0 | 0 | 0 | 0
7. 2. 10. |  | Electrical Installations General | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
7. 2. 20. |  | Exterior Lighting | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
7. 2. 30. |  | Emergency Lighting | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
7. 2. 40. |  | Building service connections | 1 | 1 | PSCH |  |  |  | 449449440 | 94825780 | 544275220 |  |  | 0% |  |  | 0 | 0 | 0 | 0
|  | Single Mode OS2 48 fibers SC- Duplex | 1325 | 2141.26 | m | 144000 | 28000 | 172000 | 308341440 | 59955280 | 368296720 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Commscope
|  | 20 x 0,8 pair copper phone wire (20P cat3) | 0 |  | m | 117360 | 13798.4 | 131158.4 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 1499418-1, Commscope/ China
|  | ODF F.O Singlemode, 48F add to MDF at server rooms | 5 | 5 | pcs | 6490000 | 490500 | 6980500 | 32450000 | 2452500 | 34902500 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 4-1671002-4+760241378, Commscope/ China
|  | Patch panel 24 Port cat 5e | 5 | 5 | pcs | 2195600 | 654000 | 2849600 | 10978000 | 3270000 | 14248000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760237040+9-1375191-2, Commscope/ China
|  | Cat 6A Patch Cord, 3m | 120 |  | pcs | 198000 | 10900 | 208900 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
|  | FO Patch Cord, SC-SC Duplex, LSOH, SM,3m | 120 | 120 | pcs | 550000 | 10900 | 560900 | 66000000 | 1308000 | 67308000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FFWSCSC42-JXM003,Commscope/ China
|  | FO Pigtail LC, SM, 1m for welding to optical fibre | 120 | 240 | pcs | 132000 | 65400 | 197400 | 31680000 | 15696000 | 47376000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | EH0108-001, Commscope/ China
|  | Network cable test cost - FO cable | 120 | 240 | nos | 0 | 50600 | 50600 | 0 | 12144000 | 12144000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
|  | Network cable test cost - Cat6A cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
7. 2. 50. |  | CCTV System | 1 | 1 | PSCH |  |  |  | 60003548.9423 | 5516750.3589 | 65520299.3012 |  |  | 0% |  |  | 0 | 0 | 0 | 0
|  | For Custom fence | [6 empty] | 60003548.9423 | 5516750.3589 | 65520299.3012 |  |  | 0% |  |  | 0 | 0 | 0 | 0
|  | NVR 32 Chanel | 1 | 1 | pcs | 19810560 | 385000 | 20195560 | 19810560 | 385000 | 20195560 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | DS-7616NI-K2/ HIKVISION/ China
|  | Outside Camera CF-1-->4 | 4 | 4 | pcs | 1264480 | 137500 | 1401980 | 5057920 | 550000 | 5607920 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | DS-2CD2021G1-I, Hikvision/ China
|  | Telescopic parapet mount (T91D62) | 4 | 4 | pcs | 1803200 | 49500 | 1852700 | 7212800 | 198000 | 7410800 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Axis
|  | Overvoltage protection | 4 | 4 | pcs | 4494000 | 49050 | 4543050 | 17976000 | 196200 | 18172200 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | PNET1GB, Schneider
|  | Double data outlet RJ45 | 4 | 4 | pcs | 480000 | 81750 | 561750 | 1920000 | 327000 | 2247000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760245679+2153449-1, Commscope/ China
|  | Cat 6A Patch Cord, 3m | 12 | 12 | pcs | 198000 | 10900 | 208900 | 2376000 | 130800 | 2506800 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
|  | Cable Cat6 | 240 | 227 | m | 10032.7869 | 3360 | 13392.7869 | 2277442.623 | 762720 | 3040162.623 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Commposcope / China, or Alantek
|  | PVC conduit D20 | 96 | 100 | m | 8773.9726 | 14594.0164 | 23367.989 | 877397.2603 | 1459401.6412 | 2336798.9015 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
|  | Network cable test cost - Cat6A cable | 4 | 15 | nos | 0 | 50600 | 50600 | 0 | 759000 | 759000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
|  | Accessories | 1 | 1 | lot | 2495429.0591 | 748628.7177 | 3244057.7768 | 2495429.0591 | 748628.7177 | 3244057.7768 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
7. 3. |  | Mechanical Engineering | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
7. 3. 10. |  | Underground Compressed Air Connection | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
8. |  | Adjustments Hall 2 | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
8. 1. |  | Roof Renovation | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
8. 1. 10. |  | Roof Reinforcement Option 1 | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
8. 2. |  | Adjustment Ridge Vent | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
8. 2. 10. |  | Adjustment Ridge Vent | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
8. 3. |  | Adjustment Overhead Fans | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
8. 3. 10. |  | Adjustment Overhead Fans | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
8. 4. |  | Additonal In-Rack Sprinkler Logistic | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
8. 4. 10. |  | Additonal In-Rack Sprinkler Logistic | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
8. 5. |  | Additional Compressed Air Equipment | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
8. 5. 10. |  | Additional Compressed Air Equipment | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
8. 6. |  | Flag pole | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
8. 6. 10. |  | Flag pole | 0 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
9. |  | As built documentation | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
9. 1. |  | As built documentation all trades | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
9. 1. 10. |  | As built documentation | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
10. |  | Service of Architects and Engineers | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
10. 1. |  | Civil engineering | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 1. 10. |  | Design works | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 1. 20. |  | Geotechnical survey | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 1. 30. |  | Topographical survey | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 1. 40. |  | Fire protection report | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 1. 50. |  | Compactation report of earthworks | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 1. 60. |  | Structure and welding quality report | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 1. 70. |  | Adherence and width of paint quality control reports | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 1. 80. |  | Material quality control reports | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 1. 90. |  | Planning service Building construction | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 1. 100. |  | Planning service Structural design | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 1. 110. |  | Planning service Structural revision | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 1. 120. |  | Surveying services Inventory registration | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 1. 130. |  | Quality control laboratory for material testing (laboratory and field testing) | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 1. 140. |  | Revision fire department and civil protection | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
10. 2. |  | Electrical engineering | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 2. 10. |  | Design & approval works | 1 |  | psch | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0 | 0
10. 3. |  | Mechanical engineering | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 3. 10. |  | Design & approval works | 1 |  | psch | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[14 empty] | 0% |  |  | 0 | 0 | 0
|  | TOTAL AMOUNT (Not included VAT) | [6 empty] | 2924099307.303 | 488828772.8637 | 3412928080.1667 | [6 empty] | 111817559.8522 | 18158432.9237 | 129975992.7758
2. |  | Production and Logistic building (Hall 3) | [6 empty] | 585597305.9781 | 205702981.3661 | 791300287.3442 | [6 empty] | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
2. 3. |  | Mechanical Engineering | [6 empty] | 585597305.9781 | 205702981.3661 | 791300287.3442 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 3. 40. |  | Compressed Air Network Production 1 | 1 |  | PSCH |  |  |  | 425312121.5169 | 147070051.5988 | 572382173.1157 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | BLUE ALUMINIUM PIPE, DN63 | 470 | 485 | m | 362322.6857 | 115320.5625 | 477643.2482 | 175726502.5676 | 55930472.8125 | 231656975.3801 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 301 00 0600 01, Airpipe/ Vietnam
|  | BLUE ALUMINIUM PIPE, DN40 | 0 | 30 | pcs | 190224.1656 | 70966.5 | 261190.6656 | 5706724.968 | 2128995 | 7835719.968 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 301 00 0400 01, Airpipe/ Vietnam
|  | BLUE ALUMINIUM PIPE, DN25 | 180 | 174 | m | 94950.6667 | 42579.9 | 137530.5667 | 16521416 | 7408902.6 | 23930318.6 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 301 00 0200 01, Airpipe/ Vietnam
|  | TUBE CLIP, DN63 (POLYMER) | 162 | 172 | pcs | 54295.4118 | 82376.8 | 136672.2118 | 9338810.8362 | 14168809.6 | 23507620.4362 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | TUBE CLIP, DN40 (POLYMER) | 76 | 10 | pcs | 32609.857 | 57608.1 | 90217.957 | 326098.5696 | 576081 | 902179.5696 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | PIPE TO PIPE JOINT, DN63 | 79 | 79 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 47234236.4616 | 6507767.2 | 53742003.6616 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | PIPE TO PIPE JOINT, DN63 | 50 | 50 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 29895086.3681 | 4118840 | 34013926.3681 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | 90° ELBOW, DN63 | 6 | 8 | pcs | 326098.5696 | 82376.8 | 408475.3696 | 2608788.5568 | 659014.4 | 3267802.9568 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | EQUAL TEE, DN63 | 3 | 5 | pcs | 543443.2662 | 82376.8 | 625820.0662 | 2717216.3312 | 411884 | 3129100.3312 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | END CAP, DN63 | 1 | 1 | pcs | 380393.9814 | 82376.8 | 462770.7814 | 380393.9814 | 82376.8 | 462770.7814 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | REDUCING TEE, DN63-40 | 12 | 14 | pcs | 861389.3716 | 82376.8 | 943766.1716 | 12059451.2024 | 1153275.2 | 13212726.4024 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | QUICK DROP, DN63-25 | 32 | 32 | pcs | 372241.5172 | 82376.8 | 454618.3172 | 11911728.5503 | 2636057.6 | 14547786.1503 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | PIPE TO PIPE JOINT, DN40 | 37 | 37 | pcs | 317946.1054 | 57608.1 | 375554.2054 | 11764005.8983 | 2131499.7 | 13895505.5983 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | LOCKABLE BRASS VALVE, DN25-1/2" FEMALE THREAD, WITH FIXING PLATE | 32 | 32 | pcs | 680241.6162 | 53385.955 | 733627.5712 | 21767731.7179 | 1708350.5613 | 23476082.2792 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | TWO-WAYS PNEUMATIC CONNECTOR, FEMALE THREAD G1/2" | 0 |  | pcs | 206583.4438 | 53385.955 | 259969.3989 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | T-BOLT, M8, 6CM | 228 | 228 | pcs | 3260.9857 | 3850 | 7110.9857 | 743504.7387 | 877800 | 1621304.7387 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
|  | THREADED ROD, M8, 3 METER | 50 | 50 | pcs | 48914.7854 | 11000 | 59914.7854 | 2445739.272 | 550000 | 2995739.272 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
|  | WALL MOUNTED BRACKET, 50CM | 228 | 228 | pcs | 92448.9445 | 8250 | 100698.9445 | 21078359.3418 | 1881000 | 22959359.3418 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
|  | BEAM CLAMP, 2.5CM | 456 | 456 | pcs | 37990.4834 | 8250 | 46240.4834 | 17323660.4114 | 3762000 | 21085660.4114 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
|  | Fire Stop | 1 | 1 | lot | 2500000 | 1000000 | 3500000 | 2500000 | 1000000 | 3500000 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
|  | Accessories | 1 | 1 | lot | 33262665.7435 | 9978799.7231 | 43241465.4666 | 33262665.7435 | 9978799.7231 | 43241465.4666 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Included
|  | T&C | 1 | 1 | lot | 0 | 29398125.4019 | 29398125.4019 | 0 | 29398125.4019 | 29398125.4019 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
2. 3. 50. |  | Compressed Air Network Production 2 | 1 |  | PSCH |  |  |  | 160285184.4612 | 58632929.7673 | 218918114.2285 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | PRODUCTION 2 | [6 empty] | 83418012.7013 | 26026366.1504 | 109444378.8517 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | BLUE ALUMINIUM PIPE, DN40 | 109 | 210 | m | 190224.1656 | 70966.5 | 261190.6656 | 39947074.776 | 14902965 | 54850039.776 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 301 00 0400 01, Airpipe/ Vietnam
|  | BLUE ALUMINIUM PIPE, DN25 | 56 | 59 | m | 94950.6667 | 42579.9 | 137530.5667 | 5602089.3333 | 2512214.1 | 8114303.4333 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 301 00 0200 01, Airpipe/ Vietnam
|  | PIPE TO PIPE JOINT, DN63 | 4 | 4 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 2391606.9094 | 329507.2 | 2721114.1094 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | PIPE TO PIPE JOINT, DN40 | 19 | 19 | pcs | 317946.1054 | 57608.1 | 375554.2054 | 6040976.0018 | 1094553.9 | 7135529.9018 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | REDUCING TEE, DN63-40 | 2 | 2 | pcs | 861389.3716 | 82376.8 | 943766.1716 | 1722778.7432 | 164753.6 | 1887532.3432 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | TUBE CLIP, DN40 (POLYMER) | 40 | 70 | pcs | 32609.857 | 57608.1 | 90217.957 | 2282689.9872 | 4032567 | 6315256.9872 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | 45° ELBOW, DN40 | 6 | 6 | pcs | 741874.2458 | 57608.1 | 799482.3458 | 4451245.475 | 345648.6 | 4796894.075 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | QUICK DROP, DN40-25 | 10 | 10 | pcs | 318435.2532 | 57608.1 | 376043.3532 | 3184352.5321 | 576081 | 3760433.5321 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | BRASS VALVE, DN40-DN40 | 2 | 2 | pcs | 1451138.6347 | 57608.1 | 1508746.7347 | 2902277.2694 | 115216.2 | 3017493.4694 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | LOCKABLE BRASS VALVE, DN25-1/2" FEMALE THREAD, WITH FIXING PLATE | 10 | 10 | pcs | 680241.6162 | 53385.955 | 733627.5712 | 6802416.1619 | 533859.5504 | 7336275.7123 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | TWO-WAYS PNEUMATIC CONNECTOR, FEMALE THREAD G1/2" | 0 |  | pcs | 206583.4438 | 53385.955 | 259969.3989 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | T-BOLT, M8, 6CM | 40 | 40 | pcs | 3260.9857 | 3850 | 7110.9857 | 130439.4278 | 154000 | 284439.4278 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
|  | THREADED ROD, M8, 3 METER | 25 | 25 | pcs | 48914.7854 | 11000 | 59914.7854 | 1222869.636 | 275000 | 1497869.636 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
|  | WALL MOUNTED BRACKET, 50CM | 40 | 40 | pcs | 92448.9445 | 8250 | 100698.9445 | 3697957.7793 | 330000 | 4027957.7793 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
|  | BEAM CLAMP, 2.5CM | 80 | 80 | pcs | 37990.4834 | 8250 | 46240.4834 | 3039238.6687 | 660000 | 3699238.6687 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
|  | LOGICSTIC | [6 empty] | 76867171.7599 | 32606563.6169 | 109473735.3768 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | BLUE ALUMINIUM PIPE, DN63 | 0 | 30 | m | 362322.6857 | 115320.5625 | 477643.2482 | 10869680.5712 | 3459616.875 | 14329297.4462 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 301 00 0600 01, Airpipe/ Vietnam
|  | BLUE ALUMINIUM PIPE, DN40 | 69 | 72 | m | 190224.1656 | 70966.5 | 261190.6656 | 13696139.9232 | 5109588 | 18805727.9232 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 301 00 0400 01, Airpipe/ Vietnam
|  | BLUE ALUMINIUM PIPE, DN25 | 17 | 21 | m | 94950.6667 | 42579.9 | 137530.5667 | 1993964 | 894177.9 | 2888141.9 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 301 00 0200 01, Airpipe/ Vietnam
|  | TUBE CLIP, DN63 (POLYMER) | 0 | 6 | pcs | 54295.4118 | 82376.8 | 136672.2118 | 325772.471 | 494260.8 | 820033.271 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | PIPE TO PIPE JOINT, DN63 | 0 | 8 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 4783213.8189 | 659014.4 | 5442228.2189 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | PIPE TO PIPE JOINT, DN63 | 0 | 8 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 4783213.8189 | 659014.4 | 5442228.2189 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | EQUAL TEE, DN63 | 0 | 6 | pcs | 543443.2662 | 82376.8 | 625820.0662 | 3260659.5974 | 494260.8 | 3754920.3974 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | REDUCING TEE, DN63-40 | 2 | 2 | pcs | 861389.3716 | 82376.8 | 943766.1716 | 1722778.7432 | 164753.6 | 1887532.3432 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | END CAP, DN63 | 1 | 1 | pcs | 380393.9814 | 82376.8 | 462770.7814 | 380393.9814 | 82376.8 | 462770.7814 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | TUBE CLIP, DN40 (POLYMER) | 26 | 24 | pcs | 32609.857 | 57608.1 | 90217.957 | 782636.567 | 1382594.4 | 2165230.967 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | PIPE TO PIPE JOINT, DN40 | 12 | 12 | pcs | 317946.1054 | 57608.1 | 375554.2054 | 3815353.2643 | 691297.2 | 4506650.4643 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | 90° ELBOW, DN40 | 1 | 1 | pcs | 706492.551 | 57608.1 | 764100.651 | 706492.551 | 57608.1 | 764100.651 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | EQUAL TEE, DN40 | 1 | 1 | pcs | 1066831.4704 | 57608.1 | 1124439.5704 | 1066831.4704 | 57608.1 | 1124439.5704 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | QUICK DROP, DN63-25 | 1 | 1 | pcs | 372241.5172 | 82376.8 | 454618.3172 | 372241.5172 | 82376.8 | 454618.3172 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | QUICK DROP, DN40-25 | 2 | 2 | pcs | 318435.2532 | 57608.1 | 376043.3532 | 636870.5064 | 115216.2 | 752086.7064 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | END CAP, DN40 | 2 | 2 | pcs | 529910.1756 | 57608.1 | 587518.2756 | 1059820.3512 | 115216.2 | 1175036.5512 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | BRASS VALVE, DN40-DN40 | 2 | 2 | pcs | 1451138.6347 | 57608.1 | 1508746.7347 | 2902277.2694 | 115216.2 | 3017493.4694 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | BRASS VALVE, DN25-1/2" FEMALE THREAD, WITH FIXING PLATE | 2 | 2 | pcs | 617304.5923 | 53385.955 | 670690.5473 | 1234609.1845 | 106771.9101 | 1341381.0946 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | TWO-WAYS PNEUMATIC CONNECTOR, FEMALE THREAD G1/2" | 0 |  | pcs | 206583.4438 | 48702.5 | 255285.9438 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | T-BOLT, M8, 6CM | 40 | 40 | pcs | 3260.9857 | 3850 | 7110.9857 | 130439.4278 | 154000 | 284439.4278 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
|  | THREADED ROD, M8, 3 METER | 25 | 25 | pcs | 48914.7854 | 11000 | 59914.7854 | 1222869.636 | 275000 | 1497869.636 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
|  | WALL MOUNTED BRACKET, 50CM | 36 | 36 | pcs | 92448.9445 | 8250 | 100698.9445 | 3328162.0013 | 297000 | 3625162.0013 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
|  | BEAM CLAMP, 2.5CM | 72 | 72 | pcs | 37990.4834 | 8250 | 46240.4834 | 2735314.8018 | 594000 | 3329314.8018 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
|  | Fire Stop | 1 | 1 | lot | 2500000 | 1000000 | 3500000 | 2500000 | 1000000 | 3500000 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
|  | Accessories | 1 | 1 | lot | 12557436.286 | 3767230.8858 | 16324667.1718 | 12557436.286 | 3767230.8858 | 16324667.1718 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Included
|  | T&C | 1 | 1 | lot | 0 | 11778364.046 | 11778364.046 | 0 | 11778364.046 | 11778364.046 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
3. |  | Office, Social and Technical Areas (Hall 3) | [6 empty] | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
3. 3. |  | Mechanical Engineering | [6 empty] | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
3. 3. 120. |  | Compressed Air Connections | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Included in machine hook-up
4. |  | Machine hook-up (Hall 3) | [6 empty] | 246537484.7813 | 58813621.1675 | 305351105.9487 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0%
4. 2. |  | Mechanical Engineering | [6 empty] | 246537484.7813 | 58813621.1675 | 305351105.9487 |  |  | 0% |  |  | 0% | 0 | 0 | 0
4. 2. 10. |  | Machine hook-up | 1 | 1 | PSCH |  |  |  | 246537484.7813 | 58813621.1675 | 305351105.9487 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | BLUE ALUMINIUM PIPE, DN63 | 16 | 18 | m | 362322.6857 | 115320.5625 | 477643.2482 | 6521808.3427 | 2075770.125 | 8597578.4677 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 301 00 0600 01, Airpipe/ Vietnam
|  | BLUE ALUMINIUM PIPE, DN40 | 257 | 228 | m | 190224.1656 | 70966.5 | 261190.6656 | 43371109.7568 | 16180362 | 59551471.7568 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 301 00 0400 01, Airpipe/ Vietnam
|  | BLUE ALUMINIUM PIPE, DN25 | 23 | 27 | m | 94950.6667 | 42579.9 | 137530.5667 | 2563668 | 1149657.3 | 3713325.3 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 301 00 0200 01, Airpipe/ Vietnam
|  | PIPE TO PIPE JOINT, DN63 | 1 | 1 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 597901.7274 | 82376.8 | 680278.5274 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | REDUCING PIPE TO PIPE JOINT, DN63-DN40 | 1 | 1 | pcs | 684154.799 | 82376.8 | 766531.599 | 684154.799 | 82376.8 | 766531.599 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | TUBE CLIP, DN40 (POLYMER) | 92 | 77 | pcs | 32609.857 | 57608.1 | 90217.957 | 2510958.9859 | 4435823.7 | 6946782.6859 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | PIPE TO PIPE JOINT, DN40 | 45 | 45 | pcs | 317946.1054 | 57608.1 | 375554.2054 | 14307574.7412 | 2592364.5 | 16899939.2412 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | QUICK DROP, DN40-25 | 45 | 45 | pcs | 318435.2532 | 57608.1 | 376043.3532 | 14329586.3946 | 2592364.5 | 16921950.8946 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | Pressureless decouling | 96 | 96 | pcs | 387040 | 30056.4 | 417096.4 | 37155840 | 2885414.4 | 40041254.4 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Festo/ Vietnam
|  | BRASS VALVE, DN63-DN63 | 1 | 1 | pcs | 2445739.272 | 82376.8 | 2528116.072 | 2445739.272 | 82376.8 | 2528116.072 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | BRASS VALVE, DN40-DN40 | 2 | 2 | pcs | 1451138.6347 | 57608.1 | 1508746.7347 | 2902277.2694 | 115216.2 | 3017493.4694 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | LOCKABLE BRASS VALVE, DN25-1/2" FEMALE THREAD, WITH FIXING PLATE | 28 | 28 | pcs | 680241.6162 | 53385.955 | 733627.5712 | 19046765.2532 | 1494806.7411 | 20541571.9943 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | LOCKABLE BRASS VALVE, DN25-3/8" FEMALE THREAD, WITH FIXING PLATE | 68 | 68 | pcs | 680241.6162 | 53385.955 | 733627.5712 | 46256429.9006 | 3630244.9427 | 49886674.8433 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | BRASS VALVE, DN25-1/2" FEMALE THREAD, WITH FIXING PLATE | 6 | 6 | pcs | 617304.5923 | 53385.955 | 670690.5473 | 3703827.5535 | 320315.7302 | 4024143.2838 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | T-split 3 way outlet tap | 28 | 28 | pcs | 451350 | 27500 | 478850 | 12637800 | 770000 | 13407800 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | VN
|  | T-BOLT, M8, 6CM | 92 | 92 | pcs | 3260.9857 | 3850 | 7110.9857 | 300010.684 | 354200 | 654210.684 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
|  | THREADED ROD, M8, 3 METER | 50 | 50 | pcs | 48914.7854 | 11000 | 59914.7854 | 2445739.272 | 550000 | 2995739.272 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
|  | WALL MOUNTED BRACKET, 50CM | 92 | 92 | pcs | 92448.9445 | 8250 | 100698.9445 | 8505302.8923 | 759000 | 9264302.8923 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
|  | BEAM CLAMP, 2.5CM | 184 | 184 | pcs | 37990.4834 | 8250 | 46240.4834 | 6990248.9379 | 1518000 | 8508248.9379 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 19260740.9985 | 5778222.2996 | 25038963.2981 | 19260740.9985 | 5778222.2996 | 25038963.2981 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Included
|  | T&C | 1 | 1 | lot | 0 | 11364728.3288 | 11364728.3288 | 0 | 11364728.3288 | 11364728.3288 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
5. |  | Scooter Garage | [6 empty] | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
6. |  | Canteen | [6 empty] | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
7. |  | Exterior Area | [6 empty] | 28542816 | 17816848.8 | 46359664.8 |  |  | 0% |  |  | 0% | 16491404.8 | 0 | 16491404.8
[14 empty] | 0% |  |  | 0%
7. 3. |  | Mechanical Engineering | [6 empty] | 28542816 | 17816848.8 | 46359664.8 |  |  | 0% |  |  | 0% | 16491404.8 | 0 | 16491404.8
7. 3. 10. |  | Underground Compressed Air Connection | 1 |  | PSCH |  |  |  | 28542816 | 17816848.8 | 46359664.8 |  |  | 0% |  |  | 0% | 16491404.8 | 0 | 16491404.8
|  | HDPE Pipe DN100 | 115 | 115 | m | 179254.4 | 96096 | 275350.4 | 20614256 | 11051040 | 31665296 | 80% |  | 80% |  |  | 0% | 16491404.8 | 0 | 16491404.8 | De Nhat, VN, Ø110, 10.0mm, PN16
|  | Fitting for connecting HDPE pipes with aluminum pipes | 1 | 1 | lot | 4757136 | 1427140.8 | 6184276.8 | 4757136 | 1427140.8 | 6184276.8 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Viet Nam
|  | Hanger support & accessories | 1 | 1 | lot | 3171424 | 951427.2 | 4122851.2 | 3171424 | 951427.2 | 4122851.2 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Viet Nam
|  | T&C | 1 | 1 | lot | 0 | 4387240.8 | 4387240.8 | 0 | 4387240.8 | 4387240.8 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Viet Nam
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
8. |  | Adjustments Hall 2 | [6 empty] | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
8. 5. |  | Additional Compressed Air Equipment | [6 empty] | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | for the future, not included in this period
8. 5. 10. |  | Additional Compressed Air Equipment | 1 |  | PSCH |  |  |  | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | Main equipments | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | Rotary screw air compressor | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | ASD 35/ KAESER/ Germany
|  | Air dryer | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TE102/ KAESER/ Germany
|  | Ball Valve D63 | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | Ball Valve D40 | 6 |  | Pcs |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
|  | Oil removal filter | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Filter F83KE with ECO Drain 31F/ KAESER/ Germany
|  | Pressure maintainance system | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | DHS 50 G/ KAESER/ Germany
|  | Condensate drain pipe D19 | 15 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Hailiang/ China
|  | Condensate drain pipe D15.9 | 25 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Hailiang/ China
|  | Accessories | 1 |  | lot |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Viet Nam
|  | T&C | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Viet Nam
[8 empty] | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | Ventilation for Air compressor | [5 empty] | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | Tole 0.95mm | 12 |  | m2 |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Z08- 0.95mmT/ Hoa Sen/ VN
|  | Motor fire damper 550x500x450 | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
|  | Flexiable connection | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | Cable Cat6A | 66 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 884024508/10, Commscope/ China
|  | Cable 1 pair 18AWG | 22 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 2MKABLO/ Turkey
|  | Cable Cu/PVC/PVC 2Cx1.5mm2 | 22 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 39 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
|  | GI flexible conduct D20 | 42 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | OMI12/ Cat Van Loi/ VN
|  | Cable tray 50x50x1.0mm | 7 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
|  | Hanger support | 1 |  | lot |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Viet Nam
|  | Accessories | 1 |  | lot |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Viet Nam
[8 empty] | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | Compressed air pipes and valves | [5 empty] | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
|  | Aluminium Air pipe D63 | 11 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 301 00 0600 01, Airpipe/ Vietnam
|  | Aluminium Air pipe D40 | 8 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 301 00 0400 01, Airpipe/ Vietnam
|  | Fiiting for Aluminium pipe | 1 |  | lot |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Viet Nam
|  | Hanger support + Accessories | 1 |  | lot |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Included
[14 empty] | 0% |  |  | 0% | 0 | 0 | 0
|  | TOTAL AMOUNT (Not included VAT) | [6 empty] | 860677606.7593 | 282333451.3336 | 1143011058.0929 | [6 empty] | 16491404.8 | 0 | 16491404.8
2. |  | Production and Logistic building (Hall 3) | [6 empty] | 876156669.5216 | 245761873.2789 | 1121918542.8005 | [6 empty] | 44143514.5823 | 0 | 44143514.5823
2. 3. |  | Mechanical Engineering | [6 empty] | 876156669.5216 | 245761873.2789 | 1121918542.8005 |  |  | 0 |  |  | 0 | 44143514.5823 | 0 | 44143514.5823
2. 3. 10. |  | Ventilation System Production | 1 | 1 | PSCH |  |  |  | 304034489.6043 | 189644193.2889 | 493678682.8931 |  |  | 0 |  |  | 0 | 32145968.4485 | 0 | 32145968.4485
|  | Logistics Area | [6 empty] | 32646354.8705 | 20550720.3964 | 53197075.267 |  |  | 0 |  |  | 0 | 3957283.4015 | 0 | 3957283.4015
|  | Overhead Propeller Fans | 2 | 2 | pcs | 0 | 6300000 | 6300000 | 0 | 12600000 | 12600000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Equipment provided by Owner, Contractor only labour
|  | Control panel for Overhead Fans | 1 | 1 | pcs | 19550000 | 385000 | 19935000 | 19550000 | 385000 | 19935000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Encloser: Vietnam Equipment: Regin / Sweden
|  | Cable Cu/PVC/PVC 4Cx1.5mm2 | 160 | 163.8 | m | 25928.4 | 7485.665 | 33414.065 | 4247071.92 | 1226151.927 | 5473223.847 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | Cable Cu/PVC/PVC 2Cx1.5mm2 | 165 | 163.8 | m | 15443.88 | 5031.18 | 20475.06 | 2529707.544 | 824107.284 | 3353814.828 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 243 | 300 | m | 8773.9726 | 14594.0164 | 23367.989 | 2632191.7808 | 4378204.9235 | 7010396.7044 | 80% |  | 0.8 |  |  | 0 | 2105753.4247 | 0 | 2105753.4247 | FPC20, Nano/ VN
|  | PVC flexible conduct D20 | 7 | 7.35 | m | 3554.7229 | 5289.7059 | 8844.4288 | 26127.2135 | 38879.3382 | 65006.5517 | 80% |  | 0.8 |  |  | 0 | 20901.7708 | 0 | 20901.7708 | Nano/ VN
|  | PVC conduit D20 | 15 |  | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | Hanger, support | 1 | 1 | lot | 1220418.8041 | 366125.6412 | 1586544.4453 | 1220418.8041 | 366125.6412 | 1586544.4453 | 50% |  | 0.5 |  |  | 0 | 610209.402 | 0 | 610209.402 | Vietnam
|  | Accessories | 1 | 1 | lot | 2440837.6082 | 732251.2824 | 3173088.8906 | 2440837.6082 | 732251.2824 | 3173088.8906 | 50% |  | 0.5 |  |  | 0 | 1220418.8041 | 0 | 1220418.8041 | included
|  |  | 0 | 0 | [9 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Production Hall 1 | 0 | 0 |  |  |  |  | 233479516.9276 | 145274230.7072 | 378753747.6348 |  |  | 0 |  |  | 0 | 24800344.5567 | 0 | 24800344.5567
|  | Overhead Propeller Fans | 14 | 14 | pcs | 0 | 6300000 | 6300000 | 0 | 88200000 | 88200000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Equipment provided by Owner, Contractor only labour
|  | Control panel for Overhead Fans | 7 | 7 | m | 19550000 | 385000 | 19935000 | 136850000 | 2695000 | 139545000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Encloser: Vietnam Equipment: Regin / Sweden
|  | 4Cx-1.5mm2 Cu/PVC/PVC | 1600 | 1556.5 | m | 25928.4 | 7485.665 | 33414.065 | 40357554.6 | 11651437.5725 | 52008992.1725 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 2Cx-1.5mm2 Cu/PVC/PVC | 1050 | 1156.5 | m | 15443.88 | 5031.18 | 20475.06 | 17860847.22 | 5818559.67 | 23679406.89 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 2125 | 2100 | m | 8773.9726 | 14594.0164 | 23367.989 | 18425342.4658 | 30647434.4647 | 49072776.9305 | 80% |  | 0.8 |  |  | 0 | 14740273.9726 | 0 | 14740273.9726 | FPC20, Nano/ VN
|  | PVC flexible conduct D20 | 70 | 63 | m | 3554.7229 | 5289.7059 | 8844.4288 | 223947.544 | 333251.4706 | 557199.0145 | 80% |  | 0.8 |  |  | 0 | 179158.0352 | 0 | 179158.0352 | Nano/ VN
|  | PVC conduit D20 | 150 |  | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | Hanger, support | 1 | 1 | lot | 8982647.7718 | 2694794.3315 | 11677442.1033 | 8982647.7718 | 2694794.3315 | 11677442.1033 | 50% |  | 0.5 |  |  | 0 | 4491323.8859 | 0 | 4491323.8859 | Vietnam
|  | Accessories | 1 | 1 | lot | 10779177.3261 | 3233753.1978 | 14012930.524 | 10779177.3261 | 3233753.1978 | 14012930.524 | 50% |  | 0.5 |  |  | 0 | 5389588.6631 | 0 | 5389588.6631 | Vietnam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Production Hall 2 | 0 | 0 |  |  |  |  | 30503490.5753 | 19149107.5868 | 49652598.1621 |  |  | 0 |  |  | 0 | 3388340.4902 | 0 | 3388340.4902
|  | Overhead Propeller Fans | 2 | 2 | pcs | 0 | 6300000 | 6300000 | 0 | 12600000 | 12600000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Equipment provided by Owner, Contractor only labour
|  | Control panel for Overhead Fans | 1 | 1 | m | 19550000 | 385000 | 19935000 | 19550000 | 385000 | 19935000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Encloser: Vietnam Equipment: Regin / Sweden
|  | 4Cx-1.5mm2 Cu/PVC/PVC | 160 | 108.15 | m | 25928.4 | 7485.665 | 33414.065 | 2804156.46 | 809574.6698 | 3613731.1298 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 2Cx-1.5mm2 Cu/PVC/PVC | 165 | 170 | m | 15443.88 | 5031.18 | 20475.06 | 2625459.6 | 855300.6 | 3480760.2 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 243 | 220 | m | 8773.9726 | 14594.0164 | 23367.989 | 1930273.9726 | 3210683.6106 | 5140957.5832 | 80% |  | 0.8 |  |  | 0 | 1544219.1781 | 0 | 1544219.1781 | FPC20, Nano/ VN
|  | PVC flexible conduct D20 | 7 | 7.35 | m | 3554.7229 | 5289.7059 | 8844.4288 | 26127.2135 | 38879.3382 | 65006.5517 | 80% |  | 0.8 |  |  | 0 | 20901.7708 | 0 | 20901.7708 | Nano/ VN
|  | PVC conduit D20 | 15 | 15 | m | 8773.9726 | 14594.0164 | 23367.989 | 131609.589 | 218910.2462 | 350519.8352 | 80% |  | 0.8 |  |  | 0 | 105287.6712 | 0 | 105287.6712 | FPC20, Nano/ VN
|  | Hanger, support | 1 | 1 | lot | 1145287.9134 | 343586.374 | 1488874.2874 | 1145287.9134 | 343586.374 | 1488874.2874 | 50% |  | 0.5 |  |  | 0 | 572643.9567 | 0 | 572643.9567 | Vietnam
|  | Accessories | 1 | 1 | lot | 2290575.8268 | 687172.748 | 2977748.5748 | 2290575.8268 | 687172.748 | 2977748.5748 | 50% |  | 0.5 |  |  | 0 | 1145287.9134 | 0 | 1145287.9134 | Vietnam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Interface between fire alarm and fan system | 0 | 0 |  |  |  |  | 7405127.2308 | 4670134.5985 | 12075261.8293 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| 8 | Fire signal cable: (2x1.0)mm2 Dây tín hiệu báo cháy: (2x1.0)mm2 | 830 | 830 | M | 7457.49 | 3300 | 10757.49 | 6189716.7 | 2739000 | 8928716.7 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vcmd/ Cadivi/ Viet Nam
| 10 | D16 PVC conduit & accessories Ống bảo vệ dây dẫn D16 và phụ kiện | 140 | 140 | M | 6646.8692 | 13183.4282 | 19830.2974 | 930561.6849 | 1845679.9447 | 2776241.6296 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC16, Nano/ VN
|  | Accessories | 1 | 1 | lot | 284848.8459 | 85454.6538 | 370303.4997 | 284848.8459 | 85454.6538 | 370303.4997 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
2. 3. 60. |  | SMOKE EXHAUST SYSTEM | [6 empty] | 572122179.9173 | 56117679.99 | 628239859.9073 |  |  | 0 |  |  | 0 | 11997546.1339 | 0 | 11997546.1339
|  | Equipment | [6 empty] | 474178458 | 32835793.1 | 507014251.1 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Roof smoke exhaust FAN - SEAF @26500m3/h, 100Pa, 3.0kW, 300oC in 2hrs | 6 | 6 | pcs | 43434300 | 2241801.1 | 45676101.1 | 260605800 | 13450806.6 | 274056606.6 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | RDA900-14AA-7-7/26, Kruger/ Vietnam
|  | Roof smoke exhaust FAN - SEAF @8000m3/h, 100Pa, 0.5kW, 300oC in 2hrs | 4 | 4 | pcs | 17612370 | 923094.7 | 18535464.7 | 70449480 | 3692378.8 | 74141858.8 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | RDA500-9AA-7-7/36, Kruger/ Vietnam
|  | Wall mounted smoke exhaust FAN - SEAF @26500m3/h, 100Pa, 3kW, 300oC in 2hrs | 3 | 3 | pcs | 25306446 | 2241801.1 | 27548247.1 | 75919338 | 6725403.3 | 82644741.3 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | APN900-14AA-7-7/20, Kruger/ Vietnam
|  | Wall mounted smoke exhaust FAN - SEAF @16000m3/h, 100Pa, 1.5kW, 300oC in 2hrs | 4 | 4 | pcs | 16800960 | 2241801.1 | 19042761.1 | 67203840 | 8967204.4 | 76171044.4 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | APN630-12AA-7-7/32, Kruger/ Vietnam
|  | Cable power supply & conduit | [6 empty] | 97943721.9173 | 23281886.89 | 121225608.8073 |  |  | 0 |  |  | 0 | 11997546.1339 | 0 | 11997546.1339
|  | Cable Cu/Fr/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 1156 | 1281 | m | 60411.45 | 9350 | 69761.45 | 77387067.45 | 11977350 | 89364417.45 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D25 | 463 | 415 | m | 12762.0356 | 15805 | 28567.0356 | 5296244.7808 | 6559075 | 11855319.7808 | 80% |  | 0.8 |  |  | 0 | 4236995.8247 | 0 | 4236995.8247 | FPC25, Nano/ VN
|  | PVC flexible conduct D25 | 120 | 53.55 | m | 8113.63 | 5559 | 13672.63 | 434484.8865 | 297684.45 | 732169.3365 | 80% |  | 0.8 |  |  | 0 | 347587.9092 | 0 | 347587.9092 | Nano/ VN
|  | Accessories | 1 | 1 | lot | 14825924.8 | 4447777.44 | 19273702.24 | 14825924.8 | 4447777.44 | 19273702.24 | 50% |  | 0.5 |  |  | 0 | 7412962.4 | 0 | 7412962.4 | Vietnam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
3. |  | Office, Social and Technical Areas (Hall 3) | [6 empty] | 1272946321.0445 | 134316312.1879 | 1407262633.2324 |  |  | 0 |  |  | 0 | 22047224.0044 | 0 | 22047224.0044
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
3. 3. |  | Mechanical Engineering | [6 empty] | 1272946321.0445 | 134316312.1879 | 1407262633.2324 |  |  | 0 |  |  | 0 | 22047224.0044 | 0 | 22047224.0044
3. 3. 40. |  | Ventilation System | 1 | 1 | PSCH |  |  |  | 915624507.9952 | 94236583.2039 | 1009861091.1991 |  |  | 0 |  |  | 0 | 21336774.8612 | 0 | 21336774.8612
|  | Ground floor - west side | [6 empty] | 259524148.7256 | 33244549.9752 | 292768698.7008 |  |  | 0 |  |  | 0 | 2696279.6284 | 0 | 2696279.6284
|  | Equipments | [6 empty] | 32262384 | 3815280.7 | 36077664.7 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Exhaust air fan in-line centrifugal type (Q = 1240/620 m3/h, 220 Pa) | 1 | 1 | pcs | 7426788 | 923094.7 | 8349882.7 | 7426788 | 923094.7 | 8349882.7 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CCE 9-7T 4P-1 3SY, Kruger/ Vietnam
|  | Exhaust air fan in-line centrifugal type (Q = 460/230 m3/h, 200 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTD Silent 200/1, Kruger/ Vietnam
|  | Exhaust air fan in-line centrifugal type (Q = 680/340 m3/h, 200 Pa) | 1 | 1 | pcs | 4734816 | 495000 | 5229816 | 4734816 | 495000 | 5229816 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTD Silent 200/2, Kruger/ Vietnam
|  | Exhaust air fan in-line centrifugal type (Q = 550/275 m3/h, 180 Pa) | 2 | 2 | pcs | 4658448 | 495000 | 5153448 | 9316896 | 990000 | 10306896 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTD Silent 200/1, Kruger/ Vietnam
|  | Exhaust air fan in-line centrifugal type (Q = 120 m3/h, 120 Pa) | 1 | 1 | pcs | 4734816 | 495000 | 5229816 | 4734816 | 495000 | 5229816 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTD Silent 160, Kruger/ Vietnam
|  | Hanger support & Sub materials | 1 | 1 | lot | 1390620 | 417186 | 1807806 | 1390620 | 417186 | 1807806 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Air grille, louver | [6 empty] | 167427120 | 9290400 | 176717520 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Poppet Valves D160 | 3 | 3 | pcs | 1079160 | 84000 | 1163160 | 3237480 | 252000 | 3489480 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | LVS, Trox/ Germany
|  | Poppet Valves D100 | 43 | 43 | pcs | 921840 | 84000 | 1005840 | 39639120 | 3612000 | 43251120 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | LVS, Trox/ Germany
|  | Fresh air grille 500x200 | 18 | 18 | pcs | 1117800 | 140000 | 1257800 | 20120400 | 2520000 | 22640400 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | VAT-A//R1/S11/0/RAL9010, Trox/ Malaysia
|  | Exhaust air grille 200x200 | 1 | 1 | pcs | 797640 | 117600 | 915240 | 797640 | 117600 | 915240 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | VAT-A//R1/S11/0/RAL9010, Trox/ Malaysia
|  | Louver 200x200 + IS | 1 | 1 | pcs | 698280 | 117600 | 815880 | 698280 | 117600 | 815880 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AWK1//0/0/RAL9010, Trox/ Malaysia
|  | Louver 400x200 + IS | 1 | 1 | pcs | 844560 | 117600 | 962160 | 844560 | 117600 | 962160 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AWK1//0/0/RAL9010, Trox/ Malaysia
|  | Louver 400x250 + IS | 3 | 3 | pcs | 1073640 | 117600 | 1191240 | 3220920 | 352800 | 3573720 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AWK1//0/0/RAL9010, Trox/ Malaysia
|  | Louver 700x300 + IS | 1 | 1 | pcs | 2152800 | 140000 | 2292800 | 2152800 | 140000 | 2292800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AWK1//0/0/RAL9010, Trox/ Malaysia
|  | Volume control damper VCD D100 | 1 | 1 | pcs | 979800 | 84000 | 1063800 | 979800 | 84000 | 1063800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CBD, Trox/ Malaysia
|  | Volume control damper VCD D160 | 6 | 6 | pcs | 1208880 | 84000 | 1292880 | 7253280 | 504000 | 7757280 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CBD, Trox/ Malaysia
|  | Volume control damper VCD D200 | 1 | 1 | pcs | 1479360 | 84000 | 1563360 | 1479360 | 84000 | 1563360 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CBD, Trox/ Malaysia
|  | Volume control controller D160 | 1 | 1 | pcs | 2718600 | 84000 | 2802600 | 2718600 | 84000 | 2802600 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | BDD-A3-R/ Trox/ Malaysia
|  | Pressure release flap 345x400 | 2 | 2 | pcs | 30674640 | 280000 | 30954640 | 61349280 | 560000 | 61909280 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | ARK2-G/0, Trox/ Germany
|  | Silencer D120xL500 | 1 | 1 | pcs | 2368080 | 106400 | 2474480 | 2368080 | 106400 | 2474480 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CA50, Trox/ Malaysia
|  | Silencer D190xL500 | 6 | 6 | pcs | 3427920 | 106400 | 3534320 | 20567520 | 638400 | 21205920 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CA50, Trox/ Malaysia
|  | Ductwork sheet | [6 empty] | 59834644.7256 | 20138869.2752 | 79973514.0008 |  |  | 0 |  |  | 0 | 2696279.6284 | 0 | 2696279.6284
|  | Rigid duct Z8, thickness 0.58mm | 52 | 51.7 | m2 | 236291.3455 | 106400 | 342691.3455 | 12216262.56 | 5500880 | 17717142.56 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Z08- 0.58mmT/ Hoa Sen/ VN
|  | Insulation 6mmT | 57 | 55 | m2 | 104230.8 | 44800 | 149030.8 | 5732694 | 2464000 | 8196694 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Simili for fan | 12 | 12 | pcs | 90000 | 35000 | 125000 | 1080000 | 420000 | 1500000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Hanger support & Sub materials | 1 | 1 | lot | 15556006.38 | 4666801.914 | 20222808.294 | 15556006.38 | 4666801.914 | 20222808.294 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Cable power supply & conduit | [6 empty] | 25249681.7856 | 7087187.3612 | 32336869.1468 |  |  | 0 |  |  | 0 | 2696279.6284 | 0 | 2696279.6284
|  | Timer delay | 5 | 5 | pcs | 2875000 | 82500 | 2957500 | 14375000 | 412500 | 14787500 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Switch 1way - 1gang 10A-220V | 1 | 1 | m | 46800 | 54500 | 101300 | 46800 | 54500 | 101300 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KB31_1_WE_G19/ Schneider/ VN
|  | 3C-1.5mm2 Cu/XLPE/PVC | 330 | 308 | m | 22980.09 | 5743.9305 | 28724.0205 | 7077867.72 | 1769130.594 | 8846998.314 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC flexible conduct D20 | 9 | 9.9 | m | 3554.7229 | 5289.7059 | 8844.4288 | 35191.7569 | 52368.0882 | 87559.8451 | 80% |  | 0.8 |  |  | 0 | 28153.4055 | 0 | 28153.4055 | Vietnam
|  | PVC conduit D20 | 333 | 308 | m | 8773.9726 | 14594.0164 | 23367.989 | 2702383.5616 | 4494957.0548 | 7197340.6165 | 80% |  | 0.8 |  |  | 0 | 2161906.8493 | 0 | 2161906.8493 | FPC20, Nano/ VN
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 1012438.7471 | 303731.6241 | 1316170.3712 | 1012438.7471 | 303731.6241 | 1316170.3712 | 50% |  | 0.5 |  |  | 0 | 506219.3735 | 0 | 506219.3735 | Vietnam
|  | Ground floor - east side | [6 empty] | 540527596.8724 | 42856692.0376 | 583384288.91 |  |  | 0 |  |  | 0 | 17444464.0487 | 0 | 17444464.0487
|  | Equipments | [6 empty] | 41276280 | 4988745 | 46265025 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Exhaust air fan in-line centrifugal type (Q = 800/400 m3/h, 200 Pa) | 1 | 1 | pcs | 4734816 | 495000 | 5229816 | 4734816 | 495000 | 5229816 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTD Silent 200/2, Kruger/ Vietnam
|  | Exhaust air fan in-line centrifugal type (Q = 600/300 m3/h, 220 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTD Silent 200/2, Kruger/ Vietnam
|  | Exhaust air fan in-line centrifugal type (Q = 550/275 m3/h, 180 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTD Silent 200/1, Kruger/ Vietnam
|  | Exhaust air fan in-line centrifugal type (Q = 500 m3/h, 200 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTD Silent 200/1, Kruger/ Vietnam
|  | Exhaust air fan wall type (Q = 120 m3/h, 50 Pa) | 1 | 1 | pcs | 2324562 | 495000 | 2819562 | 2324562 | 495000 | 2819562 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | APM 200, Kruger/ Vietnam
|  | Exhaust air fan wall type (Q = 1210 m3/h, 50 Pa) | 4 | 4 | pcs | 4615602 | 495000 | 5110602 | 18462408 | 1980000 | 20442408 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | APL 315 4P-1 1S, Kruger/ Vietnam
|  | Hanger support & Sub materials | 1 | 1 | lot | 1779150 | 533745 | 2312895 | 1779150 | 533745 | 2312895 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Air grille, louver | [6 empty] | 429116520 | 10169600 | 439286120 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Poppet Valves D160 | 1 | 1 | pcs | 1079160 | 84000 | 1163160 | 1079160 | 84000 | 1163160 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | LVS, Trox/ Germany
|  | Poppet Valves D100 | 23 | 23 | pcs | 921840 | 84000 | 1005840 | 21202320 | 1932000 | 23134320 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | LVS, Trox/ Germany
|  | Fresh air grille 500x200 | 18 | 18 | pcs | 1117800 | 140000 | 1257800 | 20120400 | 2520000 | 22640400 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | VAT-A//R1/S11/0/RAL9010, Trox/ Malaysia
|  | Exhaust air grille 200x200 | 1 | 1 | pcs | 797640 | 117600 | 915240 | 797640 | 117600 | 915240 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | VAT-A//R1/S11/0/RAL9010, Trox/ Malaysia
|  | Exhaust air grille 500x200 + OBD | 13 | 13 | pcs | 1349640 | 140000 | 1489640 | 17545320 | 1820000 | 19365320 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | VAT-A//R1/S11/0/RAL9010, Trox/ Malaysia
|  | Louver 200x200 + IS | 1 | 1 | pcs | 698280 | 117600 | 815880 | 698280 | 117600 | 815880 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AWK1//0/0/RAL9010, Trox/ Malaysia
|  | Louver 400x250 + IS | 3 | 3 | pcs | 1073640 | 117600 | 1191240 | 3220920 | 352800 | 3573720 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AWK1//0/0/RAL9010, Trox/ Malaysia
|  | Louver 500x500 + IS | 4 | 4 | pcs | 2484000 | 140000 | 2624000 | 9936000 | 560000 | 10496000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AWK1//0/0/RAL9010, Trox/ Malaysia
|  | Louver 700x250 + IS | 1 | 1 | pcs | 2152800 | 140000 | 2292800 | 2152800 | 140000 | 2292800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AWK1//0/0/RAL9010, Trox/ Malaysia
|  | Volume control damper VCD D100 | 1 | 1 | pcs | 979800 | 84000 | 1063800 | 979800 | 84000 | 1063800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CBD, Trox/ Malaysia
|  | Volume control damper VCD D160 | 3 | 3 | pcs | 1208880 | 84000 | 1292880 | 3626640 | 252000 | 3878640 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CBD, Trox/ Malaysia
|  | Volume control controller D160 | 1 | 1 | pcs | 2718600 | 84000 | 2802600 | 2718600 | 84000 | 2802600 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | BDD-A3-R/ Trox/ Malaysia
|  | Pressure release flap 345x400 | 2 | 2 | pcs | 30674640 | 280000 | 30954640 | 61349280 | 560000 | 61909280 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | ARK2-G/0, Trox/ Germany
|  | Fire damper D250 | 2 | 2 | pcs | 21834360 | 140000 | 21974360 | 43668720 | 280000 | 43948720 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FKRS-EU-1/EN//Z43, Trox/ Germany
|  | Overflow air via fire protection flaps 400x250 | 3 | 3 | pcs | 75789600 | 280000 | 76069600 | 227368800 | 840000 | 228208800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FK2-EU/EN/AA/Z43RM, Trox/ Germany
|  | Silencer D120xL500 | 1 | 1 | pcs | 2368080 | 106400 | 2474480 | 2368080 | 106400 | 2474480 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CA50, Trox/ Malaysia
|  | Silencer D190xL500 | 3 | 3 | pcs | 3427920 | 106400 | 3534320 | 10283760 | 319200 | 10602960 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CA50, Trox/ Malaysia
|  | Ductwork sheet | [6 empty] | 42937395.394 | 15270557.0262 | 58207952.4202 |  |  | 0 |  |  | 0 | 13013328.377 | 0 | 13013328.377
|  | Rigid duct Z8, thickness 0.58mm | 44 | 46.2 | m2 | 236291.3455 | 106400 | 342691.3455 | 10916660.16 | 4915680 | 15832340.16 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Z08- 0.58mmT/ Hoa Sen/ VN
|  | Insulation 6mmT | 50 | 50.6 | m2 | 104230.8 | 44800 | 149030.8 | 5274078.48 | 2266880 | 7540958.48 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Simili for fan | 8 | 8 | pcs | 90000 | 35000 | 125000 | 720000 | 280000 | 1000000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Hanger support & Sub materials | 1 | 1 | lot | 26026656.754 | 7807997.0262 | 33834653.7802 | 26026656.754 | 7807997.0262 | 33834653.7802 | 50% |  | 0.5 |  |  | 0 | 13013328.377 | 0 | 13013328.377
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Cable power supply & conduit | [6 empty] | 27197401.4784 | 12427790.0114 | 39625191.4898 |  |  | 0 |  |  | 0 | 4431135.6717 | 0 | 4431135.6717
|  | Timer delay | 2 | 2 | pcs | 2875000 | 82500 | 2957500 | 5750000 | 165000 | 5915000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Switch 1way - 1gang 10A-220V | 1 | 1 | m | 46800 | 54500 | 101300 | 46800 | 54500 | 101300 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KB31_1_WE_G19/ Schneider/ VN
|  | Contactor + Box | 3 | 3 | m | 900000 | 163500 | 1063500 | 2700000 | 490500 | 3190500 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | A9C20731,Schneider/ VN
|  | 3C-1.5mm2 Cu/XLPE/PVC | 495 | 495 | m | 22980.09 | 5743.9305 | 28724.0205 | 11375144.55 | 2843245.5975 | 14218390.1475 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 2C-1.5mm2 Cu/PVC/PVC | 90 | 90 | m | 15443.88 | 5031.18 | 20475.06 | 1389949.2 | 452806.2 | 1842755.4 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC flexible conduct D20 | 14 | 14.7 | m | 3554.7229 | 5289.7059 | 8844.4288 | 52254.4269 | 77758.6765 | 130013.1034 | 80% |  | 0.8 |  |  | 0 | 41803.5415 | 0 | 41803.5415 | Vietnam
|  | PVC conduit D16 | 495 |  | m | 6646.8692 | 13183.4282 | 19830.2974 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC16, Nano/ VN
|  | PVC conduit D20 | 498 | 550 | m | 8773.9726 | 14594.0164 | 23367.989 | 4825684.9315 | 8026709.0265 | 12852393.958 | 80% |  | 0.8 |  |  | 0 | 3860547.9452 | 0 | 3860547.9452 | FPC20, Nano/ VN
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 1057568.3699 | 317270.511 | 1374838.8809 | 1057568.3699 | 317270.511 | 1374838.8809 | 50% |  | 0.5 |  |  | 0 | 528784.185 | 0 | 528784.185
|  | Fist floor - west side | [6 empty] | 95572762.3972 | 15135341.1911 | 110708103.5883 |  |  | 0 |  |  | 0 | 1196031.1841 | 0 | 1196031.1841
|  | Equipments | [6 empty] | 19632768 | 2233872 | 21866640 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Exhaust air fan in-line centrifugal type (Q = 830/415 m3/h, 150 Pa) | 2 | 2 | pcs | 4734816 | 495000 | 5229816 | 9469632 | 990000 | 10459632 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTD Silent 200/2, Kruger/ Vietnam
|  | Exhaust air fan in-line centrifugal type (Q = 480/240 m3/h, 150 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTD Silent 200/1, Kruger/ Vietnam
|  | Exhaust air fan in-line centrifugal type (Q = 420/210 m3/h, 150 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTD Silent 200/1, Kruger/ Vietnam
|  | Hanger support & Sub materials | 1 | 1 | lot | 846240 | 253872 | 1100112 | 846240 | 253872 | 1100112 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Air grille, louver | [6 empty] | 47615520 | 2996000 | 50611520 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Poppet Valves D100 | 15 | 15 | pcs | 921840 | 84000 | 1005840 | 13827600 | 1260000 | 15087600 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | LVS, Trox/ Germany
|  | Louver 700x250 + IS | 2 | 2 | pcs | 2152800 | 140000 | 2292800 | 4305600 | 280000 | 4585600 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AWK1//0/0/RAL9010, Trox/ Malaysia
|  | Louver 400x200 + IS | 2 | 2 | pcs | 844560 | 117600 | 962160 | 1689120 | 235200 | 1924320 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AWK1//0/0/RAL9010, Trox/ Malaysia
|  | Exhaust air grille EAG-600x600 | 2 | 2 | pcs | 3960600 | 140000 | 4100600 | 7921200 | 280000 | 8201200 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | VAT-A//R1/S11/0/RAL9010, Trox/ Malaysia
|  | Supply air grille EAG-300x300 | 8 | 8 | pcs | 2484000 | 117600 | 2601600 | 19872000 | 940800 | 20812800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | DLQ-A, Trox/ Malaysia
|  | Ductwork sheet | [6 empty] | 12042039.2045 | 4956818.7105 | 16998857.915 |  |  | 0 |  |  | 0 | 1196031.1841 | 0 | 1196031.1841
|  | Rigid duct Z8, thickness 0.58mm | 25 | 25 | m2 | 236291.3455 | 106400 | 342691.3455 | 5907283.6364 | 2660000 | 8567283.6364 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Z08- 0.58mmT/ Hoa Sen/ VN
|  | Insulation 6mmT | 29 | 29 | m2 | 104230.8 | 44800 | 149030.8 | 3022693.2 | 1299200 | 4321893.2 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Simili for fan | 8 | 8 | pcs | 90000 | 35000 | 125000 | 720000 | 280000 | 1000000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Hanger support & Sub materials | 1 | 1 | lot | 2392062.3682 | 717618.7105 | 3109681.0786 | 2392062.3682 | 717618.7105 | 3109681.0786 | 50% |  | 0.5 |  |  | 0 | 1196031.1841 | 0 | 1196031.1841
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Cable power supply & conduit | [6 empty] | 16282435.1926 | 4948650.4806 | 21231085.6733 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Timer delay | 3 | 3 | pcs | 2875000 | 82500 | 2957500 | 8625000 | 247500 | 8872500 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | 3C-1.5mm2 Cu/XLPE/PVC | 220 | 220 | m | 22980.09 | 5743.9305 | 28724.0205 | 5055619.8 | 1263664.71 | 6319284.51 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 220 | 220 | m | 8773.9726 | 14594.0164 | 23367.989 | 1930273.9726 | 3210683.6106 | 5140957.5832 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | PVC flexible conduct D20 | 6 | 6 | m | 3554.7229 | 5289.7059 | 8844.4288 | 21328.3375 | 31738.2353 | 53066.5728 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Nano/ VN
|  | Accessories | 1 | 1 | lot | 650213.0825 | 195063.9248 | 845277.0073 | 650213.0825 | 195063.9248 | 845277.0073 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Fist floor - esat side | [6 empty] | 20000000 | 3000000 | 23000000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Equipments | [6 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Exhaust air fan in-line centrifugal type (Q = 440/220m3/h, 150 Pa) | 3 |  | pcs | 4658448 | 495000 | 5153448 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTD Silent 200/1, Kruger/ Vietnam
|  | Hanger support & Sub materials | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Air grille, louver | [6 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Poppet Valves D220 | 4 |  | pcs | 1484880 | 84000 | 1568880 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | LVS, Trox/ Germany
|  | Poppet Valves D100 | 19 |  | pcs | 921840 | 84000 | 1005840 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | LVS, Trox/ Germany
|  | Louver 400x200 + IS | 3 |  | pcs | 844560 | 117600 | 962160 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AWK1//0/0/RAL9010, Trox/ Malaysia
|  | Volume control damper VCD D100 | 1 |  | pcs | 979800 | 84000 | 1063800 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CBD, Trox/ Malaysia
|  | Volume control damper VCD D160 | 2 |  | pcs | 1208880 | 84000 | 1292880 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CBD, Trox/ Malaysia
|  | Supply air grille EAG-300x300 | 4 |  | pcs | 2484000 | 117600 | 2601600 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | DLQ-A, Trox/ Malaysia
|  | Silencer D120xL500 | 1 |  | pcs | 2368080 | 106400 | 2474480 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CA50, Trox/ Malaysia
|  | Silencer D190xL500 | 2 |  | pcs | 3427920 | 106400 | 3534320 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CA50, Trox/ Malaysia
|  | Ductwork sheet | [6 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Rigid duct Z8, thickness 0.58mm | 18 |  | m2 | 236291.3455 | 106400 | 342691.3455 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Z08- 0.58mmT/ Hoa Sen/ VN
|  | Insulation 6mmT | 22 |  | m2 | 104230.8 | 44800 | 149030.8 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Simili for fan | 6 |  | pcs | 90000 | 35000 | 125000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Hanger support & Sub materials | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Cable power supply & conduit | [6 empty] | 20000000 | 3000000 | 23000000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Timer delay | 2 |  | pcs | 2875000 | 82500 | 2957500 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | 3C-1.5mm2 Cu/XLPE/PVC | 165 |  | m | 22980.09 | 5743.9305 | 28724.0205 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 165 |  | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | PVC flexible conduct D20 | 6 |  | m | 3554.7229 | 5289.7059 | 8844.4288 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Nano/ VN
|  | Fire stop | 3 | 1 | lot | 20000000 | 3000000 | 23000000 | 20000000 | 3000000 | 23000000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam(Tính chung cho toàn hệ thống)
|  | Accessories | 1 |  | lot | 1000000 | 300000 | 1300000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
3. 3. 50. |  | Ventilation System 1st Floor Offices Ventilation Units | 1 | 1 | PSCH |  |  |  | 84938287.2586 | 5889562.8377 | 90827850.0963 |  |  | 0 |  |  | 0 | 710449.1432 | 0 | 710449.1432
|  | west side | 0 | 0 |  |  |  | 0 | 84938287.2586 | 5889562.8377 | 90827850.0963 |  |  | 0 |  |  | 0 | 710449.1432 | 0 | 710449.1432
|  | Equipments | [6 empty] | 80634445.35 | 3616553.635 | 84250998.985 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Heat Recovery Ventilation 390 m3/h | 1 | 1 | pcs | 19802999.7 | 1064000 | 20866999.7 | 19802999.7 | 1064000 | 20866999.7 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | LZ-H050GBA4, LG/ Korea
|  | Heat Recovery Ventilation 2000 m3/h | 1 | 1 | pcs | 54096000.2 | 1400000 | 55496000.2 | 54096000.2 | 1400000 | 55496000.2 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | LZ-H200GBA4, LG/ Korea
|  | Remote wirring for ERV | 2 | 2 | pcs | 1614800 | 50400 | 1665200 | 3229600 | 100800 | 3330400 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | PREMTB001 / LG/Korea
|  | Hanger support & Accessories | 1 | 1 | lot | 3505845.45 | 1051753.635 | 4557599.085 | 3505845.45 | 1051753.635 | 4557599.085 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Cable power supply & conduit | [6 empty] | 4303841.9086 | 2273009.2027 | 6576851.1113 |  |  | 0 |  |  | 0 | 710449.1432 | 0 | 710449.1432
|  | 3C-2.5mm2 Cu/XLPE/PVC | 100 | 100 | m | 32518.74 | 7485.665 | 40004.405 | 3251874 | 748566.5 | 4000440.5 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 100 | 100 | m | 8773.9726 | 14594.0164 | 23367.989 | 877397.2603 | 1459401.6412 | 2336798.9015 | 80% |  | 0.8 |  |  | 0 | 701917.8082 | 0 | 701917.8082 | FPC20, Nano/ VN
|  | PVC flexible conduct D20 | 3 | 3 | m | 3554.7229 | 5289.7059 | 8844.4288 | 10664.1688 | 15869.1176 | 26533.2864 | 80% |  | 0.8 |  |  | 0 | 8531.335 | 0 | 8531.335 | Nano/ VN
|  | PVC conduit D20 | 3 |  | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 | 80% |  | 0.8 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 163906.4796 | 49171.9439 | 213078.4235 | 163906.4796 | 49171.9439 | 213078.4235 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
3. 3. 60. |  | Ventilation System 1st Floor Offices Ducting | 1 | 1 | PSCH |  |  |  | 272383525.7906 | 34190166.1463 | 306573691.937 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | west side | 0 | 0 |  |  |  | 0 | 272383525.7906 | 34190166.1463 | 306573691.937 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Equipments | [6 empty] | 262643773.8955 | 29033956.5687 | 291677730.4642 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Exhaust air fan in-line centrifugal type (Q = 2000m3/h, 300 Pa) | 2 | 2 | pcs | 7379058 | 923094.7 | 8302152.7 | 14758116 | 1846189.4 | 16604305.4 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CCE 9-9 4P-1 3SY, Kruger/ Vietnam
|  | Duct smoke detector | 4 | 4 | pcs | 4140000 | 128800 | 4268800 | 16560000 | 515200 | 17075200 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | SL-2000-P, Apollo/ USA
|  | Rigid duct Z8, thickness 0.58mm | 132 | 132 | m2 | 236291.3455 | 106400 | 342691.3455 | 31190457.6 | 14044800 | 45235257.6 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Z08- 0.58mmT/ Hoa Sen/ VN
|  | Insulation 16mmT | 142 | 143 | m2 | 207754.8 | 44800 | 252554.8 | 29708936.4 | 6406400 | 36115336.4 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Supply air grill 300x300 | 6 | 6 | pcs | 2484000 | 117600 | 2601600 | 14904000 | 705600 | 15609600 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | DLQ-A, Trox/ Malaysia
|  | Supply air grill 600x600 | 3 | 3 | pcs | 3960600 | 140000 | 4100600 | 11881800 | 420000 | 12301800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | DLQ-A, Trox/ Malaysia
|  | Exhaust air grill 600x600 | 5 | 5 | pcs | 3960600 | 140000 | 4100600 | 19803000 | 700000 | 20503000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | VAT-A//R1/S11/0/RAL9010, Trox/ Malaysia
|  | Louver 400x200 + IS | 2 | 2 | pcs | 844560 | 117600 | 962160 | 1689120 | 235200 | 1924320 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AWK1//0/0/RAL9010, Trox/ Malaysia
|  | Louver 900x400 + IS | 2 | 2 | pcs | 3759120 | 140000 | 3899120 | 7518240 | 280000 | 7798240 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AWK1//0/0/RAL9010, Trox/ Malaysia
|  | Siliencer D240xL1000 | 2 | 2 | pcs | 6668160 | 106400 | 6774560 | 13336320 | 212800 | 13549120 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CA50, Trox/ Malaysia
|  | Siliencer D300xL800 | 6 | 6 | pcs | 7998480 | 106400 | 8104880 | 47990880 | 638400 | 48629280 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CA50, Trox/ Malaysia
|  | Siliencer D420XL1000 | 4 | 4 | pcs | 11155920 | 106400 | 11262320 | 44623680 | 425600 | 45049280 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CA50, Trox/ Malaysia
|  | Hanger support & Accessories | 1 | 1 | lot | 8679223.8955 | 2603767.1687 | 11282991.0642 | 8679223.8955 | 2603767.1687 | 11282991.0642 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Cable power supply & conduit | [6 empty] | 9739751.8951 | 5156209.5777 | 14895961.4728 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Switch 1way - 2gang 10A-220V | 1 | 1 | m | 46800 | 54500 | 101300 | 46800 | 54500 | 101300 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KB31_WE/ Schneider/ VN
|  | Contactor + Box | 4 | 4 | m | 900000 | 163500 | 1063500 | 3600000 | 654000 | 4254000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | A9C20731,Schneider/ VN
|  | 3C-2.5mm2 Cu/XLPE/PVC | 80 | 79.2 | m | 32518.74 | 7485.665 | 40004.405 | 2575484.208 | 592864.668 | 3168348.876 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 2C-1.5mm2 Cu/PVC/PVC | 80 | 79.2 | m | 15443.88 | 5031.18 | 20475.06 | 1223155.296 | 398469.456 | 1621624.752 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 76 | 160 | m | 8773.9726 | 14594.0164 | 23367.989 | 1403835.6164 | 2335042.6259 | 3738878.2423 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | PVC flexible conduct D20 | 3 | 3 | m | 3554.7229 | 5289.7059 | 8844.4288 | 10664.1688 | 15869.1176 | 26533.2864 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Nano/ VN
|  | PVC conduit D20 | 3 | 3 | m | 8773.9726 | 14594.0164 | 23367.989 | 26321.9178 | 43782.0492 | 70103.967 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | PVC conduit D16 | 72 | 72 | m | 6646.8692 | 13183.4282 | 19830.2974 | 478574.5808 | 949206.8287 | 1427781.4095 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC16, Nano/ VN
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 374916.1073 | 112474.8322 | 487390.9395 | 374916.1073 | 112474.8322 | 487390.9395 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
3. 3. 130. |  | SMOKE EXHAUST SYSTEM | [6 empty] | 143640024.0078 | 24229831.2332 | 167869855.241 |  |  | 0 |  |  | 0 | 6864379.726 | 0 | 6864379.726
|  | WEST SIDE | [6 empty] | 32042422.6672 | 2927603.7911 | 34970026.4583 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Equipment | [6 empty] | 26144496 | 990000 | 27134496 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Wall mounted smoke exhaust FAN - SEAF @11550m3/h, 100Pa, 1.5kW, 300oC in 2hrs | 2 | 2 | pcs | 13072248 | 495000 | 13567248 | 26144496 | 990000 | 27134496 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | APN560-9AA-5-5/22, Kruger/ Vietnam
|  | Cable power supply & conduit | [6 empty] | 5897926.6672 | 1937603.7911 | 7835530.4583 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Cable Cu/Fr/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 70 | 66 | m | 60411.45 | 9350 | 69761.45 | 3987155.7 | 617100 | 4604255.7 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 63 | 60 | m | 8773.9726 | 14594.0164 | 23367.989 | 526438.3562 | 875640.9847 | 1402079.3409 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | PVC flexible conduct D20 | 7 | 7 | m | 3554.7229 | 5289.7059 | 8844.4288 | 24883.0604 | 37027.9412 | 61911.0016 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Nano/ VN
|  | Accessories | 1 | 1 | lot | 1359449.5506 | 407834.8652 | 1767284.4158 | 1359449.5506 | 407834.8652 | 1767284.4158 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | EAST SIDE | [6 empty] | 111597601.3406 | 21302227.4421 | 132899828.7827 |  |  | 0 |  |  | 0 | 6864379.726 | 0 | 6864379.726
|  | Equipment | [6 empty] | 23339970 | 2769284.1 | 26109254.1 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | AXIAL Smoke exhaust FAN - SEAF @7320m3/h, 180Pa, 1.25kW, 300oC in 2hrs | 3 | 3 | pcs | 7779990 | 923094.7 | 8703084.7 | 23339970 | 2769284.1 | 26109254.1 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TDA400-9AA-5-5/28, Kruger/ Vietnam
|  | Hanger support & Sub materials | 1 | 1 | lot | 1051350 | 315405 | 1366755 | 1051350 | 315405 | 1366755 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Air grille, louver | [6 empty] | 23084640 | 840000 | 23924640 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Smoke Exhaust grille 1200x600 + OBD | 3 | 3 | pcs | 3281640 | 140000 | 3421640 | 9844920 | 420000 | 10264920 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AT-AG/R1/S11/0/RAL9010, Trox/ Malaysia
|  | Louver 1000x400 + IS | 3 | 3 | pcs | 4413240 | 140000 | 4553240 | 13239720 | 420000 | 13659720 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | WGK-AL-1/ ER/P1/RAL9010, Trox/ Malaysia
|  | Ductwork sheet | [6 empty] | 48893376.2182 | 12696041.9127 | 61589418.1309 |  |  | 0 |  |  | 0 | 4738069.8545 | 0 | 4738069.8545
|  | Rigid duct Z8, thickness 0.58mm | 47 | 42 | m2 | 236291.3455 | 106400 | 342691.3455 | 9924236.5091 | 4468800 | 14393036.5091 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Z08- 0.58mmT/ Hoa Sen/ VN
|  | Rockwool 50mmT | 36 | 36 | m2 | 408250 | 61600 | 469850 | 14697000 | 2217600 | 16914600 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Dragon rock wool/ Vietnam
|  | Fireproof paint for smoke duct | 33 | 33 | m2 | 432000 | 89600 | 521600 | 14256000 | 2956800 | 17212800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FLAMEBAR BW11, UK or MALAYSIA
|  | Simili for fan | 6 | 6 | pcs | 90000 | 35000 | 125000 | 540000 | 210000 | 750000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Hanger support & Sub materials | 1 | 1 | lot | 9476139.7091 | 2842841.9127 | 12318981.6218 | 9476139.7091 | 2842841.9127 | 12318981.6218 | 50% |  | 0.5 |  |  | 0 | 4738069.8545 | 0 | 4738069.8545 | Vietnam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Cable power supply & conduit | [6 empty] | 15228265.1224 | 4681496.4294 | 19909761.5518 |  |  | 0 |  |  | 0 | 2126309.8715 | 0 | 2126309.8715
|  | Cable Cu/Fr/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 195 | 195 | m | 60411.45 | 9350 | 69761.45 | 11780232.75 | 1823250 | 13603482.75 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 176 | 150 | m | 8773.9726 | 14594.0164 | 23367.989 | 1316095.8904 | 2189102.4618 | 3505198.3522 | 80% |  | 0.8 |  |  | 0 | 1052876.7123 | 0 | 1052876.7123 | FPC20, Nano/ VN
|  | PVC flexible conduct D20 | 7 | 7 | m | 3554.7229 | 5289.7059 | 8844.4288 | 24883.0604 | 37027.9412 | 61911.0016 | 80% |  | 0.8 |  |  | 0 | 19906.4484 | 0 | 19906.4484 | Nano/ VN
|  | Accessories | 1 | 1 | lot | 2107053.4216 | 632116.0265 | 2739169.448 | 2107053.4216 | 632116.0265 | 2739169.448 | 50% |  | 0.5 |  |  | 0 | 1053526.7108 | 0 | 1053526.7108 | Vietnam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
4. |  | Machine hook-up (Hall 3) | [6 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
5. |  | Scooter Garage | [6 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
6. |  | Canteen | [6 empty] | 435189667.08 | 72472708.1683 | 507662375.2483 |  |  | 0 |  |  | 0 | 334665000 | 0 | 334665000
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
6. 3. 60. |  | Ventilation System Overhead Fans | 1 | 1 | PSCH |  |  |  | 413174538.3791 | 66328606.8362 | 479503145.2154 |  |  | 0 |  |  | 0 | 334665000 | 0 | 334665000
|  | Overhead Propeller Fans, D=3m | 10 | 10 | pcs | 37185000 | 4950000 | 42135000 | 371850000 | 49500000 | 421350000 | 90% |  | 0.9 |  |  | 0 | 334665000 | 0 | 334665000 | HVLS-3DC, HVLS/ China
|  | 3C-2.5mm2 Cu/XLPE/PVC | 250 | 245 | m | 32518.74 | 7485.665 | 40004.405 | 7967091.3 | 1833987.925 | 9801079.225 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | Control Cable Cu/PVC 2cx1.5mm2 | 450 | 350 | m | 15443.88 | 5031.18 | 20475.06 | 5405358 | 1760913 | 7166271 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 515 | 400 | m | 8773.9726 | 14594.0164 | 23367.989 | 3509589.0411 | 5837606.5647 | 9347195.6058 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | PVC flexible conduct D20 | 20 | 15 | m | 3554.7229 | 5289.7059 | 8844.4288 | 53320.8438 | 79345.5882 | 132666.432 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Hanger, support | 1 | 1 | lot | 10452505.369 | 3135751.6107 | 13588256.9797 | 10452505.369 | 3135751.6107 | 13588256.9797 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Accessories | 1 | 1 | lot | 13936673.8253 | 4181002.1476 | 18117675.9729 | 13936673.8253 | 4181002.1476 | 18117675.9729 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
6. 3. 70. |  | Ventilation System | 1 | 1 | PSCH |  |  |  | 22015128.7008 | 6144101.3321 | 28159230.0329 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Exhaust air fan Q=100m3/h, 50Pa, type wall | 2 | 2 | pcs | 2324562 | 495000 | 2819562 | 4649124 | 990000 | 5639124 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | APM 200, Kruger/ Vietnam
|  | Exhaust air fan Q=140m3/h, 50Pa, type wall | 1 | 1 | pcs | 2324562 | 495000 | 2819562 | 2324562 | 495000 | 2819562 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | APM 200, Kruger/ Vietnam
|  | Exhaust air fan Q=180m3/h, 50Pa, type wall | 1 | 1 | pcs | 2324562 | 495000 | 2819562 | 2324562 | 495000 | 2819562 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | APM 200, Kruger/ Vietnam
|  | Exhaust air fan Q=300m3/h, 50Pa, type wall | 1 | 1 | pcs | 2735040 | 495000 | 3230040 | 2735040 | 495000 | 3230040 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | APM 250, Kruger/ Vietnam
|  | Louver 250x250 + IS | 5 | 5 | pcs | 897000 | 117600 | 1014600 | 4485000 | 588000 | 5073000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AWK1//0/0/RAL9010, Trox/ Malaysia
|  | Switch 1way - 1gang 10A-250V | 5 | 5 | pcs | 46800 | 54500 | 101300 | 234000 | 272500 | 506500 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KB31_1_WE_G19/ Schneider/ VN
|  | 3C-1.5mm2 Cu/XLPE/PVC | 111 | 109.25 | m | 22980.09 | 5743.9305 | 28724.0205 | 2510574.8325 | 627524.4071 | 3138099.2396 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC flexible conduct D20 | 8 | 11.5 | m | 3554.7229 | 5289.7059 | 8844.4288 | 40879.3136 | 60831.6176 | 101710.9312 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | PVC conduit D20 | 119 | 109.25 | m | 8773.9726 | 14594.0164 | 23367.989 | 958556.5068 | 1594396.293 | 2552952.7998 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | Hanger, support, Accessories | 1 | 1 | lot | 1752830.0479 | 525849.0144 | 2278679.0623 | 1752830.0479 | 525849.0144 | 2278679.0623 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | TOTAL AMOUNT (Not included VAT) | [6 empty] | 2727932681.6538 | 476780724.8683 | 3204713406.5221 | [6 empty] | 407720118.3127 | 0 | 407720118.3127
3. |  | Office, Social and Technical Areas (Hall 3) | [6 empty] | 1992902350.6879 | 211748078.3635 | 2204650429.0514 | [6 empty] | 20593863.5681 | 0 | 20593863.5681
3. 3. 70. |  | Air Conditioning | 1 | 1 | PSCH |  |  |  | 1992902350.6879 | 211748078.3635 | 2204650429.0514 |  |  | 0 |  |  | 0 | 20593863.5681 | 0 | 20593863.5681
|  | west side | [6 empty] | 1284913905.8615 | 131256535.4444 | 1416170441.3058 |  |  | 0 |  |  | 0 | 13168730.4268 | 0 | 13168730.4268
|  | Equipments | [6 empty] | 1094815450 | 55012677.04 | 1149828127.04 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Outdoor unit 56KW | 1 | 1 | pcs | 109143100 | 4434383.52 | 113577483.52 | 109143100 | 4434383.52 | 113577483.52 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM200MXVAGC/TS, SamSung/ China
|  | Outdoor unit 50.4KW | 1 | 1 | pcs | 102932500 | 4434383.52 | 107366883.52 | 102932500 | 4434383.52 | 107366883.52 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM180MXVAGC/TS, SamSung/ China
|  | Outdoor unit 40KW | 1 | 1 | pcs | 72590100 | 3920000 | 76510100 | 72590100 | 3920000 | 76510100 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM140TXMDNC/EA, SamSung/ China
|  | Outdoor unit 33.6KW | 1 | 1 | pcs | 62381000 | 3920000 | 66301000 | 62381000 | 3920000 | 66301000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM120TXMDNC/EA, SamSung/ China
|  | Outdoor unit 14KW | 1 | 1 | pcs | 30222170 | 840000 | 31062170 | 30222170 | 840000 | 31062170 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM050TXMDNC/EA, SamSung/ China
|  | Indoor unit cassette type, 9.0kW | 6 | 6 | pcs | 9845660 | 537600 | 10383260 | 59073960 | 3225600 | 62299560 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM090NN4DEH/EU+PC4NUFMAN, SamSung/ Korea
|  | Indoor unit cassette type, 7.1kW | 11 | 11 | pcs | 9569780 | 537600 | 10107380 | 105267580 | 5913600 | 111181180 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM071NN4DEH/EU+PC4NUFMAN, SamSung/ Korea
|  | Indoor unit cassette type, 6kW | 7 | 7 | pcs | 8741260 | 504000 | 9245260 | 61188820 | 3528000 | 64716820 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM060NNNDEH/EU+PC4SUFMAN, SamSung/ Korea
|  | Indoor unit cassette type, 5.6kW | 4 | 4 | pcs | 8464170 | 504000 | 8968170 | 33856680 | 2016000 | 35872680 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM056NNNDEH/EU+PC4SUFMAN, SamSung/ Korea
|  | Indoor unit cassette type, 3.6kW | 1 | 1 | pcs | 7911200 | 504000 | 8415200 | 7911200 | 504000 | 8415200 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM036NNNDEH/EU+PC4SUFMAN, SamSung/ Korea
|  | Split Air conditioner, indoor unit wall type, cooling capacity 4.5kW | 4 | 4 | pcs | 12599730 | 621600 | 13221330 | 50398920 | 2486400 | 52885320 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AR18TYAACWKNSV +AR18TYAACWKXSV, SamSung/ Thailand
|  | Split Air conditioner, indoor unit wall type, cooling capacity 6.3kW | 2 | 2 | pcs | 16773020 | 733600 | 17506620 | 33546040 | 1467200 | 35013240 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AR24TYHYCWKNSV +AR24TYHYCWKXSV, SamSung/ Thailand
|  | Split Air conditioner, indoor unit wall type, cooling capacity 7.1kW | 1 | 1 | pcs | 31227680 | 733600 | 31961280 | 31227680 | 733600 | 31961280 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AR28TYHYCWKNSV +AR28TYHYCWKXSV, SamSung/ Thailand
|  | Dehumidifiers 1200m3/h | 6 | 6 | pcs | 19690000 | 168000 | 19858000 | 118140000 | 1008000 | 119148000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | DID-150/ Decker/Vietnam
|  | Controller center for AC | 1 | 1 | pcs | 11532400 | 168000 | 11700400 | 11532400 | 168000 | 11700400 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MCM-A300N, SamSung/ Korea
|  | Remote wirring for AC | 36 | 36 | pcs | 1614800 | 50400 | 1665200 | 58132800 | 1814400 | 59947200 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MWR-WG00JN / SamSung/ Korea
|  | Controller for AC Split (IT Room, UPS room) | 2 | 2 | pcs | 873400 | 140000 | 1013400 | 1746800 | 280000 | 2026800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MIM-A00N+DB93-17178A , SamSung/ Korea
|  | DB controller | 1 | 1 | pcs | 13200000 | 280000 | 13480000 | 13200000 | 280000 | 13480000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | VN
|  | Gas splitter | 16 | 44 | pcs | 1815000 | 0 | 1815000 | 79860000 | 0 | 79860000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | SamSung/ Korea
|  | Concrete base for outdoor unit | 5 | 5 | pcs | 1300000 | 500000 | 1800000 | 6500000 | 2500000 | 9000000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Extra refrigerant charge R410a or R32 | 1 | 1 | lot | 7500000 | 0 | 7500000 | 7500000 | 0 | 7500000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Hanger support & Sub materials | 1 | 1 | lot | 38463700 | 11539110 | 50002810 | 38463700 | 11539110 | 50002810 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Copper pipe | [6 empty] | 67284685.7759 | 24357916.6293 | 91642602.4052 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Ø6.4mm-0.81mmT | 78 | 112.7 | m | 38160 | 22400 | 60560 | 4300632 | 2524480 | 6825112 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
|  | Ø9.5mm-0.81mmT | 249 | 203.55 | m | 60000 | 23520 | 83520 | 12213000 | 4787496 | 17000496 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
|  | Ø12.7mm-0.81mmT | 90 | 119.6 | m | 81840 | 28000 | 109840 | 9788064 | 3348800 | 13136864 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
|  | Ø15.9mm-0.81mmT | 262 | 210.45 | m | 103760 | 38808 | 142568 | 21836292 | 8167143.6 | 30003435.6 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
|  | Ø19.1mm-0.81mmT | 0 | 0 | m | 129600 | 42560 | 172160 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
|  | Ø22.2mm-0.81mmT | 18 | 27.6 | m | 147310.3448 | 49392 | 196702.3448 | 4065765.5172 | 1363219.2 | 5428984.7172 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
|  | Ø28.6mm-1.0mmT | 54 | 52.9 | m | 234206.8966 | 63504 | 297710.8966 | 12389544.8276 | 3359361.6 | 15748906.4276 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
|  | Hanger support & Accessories | 1 | 1 | lot | 2691387.431 | 807416.2293 | 3498803.6603 | 2691387.431 | 807416.2293 | 3498803.6603 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Insulation copper pipe | [6 empty] | 14380586.125 | 5959615.4335 | 20340201.5585 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Ø6.4mm-15mmT | 78 | 112.7 | m | 15358.8 | 5600 | 20958.8 | 1730936.76 | 631120 | 2362056.76 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Ø9.5mm-15mmT | 249 | 203.55 | m | 16754.4 | 5644.8 | 22399.2 | 3410358.12 | 1148999.04 | 4559357.16 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Ø12.7mm-15mmT | 90 | 119.6 | m | 17871.6 | 7728 | 25599.6 | 2137443.36 | 924268.8 | 3061712.16 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Ø15.9mm-15mmT | 262 | 210.45 | m | 20664 | 9172.8 | 29836.8 | 4348738.8 | 1930415.76 | 6279154.56 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Ø19.1mm-15mmT | 0 | 0 | m | 23176.8 | 101595.2 | 124772 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Ø22.2mm-15mmT | 18 | 27.6 | m | 24852 | 11995.2 | 36847.2 | 685915.2 | 331067.52 | 1016982.72 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Ø28.6mm-15mmT | 54 | 52.9 | m | 28203.6 | 15523.2 | 43726.8 | 1491970.44 | 821177.28 | 2313147.72 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Accessories | 1 | 1 | lot | 575223.445 | 172567.0335 | 747790.4785 | 575223.445 | 172567.0335 | 747790.4785 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Condensate pipe | [6 empty] | 3756725.28 | 3113650.848 | 6870376.128 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | uPVC-Ø27mm-PN12 | 124 | 127.6 | m | 8236.8 | 11743.2 | 19980 | 1051015.68 | 1498432.32 | 2549448 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN, Ø34 2.1mm, PN12.5
|  | uPVC-Ø34mm-PN12 | 59 | 72.6 | m | 16286.4 | 12639.2 | 28925.6 | 1182392.64 | 917605.92 | 2099998.56 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN, Ø34 2.1mm, PN12.5
|  | uPVC-Ø42mm-PN12 | 33 | 29.7 | m | 21528 | 14560 | 36088 | 639381.6 | 432432 | 1071813.6 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN, Ø42 2.1mm, PN12
|  | Fitting for UpVC | 1 | 1 | lot | 662951.52 | 198885.456 | 861836.976 | 662951.52 | 198885.456 | 861836.976 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Hanger support & Accessories | 1 | 1 | lot | 220983.84 | 66295.152 | 287278.992 | 220983.84 | 66295.152 | 287278.992 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Insulation condensate pipe | 0 | 0 |  |  |  |  | 3118303.375 | 3148490.6805 | 6266794.0555 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Ø27mm-10mmT | 124 | 127.6 | m | 11169.6 | 11743.2 | 22912.8 | 1425240.96 | 1498432.32 | 2923673.28 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Ø34mm-10mmT | 59 | 72.6 | m | 14520 | 15523.2 | 30043.2 | 1054152 | 1126984.32 | 2181136.32 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Ø42mm-10mmT | 33 | 29.7 | m | 17312.4 | 16352 | 33664.4 | 514178.28 | 485654.4 | 999832.68 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Accessories | 1 | 1 | lot | 124732.135 | 37419.6405 | 162151.7755 | 124732.135 | 37419.6405 | 162151.7755 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Cable power supply & conduit | [6 empty] | 101558155.3056 | 39664184.8131 | 141222340.1186 |  |  | 0 |  |  | 0 | 13168730.4268 | 0 | 13168730.4268
|  | Double socket 1P-16A-250V | 6 | 6 | pcs | 150480 | 54500 | 204980 | 902880 | 327000 | 1229880 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KB426UES2_WE_G19 / Schneider/ VN, Plastic type
|  | Cable Cu/XLPE/PVC 4x1Cx4mm2+E4mm2 | 200 | 174.9 | m | 72299.4 | 17189.865 | 89489.265 | 12645165.06 | 3006507.3885 | 15651672.4485 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 3Cx-2.5mm2Cu/XLPE/PVC | 260 | 177.1 | m | 32518.74 | 7485.665 | 40004.405 | 5759068.854 | 1325711.2715 | 7084780.1255 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 3Cx-1.5mm2Cu/XLPE/PVC | 450 | 338.8 | m | 22980.09 | 5743.9305 | 28724.0205 | 7785654.492 | 1946043.6534 | 9731698.1454 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 4Cx-1.5mm2Cu/PVC/PVC | 105 | 111.1 | m | 25928.4 | 7485.665 | 33414.065 | 2880645.24 | 831657.3815 | 3712302.6215 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 2Cx-1.5mm2Cu/PVC/PVC | 495 | 332.2 | m | 15443.88 | 5031.18 | 20475.06 | 5130456.936 | 1671357.996 | 6801814.932 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 18 core AWG 1 pair | 540 | 607.2 | m | 21976.8 | 3920 | 25896.8 | 13344312.96 | 2380224 | 15724536.96 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 2MKABLO/ Turkey
|  | PVC conduit D20 | 104 | 660 | m | 8773.9726 | 14594.0164 | 23367.989 | 5790821.9178 | 9632050.8318 | 15422872.7496 | 80% |  | 0.8 |  |  | 0 | 4632657.5342 | 0 | 4632657.5342 | FPC20, Nano/ VN
|  | PVC conduit D16 | 378 | 935 | m | 6646.8692 | 13183.4282 | 19830.2974 | 6214822.6815 | 12326505.345 | 18541328.0265 | 80% |  | 0.8 |  |  | 0 | 4971858.1452 | 0 | 4971858.1452 | FPC16, Nano/ VN
|  | PVC conduit D16 | 891 | 0 | m | 6646.8692 | 13183.4282 | 19830.2974 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC16, Nano/ VN
|  | PVC conduit D20 | 143 | 0 | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | PVC conduit D25 | 140 | 154 | m | 12762.0356 | 15805 | 28567.0356 | 1965353.4849 | 2433970 | 4399323.4849 | 80% |  | 0.8 |  |  | 0 | 1572282.7879 | 0 | 1572282.7879 | FPC25, Nano/ VN
|  | PVC flexible conduit D20 | 39 | 55 | m | 3554.7229 | 5289.7059 | 8844.4288 | 195509.7606 | 290933.8235 | 486443.5841 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Nano/ VN
|  | PVC flexible conduit D20 | 22 | 0 | m | 3554.7229 | 5289.7059 | 8844.4288 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Cable tray 200x100x2.0mm | 42 | 45 | m | 776880 | 51045.8655 | 827925.8655 | 34959600 | 2297063.9462 | 37256663.9462 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TGE/ VN
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 3983863.9187 | 1195159.1756 | 5179023.0944 | 3983863.9187 | 1195159.1756 | 5179023.0944 | 50% |  | 0.5 |  |  | 0 | 1991931.9594 | 0 | 1991931.9594 | Vietnam
|  | East side | [6 empty] | 707988444.8264 | 80491542.9191 | 788479987.7455 |  |  | 0 |  |  | 0 | 7425133.1413 | 0 | 7425133.1413
|  | Equipments | [6 empty] | 606357980 | 35796884 | 642154864 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Outdoor unit 33.6KW | 2 | 2 | pcs | 62381000 | 3920000 | 66301000 | 124762000 | 7840000 | 132602000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM120TXMDNC/EA, SamSung/ China
|  | Outdoor unit 22.4KW | 1 | 1 | pcs | 48310460 | 3304000 | 51614460 | 48310460 | 3304000 | 51614460 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM080TXMDNC/EA, SamSung/ China
|  | Outdoor unit 14KW | 1 | 1 | pcs | 30222170 | 840000 | 31062170 | 30222170 | 840000 | 31062170 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM050TXMDNC/EA, SamSung/ China
|  | Indoor unit cassette type, 9.0kW | 6 | 6 | pcs | 9845660 | 537600 | 10383260 | 59073960 | 3225600 | 62299560 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM090NN4DEH/EU+PC4NUFMAN, SamSung/ Korea
|  | Indoor unit cassette type, 7.1kW | 7 | 7 | pcs | 9569780 | 537600 | 10107380 | 66988460 | 3763200 | 70751660 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM071NN4DEH/EU+PC4NUFMAN, SamSung/ Korea
|  | Indoor unit cassette type, 6kW | 1 | 1 | pcs | 8741260 | 504000 | 9245260 | 8741260 | 504000 | 9245260 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM060NNNDEH/EU+PC4SUFMAN, SamSung/ Korea
|  | Split Air conditioner, indoor unit wall type, cooling capacity 4.5kW | 2 | 2 | pcs | 12599730 | 621600 | 13221330 | 25199460 | 1243200 | 26442660 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AR18TYAACWKNSV +AR18TYAACWKXSV, SamSung/ Thailand
|  | Split Air conditioner, indoor unit wall type, cooling capacity 7.1kW | 2 | 2 | pcs | 31227680 | 733600 | 31961280 | 62455360 | 1467200 | 63922560 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AR28TYHYCWKNSV +AR28TYHYCWKXSV, SamSung/ Thailand
|  | Split Air conditioner, indoor unit cassette type, cooling capacity 5.2kW | 1 | 1 | pcs | 21620170 | 733600 | 22353770 | 21620170 | 733600 | 22353770 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AC052TN4DKC/EA + AC052TXADKC/EA + PC4NUFMAN, SamSung/ Korea
|  | Dehumidifiers 1500m3/h | 3 | 3 | pcs | 19690000 | 168000 | 19858000 | 59070000 | 504000 | 59574000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | DID-150/ Decker/Vietnam
|  | Remote wirring for AC | 19 | 19 | pcs | 1614800 | 168000 | 1782800 | 30681200 | 3192000 | 33873200 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MWR-WG00JN / SamSung/ Korea
|  | Controller for AC | 2 | 10 | pcs | 873400 | 50400 | 923800 | 8734000 | 504000 | 9238000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MIM-A00N+DB93-17178A , SamSung/ Korea
|  | DB controller | 1 | 1 | pcs | 13200000 | 280000 | 13480000 | 13200000 | 280000 | 13480000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | VN
|  | Gas splitter | 5 | 8 | pcs | 1659900 | 0 | 1659900 | 13279200 | 0 | 13279200 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | SamSung/ Korea
|  | Concrete base for outdoor unit | 4 | 4 | pcs | 1300000 | 500000 | 1800000 | 5200000 | 2000000 | 7200000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Extra refrigerant charge R410a or R32 | 1 | 1 | lot | 7500000 | 0 | 7500000 | 7500000 | 0 | 7500000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Hanger support & Sub materials | 1 | 1 | lot | 21320280 | 6396084 | 27716364 | 21320280 | 6396084 | 27716364 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Copper pipe | 0 | 0 |  |  |  |  | 28355645.2586 | 9993875.3431 | 38349520.6017 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Ø6.4mm-0.81mmT | 18 | 19.95 | m | 38160 | 22400 | 60560 | 761292 | 446880 | 1208172 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
|  | Ø9.5mm-0.81mmT | 86 | 94.5 | m | 60000 | 23520 | 83520 | 5670000 | 2222640 | 7892640 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
|  | Ø12.7mm-0.81mmT | 28 | 30.45 | m | 81840 | 28000 | 109840 | 2492028 | 852600 | 3344628 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
|  | Ø15.9mm-0.81mmT | 92 | 101.85 | m | 103760 | 38808 | 142568 | 10567956 | 3952594.8 | 14520550.8 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
|  | Ø19.1mm-0.81mmT | 3 | 3.15 | m | 129600 | 42560 | 172160 | 408240 | 134064 | 542304 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
|  | Ø22.2mm-0.81mmT | 6 | 6.3 | m | 147310.3448 | 49392 | 196702.3448 | 928055.1724 | 311169.6 | 1239224.7724 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
|  | Ø28.6mm-1.0mmT | 25 | 27.3 | m | 234206.8966 | 63504 | 297710.8966 | 6393848.2759 | 1733659.2 | 8127507.4759 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
|  | Hanger support & Sub materials | 1 | 1 | lot | 1134225.8103 | 340267.7431 | 1474493.5534 | 1134225.8103 | 340267.7431 | 1474493.5534 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Insulation copper pipe | 0 | 0 |  |  |  |  | 5768802.375 | 2703324.5085 | 8472126.8835 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Ø6.4mm-15mmT | 18 | 19.95 | m | 15358.8 | 5600 | 20958.8 | 306408.06 | 111720 | 418128.06 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Ø9.5mm-15mmT | 86 | 94.5 | m | 16754.4 | 5644.8 | 22399.2 | 1583290.8 | 533433.6 | 2116724.4 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Ø12.7mm-15mmT | 28 | 30.45 | m | 17871.6 | 7728 | 25599.6 | 544190.22 | 235317.6 | 779507.82 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Ø15.9mm-15mmT | 92 | 101.85 | m | 20664 | 9172.8 | 29836.8 | 2104628.4 | 934249.68 | 3038878.08 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Ø19.1mm-15mmT | 3 | 3.15 | m | 23176.8 | 101595.2 | 124772 | 73006.92 | 320024.88 | 393031.8 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Ø22.2mm-15mmT | 6 | 6.3 | m | 24852 | 11995.2 | 36847.2 | 156567.6 | 75569.76 | 232137.36 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Ø28.6mm-15mmT | 25 | 27.3 | m | 28203.6 | 15523.2 | 43726.8 | 769958.28 | 423783.36 | 1193741.64 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Accessories | 1 | 1 | lot | 230752.095 | 69225.6285 | 299977.7235 | 230752.095 | 69225.6285 | 299977.7235 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Condensate pipe | 0 | 0 |  |  |  |  | 4058656.35 | 2146658.409 | 6205314.759 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | uPVC-Ø27mm-PN12 | 46 | 50.4 | m | 8236.8 | 11743.2 | 19980 | 415134.72 | 591857.28 | 1006992 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN, Ø34 2.1mm, PN12.5
|  | uPVC-Ø34mm-PN12 | 38 | 42 | m | 16286.4 | 12639.2 | 28925.6 | 684028.8 | 530846.4 | 1214875.2 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN, Ø34 2.1mm, PN12.5
|  | uPVC-Ø42mm-PN12 | 15 | 16.8 | m | 21528 | 14560 | 36088 | 361670.4 | 244608 | 606278.4 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN, Ø42 2.1mm, PN12
|  | Fitting for UpVC | 1 | 1 | lot | 1953259.56 | 585977.868 | 2539237.428 | 1953259.56 | 585977.868 | 2539237.428 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Hanger support & Sub materials | 1 | 1 | lot | 644562.87 | 193368.861 | 837931.731 | 644562.87 | 193368.861 | 837931.731 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Insulation condensate pipe | 0 | 0 |  |  |  |  | 1524621 | 1536840.732 | 3061461.732 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Ø27mm-10mmT | 46 | 50.4 | m | 11169.6 | 11743.2 | 22912.8 | 562947.84 | 591857.28 | 1154805.12 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Ø34mm-10mmT | 38 | 42 | m | 14520 | 15523.2 | 30043.2 | 609840 | 651974.4 | 1261814.4 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Ø42mm-10mmT | 15 | 16.8 | m | 17312.4 | 16352 | 33664.4 | 290848.32 | 274713.6 | 565561.92 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Accessories | 1 | 1 | lot | 60984.84 | 18295.452 | 79280.292 | 60984.84 | 18295.452 | 79280.292 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Cable power supply & conduit | 0 | 0 |  |  |  |  | 61922739.8428 | 28313959.9265 | 90236699.7693 |  |  | 0 |  |  | 0 | 7425133.1413 | 0 | 7425133.1413
|  | Double socket 1P-16A-250V | 3 | 3 | pcs | 150480 | 54500 | 204980 | 451440 | 163500 | 614940 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KB426UES2_WE_G19 / Schneider/ VN, Plastic type
|  | Cable Cu/XLPE/PVC 4x1Cx4mm2+E4mm2 | 135 | 168 | m | 72299.4 | 17189.865 | 89489.265 | 12146299.2 | 2887897.32 | 15034196.52 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 3Cx-2.5mm2Cu/XLPE/PVC | 155 | 43.05 | m | 32518.74 | 7485.665 | 40004.405 | 1399931.757 | 322257.8783 | 1722189.6353 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 3Cx-1.5mm2Cu/XLPE/PVC | 219 | 260.4 | m | 22980.09 | 5743.9305 | 28724.0205 | 5984015.436 | 1495719.5022 | 7479734.9382 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 4Cx-1.5mm2 Cu/PVC/PVC | 75 | 70.35 | m | 25928.4 | 7485.665 | 33414.065 | 1824062.94 | 526616.5328 | 2350679.4728 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 2Cx-1.5mm2 Cu/PVC/PVC | 546 | 176.4 | m | 15443.88 | 5031.18 | 20475.06 | 2724300.432 | 887500.152 | 3611800.584 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 18 core AWG 1 pair | 253 | 396.9 | m | 21976.8 | 3920 | 25896.8 | 8722591.92 | 1555848 | 10278439.92 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 2MKABLO/ Turkey
|  | PVC conduit D20 | 62 | 336 | m | 8773.9726 | 14594.0164 | 23367.989 | 2948054.7945 | 4903589.5144 | 7851644.3089 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | PVC conduit D16 | 327 | 840 | m | 6646.8692 | 13183.4282 | 19830.2974 | 5583370.1096 | 11074079.6682 | 16657449.7778 | 80% |  | 0.8 |  |  | 0 | 4466696.0877 | 0 | 4466696.0877 | FPC16, Nano/ VN
|  | PVC conduit D16 | 1023 | 0 | m | 6646.8692 | 13183.4282 | 19830.2974 | 0 | 0 | 0 | 80% |  | 0.8 |  |  | 0 | 0 | 0 | 0 | FPC16, Nano/ VN
|  | PVC conduit D20 | 86 | 0 | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | PVC conduit D25 | 99 | 160 | m | 12762.0356 | 15805 | 28567.0356 | 2041925.6986 | 2528800 | 4570725.6986 | 80% |  | 0.8 |  |  | 0 | 1633540.5589 | 0 | 1633540.5589 | FPC25, Nano/ VN
|  | PVC flexible conduit D20 | 21 | 31.5 | m | 3554.7229 | 5289.7059 | 8844.4288 | 111973.772 | 166625.7353 | 278599.5073 | 80% |  | 0.8 |  |  | 0 | 89579.0176 | 0 | 89579.0176 | Nano/ VN
|  | PVC flexible conduit D20 | 11 | 11 | m | 3554.7229 | 5289.7059 | 8844.4288 | 39101.9521 | 58186.7647 | 97288.7168 | 80% |  | 0.8 |  |  | 0 | 31281.5617 | 0 | 31281.5617 | Vietnam
|  | Cable tray 200x100x2.0mm | 19 | 20 | m | 776880 | 51045.8655 | 827925.8655 | 15537600 | 1020917.3094 | 16558517.3094 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TGE/ VN
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 2408071.831 | 722421.5493 | 3130493.3802 | 2408071.831 | 722421.5493 | 3130493.3802 | 50% |  | 0.5 |  |  | 0 | 1204035.9155 | 0 | 1204035.9155 | Vietnam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
4. |  | Machine hook-up (Hall 3) | [8 empty] | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
5. |  | Scooter Garage | [8 empty] | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
6. |  | Canteen | [6 empty] | 21057187.7199 | 2439460.942 | 23496648.6619 |  |  | 0 |  |  | 0 | 0 | 0 | 0
6. 3. 50. |  | Air Conditioning | 1 | 1 | PSCH |  |  |  | 21057187.7199 | 2439460.942 | 23496648.6619 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Split Air conditioner, indoor unit wall type, cooling capacity 2.5kW | 1 | 1 | pcs | 15455330 | 621600 | 16076930 | 15455330 | 621600 | 16076930 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AR13TYAACWKNSV +AR13TYAACWKXSV, SamSung/ Thailand
|  | Remote wirring for AC | 1 | 1 | pcs | 1614800 | 50400 | 1665200 | 1614800 | 50400 | 1665200 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MWR-WG00JN / SamSung/ Korea
|  | Hanger support & Sub materials | 1 | 1 | lot | 775915 | 232774.5 | 1008689.5 | 775915 | 232774.5 | 1008689.5 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Copper pipe | 0 | 0 |  |  |  |  | 1022500 | 471470 | 1493970 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Ø6.4mm-0.81mmT | 10 | 10 | m | 38160 | 22400 | 60560 | 381600 | 224000 | 605600 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
|  | Ø9.5mm-0.81mmT | 10 | 10 | m | 60000 | 23520 | 83520 | 600000 | 235200 | 835200 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
|  | Hanger support & Sub materials | 1 | 1 | lot | 40900 | 12270 | 53170 | 40900 | 12270 | 53170 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Insulation copper pipe | 0 | 0 |  |  |  |  | 334512.5 | 116462.15 | 450974.65 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Ø6.4mm-15mmT | 10 | 10 | m | 15358.8 | 5600 | 20958.8 | 153588 | 56000 | 209588 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Ø9.5mm-15mmT | 10 | 10 | m | 16754.4 | 5644.8 | 22399.2 | 167544 | 56448 | 223992 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Accessories | 1 | 1 | lot | 13380.5 | 4014.15 | 17394.65 | 13380.5 | 4014.15 | 17394.65 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Condensate pipe | 0 | 0 |  |  |  |  | 107712 | 125035.2 | 232747.2 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | uPVC-Ø27mm-PN12 | 10 | 10 | m | 8236.8 | 11743.2 | 19980 | 82368 | 117432 | 199800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN, Ø34 2.1mm, PN12.5
|  | Fitting for UpVC | 1 | 1 | lot | 19008 | 5702.4 | 24710.4 | 19008 | 5702.4 | 24710.4 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Hanger support & Sub materials | 1 | 1 | lot | 6336 | 1900.8 | 8236.8 | 6336 | 1900.8 | 8236.8 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Insulation condensate pipe | 0 | 0 |  |  |  |  | 116350 | 118828.2 | 235178.2 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Ø27mm-10mmT | 10 | 10 | m | 11169.6 | 11743.2 | 22912.8 | 111696 | 117432 | 229128 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Accessories | 1 | 1 | lot | 4654 | 1396.2 | 6050.2 | 4654 | 1396.2 | 6050.2 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Cable power supply & conduit | 0 | 0 |  |  |  |  | 1630068.2199 | 702890.892 | 2332959.1119 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | 3Cx-2.5mm2Cu/XLPE/PVC | 15 | 15 | m | 32518.74 | 7485.665 | 40004.405 | 487781.1 | 112284.975 | 600066.075 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 3Cx-1.5mm2Cu/XLPE/PVC | 15 | 15 | m | 22980.09 | 5743.9305 | 28724.0205 | 344701.35 | 86158.9575 | 430860.3075 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 4Cx-1.5mm2 Cu/PVC/PVC | 10 | 10 | m | 25928.4 | 7485.665 | 33414.065 | 259284 | 74856.65 | 334140.65 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 18 core AWG 1 pair | 10 | 10 | m | 26400 | 3360 | 29760 | 264000 | 33600 | 297600 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 2MKABLO/ Turkey
|  | PVC conduit D20 | 15 | 15 | m | 8773.9726 | 14594.0164 | 23367.989 | 131609.589 | 218910.2462 | 350519.8352 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | PVC conduit D16 | 12 | 12 | m | 6646.8692 | 13183.4282 | 19830.2974 | 79762.4301 | 158201.1381 | 237963.5683 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC16, Nano/ VN
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 62929.7507 | 18878.9252 | 81808.6759 | 62929.7507 | 18878.9252 | 81808.6759 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | TOTAL AMOUNT (Not included VAT) | [6 empty] | 2013959538.4077 | 214187539.3055 | 2228147077.7132 | [6 empty] | 20593863.5681 | 0 | 20593863.5681
3. |  | Office, Social and Technical Areas (Hall 3) | [6 empty] | 2135112119.4552 | 210437879.8945 | 2345549999.3497 | [6 empty] | 92683593.5967 | 0 | 92683593.5967
[14 empty] | 0 |  |  | 0
3. 3. |  | Mechanical Engineering | [6 empty] | 2135112119.4552 | 210437879.8945 | 2345549999.3497 |  |  | 0 |  |  | 0 | 92683593.5967 | 0 | 92683593.5967
3. 3. 10. |  | Waste Water System | 1 | 1 | PSCH |  |  |  | 195924697.8575 | 71484007.4162 | 267408705.2737 |  |  | 0 |  |  | 0 | 74806310.3967 | 0 | 74806310.3967
|  | West side | 0 | 0 | m | 0 | 0 | 0 | 79936135.2 | 44199519.52 | 124135654.72 |  |  | 0 |  |  | 0 | 52663806.72 | 0 | 52663806.72
|  | uPVC pipe D200 - PN6 | 35 | 40 | m | 356616 | 71941.408 | 428557.408 | 14264640 | 2877656.32 | 17142296.32 | 70% |  | 70% |  |  | 0 | 9985248 | 0 | 9985248 | De Nhat, VN, Ø220 5.9mm, PN6
|  | uPVC pipe D168 - PN6 | 40 | 65 | m | 179337.6 | 57600.928 | 236938.528 | 11656944 | 3744060.32 | 15401004.32 | 70% |  | 70% |  |  | 0 | 8159860.8 | 0 | 8159860.8 | De Nhat, VN, Ø168 4.7mm, PN6
|  | uPVC pipe D114 - PN6 | 115 | 156 | m | 93225.6 | 42504 | 135729.6 | 14543193.6 | 6630624 | 21173817.6 | 70% |  | 70% |  |  | 0 | 10180235.52 | 0 | 10180235.52 | De Nhat, VN, Ø114 3.2mm, PN6
|  | uPVC pipe D90 - PN6 | 185 | 209 | m | 65145.6 | 36064 | 101209.6 | 13615430.4 | 7537376 | 21152806.4 | 70% |  | 70% |  |  | 0 | 9530801.28 | 0 | 9530801.28 | De Nhat, VN, Ø90 2.7mm, PN6
|  | uPVC pipe D60 - PN6 | 153 | 187 | m | 29858.4 | 24884.16 | 54742.56 | 5583520.8 | 4653337.92 | 10236858.72 | 70% |  | 70% |  |  | 0 | 3908464.56 | 0 | 3908464.56 | De Nhat, VN, Ø60 2.0mm, PN6
|  | uPVC pipe D42 - PN6 | 65 | 68 | m | 21528 | 17851.68 | 39379.68 | 1463904 | 1213914.24 | 2677818.24 | 70% |  | 70% |  |  | 0 | 1024732.8 | 0 | 1024732.8 | De Nhat, VN, Ø42 2.1mm, PN12
|  | uPVC Fitting | 1 | 1 | lot | 14106376.8 | 4231913.04 | 18338289.84 | 14106376.8 | 4231913.04 | 18338289.84 | 70% |  | 70% |  |  | 0 | 9874463.76 | 0 | 9874463.76 | Viet Nam
|  | Excavation & backfill | 37 | 37 | m3 | 0 | 200000 | 200000 | 0 | 7400000 | 7400000 | 70% |  | 70% |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Connect to existing manhole | 1 | 1 | lot | 0 | 3000000 | 3000000 | 0 | 3000000 | 3000000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Connect to existing pipe | 1 | 1 | lot | 0 | 1500000 | 1500000 | 0 | 1500000 | 1500000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Accessories | 1 | 1 | lot | 4702125.6 | 1410637.68 | 6112763.28 | 4702125.6 | 1410637.68 | 6112763.28 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | East side | 0 |  | m |  |  |  | 115988562.6575 | 27284487.8962 | 143273050.5537 |  |  | 0 |  |  | 0 | 22142503.6767 | 0 | 22142503.6767
|  | Submersible Pump Q=5M3/H, H=8MH20 | 2 | 2 | pcs | 19613000 | 616000 | 20229000 | 39226000 | 1232000 | 40458000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AP50B.50.11.3.V./ Grundfos/ Hungary
|  | Auto coupling Rp2' | 2 | 2 | pcs | 4488000 | 0 | 4488000 | 8976000 | 0 | 8976000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Grundfos
|  | Slider + chain | 2 | 2 | pcs | 3850000 | 0 | 3850000 | 7700000 | 0 | 7700000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Float for submersible pump | 2 | 2 | pcs | 3850000 | 168000 | 4018000 | 7700000 | 336000 | 8036000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Electrical control panel for submeriable pump | 1 | 1 | pcs | 13420000 | 840000 | 14260000 | 13420000 | 840000 | 14260000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Check valve DN50 | 1 | 1 | pcs | 174200 | 61600 | 235800 | 174200 | 61600 | 235800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN
|  | Gate valve DN50 | 1 | 1 | pcs | 128700 | 61600 | 190300 | 128700 | 61600 | 190300 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 30 | 30 | m | 40467 | 9350 | 49817 | 1214010 | 280500 | 1494510 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 30 | 30 | m | 8773.9726 | 14594.0164 | 23367.989 | 263219.1781 | 437820.4924 | 701039.6704 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | uPVC pipe D168 - PN6 | 29 | 35 | m | 179337.6 | 57600.928 | 236938.528 | 6276816 | 2016032.48 | 8292848.48 | 70% |  | 0.7 |  |  | 0 | 4393771.2 | 0 | 4393771.2 | De Nhat, VN, Ø168 4.7mm, PN6
|  | uPVC pipe D114 - PN6 | 39 | 45 | m | 93225.6 | 42504 | 135729.6 | 4195152 | 1912680 | 6107832 | 70% |  | 0.7 |  |  | 0 | 2936606.4 | 0 | 2936606.4 | De Nhat, VN, Ø114 3.2mm, PN6
|  | uPVC pipe D90 - PN6 | 149 | 167 | m | 65145.6 | 36064 | 101209.6 | 10879315.2 | 6022688 | 16902003.2 | 70% |  | 0.7 |  |  | 0 | 7615520.64 | 0 | 7615520.64 | De Nhat, VN, Ø90 2.7mm, PN6
|  | uPVC pipe D60 - PN6 | 101 | 124 | m | 29858.4 | 24884.16 | 54742.56 | 3702441.6 | 3085635.84 | 6788077.44 | 70% |  | 0.7 |  |  | 0 | 2591709.12 | 0 | 2591709.12 | De Nhat, VN, Ø60 2.0mm, PN6
|  | uPVC pipe D42 - PN6 | 18 | 23 | m | 21528 | 17851.68 | 39379.68 | 495144 | 410588.64 | 905732.64 | 70% |  | 0.7 |  |  | 0 | 346600.8 | 0 | 346600.8 | De Nhat, VN, Ø42 2.1mm, PN12
|  | Pipe clean out D60 | 1 | 1 | pcs | 106423.2 | 28000 | 134423.2 | 106423.2 | 28000 | 134423.2 | 70% |  | 0.7 |  |  | 0 | 74496.24 | 0 | 74496.24 | Viet Nam
|  | uPVC Fitting | 1 | 1 | lot | 5976856.1096 | 1793056.8329 | 7769912.9425 | 5976856.1096 | 1793056.8329 | 7769912.9425 | 70% |  | 0.7 |  |  | 0 | 4183799.2767 | 0 | 4183799.2767 | Viet Nam
|  | Excavation & backfill | 21 | 28 | m3 | 0 | 200000 | 200000 | 0 | 5600000 | 5600000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Connect to existing manhole | 1 | 1 | lot | 0 | 1500000 | 1500000 | 0 | 1500000 | 1500000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Accessories | 1 | 1 | lot | 5554285.3699 | 1666285.611 | 7220570.9808 | 5554285.3699 | 1666285.611 | 7220570.9808 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
3. 3. 20. |  | Service Water System | 1 | 1 | PSCH |  |  |  | 350026408.4568 | 59395813.3191 | 409422221.7759 |  |  | 0 |  |  | 0 | 17877283.2 | 0 | 17877283.2
|  | West side | [6 empty] | 205749865.9577 | 34591531.4404 | 240341397.398 |  |  | 0 |  |  | 0 | 13261248 | 0 | 13261248
|  | Pump room | [6 empty] | 149717065.9577 | 8068928.1916 | 157785994.1492 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Booster pump Q=9.3 m3, H=30m | 2 | 2 | set | 30745000 | 728000 | 31473000 | 61490000 | 1456000 | 62946000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CM 25-2, Grundfos/ Taiwan
|  | Electrical control panel for booster pump | 1 | 1 | set | 44440000 | 1400000 | 45840000 | 44440000 | 1400000 | 45840000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Encloser: VN Circuit breaker: LS/ Korea
|  | Pressure tank 100l | 1 | 1 | pcs | 7915200 | 168000 | 8083200 | 7915200 | 168000 | 8083200 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Varem/ Italia
|  | Storage tank 3m3 | 1 | 1 | pcs | 9970909.0909 | 322000 | 10292909.0909 | 9970909.0909 | 322000 | 10292909.0909 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | SHN3000 (Φ1380)/ Son Ha/ VN
|  | Filter | 1 | 1 | set | 10800000 | 225400 | 11025400 | 10800000 | 225400 | 11025400 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | VN
|  | Water metter DN40 | 1 | 1 | pcs | 2154000 | 75152 | 2229152 | 2154000 | 75152 | 2229152 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTM-55, KVS / Turkey
|  | Cable Cu/PVC/PVC 2Cx1.5mm2 | 20 | 25 | m | 15443.88 | 5031.18 | 20475.06 | 386097 | 125779.5 | 511876.5 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 20 | 25 | m | 40467 | 9350 | 49817 | 1011675 | 233750 | 1245425 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 40 | 50 | m | 8773.9726 | 14594.0164 | 23367.989 | 438698.6301 | 729700.8206 | 1168399.4507 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | Hanger + Support | 1 | 1 | lot | 6172492.3537 | 1851747.7061 | 8024240.0598 | 6172492.3537 | 1851747.7061 | 8024240.0598 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Accessories | 1 | 1 | lot | 4937993.8829 | 1481398.1649 | 6419392.0478 | 4937993.8829 | 1481398.1649 | 6419392.0478 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Valve | [6 empty] | 31053568.8 | 3110074.6696 | 34163643.4696 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Pressure Gauges | 1 | 1 | pcs | 1008000 | 49588 | 1057588 | 1008000 | 49588 | 1057588 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | P - 260, KVS/ Turkey
|  | Flexible DN40 | 4 | 4 | pcs | 825600 | 75152 | 900752 | 3302400 | 300608 | 3603008 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KVS - 501 T/KVS/ Turkey
|  | Float level indicator | 1 | 1 | pcs | 4200000 | 168000 | 4368000 | 4200000 | 168000 | 4368000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Omron/ Aisa
|  | Float valve DN40 | 1 | 1 | pcs | 2809200 | 75152 | 2884352 | 2809200 | 75152 | 2884352 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KVS-703T, KVS/ Turkey
|  | Y-Strainer DN40 | 2 | 2 | pcs | 726000 | 75152 | 801152 | 1452000 | 150304 | 1602304 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KVS 200 - T/ KVS/ Turkey
|  | Safety valve DN40 | 3 | 3 | pcs | 3133200 | 75152 | 3208352 | 9399600 | 225456 | 9625056 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 3110N, KVS/ Turkey
|  | Check valve DN40 | 3 | 3 | pcs | 867600 | 75152 | 942752 | 2602800 | 225456 | 2828256 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KVS - 101/ LVS/ Turkey
|  | Gate valve DN40 | 4 | 4 | pcs | 726000 | 75152 | 801152 | 2904000 | 300608 | 3204608 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 402, KVS/Turkey
|  | Gate valve DN25 | 1 | 1 | pcs | 322800 | 50880.368 | 373680.368 | 322800 | 50880.368 | 373680.368 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 402, KVS/Turkey
|  | Gate valve DN32 PPR | 5 | 7 | pcs | 99122.4 | 58877.3007 | 157999.7007 | 693856.8 | 412141.105 | 1105997.905 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN
|  | Gate valve DN25 PPR | 3 | 2 | pcs | 85924.8 | 49415.0989 | 135339.8989 | 171849.6 | 98830.1978 | 270679.7978 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN
|  | Gate valve DN20 PPR | 10 | 15 | pcs | 63367.2 | 45472.3119 | 108839.5119 | 950508 | 682084.6788 | 1632592.6788 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN
|  | Accessories | 1 | 1 | lot | 1236554.4 | 370966.32 | 1607520.72 | 1236554.4 | 370966.32 | 1607520.72 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Cold water pipe | [6 empty] | 21159921.6 | 22158696.668 | 43318618.268 |  |  | 0 |  |  | 0 | 13166173.44 | 0 | 13166173.44
|  | PPR pipe D75 - PN10 | 10 | 11 | m | 99964.8 | 39200 | 139164.8 | 1099612.8 | 431200 | 1530812.8 | 70% |  | 70% |  |  | 0 | 769728.96 | 0 | 769728.96 | De Nhat, VN, Ø75, 6.8mm, PN10
|  | PPR pipe D63 - PN10 | 23 | 25 | m | 71884.8 | 34720 | 106604.8 | 1797120 | 868000 | 2665120 | 70% |  | 70% |  |  | 0 | 1257984 | 0 | 1257984 | De Nhat, VN, Ø63, 5.8mm, PN10
|  | PPR pipe D50 - PN10 | 21 | 26 | m | 45208.8 | 28000 | 73208.8 | 1175428.8 | 728000 | 1903428.8 | 70% |  | 70% |  |  | 0 | 822800.16 | 0 | 822800.16 | De Nhat, VN, Ø50, 4.6mm, PN10
|  | PPR pipe D40 - PN10 | 29 | 31 | m | 30841.2 | 25388.1544 | 56229.3544 | 956077.2 | 787032.7864 | 1743109.9864 | 70% |  | 70% |  |  | 0 | 669254.04 | 0 | 669254.04 | De Nhat, VN, Ø40, 3.7mm, PN10
|  | PPR pipe D32 - PN10 | 47 | 72 | m | 22978.8 | 22306.7432 | 45285.5432 | 1654473.6 | 1606085.5104 | 3260559.1104 | 70% |  | 70% |  |  | 0 | 1158131.52 | 0 | 1158131.52 | De Nhat, VN, Ø32, 2.9mm, PN10
|  | PPR pipe D25 - PN10 | 68 | 87 | m | 17737.2 | 18258.8168 | 35996.0168 | 1543136.4 | 1588517.0616 | 3131653.4616 | 70% |  | 70% |  |  | 0 | 1080195.48 | 0 | 1080195.48 | De Nhat, VN, Ø25, 2.8mm, PN10
|  | PPR pipe D20 - PN10 | 272 | 297 | m | 9921.6 | 15682.8168 | 25604.4168 | 2946715.2 | 4657796.5896 | 7604511.7896 | 70% |  | 70% |  |  | 0 | 2062700.64 | 0 | 2062700.64 | De Nhat, VN, Ø20, 2.3mm, PN10
|  | PPR Fitting | 1 | 1 | lot | 2578284 | 773485.2 | 3351769.2 | 2578284 | 773485.2 | 3351769.2 | 70% |  | 70% |  |  | 0 | 1804798.8 | 0 | 1804798.8 | Viet Nam
|  | uPVC pipe D60 - PN10 | 54 | 62 | m | 35287.2 | 24884.16 | 60171.36 | 2187806.4 | 1542817.92 | 3730624.32 | 70% |  | 70% |  |  | 0 | 1531464.48 | 0 | 1531464.48 | De Nhat, VN, Ø60 2.5mm, PN10
|  | uPVC pipe D34 - PN10 | 104 | 118 | m | 16286.4 | 13440 | 29726.4 | 1921795.2 | 1585920 | 3507715.2 | 70% |  | 70% |  |  | 0 | 1345256.64 | 0 | 1345256.64 | De Nhat, VN, Ø34 2.1mm, PN12.5
|  | uPVC Fitting | 1 | 1 | lot | 948369.6 | 284510.88 | 1232880.48 | 948369.6 | 284510.88 | 1232880.48 | 70% |  | 70% |  |  | 0 | 663858.72 | 0 | 663858.72 | Viet Nam
|  | Connect to existing pipe | 1 | 1 | lot | 0 | 1000000 | 1000000 | 0 | 1000000 | 1000000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Excavation & backfill | 14 | 28 | m3 | 0 | 200000 | 200000 | 0 | 5600000 | 5600000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Accessories + Support | 1 | 1 | lot | 2351102.4 | 705330.72 | 3056433.12 | 2351102.4 | 705330.72 | 3056433.12 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Hot water pipe | [6 empty] | 3819309.6 | 1253831.9112 | 5073141.5112 |  |  | 0 |  |  | 0 | 95074.56 | 0 | 95074.56
|  | PPR pipe D20 - PN20 | 7 | 9 | m | 12261.6 | 15682.8168 | 27944.4168 | 110354.4 | 141145.3512 | 251499.7512 | 70% |  | 0.7 |  |  | 0 | 77248.08 | 0 | 77248.08 | De Nhat, VN, Ø20, 3.4mm, PN20
|  | PPR Fitting | 1 | 1 | lot | 25466.4 | 7639.92 | 33106.32 | 25466.4 | 7639.92 | 33106.32 | 70% |  | 0.7 |  |  | 0 | 17826.48 | 0 | 17826.48 | Viet Nam
|  | Fire stop | 1 | 1 | lot | 3500000 | 1050000 | 4550000 | 3500000 | 1050000 | 4550000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Accessories + Support | 1 | 1 | lot | 183488.8 | 55046.64 | 238535.44 | 183488.8 | 55046.64 | 238535.44 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | East side | [6 empty] | 144276542.4991 | 24804281.8787 | 169080824.3779 |  |  | 0 |  |  | 0 | 4616035.2 | 0 | 4616035.2
|  | Pump room | [6 empty] | 121538562.8991 | 7728105.642 | 129266668.5411 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Booster pump Q=9.3 m3, H=30m | 2 | 2 | set | 17380000 | 616000 | 17996000 | 34760000 | 1232000 | 35992000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CM 10-3, Grundfos/ Taiwan
|  | Electrical control panel for booster pump | 1 | 1 | set | 44440000 | 1400000 | 45840000 | 44440000 | 1400000 | 45840000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Encloser: VN Circuit breaker: LS/ Korea
|  | Pressure tank 100l | 1 | 1 | pcs | 7915200 | 168000 | 8083200 | 7915200 | 168000 | 8083200 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Varem/ Italia
|  | Storage tank 3m3 | 1 | 1 | pcs | 9970909.0909 | 322000 | 10292909.0909 | 9970909.0909 | 322000 | 10292909.0909 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | SHN3000 (Φ1380)/ Son Ha/ VN
|  | Filter | 1 | 1 | set | 10800000 | 225400 | 11025400 | 10800000 | 225400 | 11025400 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | VN
|  | Water metter DN25 | 1 | 1 | pcs | 1014000 | 50880.368 | 1064880.368 | 1014000 | 50880.368 | 1064880.368 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTM-55, KVS / Turkey
|  | Cable Cu/PVC/PVC 2Cx1.5mm2 | 20 | 25 | m | 15443.88 | 5031.18 | 20475.06 | 386097 | 125779.5 | 511876.5 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 20 | 25 | m | 40467 | 9350 | 49817 | 1011675 | 233750 | 1245425 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 40 | 50 | m | 8773.9726 | 14594.0164 | 23367.989 | 438698.6301 | 729700.8206 | 1168399.4507 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | Hanger + Support | 1 | 1 | lot | 4909992.3537 | 1472997.7061 | 6382990.0598 | 4909992.3537 | 1472997.7061 | 6382990.0598 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Accessories | 1 | 1 | lot | 5891990.8244 | 1767597.2473 | 7659588.0717 | 5891990.8244 | 1767597.2473 | 7659588.0717 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Valve | [6 empty] | 15191076.4 | 2017377.4463 | 17208453.8463 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Pressure Gauges | 1 | 1 | pcs | 1008000 | 49588 | 1057588 | 1008000 | 49588 | 1057588 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | P - 260, KVS/ Turkey
|  | Flexible DN25 | 4 | 4 | pcs | 568800 | 50880.368 | 619680.368 | 2275200 | 203521.472 | 2478721.472 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KVS - 501 T/KVS/ Turkey
|  | Float level indicator | 1 | 1 | pcs | 4200000 | 168000 | 4368000 | 4200000 | 168000 | 4368000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Omron/ Aisa
|  | Float valve DN25 | 1 | 1 | pcs | 770400 | 50880.368 | 821280.368 | 770400 | 50880.368 | 821280.368 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KVS-703T, KVS/ Turkey
|  | Y-Strainer DN25 | 2 | 2 | pcs | 322800 | 50880.368 | 373680.368 | 645600 | 101760.736 | 747360.736 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KVS 200 - T/ KVS/ Turkey
|  | Safety valve DN25 | 1 | 1 | pcs | 1376400 | 50880.368 | 1427280.368 | 1376400 | 50880.368 | 1427280.368 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 3110N, KVS/ Turkey
|  | Check valve DN25 | 3 | 3 | pcs | 480000 | 50880.368 | 530880.368 | 1440000 | 152641.104 | 1592641.104 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KVS - 101/ LVS/ Turkey
|  | Gate valve DN25 | 5 | 5 | pcs | 322800 | 50880.368 | 373680.368 | 1614000 | 254401.84 | 1868401.84 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 402, KVS/Turkey
|  | Gate valve DN25 PPR | 8 | 8 | pcs | 85924.8 | 49415.0989 | 135339.8989 | 687398.4 | 395320.791 | 1082719.191 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN
|  | Gate valve DN20 PPR | 9 | 9 | pcs | 63367.2 | 45472.3119 | 108839.5119 | 570304.8 | 409250.8073 | 979555.6073 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN
|  | Accessories | 1 | 1 | lot | 603773.2 | 181131.96 | 784905.16 | 603773.2 | 181131.96 | 784905.16 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Cold water pipe | [6 empty] | 7418628 | 14924281.536 | 22342909.536 |  |  | 0 |  |  | 0 | 4616035.2 | 0 | 4616035.2
|  | PPR pipe D63 - PN10 | 10 | 12 | m | 71884.8 | 34720 | 106604.8 | 862617.6 | 416640 | 1279257.6 | 70% |  | 70% |  |  | 0 | 603832.32 | 0 | 603832.32 | De Nhat, VN, Ø63, 5.8mm, PN10
|  | PPR pipe D40 - PN10 | 5 | 7 | m | 30841.2 | 25388.1544 | 56229.3544 | 215888.4 | 177717.0808 | 393605.4808 | 70% |  | 70% |  |  | 0 | 151121.88 | 0 | 151121.88 | De Nhat, VN, Ø40, 3.7mm, PN10
|  | PPR pipe D32 - PN10 | 29 | 32 | m | 22978.8 | 22306.7432 | 45285.5432 | 735321.6 | 713815.7824 | 1449137.3824 | 70% |  | 70% |  |  | 0 | 514725.12 | 0 | 514725.12 | De Nhat, VN, Ø32, 2.9mm, PN10
|  | PPR pipe D25 - PN10 | 21 | 28 | m | 17737.2 | 18258.8168 | 35996.0168 | 496641.6 | 511246.8704 | 1007888.4704 | 70% |  | 70% |  |  | 0 | 347649.12 | 0 | 347649.12 | De Nhat, VN, Ø25, 2.8mm, PN10
|  | PPR pipe D20 - PN10 | 130 | 143 | m | 9921.6 | 15682.8168 | 25604.4168 | 1418788.8 | 2242642.8024 | 3661431.6024 | 70% |  | 70% |  |  | 0 | 993152.16 | 0 | 993152.16 | De Nhat, VN, Ø20, 2.3mm, PN10
|  | PPR Fitting | 1 | 1 | lot | 860598 | 258179.4 | 1118777.4 | 860598 | 258179.4 | 1118777.4 | 70% |  | 70% |  |  | 0 | 602418.6 | 0 | 602418.6 | Viet Nam
|  | uPVC pipe D34 - PN10 | 104 | 100 | m | 16286.4 | 13440 | 29726.4 | 1628640 | 1344000 | 2972640 | 70% |  | 70% |  |  | 0 | 1140048 | 0 | 1140048 | De Nhat, VN, Ø34 2.1mm, PN12.5
|  | uPVC Fitting | 1 | 1 | lot | 375840 | 112752 | 488592 | 375840 | 112752 | 488592 | 70% |  | 70% |  |  | 0 | 263088 | 0 | 263088 | Viet Nam
|  | Connect to existing pipe | 1 | 1 | lot | 0 | 1000000 | 1000000 | 0 | 1000000 | 1000000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Excavation & backfill | 10 | 20 | m3 | 0 | 200000 | 200000 | 0 | 4000000 | 4000000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Cut wall and backfill | 91 | 130 | m | 0 | 30000 | 30000 | 0 | 3900000 | 3900000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Accessories + Support | 1 | 1 | lot | 824292 | 247287.6 | 1071579.6 | 824292 | 247287.6 | 1071579.6 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Hot water pipe | [6 empty] | 128275.2 | 134517.2544 | 262792.4544 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | PPR pipe D20 - PN20 | 7 | 8 | m | 12261.6 | 15682.8168 | 27944.4168 | 98092.8 | 125462.5344 | 223555.3344 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN, Ø20, 3.4mm, PN20
|  | PPR Fitting | 1 | 1 | lot | 22636.8 | 6791.04 | 29427.84 | 22636.8 | 6791.04 | 29427.84 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Accessories + Support | 1 | 1 | lot | 7545.6 | 2263.68 | 9809.28 | 7545.6 | 2263.68 | 9809.28 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
3. 3. 30. |  | Sanitary Furnishings | 1 | 1 | PSCH |  |  |  | 1589161013.1409 | 79558059.1592 | 1668719072.3001 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | West side | 0 |  | m |  |  |  |  | 50588775.2524 | 1032592350.3478 |  |  | 0 |  |  | 0 |  | 0 | 0
|  | Santinary | [6 empty] | 982003575.0955 | 50588775.2524 | 1032592350.3478 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Water closet one block, included stop valve | 37 | 37 | pcs | 14750000 | 413200.4464 | 15163200.4464 | 545750000 | 15288416.5168 | 561038416.5168 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CW762#XW TC384CVK#W + WH172A + MB174P#WH, Toto/ VN, China
|  | Water closet spray | 37 | 37 | pcs | 638000 | 50232 | 688232 | 23606000 | 1858584 | 25464584 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TVCF201/ Toto/ VN
|  | Paper holder | 37 | 37 | pcs | 653000 | 50232 | 703232 | 24161000 | 1858584 | 26019584 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | YH406RV/ Toto/ China
|  | Lavatory under-mounted type | 43 | 43 | pcs | 1443000 | 300710.7768 | 1743710.7768 | 62049000 | 12930563.4024 | 74979563.4024 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | L501C#W+TVLF405/ Toto/ VN, China
|  | Water tap for lavatory (cold) | 43 | 43 | pcs | 953000 | 50232 | 1003232 | 40979000 | 2159976 | 43138976 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TVLC101NSR/ Toto/ VN
|  | Mirror (H=1m, L according to the lavabo table) | 33 | 33 | m2 | 768883.5 | 123200 | 892083.5 | 25373155.5 | 4065600 | 29438755.5 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | t=5mm, Vietnam
|  | Hand Dryer | 8 | 8 | pcs | 5018000 | 61600 | 5079600 | 40144000 | 492800 | 40636800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TYC322WF/ Toto/ China
|  | Uniral included flush valve | 15 | 15 | pcs | 11003000 | 280000 | 11283000 | 165045000 | 4200000 | 169245000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | UT57S#W + DU601N/ Toto/ VN, China
|  | Floor drain DN80 | 16 | 16 | pcs | 855000 | 88480 | 943480 | 13680000 | 1415680 | 15095680 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TVBA407/ Toto/ Vietnam
|  | Floor drain W100xL5100 | 1 | 1 | pcs | 5417500 | 476000 | 5893500 | 5417500 | 476000 | 5893500 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Inox 304, ZT758-100(75x1000mm), Zento
|  | Floor drain W100xL3800 | 1 | 1 | pcs | 4334000 | 380800 | 4714800 | 4334000 | 380800 | 4714800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Inox 304, ZT758-100(75x1000mm), Zento
|  | Floor drain W100xL3000 | 1 | 1 | pcs | 3250500 | 285600 | 3536100 | 3250500 | 285600 | 3536100 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Inox 304, ZT758-100(75x1000mm), Zento
|  | Shower | 1 | 1 | pcs | 7305000 | 196000 | 7501000 | 7305000 | 196000 | 7501000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TVSM104NSR DM907CS/ Toto/ China
|  | Heat Water 5L for kitchen | 2 | 2 | pcs | 1628727.2727 | 168000 | 1796727.2727 | 3257454.5455 | 336000 | 3593454.5455 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | HOT DOG 5L, Ferroli/ Asia
|  | Heat Water 50L for shower | 1 | 1 | pcs | 3104727.2727 | 280000 | 3384727.2727 | 3104727.2727 | 280000 | 3384727.2727 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aqua 50L, Ferroli/ Asia
|  | Waterproof for neck pipe | 114 | 114 | nos | 50000 | 15000 | 65000 | 5700000 | 1710000 | 7410000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Accessories | 1 | 1 | lot | 8847237.7773 | 2654171.3332 | 11501409.1105 | 8847237.7773 | 2654171.3332 | 11501409.1105 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | East side | [6 empty] | 607157438.0455 | 28969283.9068 | 636126721.9523 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Santinary | [6 empty] | 607157438.0455 | 28969283.9068 | 636126721.9523 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Water closet one block, included stop valve | 24 | 24 | pcs | 14750000 | 413200.4464 | 15163200.4464 | 354000000 | 9916810.7136 | 363916810.7136 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CW762#XW TC384CVK#W + WH172A + MB174P#WH, Toto/ VN, China
|  | Water closet spray | 24 | 24 | pcs | 638000 | 50232 | 688232 | 15312000 | 1205568 | 16517568 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TVCF201/ Toto/ VN
|  | Paper holder | 24 | 24 | pcs | 653000 | 50232 | 703232 | 15672000 | 1205568 | 16877568 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | YH406RV/ Toto/ China
|  | Lavatory under-mounted type | 12 | 24 | pcs | 1443000 | 300710.7768 | 1743710.7768 | 34632000 | 7217058.6432 | 41849058.6432 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | L501C#W+TVLF405/ Toto/ VN, China
|  | Water tap for lavatory (cold) | 12 | 12 | pcs | 953000 | 50232 | 1003232 | 11436000 | 602784 | 12038784 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TVLC101NSR/ Toto/ VN
|  | Mirror (H=1m, L according to the lavabo table) | 10 | 10 | m2 | 768883.5 | 123200 | 892083.5 | 7688835 | 1232000 | 8920835 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | t=5mm, Vietnam
|  | Hand Dryer | 4 | 4 | pcs | 5018000 | 61600 | 5079600 | 20072000 | 246400 | 20318400 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TYC322WF/ Toto/ China
|  | Uniral included flush valve | 11 | 11 | pcs | 11003000 | 280000 | 11283000 | 121033000 | 3080000 | 124113000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | UT57S#W + DU601N/ Toto/ VN, China
|  | Floor drain DN80 | 10 | 10 | pcs | 855000 | 88480 | 943480 | 8550000 | 884800 | 9434800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TVBA407/ Toto/ Vietnam
|  | Floor drain W100xL4400 | 1 | 1 | pcs | 4334000 | 380800 | 4714800 | 4334000 | 380800 | 4714800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Inox 304, ZT758-100(75x1000mm), Zento
|  | Floor drain W100xL3200 | 1 | 1 | pcs | 3250500 | 285600 | 3536100 | 3250500 | 285600 | 3536100 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Inox 304, ZT758-100(75x1000mm), Zento
|  | Heat Water 5L for kitchen | 2 | 2 | pcs | 1628727.2727 | 168000 | 1796727.2727 | 3257454.5455 | 336000 | 3593454.5455 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | HOT DOG 5L, Ferroli/ Asia
|  | Waterproof for neck pipe | 49 | 49 | nos | 50000 | 15000 | 65000 | 2450000 | 735000 | 3185000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Accessories | 1 | 1 | lot | 5469648.5 | 1640894.55 | 7110543.05 | 5469648.5 | 1640894.55 | 7110543.05 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
4. |  | Machine hook-up (Hall 3) | [8 empty] | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
5. |  | Scooter Garage | [6 empty] | 36457255.9273 | 16528783.2582 | 52986039.1855 |  |  | 0 |  |  | 0 | 12798873.36 | 0 | 12798873.36
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
5. 3. |  | Mechancial Engineering | [6 empty] | 36457255.9273 | 16528783.2582 | 52986039.1855 |  |  | 0 |  |  | 0 | 12798873.36 | 0 | 12798873.36
5. 3. 10. |  | Rainwater System | 1 | 1 | PSCH |  |  |  | 36457255.9273 | 16528783.2582 | 52986039.1855 |  |  | 0 |  |  | 0 | 12798873.36 | 0 | 12798873.36
|  | uPVC pipe D220-PN6 | 12 | 15 | m | 356616 | 71941.408 | 428557.408 | 5349240 | 1079121.12 | 6428361.12 | 70% |  | 0.7 |  |  | 0 | 3744468 | 0 | 3744468 | De Nhat, VN, Ø220 5.9mm, PN6
|  | uPVC pipe D110-PN6 | 92 | 112 | m | 93225.6 | 42504 | 135729.6 | 10441267.2 | 4760448 | 15201715.2 | 70% |  | 0.7 |  |  | 0 | 7308887.04 | 0 | 7308887.04 | De Nhat, VN, Ø114 3.2mm, PN6
|  | uPVC pipe D60-PN6 | 59 | 55 | m | 29858.4 | 24884.16 | 54742.56 | 1642212 | 1368628.8 | 3010840.8 | 70% |  | 0.7 |  |  | 0 | 1149548.4 | 0 | 1149548.4 | De Nhat, VN, Ø60 2.0mm, PN6
|  | uPVC Cleanout DN100 | 8 | 8 | pcs | 106423.2 | 28000 | 134423.2 | 851385.6 | 224000 | 1075385.6 | 70% |  | 0.7 |  |  | 0 | 595969.92 | 0 | 595969.92 | De Nhat, VN
|  | Leaf gaurd DN100 | 8 | 8 | pcs | 231000 | 50400 | 281400 | 1848000 | 403200 | 2251200 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Ngoc Thao, VN
|  | Floor Drain DN50 | 8 | 8 | pcs | 855000 | 88480 | 943480 | 6840000 | 707840 | 7547840 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TVBA407/ Toto/ Vietnam
|  | Fitting for uPVC piping | 8 | 1 | lot | 6588863.3455 | 1976659.0036 | 8565522.3491 | 6588863.3455 | 1976659.0036 | 8565522.3491 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Excavation and backfill | 15 | 18 | m3 | 0 | 200000 | 200000 | 0 | 3600000 | 3600000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Hanger/ support and Accessories | 1 | 1 | lot | 2196287.7818 | 658886.3345 | 2855174.1164 | 2196287.7818 | 658886.3345 | 2855174.1164 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Conection existing drain stormwater | 1 | 1 | lot | 700000 | 1750000 | 2450000 | 700000 | 1750000 | 2450000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
6. |  | Canteen | [6 empty] | 420920023.6422 | 58959472.3741 | 479879496.0162 |  |  | 0 |  |  | 0 | 9151168.32 | 0 | 9151168.32
[14 empty] | 0 |  |  | 0
6. 3. |  | Mechancial Engineering | [6 empty] | 420920023.6422 | 58959472.3741 | 479879496.0162 |  |  | 0 |  |  | 0 | 9151168.32 | 0 | 9151168.32
6. 3. 10. |  | Rainwater System | 1 | 1 | PSCH |  |  |  | 16378977.6 | 11954799.36 | 28333776.96 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | uPVC pipe D110-PN6 | 93 | 112 | m | 93225.6 | 42504 | 135729.6 | 10441267.2 | 4760448 | 15201715.2 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN, Ø114 3.2mm, PN6
|  | Leaf gaurd DN100 | 6 | 6 | pcs | 231000 | 50400 | 281400 | 1386000 | 302400 | 1688400 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Ngoc Thao, VN
|  | uPVC Cleanout DN100 | 6 | 6 | pcs | 106423.2 | 28000 | 134423.2 | 638539.2 | 168000 | 806539.2 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN
|  | Fitting for uPVC piping | 1 | 1 | lot | 2934878.4 | 880463.52 | 3815341.92 | 2934878.4 | 880463.52 | 3815341.92 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Excavation and backfill | 13 | 19 | m3 | 0 | 200000 | 200000 | 0 | 3800000 | 3800000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Hanger/ support and Accessories | 1 | 1 | lot | 978292.8 | 293487.84 | 1271780.64 | 978292.8 | 293487.84 | 1271780.64 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Conection existing drain stormwater | 1 | 1 | lot | 0 | 1750000 | 1750000 | 0 | 1750000 | 1750000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
6. 3. 20. |  | Waste Water System | 1 | 1 | PSCH |  |  |  | 20651731.2 | 14688997.44 | 35340728.64 |  |  | 0 |  |  | 0 | 6678977.76 | 0 | 6678977.76
|  | Piping for Bain maries | [11 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | uPVC pipe DN80 | 43 | 50 | m | 65145.6 | 36064 | 101209.6 | 3257280 | 1803200 | 5060480 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN, Ø90 2.7mm, PN6
|  | Water pipe heating system | 1 | 1 | lot |  |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Not included
|  | Fitting for uPVC piping | 1 | 1 | lot | 751680 | 225504 | 977184 | 751680 | 225504 | 977184 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Hanger/ support and Accessories | 1 | 1 | lot | 250560 | 75168 | 325728 | 250560 | 75168 | 325728 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Piping | [6 empty] | 16392211.2 | 12585125.44 | 28977336.64 |  |  | 0 |  |  | 0 | 6678977.76 | 0 | 6678977.76
|  | uPVC pipe DN100 - PN6 | 7 | 9 | m | 93225.6 | 42504 | 135729.6 | 839030.4 | 382536 | 1221566.4 | 70% |  | 0.7 |  |  | 0 | 587321.28 | 0 | 587321.28 | De Nhat, VN, Ø114 3.2mm, PN6
|  | uPVC pipe DN80 - PN6 | 89 | 96 | m | 65145.6 | 36064 | 101209.6 | 6253977.6 | 3462144 | 9716121.6 | 70% |  | 0.7 |  |  | 0 | 4377784.32 | 0 | 4377784.32 | De Nhat, VN, Ø90 2.7mm, PN6
|  | uPVC pipe DN50 - PN6 | 75 | 82 | m | 29858.4 | 24884.16 | 54742.56 | 2448388.8 | 2040501.12 | 4488889.92 | 70% |  | 0.7 |  |  | 0 | 1713872.16 | 0 | 1713872.16 | De Nhat, VN, Ø60 2.0mm, PN6
|  | Clean Out DN50 | 1 | 1 | m | 297000 | 84000 | 381000 | 297000 | 84000 | 381000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Model O2,Ngoc Thao, VN
|  | Clean Out DN80 | 7 | 7 | m | 319000 | 84000 | 403000 | 2233000 | 588000 | 2821000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Model O2,Ngoc Thao, VN
|  | Clean Out DN100 | 1 | 1 | m | 341000 | 84000 | 425000 | 341000 | 84000 | 425000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Model O2,Ngoc Thao, VN
|  | Fitting for uPVC piping | 1 | 1 | lot | 2984860.8 | 895458.24 | 3880319.04 | 2984860.8 | 895458.24 | 3880319.04 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Connect pipes to existing manhole | 1 | 1 | lot | 0 | 1750000 | 1750000 | 0 | 1750000 | 1750000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Excavation and backfill | 8 | 15 | m3 | 0 | 200000 | 200000 | 0 | 3000000 | 3000000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Hanger/ support and Accessories | 1 | 1 | lot | 994953.6 | 298486.08 | 1293439.68 | 994953.6 | 298486.08 | 1293439.68 |  |  | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
6. 3. 30. |  | Service Water System | 1 | 1 | PSCH |  |  |  | 10371428 | 9116560.5373 | 19487988.5373 |  |  | 0 |  |  | 0 | 2472190.56 | 0 | 2472190.56
|  | Valve | [6 empty] | 2328612.8 | 1693755.9317 | 4022368.7317 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Gate valve DN25 | 1 | 1 | pcs | 322800 | 50880.368 | 373680.368 | 322800 | 50880.368 | 373680.368 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 402, KVS/Turkey
|  | Gate valve DN25 PPR | 7 | 7 | pcs | 85924.8 | 49415.0989 | 135339.8989 | 601473.6 | 345905.6922 | 947379.2922 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN
|  | Gate valve DN20 PPR | 6 | 6 | pcs | 63367.2 | 45472.3119 | 108839.5119 | 380203.2 | 272833.8715 | 653037.0715 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN
|  | Accessories | 1 | 1 | lot | 1024136 | 1024136 | 2048272 | 1024136 | 1024136 | 2048272 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Cold water pipe | [6 empty] | 4239540 | 3735787.3512 | 7975327.3512 |  |  | 0 |  |  | 0 | 2472190.56 | 0 | 2472190.56
|  | PPR pipe DN40 - PN10 | 12 | 8 | m | 45208.8 | 28000 | 73208.8 | 361670.4 | 224000 | 585670.4 | 70% |  | 0.7 |  |  | 0 | 253169.28 | 0 | 253169.28 | De Nhat, VN, Ø40, 3.7mm, PN10
|  | PPR pipe DN32 - PN10 | 5 | 6 | m | 30841.2 | 25388.1544 | 56229.3544 | 185047.2 | 152328.9264 | 337376.1264 | 70% |  | 0.7 |  |  | 0 | 129533.04 | 0 | 129533.04 | De Nhat, VN, Ø32, 2.9mm, PN10
|  | PPR pipe DN25 - PN10 | 7 | 10 | m | 22978.8 | 22306.7432 | 45285.5432 | 229788 | 223067.432 | 452855.432 | 70% |  | 0.7 |  |  | 0 | 160851.6 | 0 | 160851.6 | De Nhat, VN, Ø25, 2.8mm, PN10
|  | PPR pipe DN20 - PN10 | 61 | 71 | m | 17737.2 | 18258.8168 | 35996.0168 | 1259341.2 | 1296375.9928 | 2555717.1928 | 70% |  | 0.7 |  |  | 0 | 881538.84 | 0 | 881538.84 | De Nhat, VN, Ø20, 2.3mm, PN10
|  | PPR Fitting | 1 | 1 | lot | 469810.8 | 140943.24 | 610754.04 | 469810.8 | 140943.24 | 610754.04 | 70% |  | 0.7 |  |  | 0 | 328867.56 | 0 | 328867.56 | Viet Nam
|  | uPVC pipe D34 - PN10 | 60 | 63 | m | 16286.4 | 13440 | 29726.4 | 1026043.2 | 846720 | 1872763.2 | 70% |  | 0.7 |  |  | 0 | 718230.24 | 0 | 718230.24 | De Nhat, VN, Ø34 2.1mm, PN12.5
|  | Fitting for uPVC piping | 1 | 1 | lot | 236779.2 | 71033.76 | 307812.96 | 236779.2 | 71033.76 | 307812.96 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Excavation and backfill | 2 | 3.2 | m3 | 0 | 200000 | 200000 | 0 | 640000 | 640000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Accessories + Support | 1 | 1 | lot | 471060 | 141318 | 612378 | 471060 | 141318 | 612378 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | hot water pipe | [6 empty] | 3803275.2 | 3687017.2544 | 7490292.4544 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | PPR pipe DN15 - PN20 | 10 | 8 | m | 12261.6 | 15682.8168 | 27944.4168 | 98092.8 | 125462.5344 | 223555.3344 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN, Ø20, 3.4mm, PN20
|  | PPR Fitting | 1 | 1 | lot | 22636.8 | 6791.04 | 29427.84 | 22636.8 | 6791.04 | 29427.84 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Fire stop | 1 | 1 | lot | 3500000 | 3500000 | 7000000 | 3500000 | 3500000 | 7000000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Accessories + Support | 1 | 1 | lot | 182545.6 | 54763.68 | 237309.28 | 182545.6 | 54763.68 | 237309.28 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
6. 3. 40. |  | Sanitary Furnishings | 1 | 1 | PSCH |  |  |  | 240793394.3675 | 15204292.8421 | 255997687.2095 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Lavatory under-mounted type | 2 | 2 | pcs | 1443000 | 300710.7768 | 1743710.7768 | 2886000 | 601421.5536 | 3487421.5536 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | L501C#W+TVLF405/ Toto/ VN, China
|  | Lavatory wall mounted type | 1 | 1 | pcs | 1253000 | 300710.7768 | 1553710.7768 | 1253000 | 300710.7768 | 1553710.7768 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | LT300C#W+TVLF405/ Toto/ VN, China
|  | Water tap for lavatory (hot and cold) | 2 | 2 | pcs | 1320000 | 50232 | 1370232 | 2640000 | 100464 | 2740464 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TVLM102NSR/ Toto/ VN
|  | Water tap for lavatory (cold) | 1 | 1 | pcs | 953000 | 50232 | 1003232 | 953000 | 50232 | 1003232 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TVLC101NSR/ Toto/ VN
|  | Mirror 700x500x6mm | 3 | 3 | pcs | 2896300 | 61600 | 2957900 | 8688900 | 184800 | 8873700 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | YM6075FA/ Toto/ Japan
|  | Water closet one block, included stop valve | 2 | 2 | set | 14750000 | 413200.4464 | 15163200.4464 | 29500000 | 826400.8928 | 30326400.8928 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CW762#XW TC384CVK#W + WH172A + MB174P#WH, Toto/ VN, China
|  | Water closet spray | 2 | 2 | pcs | 638000 | 50232 | 688232 | 1276000 | 100464 | 1376464 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TVCF201/ Toto/ VN
|  | Paper holder | 2 | 2 | pcs | 653000 | 50232 | 703232 | 1306000 | 100464 | 1406464 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | YH406RV/ Toto/ China
|  | Hand Dryer | 1 | 1 | pcs | 5018000 | 61600 | 5079600 | 5018000 | 61600 | 5079600 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TYC322WF/ Toto/ China
|  | Floor Drain DN50 | 1 | 1 | m | 855000 | 88480 | 943480 | 855000 | 88480 | 943480 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TVBA407/ Toto/ Vietnam
|  | Floor Drain DN80 | 12 | 12 | m | 855000 | 88480 | 943480 | 10260000 | 1061760 | 11321760 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TVBA407/ Toto/ Vietnam
|  | Stainless steel hand washing channel: L10000xH170xD500 | 1 | 1 | pcs | 44000000 | 2240000 | 46240000 | 44000000 | 2240000 | 46240000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Inox304, 3mm/ Vietnam
|  | Taps for hand washing (Cold) | 14 | 14 | pcs | 7755000 | 50400 | 7805400 | 108570000 | 705600 | 109275600 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TLE29002A+TLE01502A1+TLN01102A/ Toto/ China
|  | Heat Water 5l | 2 | 2 | pcs | 1628727.2727 | 168000 | 1796727.2727 | 3257454.5455 | 336000 | 3593454.5455 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | HOT DOG 5L, Ferroli/ Asia
|  | Double Socket 16A/230V | 3 | 3 | pcs | 150480 | 54500 | 204980 | 451440 | 163500 | 614940 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KB426UES2_WE_G19/ Schneider/ VN, Plastic type
|  | Single Socket 16A/230V | 14 | 14 | pcs | 124560 | 54500 | 179060 | 1743840 | 763000 | 2506840 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KB426UEST_G19 / Schneider/ VN, Plastic type
|  | 3C-2.5mm2 Cu/XLPE/PVC | 105 | 112 | m | 32518.74 | 7485.665 | 40004.405 | 3642098.88 | 838394.48 | 4480493.36 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 3C-1.5mm2 Cu/XLPE/PVC | 84 | 95 | m | 22980.09 | 5743.9305 | 28724.0205 | 2183108.55 | 545673.3975 | 2728781.9475 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 105 | 110 | m | 8773.9726 | 14594.0164 | 23367.989 | 965136.9863 | 1605341.8053 | 2570478.7916 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | PVC conduit D20 | 8 | 10 | m | 8773.9726 | 14594.0164 | 23367.989 | 87739.726 | 145940.1641 | 233679.8901 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | PVC conduit D16 | 84 | 90 | m | 6646.8692 | 13183.4282 | 19830.2974 | 598218.226 | 1186508.5359 | 1784726.7619 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC16, Nano/ VN
|  | Waterproof for neck pipe | 5 | 5 | nos | 50000 | 15000 | 65000 | 250000 | 75000 | 325000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Accessories | 1 | 1 | lot | 10408457.4536 | 3122537.2361 | 13530994.6897 | 10408457.4536 | 3122537.2361 | 13530994.6897 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
6. 3. 90. |  | Booster pump assembly | 1 |  | PSCH |  |  |  | 132724492.4747 | 7994822.1947 | 140719314.6694 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | PUMP ROOM | [6 empty] | 119059072.0747 | 5427258.3947 | 125718330.4694 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Booster pump Q=11.7 m3, H=30m | 2 | 2 | set | 17380000 | 616000 | 17996000 | 34760000 | 1232000 | 35992000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CM 10-3, Grundfos/ Taiwan
|  | Electrical control panel for booster pump | 1 | 1 | set | 44440000 | 1400000 | 45840000 | 44440000 | 1400000 | 45840000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Encloser: VN Circuit breaker: LS/ Korea
|  | Pressure tank 100l | 1 | 1 | pcs | 7915200 | 168000 | 8083200 | 7915200 | 168000 | 8083200 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Varem/ Italia
|  | Storage tank 3m3 | 1 | 1 | pcs | 9970909.0909 | 322000 | 10292909.0909 | 9970909.0909 | 322000 | 10292909.0909 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | SHN3000 (Φ1380)/ Son Ha/ VN
|  | Filter | 1 | 1 | set | 10800000 | 225400 | 11025400 | 10800000 | 225400 | 11025400 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | VN
|  | Water metter DN25 | 1 | 1 | pcs | 1014000 | 50880.368 | 1064880.368 | 1014000 | 50880.368 | 1064880.368 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTM-55, KVS / Turkey
|  | Cable Cu/PVC/PVC 2Cx1.5mm2 | 20 | 25 | m | 15443.88 | 5031.18 | 20475.06 | 386097 | 125779.5 | 511876.5 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 20 | 25 | m | 40467 | 9350 | 49817 | 1011675 | 233750 | 1245425 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 40 | 50 | m | 8773.9726 | 14594.0164 | 23367.989 | 438698.6301 | 729700.8206 | 1168399.4507 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | Concrete base for pump | 1 | 1 | lot | 2500000 | 450000 | 2950000 | 2500000 | 450000 | 2950000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Cover for pump | 1 | 1 | lot | 750000 | 200000 | 950000 | 750000 | 200000 | 950000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Hanger + Support | 1 | 1 | lot | 3043495.4122 | 913048.6237 | 3956544.0359 | 3043495.4122 | 913048.6237 | 3956544.0359 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 2028996.9415 | 608699.0824 | 2637696.0239 | 2028996.9415 | 608699.0824 | 2637696.0239 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Valve | [6 empty] | 13303750 | 1140438.52 | 14444188.52 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Pressure Gauges | 1 | 1 | pcs | 1008000 | 49588 | 1057588 | 1008000 | 49588 | 1057588 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | P - 260, KVS/ Turkey
|  | Flexible DN25 | 4 | 4 | pcs | 568800 | 50880.368 | 619680.368 | 2275200 | 203521.472 | 2478721.472 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KVS - 501 T/KVS/ Turkey
|  | Float level indicator | 1 | 1 | pcs | 4200000 | 168000 | 4368000 | 4200000 | 168000 | 4368000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Omron/ Aisa
|  | Float valve DN25 | 1 | 1 | pcs | 770400 | 50880.368 | 821280.368 | 770400 | 50880.368 | 821280.368 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KVS-703T, KVS/ Turkey
|  | Y-Strainer DN25 | 2 | 2 | pcs | 322800 | 50880.368 | 373680.368 | 645600 | 101760.736 | 747360.736 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KVS 200 - T/ KVS/ Turkey
|  | Safety valve DN25 | 1 | 1 | pcs | 1376400 | 50880.368 | 1427280.368 | 1376400 | 50880.368 | 1427280.368 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 3110N, KVS/ Turkey
|  | Check valve DN25 | 3 | 3 | pcs | 480000 | 50880.368 | 530880.368 | 1440000 | 152641.104 | 1592641.104 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KVS - 101/ LVS/ Turkey
|  | Gate valve DN25 | 4 | 4 | pcs | 264000 | 50880.368 | 314880.368 | 1056000 | 203521.472 | 1259521.472 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 402, KVS/Turkey
|  | Accessories | 1 | 1 | lot | 532150 | 159645 | 691795 | 532150 | 159645 | 691795 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Cold water pipe | [6 empty] | 361670.4 | 195125.28 | 556795.68 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | PPR pipe DN50 - PN10 | 5 | 6 | m | 45208.8 | 28000 | 73208.8 | 271252.8 | 168000 | 439252.8 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN, Ø50, 4.6mm, PN10
|  | PPR Fitting | 1 | 1 | lot | 52164 | 15649.2 | 67813.2 | 52164 | 15649.2 | 67813.2 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | Accessories + Support | 1 | 1 | lot | 38253.6 | 11476.08 | 49729.68 | 38253.6 | 11476.08 | 49729.68 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | TOTAL AMOUNT (Not included VAT) | [6 empty] | 2592489399.0247 | 285926135.5267 | 2878415534.5514 | [6 empty] | 114633635.2767 | 0 | 114633635.2767
7. |  | Exterior Area | [6 empty] | 187529525 | 150438500 | 337968025
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
7. 1. |  | Civil Engineering | [6 empty] | 187529525 | 150438500 | 337968025 |  |  | 0 |  |  | 0 | 76910400 | 33266800 | 110177200
7. 1. 50. |  | Excavation | 1 | 1 | PSCH |  |  |  | 86750000 | 108855000 | 195605000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | LV | [6 empty] | 58500000 | 54800000 | 115800000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Manhole 1000x1000x1000 | 5 | 5 | m | 4500000 | 2000000 | 6500000 | 22500000 | 10000000 | 32500000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Excavation and backfilling | 164 | 164 | m3 | 0 | 200000 | 200000 | 0 | 32800000 | 32800000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Concrete crossroads protection | 190 | 120 | m | 300000 | 100000 | 400000 | 36000000 | 12000000 | 48000000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Labor (Remove old cable) | 1 | 1 | m | 0 | 2500000 | 2500000 | 0 | 2500000 | 2500000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | AIR COMPRESSOR | [6 empty] | 1250000 | 4515000 | 5765000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Excavation and backfill | 31 | 20.7 | m3 | 0 | 200000 | 200000 | 0 | 4140000 | 4140000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | The cost of cutting and refinishing the concrete path for the undergruond pipe | 15 | 10 | m | 125000 | 37500 | 162500 | 1250000 | 375000 | 1625000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
|  | ELV |  | 11 |  |  |  |  | 27000000 | 47040000 | 74040000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Khoan đường đi ống | 52 | 52 | m | 0 | 300000 | 300000 | 0 | 15600000 | 15600000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | VN
|  | Manhole 1200x1200x1200 | 4 | 6 | pcs | 4500000 | 2000000 | 6500000 | 27000000 | 12000000 | 39000000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Included labour
|  | Spare fee for Move and reinstall lighting pole if can't excavation pavement | 6 | 6 | pcs | 0 | 1200000 | 1200000 | 0 | 7200000 | 7200000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | VN
|  | Excavation and backfill | 100 | 61.2 | m3 | 0 | 200000 | 200000 | 0 | 12240000 | 12240000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
7. 1. 60. |  | Laying conduits, pipes, etc. | 1 |  | PSCH |  |  |  | 100779525 | 41583500 | 142363025 |  |  | 0 |  |  | 0 | 76910400 | 33266800 | 110177200
|  | LV | [6 empty] | 41773725 | 16061150 | 57834875 |  |  | 0 |  |  | 0 | 29705760 | 12848920 | 42554680
|  | HDPE pipe D160/125 | 340 | 421 | m | 88200 | 38150 | 126350 | 37132200 | 16061150 | 53193350 | 80% |  | 80% | 80% |  | 0.8 | 29705760 | 12848920 | 42554680 | Vietnam
|  | Accessories | 1 | 1 | lot | 4641525 | 0 | 4641525 | 4641525 | 0 | 4641525 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | ELV | [6 empty] | 59005800 | 25522350 | 84528150 |  |  | 0 |  |  | 0 | 47204640 | 20417880 | 67622520
|  | HDPE pipe D160/125 | 848 | 669 | m | 88200 | 38150 | 126350 | 59005800 | 25522350 | 84528150 | 80% |  | 0.8 | 80% |  | 0.8 | 47204640 | 20417880 | 67622520 | Vietnam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | TOTAL AMOUNT (Not included VAT) | [6 empty] | 187529525 | 150438500 | 337968025 | [6 empty] | 76910400 | 33266800 | 110177200
3. |  | Office, Social and Technical Areas (Hall 3) | [6 empty] | 225500372.3178 | 4188800 | 229689172.3178 | [6 empty] | 0 | 0 | 0
[14 empty] | 0 |  |  | 0
3. 3. |  | Mechanical Engineering | [6 empty] | 225500372.3178 | 4188800 | 229689172.3178 |  |  | 0 |  |  | 0 | 0 | 0 | 0
3. 3. 30. |  | Sanitary Furnishings | 1 | 1 | PSCH |  |  |  | 225500372.3178 | 4188800 | 229689172.3178 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | West side | 0 | 0 | m |  |  | 0 | 107848004.152 | 2094400 | 109942404.152 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Equiment kitchen | [6 empty] | 107848004.152 | 2094400 | 109942404.152 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Hafele refrigerator (1-wing refrigerator) | 2 | 2 | pcs | 20093299.732 | 224000 | 20317299.732 | 40186599.464 | 448000 | 40634599.464 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | HF-SBSID.562L/ Hafele/ China
|  | Single sink for kitchen included faucet waster pop up, flexiable, stop valve | 2 | 2 | pcs | 3486000.21 | 280000 | 3766000.21 | 6972000.42 | 560000 | 7532000.42 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | HS19-SSD1R60+HT19-CH1F220/ Hafele/ China
|  | Hafele semi-sonic dishwasher | 2 | 2 | pcs | 15336300.067 | 168000 | 15504300.067 | 30672600.134 | 336000 | 31008600.134 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | HDW-HI60B/ Hafele/ China
|  | Hafele standalone microwave oven | 2 | 2 | pcs | 2807300.067 | 95200 | 2902500.067 | 5614600.134 | 190400 | 5805000.134 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | HW-F23B/ Hafele/ China
|  | Domino's Induction Cooker | 4 | 4 | pcs | 6100551 | 140000 | 6240551 | 24402204 | 560000 | 24962204 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | HC-I302D/ Hafele/ China
|  | Accessories | 1 | 1 | lot | 4902182.0069 | 0 | 4902182.0069 | 4902182.0069 | 0 | 4902182.0069 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | East side | [6 empty] | 112750186.1589 | 2094400 | 114844586.1589 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Equiment kitchen | [6 empty] | 107848004.152 | 2094400 | 109942404.152 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Hafele refrigerator (1-wing refrigerator) | 2 | 2 | pcs | 20093299.732 | 224000 | 20317299.732 | 40186599.464 | 448000 | 40634599.464 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | HF-SBSID.562L/ Hafele/ China
|  | Single sink for kitchen included faucet waster pop up, flexiable, stop valve | 2 | 2 | pcs | 3486000.21 | 280000 | 3766000.21 | 6972000.42 | 560000 | 7532000.42 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | HS19-SSD1R60+HT19-CH1F220/ Hafele/ China
|  | Hafele semi-sonic dishwasher | 2 | 2 | pcs | 15336300.067 | 168000 | 15504300.067 | 30672600.134 | 336000 | 31008600.134 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | HDW-HI60B/ Hafele/ China
|  | Hafele standalone microwave oven | 2 | 2 | pcs | 2807300.067 | 95200 | 2902500.067 | 5614600.134 | 190400 | 5805000.134 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | HW-F23B/ Hafele/ China
|  | Domino's Induction Cooker | 4 | 4 | pcs | 6100551 | 140000 | 6240551 | 24402204 | 560000 | 24962204 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | HC-I302D/ Hafele/ China
|  | Accessories | 1 | 1 | lot | 4902182.0069 | 0 | 4902182.0069 | 4902182.0069 | 0 | 4902182.0069 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | TOTAL AMOUNT (Not included VAT) | [6 empty] | 225500372.3178 | 4188800 | 229689172.3178 | [6 empty] | 0 | 0 | 0
6. |  | Canteen | [6 empty] | 280000000 | 0 | 280000000
6. 1. |  | Civil Engineering | [6 empty] | 280000000 | 0 | 280000000
6. 1. 260. |  | Elevator for goods | [6 empty] | 280000000 | 0 | 280000000 |  |  | 0 |  |  | 0 | 0 |  | 0
|  | Food elevator without person, no loading machine room weight 200kg/02stop/30m/min | 1 | 1 | lot | 280000000 | 0 | 280000000 | 280000000 | 0 | 280000000 |  |  | 0 |  |  | 0 | 0 |  | 0 | DNWW 200-02S-30m/P/DAINAM ELEVATOR Engine with gearbox: Mitsubishi/ Thailand
|  | TOTAL AMOUNT (Not included VAT) | [8 empty] | 280000000 | [8 empty] | 0
0
NHÀ THẦU PHỤ: CÔNG TY CỔ PHẦN HMEP | [12 empty] | NHÀ THẦU CHÍNH: CÔNG TY CỔ PHẦN KỸ THUẬT XÂY DỰNG DINCO | [8 empty] | 0
ĐẠI DIỆN NHÀ THẦU HMEP | [21 empty] | 0
[15 empty] | GIÁM SÁT THI CÔNG | CHỈ HUY TRƯỞNG | [5 empty] | 0
0
0
Note on C224: PC: Cho group A
Note on C227: PC: cho group A

## Bìa
HỒ SƠ THANH TOÁN
ĐỢT 2
DỰ ÁN: VN-RENTAL BUILDING HALL 3 ELECTRIC
HẠNG MỤC: Lắp đặt hệ thống cơ điện
ĐỊA ĐIỂM: Lô D1, Khu công nghiệp Tam Thăng, Huyện Tam Thăng, thành Phố Tam Kỳ, Tỉnh Quảng Nam, Việt Nam
Đà Nẵng, tháng 7 năm 2022

## TONG HOP TT
ADD : 76-78 BACH DANG STREET HAI CHAU DIST, DANANG CITY TEL: (+84-236) 374 3003 FAX: (+84-236) 374 3003
BẢNG TỔNG HỢP GIÁ TRỊ ĐỀ NGHỊ THANH TOÁN
Công trình: |  | VN-RENTAL BUILDING HALL 3 ELECTRIC
Hạng mục: |  | HỆ THỐNG CƠ ĐIỆN
Tên/số hợp đồng thực hiện: |  | 0310/2022/HĐKT-DRX2/DITECHCO-HMEP
Giai đoạn thanh toán / lần thanh toán số: 02
Căn cứ khối lượng đã được nghiệm thu, Nhà thầu xác định giá trị đề nghị thanh toán như sau:
Số TT | Nội dung |  | Đơn vị tính | Thành tiền | Ghi chú
I | GIÁ TRỊ THANH TOÁN KHỐI LƯỢNG HOÀN THÀNH
1 | Giá trị hợp đồng + Phụ lục hợp đồng (trước thuế) |  | VNĐ | 33142000000
2 | Lũy kế giá trị hoàn thành đến cuối kỳ này(Sau thuế) |  | VNĐ | 7800163054
3 | Lũy kế giá trị hoàn thành đến cuối kỳ trước(Sau thuế) |  | VNĐ | 2750518902
4 | Giá trị thực hiện kỳ này(Sau thuế) |  | VNĐ | 5049644152
5 | Giá trị khấu trừ |  | VNĐ
6 | Tổng giá trị thanh toán đến cuối kỳ trước |  | VNĐ | 5779751121.8836
6.1 | Giá trị thanh toán tạm ứng hợp đồng |  | VNĐ | 3579336000
6.2 | Giá trị thanh toán đợt 1 |  | VNĐ | 2200415121.8836
6.3 | Giá trị thanh toán đợt 2 |  | VNĐ
7 | Thanh toán 90% giá trị đợt này((4+5)*90%) |  | VNĐ | 4544679736.8
8 | Khấu trừ giá trị tạm ứng hợp đồng (4*10%) |  | VNĐ | 504964415.2
| Giá trị đề nghị thanh toán đợt 2 (gồm VAT) |  | VNĐ | 4039715321.6
Bằng chữ: | Bốn tỷ không trăm ba mươi chín triệu bảy trăm mười lăm ngàn ba trăm hai hai đồng
NHÀ THẦU CHÍNH : CÔNG TY CỔ PHẦN CƠ ĐIỆN DITECHCO |  |  |  | NHÀ THẦU PHỤ: CÔNG TY CỔ PHẦN HMEP
GIÁM ĐỐC CHỈ HUY TRƯỞNG
NGUYỄN NGỌC TUẤN CAO XUÂN TRƯỜNG |  |  |  | NGUYỄN HỮU HUẤN

## GT TTHT CV DOT 2
BẢNG GIÁ TRỊ HOÀN THÀNH THANH TOÁN ĐỢT 2
- Tên/số hợp đồng xây dựng :0310/2022/HĐKT-DRX2/DITECHCO-HMEP
- Bên giao thầu :CÔNG TY CỔ PHẦN CƠ ĐIỆN DITECHCO
- Bên nhận thầu : CÔNG TY CỔ PHẦN HMEP
- Hạng mục :Hệ thống Cơ điện
- Dự án: VN-RENTAL BUILDING HALL 3 ELECTRIC
- Giai đoạn :Thanh toán đợt 2
Position |  | Headline | Quantity | Quantity By contractor | Unit | Material Unit | Labor Unit | Unit rate | Material Amount | Labor Amount | Amount (VND) | % Công việc hoàn thành công việc |  | % Công việc hoàn thành đến cuối kỳ này |  |  |  |  | Giá trị hoàn thành đợt 1 |  |  | Giá trị hoàn thành đợt 2 |  |  | Giá trị lũy kế hoàn thành đế kỳ này
[12 empty] | Đợt 1 | Đợt 2 |  | % KL hoàn thành lũy kế | Đợt 2 | Đợt 3 | % KL hoàn thành lũy kế | Vật tư | Nhân công | Tổng | Vật tư | Nhân công | Tổng
[9 empty] | 28376030449.4456 | 4765969550.5543 | 33142000000 | [7 empty] | 1910783535.5017 | 389293225.9376 | 2546776761.4393 | 3829523852.514 | 632672584.8418 | 4675596437.3559 | 7222373198.7952
|  | I. ELEC | [6 empty] | 16563842018.9792 | 1773285626.6565 | 18337127645.6357
1. |  | Construction site facilities | [8 empty] | 0
[12 empty] | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. 1. |  | Construction site facilities | 1 |  | psch | [5 empty] | 0 | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. 2. |  | Construction site cameras | 1 |  | psch | [5 empty] | 0 | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. |  | Production and Logistic building (Hall 3) | [6 empty] | 4384819997.1499 | 819871975.3259 | 5204691972.4758 |  |  |  | 0% |  |  | #REF! | 972736489.7747 | 215672140.723 | 1188408630.4977 | 1144321266.1001 | 237469724.5256 | 1381790990.6257 | 2570199621.1234
[12 empty] | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1. |  | Civil Engineering | 1 |  | PSCH | [9 empty] | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 10. |  | Calculations | 1 |  | PSCH | [5 empty] | 0 | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 20. |  | Rainwater and waste water sewer | 1 |  | PSCH | [5 empty] | 0 | 0 |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 30. |  | Earthworks | 1 |  | PSCH | [5 empty] | 0 | 0 |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 40. |  | Demolition, removal and dismantling works | 1 |  | PSCH | [5 empty] | 0 | 0 |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 50. |  | Foundation | 1 |  | PSCH | [5 empty] | 0 | 0 |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 60. |  | Building structure | 1 |  | PSCH | [5 empty] | 0 | 0 |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 70. |  | General concrete- / reinforced concrete works | 1 |  | PSCH | [5 empty] | 0 | 0 |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 80. |  | Fire protection | 1 |  | PSCH | [5 empty] | 0 | 0 |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 90. |  | Fire rated walls | 1 |  | PSCH | [5 empty] | 0 | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 100. |  | Cutting base slabs / ceilings / floors | 1 |  | PSCH | [5 empty] | 0 | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 110. |  | Cutting holes into existing facades, walls and roofs | 1 |  | PSCH | [5 empty] | 0 | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 120. |  | Exterior walls | 1 |  | PSCH | [5 empty] | 0 | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 130. |  | Exterior doors and windows | 1 |  | PSCH | [5 empty] | 0 | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 140. |  | Fire protection doors | 1 |  | PSCH | [5 empty] | 0 | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 150. |  | Internal doors | 1 |  | PSCH | [5 empty] | 0 | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 160. |  | Fire protection roller shutter door | 1 |  | PSCH | [5 empty] | 0 | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 170. |  | Fire protection bulkhead | 1 |  | PSCH | [5 empty] | 0 | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 180. |  | High speed roller shutter | 1 |  | PSCH | [5 empty] | 0 | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 190. |  | Fitting and metal work - general | 1 |  | PSCH | [5 empty] | 0 | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 200. |  | Railings and hand rails | 1 |  | PSCH | [5 empty] | 0 | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 210. |  | Steel stage for installations | 1 |  | PSCH | [5 empty] | 0 | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 220. |  | Collision protection | 1 |  | PSCH | [5 empty] | 0 | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 230. |  | canopies of exterior doors | 1 |  | PSCH | [5 empty] | 0 | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 240. |  | Concerete steps in front of the hall | 1 |  | PSCH | [5 empty] | 0 | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 250. |  | Painting and varnishing works | 1 |  | PSCH | [5 empty] | 0 | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 260. |  | Guidance systems | 1 |  | PSCH | [5 empty] | 0 | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 270. |  | Locking system | 1 |  | PSCH | [5 empty] | 0 | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 280. |  | Internal signage | 1 |  | PSCH | [5 empty] | 0 | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 290. |  | Adjustment ridge vent | 1 |  | PSCH | [5 empty] | 0 | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 300. |  | Roof reinforcment Option 1 | 1 |  | PSCH | [5 empty] | 0 | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 310. |  | Insert new ventilation louvers | 1 |  | PSCH | [5 empty] | 0 | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 1. 320. |  | Metal louvers to cover mechanical units | 1 |  | PSCH | [5 empty] | 0 | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% |  |  | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 2. |  | Electrical Engineering | 1 |  | PSCH |  |  |  | 4384819997.1499 | 819871975.3259 | 5204691972.4758 |  |  |  | 0% |  |  | #REF! | 972736489.7747 | 215672140.723 | 1188408630.4977 | 1144321266.1001 | 237469724.5256 | 1381790990.6257 | 2570199621.1234
2. 2. 10. |  | Adjustment of existing facilities, dismantling and disposal works | 1 | 1 | PSCH |  |  |  | 0 | 24400000 | 24400000 |  | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 11200000 | 11200000 | 11200000
|  | The cost of dismantling electrical distribution board, trunking & ladder and lighting system existing system | 1 | 1 | lot | 0 | 14000000 | 14000000 | 0 | 14000000 | 14000000 | 0% | 80% | 80% | 160% |  |  | #REF! | 0 | 0 | 0 | 0 | 11200000 | 11200000 | 11200000
|  | Opening (inluded supports & waterproof) for wall through ductwork fee | 1 | 1 | lot | 0 | 10400000 | 10400000 | 0 | 10400000 | 10400000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 2. 20. |  | Rennovation existing grounding system and lightning protection | 1 | 1 | PSCH | 0 | 5000000 | 5000000 | 0 | 5000000 | 5000000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 2. 30. |  | Rennovation existing grounding and equipotential bonding | 1 | 1 | PSCH | 0 | 2500000 | 2500000 | 0 | 2500000 | 2500000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 2. 40. |  | Power supply | 1 | 1 | PSCH |  |  |  | 1266144274.1142 | 405876628.1459 | 1672020902.2601 | 0% | 0% | 0% | 0% |  |  | #REF! | 438165176.5775 | 140647592.8893 | 578812769.4668 | 397467099.9608 | 125341531.1352 | 522808631.096 | 1101621400.5628
|  | From DB SYN-TR1 Panel to Building 3_BMDP | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 6x(4x1Cx300mm2)+E240mm2 | 67 | 64.9 | m | 2672599.35 | 818400 | 3490999.35 | 173451697.815 | 53114160 | 226565857.815 | 36% | 39% | 75% | 150% |  |  | #REF! | 62442611.2134 | 19121097.6 | 81563708.8134 | 67646162.1479 | 20714522.4 | 88360684.5479 | 169924393.3613
| Option1 | From DB SYN-TR1 Panel to Building 3_BMDP | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 5x(4x1Cx240mm2)+E240mm2 | 67 | 67 | m | 15029239.743 | 686400 |  |  |  |  | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | From Building 3_BMDP Panel to Building 3_PDP 1.0 | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 4x1Cx300mm2+E150mm2 | 15 | 14 | m | 481493.34 | 158400 | 639893.34 | 6740906.76 | 2217600 | 8958506.76 | 36% | 39% | 75% | 150% |  |  | #REF! | 2426726.4336 | 798336 | 3225062.4336 | 2628953.6364 | 864864 | 3493817.6364 | 6718880.07
|  | From Building 3_BMDP Panel to Building 3_PDP 1.1 | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 2x(4x1Cx185mm2)+E185mm2 | 116 | 106 | m | 618512.88 | 176000 | 794512.88 | 65562365.28 | 18656000 | 84218365.28 | 36% | 39% | 75% | 150% |  |  | #REF! | 23602451.5008 | 6716160 | 30318611.5008 | 25569322.4592 | 7275840 | 32845162.4592 | 63163773.96
|  | From Building 3_BMDP Panel to Building 3_PDP 2.0 | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 3x(3x1Cx240mm2)+N1Cx240mm2+E120mm2 | 182 | 203.5 | m | 909229.53 | 304700 | 1213929.53 | 185028209.355 | 62006450 | 247034659.355 | 36% | 39% | 75% | 150% |  |  | #REF! | 66610155.3678 | 22322322 | 88932477.3678 | 72161001.6485 | 24182515.5 | 96343517.1485 | 185275994.5163
|  | From Building 3_BMDP Panel to Building 3_PDP 1.2 | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 3x(3x1Cx240mm2)+N2x1Cx240mm2+E185mm2 | 135 | 143 | m | 1018095.6 | 304700 | 1322795.6 | 145587670.8 | 43572100 | 189159770.8 | 36% | 39% | 75% | 150% |  |  | #REF! | 52411561.488 | 15685956 | 68097517.488 | 56779191.612 | 16993119 | 73772310.612 | 141869828.1
|  | From Building 3_BMDP Panel to Building 3_PDP 2.1 | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 3x(3x1Cx240mm2)+N2x1Cx240mm2+E185mm2 | 136 | 137 | m | 1018095.6 | 304700 | 1322795.6 | 139479097.2 | 41743900 | 181222997.2 | 36% | 39% | 75% | 150% |  |  | #REF! | 50212474.992 | 15027804 | 65240278.992 | 54396847.908 | 16280121 | 70676968.908 | 135917247.9
|  | From Building 3_BMDP Panel to Building 3_BDP 1.0 | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 4x1Cx150mm2+E70mm2 | 70 | 16.5 | m | 247104.54 | 116765.3025 | 363869.8425 | 4077224.91 | 1926627.4913 | 6003852.4013 | 36% | 39% | 75% | 150% |  |  | #REF! | 1467800.9676 | 693585.8969 | 2161386.8645 | 1590117.7149 | 751384.7216 | 2341502.4365 | 4502889.3009
|  | From Building 3_BMDP Panel to Building 3_BDP 1.1 | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 2x(4x1Cx150mm2)+E150mm2 | 15 | 99 | m | 497079.9 | 138600 | 635679.9 | 49210910.1 | 13721400 | 62932310.1 | 36% | 39% | 75% | 150% |  |  | #REF! | 17715927.636 | 4939704 | 22655631.636 | 19192254.939 | 5351346 | 24543600.939 | 47199232.575
|  | From Building 3_BMDP Panel to Building 3_BDP 2.0 | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 3x(3x1Cx240mm2)+N2x1Cx185mm2+E185mm2 | 116 | 191.1 | m | 1018095.6 | 304700 | 1322795.6 | 194558069.16 | 58228170 | 252786239.16 | 36% | 39% | 75% | 150% |  |  | #REF! | 70040904.8976 | 20962141.2 | 91003046.0976 | 75877646.9724 | 22708986.3 | 98586633.2724 | 189589679.37
|  | From Building 3_BMDP Panel to Scooter garage BDP 1.0 | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 4x1Cx35mm2+E16mm2 | 131 | 86 | m | 70862.76 | 46119.15 | 116981.91 | 6094197.36 | 3966246.9 | 10060444.26 | 36% | 0% | 36% | 72% |  |  | #REF! | 2193911.0496 | 1427848.884 | 3621759.9336 | 0 | 0 | 0 | 3621759.9336
|  | From Building 3_BMDP Panel to Canteen BDP 1.0 | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 3x1Cx120mm2+N1Cx25mm2+E16mm2 | 174 | 181 | m | 165603.51 | 101462.13 | 267065.64 | 29974235.31 | 18364645.53 | 48338880.84 | 36% | 0% | 36% | 72% |  |  | #REF! | 10790724.7116 | 6611272.3908 | 17401997.1024 | 0 | 0 | 0 | 17401997.1024
|  | From Building 3_BDP 1.1 Panel to Building 3_UPS1-100 kVA | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 4x1Cx70mm2+E35mm2 | 106 | 121 | m | 128659.23 | 83182.176 | 211841.406 | 15567766.83 | 10065043.296 | 25632810.126 | 36% | 0% | 36% | 72% |  |  | #REF! | 5604396.0588 | 3623415.5866 | 9227811.6454 | 0 | 0 | 0 | 9227811.6454
|  | From Building 3 UPS1-MDP Panel to Building 3_UPS 1 DP 1.3 35kVA | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 4x1Cx70mm2+E35mm2 | 20 | 18.7 | m | 128659.23 | 83182.176 | 211841.406 | 2405927.601 | 1555506.6912 | 3961434.2922 | 36% | 0% | 36% | 72% |  |  | #REF! | 866133.9364 | 559982.4088 | 1426116.3452 | 0 | 0 | 0 | 1426116.3452
|  | From Building 3_BDP 2.0 Panel to Building 3_UPS2-100 kVA | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 4x1Cx70mm2+E35mm2 | 18 | 27.5 | m | 128659.23 | 83182.176 | 211841.406 | 3538128.825 | 2287509.84 | 5825638.665 | 36% | 0% | 36% | 72% |  |  | #REF! | 1273726.377 | 823503.5424 | 2097229.9194 | 0 | 0 | 0 | 2097229.9194
|  | From Building 3 UPS1-MDP Panel to Building 3_UPS 2 DP 1.3 35kVA | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 4x1Cx70mm2+E35mm2 | 25 | 27.5 | m | 128659.23 | 83182.176 | 211841.406 | 3538128.825 | 2287509.84 | 5825638.665 | 36% | 0% | 36% | 72% |  |  | #REF! | 1273726.377 | 823503.5424 | 2097229.9194 | 0 | 0 | 0 | 2097229.9194
|  | From Building 3 UPS1-MDP Panel to Building 3 UPS 2-DP1.2 | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 3Cx10mm2 | 185 | 184.8 | m | 102150.27 | 17818.7625 | 119969.0325 | 18877369.896 | 3292907.31 | 22170277.206 | 36% | 0% | 36% | 72% |  |  | #REF! | 6795853.1626 | 1185446.6316 | 7981299.7942 | 0 | 0 | 0 | 7981299.7942
|  | From Building 3 UPS1-MDP Panel to Building 3 UPS 2-DP1.3 | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 3Cx6mm2 | 115 | 105 | m | 65470.44 | 17189.865 | 82660.305 | 6874396.2 | 1804935.825 | 8679332.025 | 36% | 0% | 36% | 72% |  |  | #REF! | 2474782.632 | 649776.897 | 3124559.529 | 0 | 0 | 0 | 3124559.529
|  | From Building 3 UPS1-MDP Panel to Building 3_UPS 1 DP 1.3 35kVA | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 4x1Cx50mm2+E10mm2 | 115 | 90 | m | 166514.94 | 52580 | 219094.94 | 14986344.6 | 4732200 | 19718544.6 | 36% | 0% | 36% | 72% |  |  | #REF! | 5395084.056 | 1703592 | 7098676.056 | 0 | 0 | 0 | 7098676.056
|  | From Building 3 UPS1-MDP Panel to PDU | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 590 | 480 | m | 32518.74 | 7485.665 | 40004.405 | 15608995.2 | 3593119.2 | 19202114.4 | 36% | 0% | 36% | 72% |  |  | #REF! | 5619238.272 | 1293522.912 | 6912761.184 | 0 | 0 | 0 | 6912761.184
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | From Building 3_BDP 2.0 Panel to Building 3_UPS2-100 kVA | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 4x1Cx35mm2+E16mm2 | 18 | 27.5 | m | 448964.76 | 46119.15 | 495083.91 | 12346530.9 | 1268276.625 | 13614807.525 | 36% | 0% | 36% | 72% |  |  | #REF! | 4444751.124 | 456579.585 | 4901330.709 | 0 | 0 | 0 | 4901330.709
|  | From Building 3 UPS2-MDP Panel to Building 3 UPS 2-DP1.2 | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 3Cx4mm2 | 25 | 20 | m | 46999.53 | 9969.2395 | 56968.7695 | 939990.6 | 199384.79 | 1139375.39 | 36% | 0% | 36% | 72% |  |  | #REF! | 338396.616 | 71778.5244 | 410175.1404 | 0 | 0 | 0 | 410175.1404
|  | From Building 3 UPS1-MDP Panel to Building 3 UPS 2-DP1.2 | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 3Cx10mm2 | 180 | 193.6 | m | 102150.27 | 17818.7625 | 119969.0325 | 19776292.272 | 3449712.42 | 23226004.692 | 36% | 0% | 36% | 72% |  |  | #REF! | 7119465.2179 | 1241896.4712 | 8361361.6891 | 0 | 0 | 0 | 8361361.6891
|  | From Building 3 UPS1-MDP Panel to Building 3 UPS 2-DP1.2 | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 3Cx6mm2 | 115 | 187 | m | 65470.44 | 14173.4395 | 79643.8795 | 12242972.28 | 2650433.1865 | 14893405.4665 | 36% | 0% | 36% | 72% |  |  | #REF! | 4407470.0208 | 954155.9471 | 5361625.9679 | 0 | 0 | 0 | 5361625.9679
|  | From Building 3 UPS1-MDP Panel to Building 3_UPS 2 DP 1.3 35kVA | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 4x1Cx50mm2+E10mm2 | 115 | 117.7 | m | 166514.94 | 52580 | 219094.94 | 19598808.438 | 6188666 | 25787474.438 | 36% | 0% | 36% | 72% |  |  | #REF! | 7055571.0377 | 2227919.76 | 9283490.7977 | 0 | 0 | 0 | 9283490.7977
|  | From Building 3 UPS2-MDP Panel to PDU | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 590 | 480 | m | 32518.74 | 7485.665 | 40004.405 | 15608995.2 | 3593119.2 | 19202114.4 | 36% | 0% | 36% | 72% |  |  | #REF! | 5619238.272 | 1293522.912 | 6912761.184 | 0 | 0 | 0 | 6912761.184
|  | From DB PDP 1.2 Panel to Cetral feeding unit 1 | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 4x1Cx150mm2+E70mm2 | 24 | 26.4 | m | 247104.54 | 116765.3025 | 363869.8425 | 6523559.856 | 3082603.986 | 9606163.842 | 36% | 39% | 75% | 150% |  |  | #REF! | 2348481.5482 | 1109737.435 | 3458218.9831 | 2544188.3438 | 1202215.5545 | 3746403.8984 | 7204622.8815
|  | From DB PDP 1.2 Panel to Cetral feeding unit 2 | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 4x1Cx150mm2+E70mm2 | 16 | 17.6 | m | 247104.54 | 116765.3025 | 363869.8425 | 4349039.904 | 2055069.324 | 6404109.228 | 36% | 39% | 75% | 150% |  |  | #REF! | 1565654.3654 | 739824.9566 | 2305479.3221 | 1696125.5626 | 801477.0364 | 2497602.5989 | 4803081.921
|  | From DB PDP 1.2 Panel to Cetral feeding unit 3 | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 4x1Cx150mm2+E70mm2 | 57 | 68.2 | m | 247104.54 | 116765.3025 | 363869.8425 | 16852529.628 | 7963393.6305 | 24815923.2585 | 36% | 39% | 75% | 150% |  |  | #REF! | 6066910.6661 | 2866821.707 | 8933732.3731 | 6572486.5549 | 3105723.5159 | 9678210.0708 | 18611942.4439
|  | From DB PDP 2.1 Panel to Cetral feeding unit 1 | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 4x1Cx150mm2+E70mm2 | 24 | 26.4 | m | 247104.54 | 116765.3025 | 363869.8425 | 6523559.856 | 3082603.986 | 9606163.842 | 36% | 39% | 75% | 150% |  |  | #REF! | 2348481.5482 | 1109737.435 | 3458218.9831 | 2544188.3438 | 1202215.5545 | 3746403.8984 | 7204622.8815
|  | From DB PDP 2.1 Panel to Cetral feeding unit 2 | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 4x1Cx150mm2+E70mm2 | 16 | 17.6 | m | 247104.54 | 116765.3025 | 363869.8425 | 4349039.904 | 2055069.324 | 6404109.228 | 36% | 39% | 75% | 150% |  |  | #REF! | 1565654.3654 | 739824.9566 | 2305479.3221 | 1696125.5626 | 801477.0364 | 2497602.5989 | 4803081.921
|  | From DB PDP 2.1 Panel to Cetral feeding unit 3 | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable AL/XLPE/PVC 4x1Cx150mm2+E70mm2 | 57 | 68.2 | m | 247104.54 | 116765.3025 | 363869.8425 | 16852529.628 | 7963393.6305 | 24815923.2585 | 36% | 39% | 75% | 150% |  |  | #REF! | 6066910.6661 | 2866821.707 | 8933732.3731 | 6572486.5549 | 3105723.5159 | 9678210.0708 | 18611942.4439
|  | Accessories | 1 | 1 | lot | 49018783.6212 | 15188870.1199 | 64207653.7411 | 49018783.6212 | 15188870.1199 | 64207653.7411 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 2. 50. |  | Energy measurement system | 1 | 1 | PSCH |  |  |  | 315804122.0768 | 12524296.2357 | 328328418.3125 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | SOFTWARE PRODUCTS | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pre-parameterization per device | 11 | 11 | pcs | 343200 | 0 | 343200 | 3775200 | 0 | 3775200 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | visual energy ZP5 | 3 | 3 | pcs | 6063200 | 0 | 6063200 | 18189600 | 0 | 18189600 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hourly rate for remote services, Costs per hour / co-worker | 11 | 11 | pcs | 3832400 | 0 | 3832400 | 42156400 | 0 | 42156400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Freight charges | 1 | 1 | lot | 5291000 | 0 | 5291000 | 5291000 | 0 | 5291000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 3344406 | 1003321.8 | 4347727.8 | 3344406 | 1003321.8 | 4347727.8 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MULTI METERS | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Multimess F144 | 11 | 11 | pcs | 21251230 | 275000 | 21526230 | 233763530 | 3025000 | 236788530 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ELV cable | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cat6A | 330 | 330 | m | 21639.3443 | 3360 | 24999.3443 | 7140983.6066 | 1108800 | 8249783.6066 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 150 | 150 | m | 8773.9726 | 14594.0164 | 23367.989 | 1316095.8904 | 2189102.4618 | 3505198.3522 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 826906.5798 | 248071.974 | 1074978.5538 | 826906.5798 | 248071.974 | 1074978.5538 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ENGINEERING SERVICES | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Labour cost for support DRX test funtion of Access control system | 1 | 1 | lot | 0 | 4950000 | 4950000 | 0 | 4950000 | 4950000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 2. 60. |  | Electrical installation in the production hall | 1 | 1 | PSCH |  |  |  | 2359220157.2575 | 298880144.662 | 2658100301.9195 | 0% | 0% | 0% | 0% |  |  | #REF! | 456722250.1452 | 62718946.9424 | 519441197.0876 | 652931167.4073 | 87736023.8099 | 740667191.2172 | 1260108388.3049
|  | Cable trays_Hot dip-Galvanized Steel | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
|  | Production hall 01 | [6 empty] | 1059238180 | 131854511.8676 | 1191092691.8676 | 0% | 0% | 0% | 0% |  |  | #REF! | 317771454 | 39556353.5603 | 357327807.5603 | 476657181 | 59334530.3404 | 535991711.3404 | 893319518.9007
|  | Cable tray 500x100x2.0mm | 0 | 0 | m | 1443780 | 81001.3848 | 1524781.3848 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable tray 300x100x2.0mm | 0 | 129.8 | m | 1009710 | 61078.452 | 1070788.452 | 131060358 | 7927983.0721 | 138988341.0721 | 30% | 45% | 75% | 25% |  |  | #REF! | 39318107.4 | 2378394.9216 | 41696502.3216 | 58977161.1 | 3567592.3824 | 62544753.4824 | 104241255.8041
|  | Cable tray 200x100x2.0mm | 13 | 129.8 | m | 776880 | 51045.8655 | 827925.8655 | 100839024 | 6625753.3383 | 107464777.3383 | 30% | 45% | 75% | 25% |  |  | #REF! | 30251707.2 | 1987726.0015 | 32239433.2015 | 45377560.8 | 2981589.0022 | 48359149.8022 | 80598583.0037
|  | Cable tray 500x100 with separating bar, c/w cover | 185 | 215.6 | m | 1525680 | 81001.3848 | 1606681.3848 | 328936608 | 17463898.5532 | 346400506.5532 | 30% | 45% | 75% | 25% |  |  | #REF! | 98680982.4 | 5239169.566 | 103920151.966 | 148021473.6 | 7858754.3489 | 155880227.9489 | 259800379.9149
|  | Cable tray 400x100 with separating bar, c/w cover | 232 | 269.5 | m | 826020 | 68320 | 894340 | 222612390 | 18412240 | 241024630 | 30% | 45% | 75% | 25% |  |  | #REF! | 66783717 | 5523672 | 72307389 | 100175575.5 | 8285508 | 108461083.5 | 180768472.5
|  | Cable tray 300x100 with separating bar, c/w cover | 112 | 0 | m | 1091610 | 61078.452 | 1152688.452 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable tray 200x100 with separating bar, c/w cover | 112 | 0 | m | 858780 | 51045.8655 | 909825.8655 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable tray 200x50 with separating bar, c/w cover | 187 | 0 | m | 669240 | 51045.8655 | 720285.8655 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable ladder 600x100x2.0mm, c/w cover | 9 | 0 | m | 1199250 | 91952 | 1291202 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable ladder 500x100x2.0mm, c/w cover | 0 | 0 | m | 1067040 | 81001.3848 | 1148041.3848 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable ladder 400x100x2.0mm, c/w cover | 5 | 5 | m | 933660 | 68320 | 1001980 | 4668300 | 341600 | 5009900 | 30% | 45% | 75% | 25% |  |  | #REF! | 1400490 | 102480 | 1502970 | 2100735 | 153720 | 2254455 | 3757425
|  | Cable ladder 300x100x1.5mm, c/w cover | 2 | 2 | m | 625950 | 61078.452 | 687028.452 | 1251900 | 122156.904 | 1374056.904 | 30% | 45% | 75% | 25% |  |  | #REF! | 375570 | 36647.0712 | 412217.0712 | 563355 | 54970.6068 | 618325.6068 | 1030542.678
|  | Fitting and accessories | 1 | 1 | lot | 269869600 | 80960880 | 350830480 | 269869600 | 80960880 | 350830480 | 30% | 45% | 75% | 25% |  |  | #REF! | 80960880 | 24288264 | 105249144 | 121441320 | 36432396 | 157873716 | 263122860
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Production hall 02 | [6 empty] | 205951658 | 26469471.7777 | 232421129.7777 | 0% | 0% | 0% | 0% |  |  | #REF! | 61785497.4 | 7940841.5333 | 69726338.9333 | 92678246.1 | 11911262.3 | 104589508.4 | 174315847.3333
|  | Cable tray 500x100x2.0mm | 0 |  | m | 1443780 | 81001.3848 | 1524781.3848 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable tray 300x100x2.0mm | 0 |  | m | 1009710 | 61078.452 | 1070788.452 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable tray 200x100x2.0mm | 10 |  | m | 776880 | 51045.8655 | 827925.8655 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable tray 500x100 with separating bar, c/w cover | 0 |  | m | 1525680 | 81001.3848 | 1606681.3848 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable tray 400x100 with separating bar, c/w cover | 64 | 73.7 | m | 826020 | 68320 | 894340 | 60877674 | 5035184 | 65912858 | 30% | 45% | 75% | 25% |  |  | #REF! | 18263302.2 | 1510555.2 | 19773857.4 | 27394953.3 | 2265832.8 | 29660786.1 | 49434643.5
|  | Cable tray 300x100 with separating bar, c/w cover | 0 | 0 | m | 1091610 | 61078.452 | 1152688.452 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable tray 200x100 with separating bar, c/w cover | 82 | 94.6 | m | 858780 | 51045.8655 | 909825.8655 | 81240588 | 4828938.8737 | 86069526.8737 | 30% | 45% | 75% | 25% |  |  | #REF! | 24372176.4 | 1448681.6621 | 25820858.0621 | 36558264.6 | 2173022.4931 | 38731287.0931 | 64552145.1552
|  | Cable tray 200x50 with separating bar, c/w cover | 66 | 0 | m | 669240 | 51045.8655 | 720285.8655 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable ladder 600x100x2.0mm, c/w cover | 0 | 0 | m | 1199250 | 91952 | 1291202 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable ladder 500x100x2.0mm, c/w cover | 0 | 0 | m | 1067040 | 81001.3848 | 1148041.3848 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable ladder 400x100x2.0mm, c/w cover | 11 | 11 | m | 933660 | 68320 | 1001980 | 10270260 | 751520 | 11021780 | 30% | 45% | 75% | 25% |  |  | #REF! | 3081078 | 225456 | 3306534 | 4621617 | 338184 | 4959801 | 8266335
|  | Cable ladder 300x100x1.5mm, c/w cover | 0 | 0 | m | 625950 | 61078.452 | 687028.452 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable ladder 200x100x1.5mm, c/w cover | 2 | 2.2 | m | 496080 | 51045.8655 | 547125.8655 | 1091376 | 112300.904 | 1203676.904 | 30% | 45% | 75% | 25% |  |  | #REF! | 327412.8 | 33690.2712 | 361103.0712 | 491119.2 | 50535.4068 | 541654.6068 | 902757.678
|  | Fitting and accessories | 1 | 1 | lot | 52471760 | 15741528 | 68213288 | 52471760 | 15741528 | 68213288 | 30% | 45% | 75% | 25% |  |  | #REF! | 15741528 | 4722458.4 | 20463986.4 | 23612292 | 7083687.6 | 30695979.6 | 51159966
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Electrical installation | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Production hall 01 | [6 empty] | 4068960 | 2081884 | 6150844 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2-Way switch, 1 gang for lighting control panel | 0 | 0 | pcs | 0 | 54500 | 54500 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single Socket NEMA5 | 10 | 10 | pcs | 124560 | 54500 | 179060 | 1245600 | 545000 | 1790600 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Double Socket NEMA5 | 0 | 0 | pcs | 249120 | 54500 | 303620 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single Socket 16A/230V, Lighting outlet general (wall) + Plug | 18 | 18 | pcs | 124560 | 54500 | 179060 | 2242080 | 981000 | 3223080 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Socket combination type 1 | 1 | 1 | pcs | 0 | 381500 | 381500 | 0 | 381500 | 381500 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 581280 | 174384 | 755664 | 581280 | 174384 | 755664 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Production hall 02 | [6 empty] | 1017240 | 425096 | 1442336 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2-Way switch, 1 gang for lighting control panel | 0 | 0 | pcs | 0 | 54500 | 54500 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single Socket NEMA5 | 2 | 2 | pcs | 124560 | 54500 | 179060 | 249120 | 109000 | 358120 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Double Socket NEMA5 | 0 | 0 | pcs | 249120 | 54500 | 303620 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single Socket 16A/230V, Lighting outlet general (wall) + Plug | 5 | 5 | pcs | 124560 | 54500 | 179060 | 622800 | 272500 | 895300 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 145320 | 43596 | 188916 | 145320 | 43596 | 188916 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lighting | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Production hall 01 | [6 empty] | 891792936.3239 | 117504814.1732 | 1009297750.4972 | 0% | 0% | 0% | 0% |  |  | #REF! | 69616780.8732 | 13464503.9872 | 83081284.8604 | 75418179.2793 | 14586545.9862 | 90004725.2655 | 173086010.1259
|  | Led Highbay light 115W, Type CI | 154 | 154 | pcs | 4081000 | 196000 | 4277000 | 628474000 | 30184000 | 658658000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Frame Lamp 1x46W, Type BII | 2 | 2 | pcs | 1607100 | 63504 | 1670604 | 3214200 | 127008 | 3341208 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Wall mounted Light 1x15W, Type E | 18 | 18 | pcs | 585200 | 63504 | 648704 | 10533600 | 1143072 | 11676672 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 19140000 | 3828000 | 22968000 | 19140000 | 3828000 | 22968000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable for lighting system (Hall 01) | [6 empty] | 230431136.3239 | 82222734.1732 | 312653870.4972 | 0% | 0% | 0% | 0% |  |  | #REF! | 69616780.8732 | 13464503.9872 | 83081284.8604 | 75418179.2793 | 14586545.9862 | 90004725.2655 | 173086010.1259
|  | Cable Cu/XLPE//PVC 3Cx4.0mm2 | 565 | 800 | m | 46999.53 | 8250 | 55249.53 | 37599624 | 6600000 | 44199624 | 36% | 39% | 75% | 150% |  |  | #REF! | 13535864.64 | 2376000 | 15911864.64 | 14663853.36 | 2574000 | 17237853.36 | 33149718
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 2404 | 2550 | m | 32518.74 | 7485.665 | 40004.405 | 82922787 | 19088445.75 | 102011232.75 | 36% | 39% | 75% | 150% |  |  | #REF! | 29852203.32 | 6871840.47 | 36724043.79 | 32339886.93 | 7444493.8425 | 39784380.7725 | 76508424.5625
|  | Cable Cu/XLPE//PVC 3Cx1.5mm2 | 359 | 889 | m | 22980.09 | 5743.9305 | 28724.0205 | 20429300.01 | 5106354.2145 | 25535654.2245 | 36% | 39% | 75% | 150% |  |  | #REF! | 7354548.0036 | 1838287.5172 | 9192835.5208 | 7967427.0039 | 1991478.1437 | 9958905.1476 | 19151740.6684
|  | PVC conduit D20 | 1061 | 1850 | m | 8773.9726 | 14594.0164 | 23367.989 | 16231849.3151 | 26998930.3618 | 43230779.6768 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D32(cho PA đổi cáp 3x6mm group A) |  | 749 | m | 19428.0822 | 20044.0164 | 39472.0986 | 14551633.5616 | 15012968.2924 | 29564601.8541 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC flexible conduct D20 | 220 | 220 | m | 3554.7229 | 5289.7059 | 8844.4288 | 782039.0424 | 1163735.2941 | 1945774.3365 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 5485667.5348 | 1645700.2604 | 7131367.7953 | 5485667.5348 | 1645700.2604 | 7131367.7953 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/XLPE//PVC 3Cx6.0mm2 |  | 800.8 | m | 65469.825 | 8250 | 73719.825 | 52428235.86 | 6606600 | 59034835.86 | 36% | 39% | 75% | 150% |  |  | #REF! | 18874164.9096 | 2378376 | 21252540.9096 | 20447011.9854 | 2576574 | 23023585.9854 | 44276126.895
|  | Production hall 02 | [6 empty] | 171116000 | 9147520 | 180263520 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Led Highbay light 115W, Type CI | 40 | 40 | pcs | 4081000 | 196000 | 4277000 | 163240000 | 7840000 | 171080000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Frame Lamp 1x46W, Type BII | 0 | 0 | pcs | 1607100 | 63504 | 1670604 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Wall mounted Light 1x15W, Type E | 5 | 5 | pcs | 585200 | 63504 | 648704 | 2926000 | 317520 | 3243520 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 4950000 | 990000 | 5940000 | 4950000 | 990000 | 5940000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable for lighting system (Hall 02) | [6 empty] | 26035182.9336 | 11396846.8435 | 37432029.777 | 0% | 0% | 0% | 0% |  |  | #REF! | 7548517.872 | 1757247.8616 | 9305765.7336 | 8177561.028 | 1903685.1834 | 10081246.2114 | 19387011.945
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 536 | 560 | m | 32518.74 | 7485.665 | 40004.405 | 18210494.4 | 4191972.4 | 22402466.8 | 36% | 39% | 75% | 150% |  |  | #REF! | 6555777.984 | 1509110.064 | 8064888.048 | 7102092.816 | 1634869.236 | 8736962.052 | 16801850.1
|  | Cable Cu/XLPE//PVC 3Cx1.5mm2 | 96 | 120 | m | 22980.09 | 5743.9305 | 28724.0205 | 2757610.8 | 689271.66 | 3446882.46 | 36% | 39% | 75% | 150% |  |  | #REF! | 992739.888 | 248137.7976 | 1240877.6856 | 1075468.212 | 268815.9474 | 1344284.1594 | 2585161.845
|  | PVC conduit D20 | 277 | 398.2 | m | 8773.9726 | 14594.0164 | 23367.989 | 3493795.8904 | 5811337.3352 | 9305133.2256 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 88 | 0 | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC flexible conduct D20 | 57 | 55 | m | 3554.7229 | 5289.7059 | 8844.4288 | 195509.7606 | 290933.8235 | 486443.5841 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 1377772.0826 | 413331.6248 | 1791103.7073 | 1377772.0826 | 413331.6248 | 1791103.7073 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 2. 70. |  | Electrical installation in the logistics hall | 1 | 1 | PSCH |  |  |  | 365728225.5911 | 45073708.1139 | 410801933.705 | 0% | 0% | 0% | 0% |  |  | #REF! | 65439911.868 | 9449071.1273 | 74888982.9953 | 93922998.732 | 13192169.5804 | 107115168.3124 | 182004151.3077
|  | Cable trays_Hot dip-Galvanized Steel | [6 empty] | 184238087 | 23645406.8737 | 207883493.8737 | 0% | 0% | 0% | 0% |  |  | #REF! | 55271426.1 | 7093622.0621 | 62365048.1621 | 82907139.15 | 10640433.0931 | 93547572.2431 | 155912620.4052
|  | Cable tray 500x100x2.0mm | 0 | 0 | m | 1443780 | 81001.3848 | 1524781.3848 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable tray 300x100x2.0mm | 0 | 0 | m | 1009710 | 61078.452 | 1070788.452 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable tray 200x100x2.0mm | 10 |  | m | 776880 | 51045.8655 | 827925.8655 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable tray 500x100 with separating bar | 9 |  | m | 1525680 | 81001.3848 | 1606681.3848 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable tray 400x100 with separating bar | 56 | 66 | m | 826020 | 68320 | 894340 | 54517320 | 4509120 | 59026440 | 30% | 45% | 75% | 25% |  |  | #REF! | 16355196 | 1352736 | 17707932 | 24532794 | 2029104 | 26561898 | 44269830
|  | Cable tray 300x100 with separating bar | 0 | 0 | m | 1091610 | 61078.452 | 1152688.452 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable tray 200x100 with separating bar | 83 | 94.6 | m | 858780 | 51045.8655 | 909825.8655 | 81240588 | 4828938.8737 | 86069526.8737 | 30% | 45% | 75% | 25% |  |  | #REF! | 24372176.4 | 1448681.6621 | 25820858.0621 | 36558264.6 | 2173022.4931 | 38731287.0931 | 64552145.1552
|  | Cable tray 200x50 with separating bar | 66 | 0 | m | 669240 | 51045.8655 | 720285.8655 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable ladder 600x100x2.0mm | 0 | 0 | m | 1199250 | 91952 | 1291202 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable ladder 500x100x2.0mm | 0 | 0 | m | 1067040 | 81001.3848 | 1148041.3848 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable ladder 400x100x2.0mm | 3 | 3.3 | m | 466830 | 68320 | 535150 | 1540539 | 225456 | 1765995 | 30% | 45% | 75% | 25% |  |  | #REF! | 462161.7 | 67636.8 | 529798.5 | 693242.55 | 101455.2 | 794697.75 | 1324496.25
|  | Cable ladder 300x100x1.5mm | 0 | 0 | m | 625950 | 61078.452 | 687028.452 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable ladder 200x100x1.5mm | 0 | 0 | m | 496080 | 51045.8655 | 547125.8655 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fitting and accessories | 1 | 1 | lot | 46939640 | 14081892 | 61021532 | 46939640 | 14081892 | 61021532 | 30% | 45% | 75% | 25% |  |  | #REF! | 14081892 | 4224567.6 | 18306459.6 | 21122838 | 6336851.4 | 27459689.4 | 45766149
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Electrical installation | [6 empty] | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2-Way switch, 1 gang for lighting control panel | 0 | 0 | pcs | 0 | 54500 | 54500 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single Socket NEMA5 | 0 | 0 | pcs | 124560 | 54500 | 179060 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Double Socket NEMA5 | 0 | 0 | pcs | 249120 | 54500 | 303620 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lighting | [6 empty] | 147378000 | 7630000 | 155008000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Led Highbay light 115W, Type CII | 35 | 35 | pcs | 4100800 | 196000 | 4296800 | 143528000 | 6860000 | 150388000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Frame Lamp 1x46W, Type BII | 0 | 0 | pcs | 1607100 | 63504 | 1670604 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 63504 | 648704 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 3850000 | 770000 | 4620000 | 3850000 | 770000 | 4620000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable for lighting system | [6 empty] | 34112138.5911 | 13798301.2403 | 47910439.8314 | 0% | 0% | 0% | 0% |  |  | #REF! | 10168485.768 | 2355449.0652 | 12523934.8332 | 11015859.582 | 2551736.4873 | 13567596.0693 | 26091530.9025
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 693 | 805 | m | 32518.74 | 7485.665 | 40004.405 | 26177585.7 | 6025960.325 | 32203546.025 | 36% | 39% | 75% | 150% |  |  | #REF! | 9423930.852 | 2169345.717 | 11593276.569 | 10209258.423 | 2350124.5268 | 12559382.9498 | 24152659.5188
|  | Cable Cu/XLPE//PVC 3Cx1.5mm2 | 96 | 90 | m | 22980.09 | 5743.9305 | 28724.0205 | 2068208.1 | 516953.745 | 2585161.845 | 36% | 39% | 75% | 150% |  |  | #REF! | 744554.916 | 186103.3482 | 930658.2642 | 806601.159 | 201611.9606 | 1008213.1196 | 1938871.3838
|  | PVC conduit D20 | 277 | 440 | m | 8773.9726 | 14594.0164 | 23367.989 | 3860547.9452 | 6421367.2212 | 10281915.1664 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 88 | 0 | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC flexible conduct D20 | 33 | 55 | m | 3554.7229 | 5289.7059 | 8844.4288 | 195509.7606 | 290933.8235 | 486443.5841 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 1810287.0853 | 543086.1256 | 2353373.2109 | 1810287.0853 | 543086.1256 | 2353373.2109 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 2. 80. |  | Power supply of building utilities | 1 | 1 | PSCH |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 2. 90. |  | Three-arm Turnstile | 1 | 1 | PSCH |  |  |  | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
2. 2. 100. |  | Emergency lighting | 1 | 1 | PSCH |  |  |  | 77923218.1103 | 25617198.1684 | 103540416.2786 | 0% | 0% | 0% | 0% |  |  | #REF! | 12409151.184 | 2856529.764 | 15265680.948 | 0 | 0 | 0 | 15265680.948
|  | Production hall 01 | [6 empty] | 18834457.2 | 3323337.16 | 22157794.36 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Emergency light | 13 | 13 | pcs | 516120 | 63504 | 579624 | 6709560 | 825552 | 7535112 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Exit light | 13 | 13 | pcs | 566280 | 63504 | 629784 | 7361640 | 825552 | 8187192 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single Socket 16A/230V | 26 | 26 | pcs | 150480 | 54500 | 204980 | 3912480 | 1417000 | 5329480 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | pcs | 850777.2 | 255233.16 | 1106010.36 | 850777.2 | 255233.16 | 1106010.36 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power supply | [6 empty] | 22294958.4377 | 8918664.6672 | 31213623.1048 | 0% | 0% | 0% | 0% |  |  | #REF! | 6661138.7016 | 1533363.6186 | 8194502.3202 | 0 | 0 | 0 | 8194502.3202
|  | Cable Cu/XLPE//PVC 3Cx2.5mm2 | 619 | 569 | m | 32518.74 | 7485.665 | 40004.405 | 18503163.06 | 4259343.385 | 22762506.445 | 36% | 0% | 36% | 72% |  |  | #REF! | 6661138.7016 | 1533363.6186 | 8194502.3202 | 0 | 0 | 0 | 8194502.3202
|  | PVC conduit D20 | 371 | 275 | m | 8773.9726 | 14594.0164 | 23367.989 | 2412842.4658 | 4013354.5132 | 6426196.979 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC flexible conduct D20 | 74 | 55 | m | 3554.7229 | 5289.7059 | 8844.4288 | 195509.7606 | 290933.8235 | 486443.5841 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 1183443.1513 | 355032.9454 | 1538476.0967 | 1183443.1513 | 355032.9454 | 1538476.0967 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Production hall 02 | [6 empty] | 8540160 | 1464048 | 10004208 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Emergency light | 6 | 6 | pcs | 516120 | 63504 | 579624 | 3096720 | 381024 | 3477744 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Exit light | 6 | 6 | pcs | 566280 | 63504 | 629784 | 3397680 | 381024 | 3778704 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single Socket 16A/230V | 12 | 12 | pcs | 150480 | 54500 | 204980 | 1805760 | 654000 | 2459760 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | pcs | 240000 | 48000 | 288000 | 240000 | 48000 | 288000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power supply | [6 empty] | 10420834.2021 | 4757933.0991 | 15178767.3011 | 0% | 0% | 0% | 0% |  |  | #REF! | 2961806.8392 | 681794.3682 | 3643601.2074 | 0 | 0 | 0 | 3643601.2074
|  | Cable Cu/XLPE//PVC 3Cx2.5mm2 | 286 | 253 | m | 32518.74 | 7485.665 | 40004.405 | 8227241.22 | 1893873.245 | 10121114.465 | 36% | 0% | 36% | 72% |  |  | #REF! | 2961806.8392 | 681794.3682 | 3643601.2074 | 0 | 0 | 0 | 3643601.2074
|  | PVC conduit D20 | 171 | 165 | m | 8773.9726 | 14594.0164 | 23367.989 | 1447705.4795 | 2408012.7079 | 3855718.1874 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC flexible conduct D20 | 34 | 55 | m | 3554.7229 | 5289.7059 | 8844.4288 | 195509.7606 | 290933.8235 | 486443.5841 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 550377.742 | 165113.3226 | 715491.0646 | 550377.742 | 165113.3226 | 715491.0646 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Logistics area | [6 empty] | 7116800 | 1220040 | 8336840 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Emergency light | 5 | 5 | pcs | 516120 | 63504 | 579624 | 2580600 | 317520 | 2898120 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Exit light | 5 | 5 | pcs | 566280 | 63504 | 629784 | 2831400 | 317520 | 3148920 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single Socket 16A/230V | 10 | 10 | pcs | 150480 | 54500 | 204980 | 1504800 | 545000 | 2049800 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | pcs | 200000 | 40000 | 240000 | 200000 | 40000 | 240000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power supply | [6 empty] | 10716008.2705 | 5933175.2421 | 16649183.5127 | 0% | 0% | 0% | 0% |  |  | #REF! | 2786205.6432 | 641371.7772 | 3427577.4204 | 0 | 0 | 0 | 3427577.4204
|  | Cable Cu/XLPE//PVC 3Cx2.5mm2 | 238 | 238 | m | 32518.74 | 7485.665 | 40004.405 | 7739460.12 | 1781588.27 | 9521048.39 | 36% | 0% | 36% | 72% |  |  | #REF! | 2786205.6432 | 641371.7772 | 3427577.4204 | 0 | 0 | 0 | 3427577.4204
|  | PVC conduit D20 | 143 | 253 | m | 8773.9726 | 14594.0164 | 23367.989 | 2219815.0685 | 3692286.1522 | 5912101.2207 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC flexible conduct D20 | 29 | 55 | m | 3554.7229 | 5289.7059 | 8844.4288 | 195509.7606 | 290933.8235 | 486443.5841 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 561223.3215 | 168366.9964 | 729590.3179 | 561223.3215 | 168366.9964 | 729590.3179 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 2. 110. |  | Fire alarm system | 1 | 1 | PSCH |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 2. 120. |  | Network infrastructure | 1 | 1 | PSCH |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 2. 130. |  | Access control preparation | 1 | 1 | PSCH |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 2. 140. |  | CCTV System | 1 | 1 | PSCH |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. |  | Office, Social and Technical Areas (Hall 3) | [6 empty] | 8556494945.4536 | 444494571.6059 | 9000989517.0595 | 0% | 0% | 0% | 0% |  |  | #REF! | 360619287.5039 | 57663243.2768 | 418282530.7807 | 192463191.4 | 24154185.7457 | 216617377.1457 | 634899907.9264
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 2. |  | Electrical engineering | 1 | 1 | PSCH |  |  |  | 8556494945.4536 | 444494571.6059 | 9000989517.0595 | 0% | 0% | 0% | 0% |  |  | #REF! | 360619287.5039 | 57663243.2768 | 418282530.7807 | 192463191.4 | 24154185.7457 | 216617377.1457 | 634899907.9264
3. 2. 10. |  | Rennovation existing grounding system and lightning protection | 1 | 1 | psch | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 2. 20. |  | Rennovation existing grounding and equipotential bonding | 1 | 1 | psch | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 2. 30. |  | Main Power supply | 1 | 1 | PSCH |  |  |  | 4272504384.025 | 197907035.9748 | 4470411419.9998 | 0% | 0% | 0% | 0% |  |  | #REF! | 244092740.09 | 31028159.6211 | 275120899.7111 | 192463191.4 | 24154185.7457 | 216617377.1457 | 491738276.8567
|  | Electrical panel | [6 empty] | 2486429270 | 40937031 | 2527366301 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Modify SYN - TR1, Add ACB 4P 2250A, 85ka, fixed type | 1 | 1 | pcs | 243347500 | 1400000 | 244747500 | 243347500 | 1400000 | 244747500 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Building3_BMDP min 1500kVA | 1 | 1 | pcs | 581849400 | 3920000 | 585769400 | 581849400 | 3920000 | 585769400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Building 3_PDP 1.0 | 1 | 1 | pcs | 137478000 | 1400000 | 138878000 | 137478000 | 1400000 | 138878000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Building 3_PDP 1.1 | 1 | 1 | pcs | 124835700 | 1400000 | 126235700 | 124835700 | 1400000 | 126235700 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Building 3_PDP 2.0 | 1 | 1 | pcs | 137478000 | 1400000 | 138878000 | 137478000 | 1400000 | 138878000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Building 3_PDP 1.2 | 1 | 1 | pcs | 160848600 | 1400000 | 162248600 | 160848600 | 1400000 | 162248600 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Building 3_PDP 2.1 | 1 | 1 | pcs | 162050900 | 1400000 | 163450900 | 162050900 | 1400000 | 163450900 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Building 3_BDP 1.0 | 1 | 1 | pcs | 113520000 | 1400000 | 114920000 | 113520000 | 1400000 | 114920000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Building 3_BDP 1.1 | 1 | 1 | pcs | 232601600 | 1400000 | 234001600 | 232601600 | 1400000 | 234001600 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Building 3_BDP 2.0 | 1 | 1 | pcs | 246041400 | 1400000 | 247441400 | 246041400 | 1400000 | 247441400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Scooter garage__BDP 1.0 | 1 | 1 | pcs | 15643100 | 840000 | 16483100 | 15643100 | 840000 | 16483100 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Canteen__BDP 1.0 | 1 | 1 | pcs | 47347300 | 1400000 | 48747300 | 47347300 | 1400000 | 48747300 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Building 3_DB SEF 1 | 1 | 1 | pcs | 28968500 | 840000 | 29808500 | 28968500 | 840000 | 29808500 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Building 3_DB SEF 2 | 1 | 1 | pcs | 24835800 | 840000 | 25675800 | 24835800 | 840000 | 25675800 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Building 3_UPS1-MDP | 1 | 1 | pcs | 91081100 | 1400000 | 92481100 | 91081100 | 1400000 | 92481100 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Building UPS1-DP1.2 | 1 | 1 | pcs | 79290200 | 1400000 | 80690200 | 79290200 | 1400000 | 80690200 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Building 3_UPS 1-DP 1.2 | 1 | 1 | pcs | 10457700 | 840000 | 11297700 | 10457700 | 840000 | 11297700 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Building 3_UPS 1 DP 1.3 | 1 | 1 | pcs | 8309400 | 840000 | 9149400 | 8309400 | 840000 | 9149400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Building 3_UPS 1 DP 1.3 35kVA | 1 | 1 | pcs | 70643100 | 1400000 | 72043100 | 70643100 | 1400000 | 72043100 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Building 3 UPS2-MD | 1 | 1 | pcs | 79290200 | 1400000 | 80690200 | 79290200 | 1400000 | 80690200 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Building UPS2-DP1.2 | 1 | 1 | pcs | 10457700 | 840000 | 11297700 | 10457700 | 840000 | 11297700 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Building 3_UPS 2-DP1.2 | 1 | 1 | pcs | 8309400 | 840000 | 9149400 | 8309400 | 840000 | 9149400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Building 3_UPS 2 DP 1.3 | 1 | 1 | pcs | 8309400 | 840000 | 9149400 | 8309400 | 840000 | 9149400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Building 3_UPS 2 DP 1.3 35kVA | 1 | 1 | pcs | 71126000 | 1400000 | 72526000 | 71126000 | 1400000 | 72526000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Building 3_DP PUMP 1 | 1 |  | pcs | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Building 3_DP PUMP 2 | 1 |  | pcs | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fitting and accessories | 1 | 1 | lot | 35656770 | 10697031 | 46353801 | 35656770 | 10697031 | 46353801 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable trays_Hot dip-Galvanized Steel | [6 empty] | 982315957 | 122770928.7283 | 1105086885.7283 | 0% | 0% | 0% | 0% |  |  | #REF! | 240578989.25 | 30192732.1821 | 270771721.4321 | 192463191.4 | 24154185.7457 | 216617377.1457 | 487389098.5777
|  | Cable tray 500x100x2.0mm | 0 | 0 | m | 1443780 | 81001.3848 | 1524781.3848 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable tray 300x100x2.0mm | 0 | 0 | m | 1009710 | 61078.452 | 1070788.452 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable tray 200x100x2.0mm | 0 | 0 | m | 776880 | 51045.8655 | 827925.8655 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable tray 500x100 with separating bar, c/w cover | 0 | 93 | m | 1525680 | 81001.3848 | 1606681.3848 | 141888240 | 7533128.7822 | 149421368.7822 | 25% | 20% | 45% | 90% |  |  | #REF! | 35472060 | 1883282.1956 | 37355342.1956 | 28377648 | 1506625.7564 | 29884273.7564 | 67239615.952
|  | Cable tray 400x100 with separating bar, c/w cover | 0 | 0 | m | 826020 | 68320 | 894340 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable tray 300x100 with separating bar, c/w cover | 0 | 0 | m | 1091610 | 61078.452 | 1152688.452 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable tray 200x100 with separating bar, c/w cover | 0 | 0 | m | 858780 | 51045.8655 | 909825.8655 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable tray 600x50 with separating bar, c/w cover | 26 | 28.6 | m | 1568970 | 87472 | 1656442 | 44872542 | 2501699.2 | 47374241.2 | 25% | 20% | 45% | 90% |  |  | #REF! | 11218135.5 | 625424.8 | 11843560.3 | 8974508.4 | 500339.84 | 9474848.24 | 21318408.54
|  | Cable tray 500x50 with separating bar, c/w cover | 6 | 6.6 | m | 1334970 | 81001.3848 | 1415971.3848 | 8810802 | 534609.1394 | 9345411.1394 | 25% | 20% | 45% | 90% |  |  | #REF! | 2202700.5 | 133652.2848 | 2336352.7848 | 1762160.4 | 106921.8279 | 1869082.2279 | 4205435.0127
|  | Cable tray 400x50 with separating bar, c/w cover | 165 | 183.7 | m | 1136070 | 68320 | 1204390 | 208696059 | 12550384 | 221246443 | 25% | 20% | 45% | 90% |  |  | #REF! | 52174014.75 | 3137596 | 55311610.75 | 41739211.8 | 2510076.8 | 44249288.6 | 99560899.35
|  | Cable tray 200x50 with separating bar, c/w cover | 303 | 453.2 | m | 669240 | 51045.8655 | 720285.8655 | 303299568 | 23133986.2319 | 326433554.2319 | 25% | 20% | 45% | 90% |  |  | #REF! | 75824892 | 5783496.558 | 81608388.558 | 60659913.6 | 4626797.2464 | 65286710.8464 | 146895099.4044
|  | Cable tray 100x50 with separating bar, c/w cover | 14 | 15.4 | m | 469170 | 51045.8655 | 520215.8655 | 7225218 | 786106.3283 | 8011324.3283 | 25% | 20% | 45% | 90% |  |  | #REF! | 1806304.5 | 196526.5821 | 2002831.0821 | 1445043.6 | 157221.2657 | 1602264.8657 | 3605095.9477
|  | Cable ladder 600x100x2.0mm, c/w cover | 0 | 0 | m | 1199250 | 91952 | 1291202 | 0 | 0 | 0 | 25% | 20% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable ladder 500x100x2.0mm, c/w cover | 2 | 2.2 | m | 1067040 | 81001.3848 | 1148041.3848 | 2347488 | 178203.0465 | 2525691.0465 | 25% | 20% | 45% | 90% |  |  | #REF! | 586872 | 44550.7616 | 631422.7616 | 469497.6 | 35640.6093 | 505138.2093 | 1136560.9709
|  | Cable ladder 400x100x2.0mm, c/w cover | 0 | 0 | m | 933660 | 68320 | 1001980 | 0 | 0 | 0 | 25% | 20% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable ladder 300x100x1.5mm, c/w cover | 0 | 0 | m | 625950 | 61078.452 | 687028.452 | 0 | 0 | 0 | 25% | 20% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable ladder 200x100x1.5mm, c/w cover | 0 | 0 | m | 496080 | 51045.8655 | 547125.8655 | 0 | 0 | 0 | 25% | 20% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fitting and accessories | 1 | 1 | lot | 245176040 | 73552812 | 318728852 | 245176040 | 73552812 | 318728852 | 25% | 20% | 45% | 90% |  |  | #REF! | 61294010 | 18388203 | 79682213 | 49035208 | 14710562.4 | 63745770.4 | 143427983.4
|  | Fire stop | 1 | 1 | set | 20000000 | 2000000 | 22000000 | 20000000 | 2000000 | 22000000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lighting control panel | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | BDP 1.0 | [6 empty] | 97882510.475 | 7025037.0385 | 104907547.5135 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 8P smart key, white plastic surface material | 1 | 1 | pcs | 17060781.92 | 137500 | 17198281.92 | 17060781.92 | 137500 | 17198281.92 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4P smart key, white plastic surface material | 2 | 2 | pcs | 13652800 | 137500 | 13790300 | 27305600 | 275000 | 27580600 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Smart light control device for 8 independent load groups - 16A/ K | 1 | 1 | pcs | 19992667.52 | 49500 | 20042167.52 | 19992667.52 | 49500 | 20042167.52 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Smart light control device for 4 independent load groups - 16A/ K | 1 | 1 | pcs | 14090720 | 49500 | 14140220 | 14090720 | 49500 | 14140220 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Power supply for control signals, 24VDC | 2 | 2 | pcs | 8376816 | 49500 | 8426316 | 16753632 | 99000 | 16852632 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Base for smart keys | 3 | 3 | pcs | 41884.08 | 49500 | 91384.08 | 125652.24 | 148500 | 274152.24 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 2553456.795 | 766037.0385 | 3319493.8335 | 2553456.795 | 766037.0385 | 3319493.8335 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | T&C | 1 | 1 | lot | 0 | 5500000 | 5500000 | 0 | 5500000 | 5500000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | BDP 1.1 | [6 empty] | 162133437.125 | 10750870.3775 | 172884307.5025 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 8P smart key, white plastic surface material | 3 | 3 | pcs | 17060781.92 | 137500 | 17198281.92 | 51182345.76 | 412500 | 51594845.76 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4P smart key, white plastic surface material | 2 | 2 | pcs | 13652800 | 137500 | 13790300 | 27305600 | 275000 | 27580600 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Smart light control device for 8 independent load groups - 16A/ K | 2 | 2 | pcs | 19992667.52 | 49500 | 20042167.52 | 39985335.04 | 99000 | 40084335.04 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Smart light control device for 4 independent load groups - 16A/ K | 1 | 1 | pcs | 14090720 | 49500 | 14140220 | 14090720 | 49500 | 14140220 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Power supply for control signals, 24VDC | 3 | 3 | pcs | 8376816 | 49500 | 8426316 | 25130448 | 148500 | 25278948 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Base for smart keys | 5 | 5 | pcs | 41884.08 | 49500 | 91384.08 | 209420.4 | 247500 | 456920.4 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 4229567.925 | 1268870.3775 | 5498438.3025 | 4229567.925 | 1268870.3775 | 5498438.3025 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | T&C | 1 | 1 | lot | 0 | 8250000 | 8250000 | 0 | 8250000 | 8250000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | BDP 2.0 | [6 empty] | 290635290.425 | 12702537.0555 | 303337827.4805 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 8P smart key, white plastic surface material | 7 | 7 | pcs | 17060781.92 | 137500 | 17198281.92 | 119425473.44 | 962500 | 120387973.44 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4P smart key, white plastic surface material | 2 | 2 | pcs | 13652800 | 137500 | 13790300 | 27305600 | 275000 | 27580600 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Smart light control device for 8 independent load groups - 16A/ K | 4 | 4 | pcs | 19992667.52 | 49500 | 20042167.52 | 79970670.08 | 198000 | 80168670.08 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Smart light control device for 4 independent load groups - 16A/ K | 1 | 1 | pcs | 14090720 | 49500 | 14140220 | 14090720 | 49500 | 14140220 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Power supply for control signals, 24VDC | 5 | 5 | pcs | 8376816 | 49500 | 8426316 | 41884080 | 247500 | 42131580 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Base for smart keys | 9 | 9 | pcs | 41884.08 | 49500 | 91384.08 | 376956.72 | 445500 | 822456.72 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 7581790.185 | 2274537.0555 | 9856327.2405 | 7581790.185 | 2274537.0555 | 9856327.2405 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | T&C | 1 | 1 | lot | 0 | 8250000 | 8250000 | 0 | 8250000 | 8250000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power supply | [6 empty] | 9760419 | 2320631.775 | 12081050.775 | 0% | 0% | 0% | 0% |  |  | #REF! | 3513750.84 | 835427.439 | 4349178.279 | 0 | 0 | 0 | 4349178.279
|  | From Building 3_BDP 1.1 Panel to DB-PUMP1 | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 4x1Cx4mm2+E4mm2 | 71 | 64 | m | 72299.4 | 17189.865 | 89489.265 | 4627161.6 | 1100151.36 | 5727312.96 | 36% | 0% | 36% | 72% |  |  | #REF! | 1665778.176 | 396054.4896 | 2061832.6656 | 0 | 0 | 0 | 2061832.6656
|  | From Building 3_BDP 2.0 Panel to DB-PUMP2 | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 4x1Cx4mm2+E4mm2 | 71 | 71 | m | 72299.4 | 17189.865 | 89489.265 | 5133257.4 | 1220480.415 | 6353737.815 | 36% | 0% | 36% | 72% |  |  | #REF! | 1847972.664 | 439372.9494 | 2287345.6134 | 0 | 0 | 0 | 2287345.6134
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 2. 40. |  | Uninterrupted power supply (UPS) | 1 | 1 | PSCH |  |  |  | 2008718012.8938 | 15050660.8087 | 2023768673.7025 | 0% | 0% | 0% | 0% |  |  | #REF! | 421914.4524 | 105458.564 | 527373.0164 | 0 | 0 | 0 | 527373.0164
|  | UPS 93PR 60kW*100%load, backup 15 Minutes, frame 125kw | 2 | 2 | set | 967016600 | 3300000 | 970316600 | 1934033200 | 6600000 | 1940633200 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 93PR 125kW Frame to contain up to max. 6 Power Modules, Back-Feed, MBS & 1 x internal PDU | 0 | 0 |  | 310491720 | 0 | 310491720 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 93PR Power Module of 25KW capacity (Rev B) | 0 | 0 |  | 101372040 | 0 | 101372040 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Industrial Gateway Card | 0 | 0 |  | 9882180 | 0 | 9882180 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Eaton battery backup 15 mins @ 75kW | 0 | 0 |  | 6021400 | 0 | 6021400 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Battery cabinet, MCB, cable to connect Battery to UPS and accesoriess. | 0 | 0 |  | 99429000 | 0 | 99429000 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 10000000 | 2000000 | 12000000 | 10000000 | 2000000 | 12000000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | water leak warning system | 2 | 2 | lot |  |  |  | 64684812.8938 | 6450660.8087 | 71135473.7025 | 0% | 0% | 0% | 0% |  |  | #REF! | 421914.4524 | 105458.564 | 527373.0164 | 0 | 0 | 0 | 527373.0164
|  | Water leak detector | 4 | 4 | pcs | 1587000 | 49500 | 1636500 | 6348000 | 198000 | 6546000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cabinet for Water leak detector | 4 | 4 | pcs | 1725000 | 220000 | 1945000 | 6900000 | 880000 | 7780000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Power supply | 4 | 4 | pcs | 862500 | 165000 | 1027500 | 3450000 | 660000 | 4110000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | water leak cable | 140 | 120 | m | 317400 | 22000 | 339400 | 38088000 | 2640000 | 40728000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Connection conductor A-LLW58; wire holder permanent | 4 | 4 | pcs | 1269600 | 49500 | 1319100 | 5078400 | 198000 | 5276400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single Socket 1P-16A-250V | 4 | 4 | pcs | 124560 | 54500 | 179060 | 498240 | 218000 | 716240 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3C-1.5mm2 Cu/XLPE/PVC | 60 | 51 | m | 22980.09 | 5743.9305 | 28724.0205 | 1171984.59 | 292940.4555 | 1464925.0455 | 36% | 0% | 36% | 72% |  |  | #REF! | 421914.4524 | 105458.564 | 527373.0164 | 0 | 0 | 0 | 527373.0164
|  | PVC conduit D20 | 58 | 35 | m | 8773.9726 | 14594.0164 | 23367.989 | 307089.0411 | 510790.5744 | 817879.6155 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 2843099.2627 | 852929.7788 | 3696029.0415 | 2843099.2627 | 852929.7788 | 3696029.0415 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 2. 50. |  | Electrical Capacitor bank | 1 | 1 | PSCH |  |  |  | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Electrical Capacitor bank Building3_BMDP min 1500kVA | 1 |  | pcs | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 2. 60. |  | Power supply of building utilities | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 2. 70. |  | Energy measurement system | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 2. 80. |  | Electrical installation in offices and meeting rooms | 1 | 1 | PSCH |  |  |  | 1229075412.0457 | 66404103.9782 | 1295479516.0239 | 0% | 0% | 0% | 0% |  |  | #REF! | 18509367.672 | 4424545.4062 | 22933913.0782 | 0 | 0 | 0 | 22933913.0782
|  | Switch & Socket | [6 empty] | 221333361.2618 | 14243567.4985 | 235576928.7604 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Push-button - (switch) | 37 | 37 | pcs | 223200 | 54500 | 277700 | 8258400 | 2016500 | 10274900 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single Socket NEMA5 | 15 | 15 | pcs | 124560 | 54500 | 179060 | 1868400 | 817500 | 2685900 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Double Socket NEMA5 | 15 | 15 | pcs | 249120 | 54500 | 303620 | 3736800 | 817500 | 4554300 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Dimmer Switch | 6 | 6 | pcs | 254400 | 54500 | 308900 | 1526400 | 327000 | 1853400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cord outlet socket with 2m cable reserve with connection terminals, E1 | 6 | 6 | pcs | 507247.2 | 54500 | 561747.2 | 3043483.2 | 327000 | 3370483.2 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cord outlet socket with 4m cable reserve with connection terminals, E2 | 0 | 0 | pcs | 507247.2 | 54500 | 561747.2 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cord outlet socket with 6m cable reserve with connection terminals, E3 | 33 | 33 | pcs | 507247.2 | 54500 | 561747.2 | 16739157.6 | 1798500 | 18537657.6 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Floor box, recessed (3xDouble Socket NEMA5, 2xIT - Double socket) | 3 | 3 | pcs | 8885676 | 272500 | 9158176 | 26657028 | 817500 | 27474528 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Floor box, recessed (4xDouble Socket NEMA5, 2xIT - Double socket) | 1 | 1 | pcs | 9467332.8 | 272500 | 9739832.8 | 9467332.8 | 272500 | 9739832.8 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Floor box, recessed (1xDouble Socket NEMA5, 1xIT - Double socket,1x HDMI connection to the projector) | 3 | 3 | pcs | 9216914.4 | 272500 | 9489414.4 | 27650743.2 | 817500 | 28468243.2 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Floor box, recessed (2xDouble Socket NEMA5, 2xIT - Double socket, 1x HDMI connection to the projector) | 1 | 1 | pcs | 10490947.2 | 272500 | 10763447.2 | 10490947.2 | 272500 | 10763447.2 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Floor box, recessed (3xDouble Socket NEMA5, 2xIT - Double socket, 1x HDMI connection to the projector) | 0 | 0 | pcs | 11072604 | 272500 | 11345104 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Floor box, recessed (4xDouble Socket NEMA5, 2xIT - Double socket, 1x HDMI connection to the projector) | 2 | 2 | pcs | 11654260.8 | 272500 | 11926760.8 | 23308521.6 | 545000 | 23853521.6 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Projector + Accessories | 3 | 3 | pcs | 18650000 | 381500 | 19031500 | 55950000 | 1144500 | 57094500 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Motion sensor | 19 | 19 | pcs | 1150224 | 54500 | 1204724 | 21854256 | 1035500 | 22889756 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 10781891.6618 | 3234567.4985 | 14016459.1604 | 10781891.6618 | 3234567.4985 | 14016459.1604 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | [7 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lighting | 0 | 0 |  |  |  |  | 643593600 | 11842000 | 655435600 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Panel 36W, Type AI | 168 | 168 | pcs | 3339600 | 56000 | 3395600 | 561052800 | 9408000 | 570460800 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Panel 36W, Type AI - Dali Dim | 23 | 23 | pcs | 3339600 | 56000 | 3395600 | 76810800 | 1288000 | 78098800 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Frame Lamp 1x46W, Type BII | 0 | 0 | pcs | 1607100 | 56000 | 1663100 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 56000 | 641200 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 5730000 | 1146000 | 6876000 | 5730000 | 1146000 | 6876000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power | [6 empty] | 364148450.7839 | 40318536.4797 | 404466987.2635 | 0% | 0% | 0% | 0% |  |  | #REF! | 18509367.672 | 4424545.4062 | 22933913.0782 | 0 | 0 | 0 | 22933913.0782
|  | 3C-1.5mm2 Cu/XLPE/PVC | 1142 | 1002 | m | 22980.09 | 5743.9305 | 28724.0205 | 23026050.18 | 5755418.361 | 28781468.541 | 36% | 0% | 36% | 72% |  |  | #REF! | 8289378.0648 | 2071950.61 | 10361328.6748 | 0 | 0 | 0 | 10361328.6748
|  | 3C-2.5mm2 Cu/XLPE/PVC | 630 | 570 | m | 32518.74 | 7485.665 | 40004.405 | 18535681.8 | 4266829.05 | 22802510.85 | 36% | 0% | 36% | 72% |  |  | #REF! | 6672845.448 | 1536058.458 | 8208903.906 | 0 | 0 | 0 | 8208903.906
|  | 3C-2.5mm2 Cu/XLPE/PVC for E1, E2, E3 | 303 | 303 | m | 32518.74 | 7485.665 | 40004.405 | 9853178.22 | 2268156.495 | 12121334.715 | 36% | 0% | 36% | 72% |  |  | #REF! | 3547144.1592 | 816536.3382 | 4363680.4974 | 0 | 0 | 0 | 4363680.4974
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 0 | 0 | m | 72299.4 | 17189.865 | 89489.265 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 0 | 0 | m | 102372.9 | 18573.4395 | 120946.3395 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Dado duct 50x130mm | 296 | 296 | m | 985945.6609 | 53025 | 1038970.6609 | 291839915.6313 | 15695400 | 307535315.6313 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 507 | 507 | m | 8773.9726 | 14594.0164 | 23367.989 | 4448404.1096 | 7399166.3208 | 11847570.4304 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 16445220.843 | 4933566.2529 | 21378787.0959 | 16445220.843 | 4933566.2529 | 21378787.0959 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | [7 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 2. 90. |  | Electrical installation in social rooms | 1 | 1 | PSCH |  |  |  | 258752977.5651 | 35385729.898 | 294138707.4631 | 0% | 0% | 0% | 0% |  |  | #REF! | 21620600.0723 | 5220940.2254 | 26841540.2977 | 0 | 0 | 0 | 26841540.2977
|  | Switch & Socket | [6 empty] | 10372584.6 | 3183623.38 | 13556207.98 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1-Way switch, 1 gang | 2 | 2 | pcs | 46800 | 54500 | 101300 | 93600 | 109000 | 202600 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single Socket NEMA5 | 29 | 29 | pcs | 124560 | 54500 | 179060 | 3612240 | 1580500 | 5192740 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Double Socket NEMA5 | 25 | 25 | pcs | 249120 | 54500 | 303620 | 6228000 | 1362500 | 7590500 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Power outlet general, 3p/4W, grounded | 0 | 0 | pcs | 150480 | 54500 | 204980 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 438744.6 | 131623.38 | 570367.98 | 438744.6 | 131623.38 | 570367.98 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lighting | [6 empty] | 180626800 | 8680000 | 189306800 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Panel 36W, Type AI | 0 | 0 | pcs | 3339600 | 56000 | 3395600 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Frame Lamp 1x30W, Type BI | 56 | 56 | pcs | 1346400 | 56000 | 1402400 | 75398400 | 3136000 | 78534400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Frame Lamp 1x46W, Type BII | 4 | 4 | pcs | 1607100 | 56000 | 1663100 | 6428400 | 224000 | 6652400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 56000 | 641200 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Ceiling mounted Light 1x19W, Type D | 80 | 80 | pcs | 1182500 | 56000 | 1238500 | 94600000 | 4480000 | 99080000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 4200000 | 840000 | 5040000 | 4200000 | 840000 | 5040000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power | [6 empty] | 67753592.9651 | 23522106.518 | 91275699.4831 | 0% | 0% | 0% | 0% |  |  | #REF! | 21620600.0723 | 5220940.2254 | 26841540.2977 | 0 | 0 | 0 | 26841540.2977
|  | 3C-1.5mm2 Cu/XLPE/PVC | 1187 | 1492.7 | m | 22980.09 | 5743.9305 | 28724.0205 | 34302380.343 | 8573965.0574 | 42876345.4004 | 36% | 0% | 36% | 72% |  |  | #REF! | 12348856.9235 | 3086627.4206 | 15435484.3441 | 0 | 0 | 0 | 15435484.3441
|  | 3C-2.5mm2 Cu/XLPE/PVC | 690 | 792 | m | 32518.74 | 7485.665 | 40004.405 | 25754842.08 | 5928646.68 | 31683488.76 | 36% | 0% | 36% | 72% |  |  | #REF! | 9271743.1488 | 2134312.8048 | 11406055.9536 | 0 | 0 | 0 | 11406055.9536
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 0 | 0 | m | 72299.4 | 17189.865 | 89489.265 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 0 | 0 | m | 102372.9 | 18573.4395 | 120946.3395 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Dado duct 50x130mm | 0 | 0 | m | 985945.6609 | 53025 | 1038970.6609 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 703 | 561 | m | 8773.9726 | 14594.0164 | 23367.989 | 4922198.6301 | 8187243.207 | 13109441.8371 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 2774171.912 | 832251.5736 | 3606423.4856 | 2774171.912 | 832251.5736 | 3606423.4856 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 2. 100. |  | Electrical installation in corridors and stairways | 1 | 1 | PSCH |  |  |  | 74974338.2247 | 17389802.6953 | 92364140.92 | 0% | 0% | 0% | 0% |  |  | #REF! | 5947056.396 | 1442536.227 | 7389592.623 | 0 | 0 | 0 | 7389592.623
|  | Switch & Socket | [6 empty] | 13582018.8 | 4641349.64 | 18223368.44 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1-Way switch, 1 gang | 6 | 6 | pcs | 46800 | 54500 | 101300 | 280800 | 327000 | 607800 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Push-button switch | 32 | 32 | pcs | 223200 | 54500 | 277700 | 7142400 | 1744000 | 8886400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single Socket NEMA5 | 12 | 12 | pcs | 124560 | 54500 | 179060 | 1494720 | 654000 | 2148720 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Double Socket NEMA5 | 0 | 0 | pcs | 249120 | 54500 | 303620 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Power outlet general, 1p/2W, grounded | 4 | 4 | pcs | 150480 | 54500 | 204980 | 601920 | 218000 | 819920 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Power outlet general, 3p/4W, grounded | 0 | 0 | pcs | 150480 | 54500 | 204980 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single Socket 16A/230V, Lighting outlet general (wall) + Plug | 28 | 28 | pcs | 124560 | 54500 | 179060 | 3487680 | 1526000 | 5013680 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 574498.8 | 172349.64 | 746848.44 | 574498.8 | 172349.64 | 746848.44 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | [7 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lighting | 0 | 0 |  |  |  |  | 40385700 | 2790000 | 43175700 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Panel 36W, Type AI | 0 | 0 | pcs | 3339600 | 56000 | 3395600 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Frame Lamp 1x30W, Type BI | 0 | 0 | pcs | 1346400 | 56000 | 1402400 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Frame Lamp 1x46W, Type BII for Canopy | 6 | 6 | pcs | 1607100 | 56000 | 1663100 | 9642600 | 336000 | 9978600 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Wall mounted Light 1x15W, Type E | 28 | 28 | pcs | 585200 | 56000 | 641200 | 16385600 | 1568000 | 17953600 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Ceiling mounted Light 1x19W, Type D | 16 | 11 | pcs | 1182500 | 56000 | 1238500 | 13007500 | 616000 | 13623500 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 0 | 1 | lot | 1350000 | 270000 | 1620000 | 1350000 | 270000 | 1620000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | [7 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power | 0 | 0 |  |  |  |  | 21006619.4247 | 9958453.0553 | 30965072.48 | 0% | 0% | 0% | 0% |  |  | #REF! | 5947056.396 | 1442536.227 | 7389592.623 | 0 | 0 | 0 | 7389592.623
|  | 3C-1.5mm2 Cu/XLPE/PVC | 478 | 450 | m | 22980.09 | 5743.9305 | 28724.0205 | 10341040.5 | 2584768.725 | 12925809.225 | 36% | 0% | 36% | 72% |  |  | #REF! | 3722774.58 | 930516.741 | 4653291.321 | 0 | 0 | 0 | 4653291.321
|  | 3C-2.5mm2 Cu/XLPE/PVC | 217 | 190 | m | 32518.74 | 7485.665 | 40004.405 | 6178560.6 | 1422276.35 | 7600836.95 | 36% | 0% | 36% | 72% |  |  | #REF! | 2224281.816 | 512019.486 | 2736301.302 | 0 | 0 | 0 | 2736301.302
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 0 | 0 | m | 72299.4 | 17189.865 | 89489.265 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 0 | 0 | m | 102372.9 | 18573.4395 | 120946.3395 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Dado duct 50x130mm | 0 | 0 | m | 985945.6609 | 53025 | 1038970.6609 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 384 | 385 | m | 8773.9726 | 14594.0164 | 23367.989 | 3377979.4521 | 5618696.3185 | 8996675.7706 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 1109038.8726 | 332711.6618 | 1441750.5344 | 1109038.8726 | 332711.6618 | 1441750.5344 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 2. 110. |  | Electrical installation in technical areas | 1 | 1 | PSCH |  |  |  | 86058509.2699 | 9713896.6252 | 95772405.895 | 0% | 0% | 0% | 0% |  |  | #REF! | 4515110.7156 | 967003.6011 | 5482114.3167 | 0 | 0 | 0 | 5482114.3167
|  | Switch & Socket | [6 empty] | 2553112.8 | 2375897.84 | 4929010.64 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1-Way switch, 1 gang | 7 | 7 | pcs | 46800 | 54500 | 101300 | 327600 | 381500 | 709100 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single Socket NEMA5 | 13 | 13 | pcs | 124560 | 54500 | 179060 | 1619280 | 708500 | 2327780 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Double Socket NEMA5 | 2 | 2 | pcs | 249120 | 54500 | 303620 | 498240 | 109000 | 607240 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Power outlet general, 3p/4W, grounded | 0 | 0 | pcs | 150480 | 54500 | 204980 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single Socket 16A/230V, Lighting outlet general (wall) + Plug | 0 | 0 | pcs | 124560 | 54500 | 179060 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Socket combination type 1 | 3 | 3 | pcs | 0 | 381500 | 381500 | 0 | 1144500 | 1144500 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 107992.8 | 32397.84 | 140390.64 | 107992.8 | 32397.84 | 140390.64 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lighting | [6 empty] | 68830900 | 2170000 | 71000900 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Panel 36W, Type AI | 0 | 0 | pcs | 3339600 | 56000 | 3395600 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Frame Lamp 1x30W, Type BI | 0 | 0 | pcs | 1346400 | 56000 | 1402400 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Frame Lamp 1x46W, Type BII | 28 | 28 | pcs | 1607100 | 56000 | 1663100 | 44998800 | 1568000 | 46566800 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 56000 | 641200 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Ceiling mounted Light 1x19W, Type D | 0 | 0 | pcs | 1182500 | 56000 | 1238500 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Battery-operated hand lamp | 7 | 7 | pcs | 3254585.7143 | 56000 | 3310585.7143 | 22782100 | 392000 | 23174100 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 1050000 | 210000 | 1260000 | 1050000 | 210000 | 1260000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power | [6 empty] | 14674496.4699 | 5167998.7852 | 19842495.255 | 0% | 0% | 0% | 0% |  |  | #REF! | 4515110.7156 | 967003.6011 | 5482114.3167 | 0 | 0 | 0 | 5482114.3167
|  | 3C-1.5mm2 Cu/XLPE/PVC | 167 | 150 | m | 22980.09 | 5743.9305 | 28724.0205 | 3447013.5 | 861589.575 | 4308603.075 | 36% | 0% | 36% | 72% |  |  | #REF! | 1240924.86 | 310172.247 | 1551097.107 | 0 | 0 | 0 | 1551097.107
|  | 3C-2.5mm2 Cu/XLPE/PVC | 100 | 110 | m | 32518.74 | 7485.665 | 40004.405 | 3577061.4 | 823423.15 | 4400484.55 | 36% | 0% | 36% | 72% |  |  | #REF! | 1287742.104 | 296432.334 | 1584174.438 | 0 | 0 | 0 | 1584174.438
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 0 | 0 | m | 72299.4 | 17189.865 | 89489.265 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 43 | 53.9 | m | 102372.9 | 18573.4395 | 120946.3395 | 5517899.31 | 1001108.3891 | 6519007.6991 | 36% | 0% | 36% | 72% |  |  | #REF! | 1986443.7516 | 360399.0201 | 2346842.7717 | 0 | 0 | 0 | 2346842.7717
|  | Dado duct 50x130mm | 0 | 0 | m | 985945.6609 | 53025 | 1038970.6609 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 150 | 154 | m | 8773.9726 | 14594.0164 | 23367.989 | 1351191.7808 | 2247478.5274 | 3598670.3082 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 781330.479 | 234399.1437 | 1015729.6228 | 781330.479 | 234399.1437 | 1015729.6228 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 2. 120. |  | Electrical installation in kitchenette areas | 1 | 1 | PSCH |  |  |  | 92827708.5941 | 16840279.0483 | 109667987.6424 | 0% | 0% | 0% | 0% |  |  | #REF! | 14230631.124 | 3404649.8178 | 17635280.9418 | 0 | 0 | 0 | 17635280.9418
|  | Switch & Socket | [6 empty] | 9916993.8 | 3613842.14 | 13530835.94 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single Socket NEMA5 | 47 | 47 | pcs | 124560 | 54500 | 179060 | 5854320 | 2561500 | 8415820 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Double Socket NEMA5 | 11 | 11 | pcs | 249120 | 54500 | 303620 | 2740320 | 599500 | 3339820 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Power outlet general, 3p/4W, grounded | 6 | 6 | pcs | 150480 | 54500 | 204980 | 902880 | 327000 | 1229880 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 419473.8 | 125842.14 | 545315.94 | 419473.8 | 125842.14 | 545315.94 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | [7 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lighting | 0 | 0 |  |  |  |  | 40075200 | 672000 | 40747200 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Panel 36W, Type AI | 12 | 12 | pcs | 3339600 | 56000 | 3395600 | 40075200 | 672000 | 40747200 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Frame Lamp 1x46W, Type BII | 0 | 0 | pcs | 1607100 | 56000 | 1663100 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 56000 | 641200 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 0 | 0 | lot | 240000 | 48000 | 288000 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | [7 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power | 0 | 0 |  |  |  |  | 42835514.7941 | 12554436.9083 | 55389951.7024 | 0% | 0% | 0% | 0% |  |  | #REF! | 14230631.124 | 3404649.8178 | 17635280.9418 | 0 | 0 | 0 | 17635280.9418
|  | 3C-1.5mm2 Cu/XLPE/PVC | 196 | 210 | m | 22980.09 | 5743.9305 | 28724.0205 | 4825818.9 | 1206225.405 | 6032044.305 | 36% | 0% | 36% | 72% |  |  | #REF! | 1737294.804 | 434241.1458 | 2171535.9498 | 0 | 0 | 0 | 2171535.9498
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 501 | 480 | m | 72299.4 | 17189.865 | 89489.265 | 34703712 | 8251135.2 | 42954847.2 | 36% | 0% | 36% | 72% |  |  | #REF! | 12493336.32 | 2970408.672 | 15463744.992 | 0 | 0 | 0 | 15463744.992
|  | Dado duct 50x130mm | 0 | 0 | m | 985945.6609 | 53025 | 1038970.6609 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 120 | 176 | m | 8773.9726 | 14594.0164 | 23367.989 | 1544219.1781 | 2568546.8885 | 4112766.0666 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 1761764.716 | 528529.4148 | 2290294.1308 | 1761764.716 | 528529.4148 | 2290294.1308 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 2. 130. |  | Electrical installation for Workshop/Formbrettbau | 1 | 1 | PSCH |  |  |  | 90067954.1041 | 12614941.0865 | 102682895.1906 | 0% | 0% | 0% | 0% |  |  | #REF! | 12494541.6216 | 2516817.6079 | 15011359.2295 | 0 | 0 | 0 | 15011359.2295
|  | Switch & Socket | [6 empty] | 596177.4 | 1315565.22 | 1911742.62 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Push-button switch | 2 | 2 | pcs | 223200 | 54500 | 277700 | 446400 | 109000 | 555400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single Socket NEMA5 | 1 | 1 | pcs | 124560 | 54500 | 179060 | 124560 | 54500 | 179060 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Double Socket NEMA5 | 0 | 0 | pcs | 249120 | 54500 | 303620 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Power outlet general, 3p/4W, grounded | 0 | 0 | pcs | 150480 | 54500 | 204980 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Socket combination type 2 | 3 | 3 | pcs | 0 | 381500 | 381500 | 0 | 1144500 | 1144500 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 25217.4 | 7565.22 | 32782.62 | 25217.4 | 7565.22 | 32782.62 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lighting | [6 empty] | 52067200 | 1920000 | 53987200 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Panel 36W, Type AI | 0 | 0 | pcs | 3339600 | 56000 | 3395600 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Frame Lamp 1x46W, Type BII | 32 | 32 | pcs | 1607100 | 56000 | 1663100 | 51427200 | 1792000 | 53219200 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 56000 | 641200 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 640000 | 128000 | 768000 | 640000 | 128000 | 768000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power | [6 empty] | 37404576.7041 | 9379375.8665 | 46783952.5706 | 0% | 0% | 0% | 0% |  |  | #REF! | 12494541.6216 | 2516817.6079 | 15011359.2295 | 0 | 0 | 0 | 15011359.2295
|  | 3C-1.5mm2 Cu/XLPE/PVC | 222 | 234 | m | 22980.09 | 5743.9305 | 28724.0205 | 5377341.06 | 1344079.737 | 6721420.797 | 36% | 0% | 36% | 72% |  |  | #REF! | 1935842.7816 | 483868.7053 | 2419711.4869 | 0 | 0 | 0 | 2419711.4869
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 94 | 80 | m | 72299.4 | 17189.865 | 89489.265 | 5783952 | 1375189.2 | 7159141.2 | 36% | 0% | 36% | 72% |  |  | #REF! | 2082222.72 | 495068.112 | 2577290.832 | 0 | 0 | 0 | 2577290.832
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 248 | 230 | m | 102372.9 | 18573.4395 | 120946.3395 | 23545767 | 4271891.085 | 27817658.085 | 36% | 0% | 36% | 72% |  |  | #REF! | 8476476.12 | 1537880.7906 | 10014356.9106 | 0 | 0 | 0 | 10014356.9106
|  | Dado duct 50x130mm | 0 | 0 | m | 985945.6609 | 53025 | 1038970.6609 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 115 | 132 | m | 8773.9726 | 14594.0164 | 23367.989 | 1158164.3836 | 1926410.1664 | 3084574.5499 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 1539352.2605 | 461805.6782 | 2001157.9387 | 1539352.2605 | 461805.6782 | 2001157.9387 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 2. 140. |  | Electrical installation at the reception | 1 | 1 | PSCH |  |  |  | 41960735.3385 | 4068070.8188 | 46028806.1573 | 0% | 0% | 0% | 0% |  |  | #REF! | 2564042.6988 | 606038.8368 | 3170081.5356 | 0 | 0 | 0 | 3170081.5356
|  | Switch & Socket | [6 empty] | 1915601.436 | 405808.1108 | 2321409.5468 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1-Way switch, 1 gang | 1 | 1 | pcs | 46800 | 54500 | 101300 | 46800 | 54500 | 101300 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single Socket NEMA5 | 1 | 1 | pcs | 124560 | 54500 | 179060 | 124560 | 54500 | 179060 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Double Socket NEMA5 | 2 | 2 | pcs | 249120 | 54500 | 303620 | 498240 | 109000 | 607240 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Power outlet general, 1p/2W, grounded | 1 | 1 | pcs | 150480 | 54500 | 204980 | 150480 | 54500 | 204980 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Power outlet general, 3p/4W, grounded | 0 | 0 | pcs | 150480 | 54500 | 204980 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cord outlet socket with 2m cable reserve with connection terminals, E1 | 2 | 2 | pcs | 507247.2 | 54500 | 561747.2 | 1014494.4 | 109000 | 1123494.4 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cord outlet socket with 4m cable reserve with connection terminals, E2 | 0 | 0 | pcs | 507247.2 | 54500 | 561747.2 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cord outlet socket with 6m cable reserve with connection terminals, E3 | 0 | 0 | pcs | 507247.2 | 54500 | 561747.2 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 81027.036 | 24308.1108 | 105335.1468 | 81027.036 | 24308.1108 | 105335.1468 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lighting | [6 empty] | 13438400 | 240000 | 13678400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Panel 36W, Type AI | 4 | 4 | pcs | 3339600 | 56000 | 3395600 | 13358400 | 224000 | 13582400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Frame Lamp 1x46W, Type BII | 0 | 0 | pcs | 1607100 | 56000 | 1663100 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 56000 | 641200 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 80000 | 16000 | 96000 | 80000 | 16000 | 96000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power | [6 empty] | 26606733.9025 | 3422262.708 | 30028996.6105 | 0% | 0% | 0% | 0% |  |  | #REF! | 2564042.6988 | 606038.8368 | 3170081.5356 | 0 | 0 | 0 | 3170081.5356
|  | 3C-1.5mm2 Cu/XLPE/PVC | 60 | 55 | m | 22980.09 | 5743.9305 | 28724.0205 | 1263904.95 | 315916.1775 | 1579821.1275 | 36% | 0% | 36% | 72% |  |  | #REF! | 455005.782 | 113729.8239 | 568735.6059 | 0 | 0 | 0 | 568735.6059
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 80 | 74.8 | m | 72299.4 | 17189.865 | 89489.265 | 5407995.12 | 1285801.902 | 6693797.022 | 36% | 0% | 36% | 72% |  |  | #REF! | 1946878.2432 | 462888.6847 | 2409766.9279 | 0 | 0 | 0 | 2409766.9279
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 3 | 4.4 | m | 102372.9 | 18573.4395 | 120946.3395 | 450440.76 | 81723.1338 | 532163.8938 | 36% | 0% | 36% | 72% |  |  | #REF! | 162158.6736 | 29420.3282 | 191579.0018 | 0 | 0 | 0 | 191579.0018
|  | Dado duct 50x130mm | 18 | 18 | m | 985945.6609 | 53025 | 1038970.6609 | 17747021.8965 | 954450 | 18701471.8965 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 26 | 22 | m | 8773.9726 | 14594.0164 | 23367.989 | 193027.3973 | 321068.3611 | 514095.7583 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 1544343.7787 | 463303.1336 | 2007646.9124 | 1544343.7787 | 463303.1336 | 2007646.9124 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 2. 150. |  | Electrical installation in other rooms/secondary rooms | 1 | 1 | PSCH |  |  |  | 275591719.5806 | 31538420.0323 | 307130139.6129 | 0% | 0% | 0% | 0% |  |  | #REF! | 21414248.4652 | 4538121.5286 | 25952369.9938 | 0 | 0 | 0 | 25952369.9938
|  | Switch & Socket | [6 empty] | 15705304.986 | 4668293.1758 | 20373598.1618 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1-Way switch, 1 gang | 7 | 7 | pcs | 46800 | 54500 | 101300 | 327600 | 381500 | 709100 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Push-button switch | 9 | 9 | pcs | 223200 | 54500 | 277700 | 2008800 | 490500 | 2499300 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single Socket NEMA5 | 10 | 10 | pcs | 124560 | 54500 | 179060 | 1245600 | 545000 | 1790600 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Double Socket NEMA5 | 9 | 9 | pcs | 249120 | 54500 | 303620 | 2242080 | 490500 | 2732580 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Power outlet general, 1p/2W, grounded | 0 | 0 | pcs | 150480 | 54500 | 204980 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Power outlet general, 3p/4W, grounded | 0 | 0 | pcs | 150480 | 54500 | 204980 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Socket combination type 1 | 4 | 4 | pcs | 0 | 381500 | 381500 | 0 | 1526000 | 1526000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Socket combination type 2 | 2 | 2 | pcs | 0 | 381500 | 381500 | 0 | 763000 | 763000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cord outlet socket with 2m cable reserve with connection terminals, E1 | 0 | 0 | pcs | 507247.2 | 54500 | 561747.2 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cord outlet socket with 4m cable reserve with connection terminals, E2 | 0 | 0 | pcs | 507247.2 | 54500 | 561747.2 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cord outlet socket with 6m cable reserve with connection terminals, E3 | 0 | 0 | pcs | 507247.2 | 54500 | 561747.2 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Floor box, recessed (1xDouble Socket NEMA5, 1xIT - Double socket,1x HDMI connection to the projector) | 1 | 1 | pcs | 9216914.4 | 272500 | 9489414.4 | 9216914.4 | 272500 | 9489414.4 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 664310.586 | 199293.1758 | 863603.7618 | 664310.586 | 199293.1758 | 863603.7618 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lighting | [6 empty] | 135827400 | 4650000 | 140477400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Panel 36W, Type AI | 9 | 9 | pcs | 3339600 | 56000 | 3395600 | 30056400 | 504000 | 30560400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Frame Lamp 1x46W, Type BII | 58 | 60 | pcs | 1607100 | 56000 | 1663100 | 96426000 | 3360000 | 99786000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 56000 | 641200 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Ceiling mounted Light 1x19W, Type D | 6 | 6 | pcs | 1182500 | 56000 | 1238500 | 7095000 | 336000 | 7431000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 2250000 | 450000 | 2700000 | 2250000 | 450000 | 2700000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power | [6 empty] | 124059014.5946 | 22220126.8565 | 146279141.4511 | 0% | 0% | 0% | 0% |  |  | #REF! | 21414248.4652 | 4538121.5286 | 25952369.9938 | 0 | 0 | 0 | 25952369.9938
|  | 3C-1.5mm2 Cu/XLPE/PVC | 693 | 684.5455 | m | 22980.09 | 5743.9305 | 28724.0205 | 15730916.1545 | 3931981.515 | 19662897.6695 | 36% | 0% | 36% | 72% |  |  | #REF! | 5663129.8156 | 1415513.3454 | 7078643.161 | 0 | 0 | 0 | 7078643.161
|  | 3C-2.5mm2 Cu/XLPE/PVC | 442 | 464 | m | 32518.74 | 7485.665 | 40004.405 | 15088695.36 | 3473348.56 | 18562043.92 | 36% | 0% | 36% | 72% |  |  | #REF! | 5431930.3296 | 1250405.4816 | 6682335.8112 | 0 | 0 | 0 | 6682335.8112
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 0 | 0 | m | 72299.4 | 17189.865 | 89489.265 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 317 | 280 | m | 102372.9 | 18573.4395 | 120946.3395 | 28664412 | 5200563.06 | 33864975.06 | 36% | 0% | 36% | 72% |  |  | #REF! | 10319188.32 | 1872202.7016 | 12191391.0216 | 0 | 0 | 0 | 12191391.0216
|  | Dado duct 50x130mm | 57 | 57 | m | 985945.6609 | 53025 | 1038970.6609 | 56198902.6722 | 3022425 | 59221327.6722 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 278 | 341 | m | 8773.9726 | 14594.0164 | 23367.989 | 2991924.6575 | 4976559.5964 | 7968484.2539 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 5384163.7503 | 1615249.1251 | 6999412.8754 | 5384163.7503 | 1615249.1251 | 6999412.8754 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 2. 160. |  | Emergency lighting | 1 | 1 | PSCH |  |  |  | 125963193.8122 | 37581630.6399 | 163544824.4521 | 0% | 0% | 0% | 0% |  |  | #REF! | 14809034.196 | 3408971.841 | 18218006.037 | 0 | 0 | 0 | 18218006.037
|  | Switch & Socket | [6 empty] | 73296840 | 12022500 | 85319340 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Emergency light | 81 | 81 | pcs | 516120 | 56000 | 572120 | 41805720 | 4536000 | 46341720 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Exit light | 24 | 24 | pcs | 566280 | 56000 | 622280 | 13590720 | 1344000 | 14934720 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single Socket 16A/230V | 105 | 105 | pcs | 150480 | 54500 | 204980 | 15800400 | 5722500 | 21522900 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | pcs | 2100000 | 420000 | 2520000 | 2100000 | 420000 | 2520000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power supply | [6 empty] | 52666353.8122 | 25559130.6399 | 78225484.4521 | 0% | 0% | 0% | 0% |  |  | #REF! | 14809034.196 | 3408971.841 | 18218006.037 | 0 | 0 | 0 | 18218006.037
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 1575 | 1265 | m | 32518.74 | 7485.665 | 40004.405 | 41136206.1 | 9469366.225 | 50605572.325 | 36% | 0% | 36% | 72% |  |  | #REF! | 14809034.196 | 3408971.841 | 18218006.037 | 0 | 0 | 0 | 18218006.037
|  | PVC conduit D20 | 882 | 950 | m | 8773.9726 | 14594.0164 | 23367.989 | 8335273.9726 | 13864315.5912 | 22199589.5638 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC flexible conduct D20 | 315 | 300 | m | 3554.7229 | 5289.7059 | 8844.4288 | 1066416.876 | 1586911.7647 | 2653328.6407 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 2128456.8636 | 638537.0591 | 2766993.9226 | 2128456.8636 | 638537.0591 | 2766993.9226 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. |  | Machine hook-up (Hall 3) | [6 empty] | 3164184545.4338 | 446703070.7456 | 3610887616.1794 | 0% | 0% | 0% | 0% |  |  | #REF! | 236724761.688 | 37440447.6647 | 274165209.3527 | 391176914.6561 | 54828713.77 | 446005628.4261 | 720170837.7788
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
4. 1. |  | Electrical engineering | 1 | 1 | PSCH |  |  |  | 3164184545.4338 | 446703070.7456 | 3610887616.1794 | 0% | 0% | 0% | 0% |  |  | #REF! | 236724761.688 | 37440447.6647 | 274165209.3527 | 391176914.6561 | 54828713.77 | 446005628.4261 | 720170837.7788
4. 1. 10. |  | Machine hook-up | 1 | 1 | PSCH |  |  |  | 3164184545.4338 | 446703070.7456 | 3610887616.1794 | 0% | 0% | 0% | 0% |  |  | #REF! | 236724761.688 | 37440447.6647 | 274165209.3527 | 391176914.6561 | 54828713.77 | 446005628.4261 | 720170837.7788
|  | Cable trays_Hot dip-Galvanized Steel | [6 empty] | 538685840 | 65789758.3358 | 604475598.3358 | 0% | 0% | 0% | 0% |  |  | #REF! | 161605752 | 19736927.5007 | 181342679.5007 | 215474336 | 26315903.3343 | 241790239.3343 | 423132918.8351
|  | Cable tray 400x100x2.0mm | 122 | 122 | m | 776880 | 68320 | 845200 | 94779360 | 8335040 | 103114400 | 30% | 40% | 70% | 140% |  |  | #REF! | 28433808 | 2500512 | 30934320 | 37911744 | 3334016 | 41245760 | 72180080
|  | Cable tray 500x100 with separating bar | 195 | 201 | m | 1525680 | 81001.3848 | 1606681.3848 | 306661680 | 16281278.3358 | 322942958.3358 | 30% | 40% | 70% | 140% |  |  | #REF! | 91998504 | 4884383.5007 | 96882887.5007 | 122664672 | 6512511.3343 | 129177183.3343 | 226060070.8351
|  | Fitting and accessories | 1 | 1 | lot | 137244800 | 41173440 | 178418240 | 137244800 | 41173440 | 178418240 | 30% | 40% | 70% | 140% |  |  | #REF! | 41173440 | 12352032 | 53525472 | 54897920 | 16469376 | 71367296 | 124892768
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Busway Canalis KSA 250A 3L+N+PE 10kA/s, IP54 | [6 empty] | 2002937565.0909 | 225436964.9679 | 2228374530.0588 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 250A Feeder,3L+N+PE | 190 | 194 | m | 7268140 | 553706.5149 | 7821846.5149 | 1410019160 | 107419063.8906 | 1517438223.8906 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 250A Cable Tap Box - End | 6 | 6 | pcs | 5043610 | 497400.75 | 5541010.75 | 30261660 | 2984404.5 | 33246064.5 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 100-250A End Cover | 6 | 6 | pcs | 551650 | 27500 | 579150 | 3309900 | 165000 | 3474900 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Joint Cover | 70 | 70 | pcs | 813560 | 27500 | 841060 | 56949200 | 1925000 | 58874200 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PIO Cover | 282 | 651 | pcs | 90090 | 27500 | 117590 | 58648590 | 17902500 | 76551090 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fixing Bracket | 70 | 70 | pcs | 109450 | 220200.75 | 329650.75 | 7661500 | 15414052.5 | 23075552.5 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Screw-on plate for blanking of unused openings | 138 | 138 | pcs | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Tap-off Unit included: - 1x Busbar tap-off unit with 16A/230V 3pin Industrial Socket CEE - 1x MCB 2P 16A | 82 | 69 | pcs | 2882070 | 497400.75 | 3379470.75 | 198862830 | 34320651.75 | 233183481.75 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Tap-off Unit included: - 1x Busbar tap-off unit with 16A/400V 5pin Industrial Socket CEE - 1x MCB 3P 16A | 56 | 56 | pcs | 3041460 | 497400.75 | 3538860.75 | 170321760 | 27854442 | 198176202 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Industrial plug 16A-230V for Industrial socket 16A-230V | 82 | 69 | pcs | 226176 | 54500 | 280676 | 15606144 | 3760500 | 19366644 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Industrial plug 16A-400V for Industrial socket 16A-400V | 56 | 56 | pcs | 282720 | 54500 | 337220 | 15832320 | 3052000 | 18884320 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 35464501.0909 | 10639350.3273 | 46103851.4182 | 35464501.0909 | 10639350.3273 | 46103851.4182 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Electrical installation Production | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Schuko-socket 16A/230V | 0 | 0 | pcs | 0 | 54500 | 54500 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 16A/230V 3pin Industrial Socket CEE | 41 | 41 | pcs | 381600 | 54500 | 436100 | 15645600 | 2234500 | 17880100 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Socket combination type 1 | 21 | 21 | pcs | 0 | 381500 | 381500 | 0 | 8011500 | 8011500 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Socket combination type 2 | 10 | 10 | pcs | 0 | 381500 | 381500 | 0 | 3815000 | 3815000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 691014 | 207304.2 | 898318.2 | 691014 | 207304.2 | 898318.2 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | From Building 3_UPS 1 DP 1.3 35kVA Panel to16A/230V Socket (19 set) | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3C-2.5mm2 Cu/XLPE/PVC | 892 | 737 | m | 32518.74 | 7485.665 | 40004.405 | 23966311.38 | 5516935.105 | 29483246.485 | 36% | 34% | 70% | 140% |  |  | #REF! | 8627872.0968 | 1986096.6378 | 10613968.7346 | 8148545.8692 | 1875757.9357 | 10024303.8049 | 20638272.5395
|  | From Building 3_UPS 2 DP 1.3 35kVA Panel to16A/230V Socket (22 set) | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3C-2.5mm2 Cu/XLPE/PVC | 1107 | 1033 | m | 32518.74 | 7485.665 | 40004.405 | 33591858.42 | 7732691.945 | 41324550.365 | 36% | 0% | 36% | 72% |  |  | #REF! | 12093069.0312 | 2783769.1002 | 14876838.1314 | 0 | 0 | 0 | 14876838.1314
|  | From PDP 1.0 Panel to Combine socket (9 set) | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 587 | 519 | m | 72299.4 | 17189.865 | 89489.265 | 37523388.6 | 8921539.935 | 46444928.535 | 36% | 0% | 36% | 72% |  |  | #REF! | 13508419.896 | 3211754.3766 | 16720174.2726 | 0 | 0 | 0 | 16720174.2726
|  | From PDP 1.1 Panel to Combine socket (3 set) | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 197 | 110 | m | 72299.4 | 17189.865 | 89489.265 | 7952934 | 1890885.15 | 9843819.15 | 36% | 0% | 36% | 72% |  |  | #REF! | 2863056.24 | 680718.654 | 3543774.894 | 0 | 0 | 0 | 3543774.894
|  | From PDP 1.2 Panel to Combine socket (4 set) | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 182 | 205 | m | 72299.4 | 17189.865 | 89489.265 | 14821377 | 3523922.325 | 18345299.325 | 36% | 0% | 36% | 72% |  |  | #REF! | 5335695.72 | 1268612.037 | 6604307.757 | 0 | 0 | 0 | 6604307.757
|  | From PDP 2.0 Panel to Combine socket (9 set) | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 830 | 811 | m | 72299.4 | 17189.865 | 89489.265 | 58634813.4 | 13940980.515 | 72575793.915 | 36% | 0% | 36% | 72% |  |  | #REF! | 21108532.824 | 5018752.9854 | 26127285.8094 | 0 | 0 | 0 | 26127285.8094
|  | From PDP 2.1 Panel to Combine socket (6 set) | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 440 | 445 | m | 72299.4 | 17189.865 | 89489.265 | 32173233 | 7649489.925 | 39822722.925 | 36% | 0% | 36% | 72% |  |  | #REF! | 11582363.88 | 2753816.373 | 14336180.253 | 0 | 0 | 0 | 14336180.253
|  | PVC conduit D20 | 246 | 250 | m | 8773.9726 | 14594.0164 | 23367.989 | 2193493.1507 | 3648504.1029 | 5841997.2536 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 9074248.7636 | 2722274.6291 | 11796523.3926 | 9074248.7636 | 2722274.6291 | 11796523.3926 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Tel-Data system | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Double data outlet RJ45 | 179 | 191 | pcs | 480000 | 81750 | 561750 | 91680000 | 15614250 | 107294250 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 41256000 | 7026412.5 | 48282412.5 | 48282412.5
|  | Cable Cat6A | 12618 | 12970 | m | 21639.3443 | 3360 | 24999.3443 | 280662295.082 | 43579200 | 324241495.082 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 126298032.7869 | 19610640 | 145908672.7869 | 145908672.7869
|  | PVC conduit D20 | 160 | 170.7263 | m | 8773.9726 | 14594.0164 | 23367.989 | 1497947.5013 | 2491581.7963 | 3989529.2977 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Network cable test cost - FO cable |  |  | nos | 0 | 50600 | 50600 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Network cable test cost - Cat6A cable | 376 | 400 | nos | 0 | 50600 | 50600 | 0 | 20240000 | 20240000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 12452626.0453 | 3735787.8136 | 16188413.8589 | 12452626.0453 | 3735787.8136 | 16188413.8589 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. |  | Scooter Garage | [6 empty] | 108075385.8789 | 16341158.0259 | 124416543.9048 | 0% | 0% | 0% | 0% |  |  | #REF! | 18341662.2 | 2739626.4095 | 21081288.6095 | 0 | 0 | 0 | 21081288.6095
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
5. 2. |  | Electrical Engineering | 1 | 1 | PSCH |  |  |  | 108075385.8789 | 16341158.0259 | 124416543.9048 | 0% | 0% | 0% | 0% |  |  | #REF! | 18341662.2 | 2739626.4095 | 21081288.6095 | 0 | 0 | 0 | 21081288.6095
5. 2. 10. |  | Grounding and Lightining protection | 1 |  | PSCH |  |  |  | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Classic lightning rod Ø16, l = 1,000mm | 9 |  | m | 312500 | 120872.0782 | 433372.0783 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Claded copper - steel grounding rod Ø 16, L = 2.4m | 9 |  | m | 210227.2727 | 120872.0782 | 331099.351 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Exothermic welding connection | 19 |  | m | 119318.1818 | 56925 | 176243.1818 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Grounding Test Link box | 1 |  | m | 562500 | 56925 | 619425 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Bare Copper wire 50sqmm | 322 |  | m | 135322.14 | 22106.7 | 157428.84 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 54 |  | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | T&C | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. 2. 20. |  | Power supply | 1 | 1 | PSCH |  |  |  | 48996560 | 6144115.6772 | 55140675.6772 | 0% | 0% | 0% | 0% |  |  | #REF! | 14698968 | 1843234.7032 | 16542202.7032 | 0 | 0 | 0 | 16542202.7032
|  | Cable trays | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable tray 200x100x2.0mm, c/w cover | 47 | 47 | m | 776880 | 51045.8655 | 827925.8655 | 36513360 | 2399155.6772 | 38912515.6772 | 30% | 0% | 30% | 60% |  |  | #REF! | 10954008 | 719746.7032 | 11673754.7032 | 0 | 0 | 0 | 11673754.7032
|  | Fitting and accessories | 1 | 1 | lot | 12483200 | 3744960 | 16228160 | 12483200 | 3744960 | 16228160 | 30% | 0% | 30% | 60% |  |  | #REF! | 3744960 | 1123488 | 4868448 | 0 | 0 | 0 | 4868448
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. 2. 30. |  | Power supply of building utilities | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. 2. 40. |  | Electrical installations | 1 | 1 | PSCH |  |  |  | 44249283.3619 | 5904426.8866 | 50153710.2486 | 0% | 0% | 0% | 0% |  |  | #REF! | 1946763.558 | 472489.6354 | 2419253.1934 | 0 | 0 | 0 | 2419253.1934
|  | Switch & Socket | [6 empty] | 11703872.04 | 857016.812 | 12560888.852 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1-Way switch, 1 gang | 2 | 2 | pcs | 46800 | 54500 | 101300 | 93600 | 109000 | 202600 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 16A/230V 3pin Industrial Socket CEE | 2 | 2 | pcs | 381600 | 54500 | 436100 | 763200 | 109000 | 872200 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Motion sensor | 9 | 9 | pcs | 1150224 | 54500 | 1204724 | 10352016 | 490500 | 10842516 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 495056.04 | 148516.812 | 643572.852 | 495056.04 | 148516.812 | 643572.852 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lighting | [6 empty] | 25171700 | 992000 | 26163700 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Frame Lamp 1x46W, Type BII | 15 | 15 | pcs | 1607100 | 56000 | 1663100 | 24106500 | 840000 | 24946500 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Wall mounted Light 1x15W, Type E | 1 | 1 | pcs | 585200 | 56000 | 641200 | 585200 | 56000 | 641200 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 480000 | 96000 | 576000 | 480000 | 96000 | 576000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power | [6 empty] | 7373711.3219 | 4055410.0746 | 11429121.3966 | 0% | 0% | 0% | 0% |  |  | #REF! | 1946763.558 | 472489.6354 | 2419253.1934 | 0 | 0 | 0 | 2419253.1934
|  | 3C-1.5mm2 Cu/XLPE/PVC | 164 | 149 | m | 22980.09 | 5743.9305 | 28724.0205 | 3424033.41 | 855845.6445 | 4279879.0545 | 36% | 0% | 36% | 72% |  |  | #REF! | 1232652.0276 | 308104.432 | 1540756.4596 | 0 | 0 | 0 | 1540756.4596
|  | 3C-2.5mm2 Cu/XLPE/PVC | 68 | 61 | m | 32518.74 | 7485.665 | 40004.405 | 1983643.14 | 456625.565 | 2440268.705 | 36% | 0% | 36% | 72% |  |  | #REF! | 714111.5304 | 164385.2034 | 878496.7338 | 0 | 0 | 0 | 878496.7338
|  | PVC conduit D20 | 12 | 180 | m | 8773.9726 | 14594.0164 | 23367.989 | 1579315.0685 | 2626922.9541 | 4206238.0226 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 386719.7034 | 116015.911 | 502735.6145 | 386719.7034 | 116015.911 | 502735.6145 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. 2. 50. |  | Emergency lighting | 1 | 1 | PSCH |  |  |  | 14829542.5169 | 4292615.4621 | 19122157.979 | 0% | 0% | 0% | 0% |  |  | #REF! | 1695930.642 | 423902.0709 | 2119832.7129 | 0 | 0 | 0 | 2119832.7129
|  | Emergency light | 6 | 12 | pcs | 516120 | 56000 | 572120 | 6193440 | 672000 | 6865440 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Exit light | 1 | 2 | pcs | 566280 | 56000 | 622280 | 1132560 | 112000 | 1244560 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single Socket 16A/230V | 8 | 8 | pcs | 124560 | 54500 | 179060 | 996480 | 436000 | 1432480 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | pcs | 440000 | 88000 | 528000 | 440000 | 88000 | 528000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power supply | [6 empty] | 6067062.5169 | 2984615.4621 | 9051677.979 | 0% | 0% | 0% | 0% |  |  | #REF! | 1695930.642 | 423902.0709 | 2119832.7129 | 0 | 0 | 0 | 2119832.7129
|  | Cable Cu/XLPE/PVC 3Cx1.5mm2 | 120 | 205 | m | 22980.09 | 5743.9305 | 28724.0205 | 4710918.45 | 1177505.7525 | 5888424.2025 | 36% | 0% | 36% | 72% |  |  | #REF! | 1695930.642 | 423902.0709 | 2119832.7129 | 0 | 0 | 0 | 2119832.7129
|  | PVC conduit D20 | 68 | 110 | m | 8773.9726 | 14594.0164 | 23367.989 | 965136.9863 | 1605341.8053 | 2570478.7916 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC flexible conduct D20 | 24 | 20 | m | 3554.7229 | 5289.7059 | 8844.4288 | 71094.4584 | 105794.1176 | 176888.576 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 319912.6222 | 95973.7867 | 415886.4089 | 319912.6222 | 95973.7867 | 415886.4089 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. |  | Canteen | [6 empty] | 350267145.0631 | 45874850.9531 | 396141996.0162 | 0% | 0% | 0% | 0% |  |  | #REF! | 19739087.9208 | 4627915.7206 | 24367003.6414 | 0 | 0 | 0 | 24367003.6414
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
6. 2. |  | Electrical Engineering | 1 | 1 | PSCH |  |  |  | 350267145.0631 | 45874850.9531 | 396141996.0162 | 0% | 0% | 0% | 0% |  |  | #REF! | 19739087.9208 | 4627915.7206 | 24367003.6414 | 0 | 0 | 0 | 24367003.6414
|  | Notes Calculation Basis | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. 2. 10. |  | Grounding and Lightining protection | 1 | 1 | PSCH |  |  |  | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Classic lightning rod Ø16, l = 1,000mm | 6 |  | m | 312500 | 120872.0782 | 433372.0783 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Claded copper - steel grounding rod Ø 16, L = 2.4m | 6 |  | m | 210227.2727 | 120872.0782 | 331099.351 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Exothermic welding connection | 21 |  | m | 119318.1818 | 56925 | 176243.1818 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Grounding Test Link box | 2 |  | m | 562500 | 56925 | 619425 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Bare Copper wire 50sqmm | 259 |  | m | 135322.14 | 22106.7 | 157428.84 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 36 |  | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | T&C | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. 2. 20. |  | Power supply | 1 | 1 | PSCH |  |  |  | 106191661.9795 | 12858262.8895 | 119049924.8689 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable trays_Hot dip-Galvanized Steel | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable tray 200x50 with separating bar | 149 | 149 | m | 669240 | 56000 | 725240 | 99716760 | 8344000 | 108060760 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 215 | 215 | m | 8773.9726 | 14594.0164 | 23367.989 | 1886404.1096 | 3137713.5285 | 5024117.6381 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fitting and accessories | 1 | 1 | lot | 4588497.8699 | 1376549.361 | 5965047.2308 | 4588497.8699 | 1376549.361 | 5965047.2308 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. 2. 30. |  | Power supply of building utilities | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. 2. 40. |  | Electrical installations | 1 | 1 | PSCH |  |  |  | 220631937.3221 | 25881817.2569 | 246513754.579 | 0% | 0% | 0% | 0% |  |  | #REF! | 17151896.9664 | 4032356.2132 | 21184253.1796 | 0 | 0 | 0 | 21184253.1796
|  | Switch & Socket | [6 empty] | 27779110.24 | 5475504.272 | 33254614.512 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1-Way switch, 1 gang | 5 | 5 | pcs | 46800 | 54500 | 101300 | 234000 | 272500 | 506500 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single Socket NEMA5 | 24 | 24 | pcs | 124560 | 54500 | 179060 | 2989440 | 1308000 | 4297440 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 16A/230V 3pin Industrial Socket CEE | 4 | 4 | pcs | 381600 | 54500 | 436100 | 1526400 | 218000 | 1744400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Socket combination type 1 | 6 | 6 | pcs | 0 | 381500 | 381500 | 0 | 2289000 | 2289000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Motion sensor | 19 | 19 | pcs | 1150224 | 54500 | 1204724 | 21854256 | 1035500 | 22889756 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 1175014.24 | 352504.272 | 1527518.512 | 1175014.24 | 352504.272 | 1527518.512 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lighting | [6 empty] | 141953700 | 6649872 | 148603572 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Frame Lamp 1x46W, Type BII | 5 | 5 | pcs | 1607100 | 63504 | 1670604 | 8035500 | 317520 | 8353020 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Frame Lamp 1x46W, Type J | 70 | 70 | pcs | 1607100 | 63504 | 1670604 | 112497000 | 4445280 | 116942280 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Wall mounted Light 1x15W, Type E | 6 | 6 | pcs | 585200 | 63504 | 648704 | 3511200 | 381024 | 3892224 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LED Ceiling mounted Light 1x19W, Type D | 12 | 12 | pcs | 1182500 | 63504 | 1246004 | 14190000 | 762048 | 14952048 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 3720000 | 744000 | 4464000 | 3720000 | 744000 | 4464000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power | [6 empty] | 50899127.0821 | 13756440.9849 | 64655568.067 | 0% | 0% | 0% | 0% |  |  | #REF! | 17151896.9664 | 4032356.2132 | 21184253.1796 | 0 | 0 | 0 | 21184253.1796
|  | 3C-1.5mm2 Cu/XLPE/PVC | 697 | 572 | m | 22980.09 | 5743.9305 | 28724.0205 | 13144611.48 | 3285528.246 | 16430139.726 | 36% | 0% | 36% | 72% |  |  | #REF! | 4732060.1328 | 1182790.1686 | 5914850.3014 | 0 | 0 | 0 | 5914850.3014
|  | 3C-2.5mm2 Cu/XLPE/PVC | 496 | 464 | m | 32518.74 | 7485.665 | 40004.405 | 15088695.36 | 3473348.56 | 18562043.92 | 36% | 0% | 36% | 72% |  |  | #REF! | 5431930.3296 | 1250405.4816 | 6682335.8112 | 0 | 0 | 0 | 6682335.8112
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 242 | 226 | m | 72299.4 | 17189.865 | 89489.265 | 16339664.4 | 3884909.49 | 20224573.89 | 36% | 0% | 36% | 72% |  |  | #REF! | 5882279.184 | 1398567.4164 | 7280846.6004 | 0 | 0 | 0 | 7280846.6004
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 30 | 30 | m | 102372.9 | 18573.4395 | 120946.3395 | 3071187 | 557203.185 | 3628390.185 | 36% | 0% | 36% | 72% |  |  | #REF! | 1105627.32 | 200593.1466 | 1306220.4666 | 0 | 0 | 0 | 1306220.4666
|  | PVC conduit D20 | 117 | 132 | m | 8773.9726 | 14594.0164 | 23367.989 | 1158164.3836 | 1926410.1664 | 3084574.5499 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 2096804.4585 | 629041.3376 | 2725845.7961 | 2096804.4585 | 629041.3376 | 2725845.7961 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. 2. 50. |  | Emergency lighting | 1 | 1 | PSCH |  |  |  | 23443545.7616 | 7134770.8067 | 30578316.5683 | 0% | 0% | 0% | 0% |  |  | #REF! | 2587190.9544 | 595559.5074 | 3182750.4618 | 0 | 0 | 0 | 3182750.4618
|  | Emergency light | 14 | 15 | pcs | 516120 | 63504 | 579624 | 7741800 | 952560 | 8694360 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Exit light | 7 | 7 | pcs | 566280 | 63504 | 629784 | 3963960 | 444528 | 4408488 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single Socket 16A/230V | 9 | 15 | pcs | 124560 | 54500 | 179060 | 1868400 | 817500 | 2685900 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | pcs | 440000 | 88000 | 528000 | 440000 | 88000 | 528000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power supply | [6 empty] | 9429385.7616 | 4832182.8067 | 14261568.5683 | 0% | 0% | 0% | 0% |  |  | #REF! | 2587190.9544 | 595559.5074 | 3182750.4618 | 0 | 0 | 0 | 3182750.4618
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 315 | 221 | m | 32518.74 | 7485.665 | 40004.405 | 7186641.54 | 1654331.965 | 8840973.505 | 36% | 0% | 36% | 72% |  |  | #REF! | 2587190.9544 | 595559.5074 | 3182750.4618 | 0 | 0 | 0 | 3182750.4618
|  | PVC conduit D20 | 177 | 190 | m | 8773.9726 | 14594.0164 | 23367.989 | 1667054.7945 | 2772863.1182 | 4439917.9128 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC flexible conduct D20 | 63 | 55 | m | 3554.7229 | 5289.7059 | 8844.4288 | 195509.7606 | 290933.8235 | 486443.5841 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 380179.6664 | 114053.8999 | 494233.5664 | 380179.6664 | 114053.8999 | 494233.5664 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | II. ELV | [8 empty] | 3412928080.1667 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 86650661.8505 |  |  | 847831186.021 | 934481847.8715
1. |  | Construction site facilities | [6 empty] | 124241733.1691 | 20176036.5818 | 144417769.7509 | 0% | 0% | 0% | 0% |  |  | #REF! | 74545039.9014 | 12105621.9491 | 86650661.8505 | 0 | 0 | 0 | 86650661.8505
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
1. 1. |  | Construction site facilities | 1 | 1 | psch | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
1. 2. |  | Construction site cameras | 1 | 1 | psch |  |  |  | 124241733.1691 | 20176036.5818 | 144417769.7509 | 60% | 0% | 60% | 50% |  |  | #REF! | 74545039.9014 | 12105621.9491 | 86650661.8505 | 0 | 0 | 0 | 86650661.8505
|  | Rack for NVR+Swtich | 1 | 1 | pcs | 1848000 | 165000 | 2013000 | 1848000 | 165000 | 2013000 | 60% | 0% | 60% | 50% |  |  | #REF! | 1108800 | 99000 | 1207800 | 0 | 0 | 0 | 1207800
|  | Camera bullet 360' + base, Resolution: 4K | 3 | 3 | pcs | 9067520 | 198000 | 9265520 | 27202560 | 594000 | 27796560 | 60% | 0% | 60% | 50% |  |  | #REF! | 16321536 | 356400 | 16677936 | 0 | 0 | 0 | 16677936
|  | NVR 8 chanel | 1 | 1 | pcs | 9431520 | 165000 | 9596520 | 9431520 | 165000 | 9596520 | 60% | 0% | 60% | 50% |  |  | #REF! | 5658912 | 99000 | 5757912 | 0 | 0 | 0 | 5757912
|  | 1KVA UPS | 1 | 1 | pcs | 2529000 | 137500 | 2666500 | 2529000 | 137500 | 2666500 | 60% | 0% | 60% | 50% |  |  | #REF! | 1517400 | 82500 | 1599900 | 0 | 0 | 0 | 1599900
|  | Switch PoE 4P | 1 | 1 | pcs | 1155000 | 81750 | 1236750 | 1155000 | 81750 | 1236750 | 60% | 0% | 60% | 50% |  |  | #REF! | 693000 | 49050 | 742050 | 0 | 0 | 0 | 742050
|  | LCD 32" | 1 | 1 | pcs | 8360000 | 163500 | 8523500 | 8360000 | 163500 | 8523500 | 60% | 0% | 60% | 50% |  |  | #REF! | 5016000 | 98100 | 5114100 | 0 | 0 | 0 | 5114100
|  | Double Socket 16A/230V | 3 | 3 | pcs | 150480 | 54500 | 204980 | 451440 | 163500 | 614940 | 60% | 0% | 60% | 50% |  |  | #REF! | 270864 | 98100 | 368964 | 0 | 0 | 0 | 368964
|  | PVC box for socket, conver at camera | 3 | 3 | pcs | 36000 | 16350 | 52350 | 108000 | 49050 | 157050 | 60% | 0% | 60% | 50% |  |  | #REF! | 64800 | 29430 | 94230 | 0 | 0 | 0 | 94230
|  | surge protection | 2 | 2 | pcs | 4494000 | 49050 | 4543050 | 8988000 | 98100 | 9086100 | 60% | 0% | 60% | 50% |  |  | #REF! | 5392800 | 58860 | 5451660 | 0 | 0 | 0 | 5451660
|  | Cable Cat6 | 10 | 10 | m | 10032.7869 | 3360 | 13392.7869 | 100327.8689 | 33600 | 133927.8689 | 60% | 0% | 60% | 50% |  |  | #REF! | 60196.7213 | 20160 | 80356.7213 | 0 | 0 | 0 | 80356.7213
|  | converter quang đồng | 6 | 6 | pcs | 770000 | 49050 | 819050 | 4620000 | 294300 | 4914300 | 60% | 0% | 60% | 50% |  |  | #REF! | 2772000 | 176580 | 2948580 | 0 | 0 | 0 | 2948580
|  | Fiber optical 2FO | 373 | 373 | m | 14400 | 3360 | 17760 | 5371200 | 1253280 | 6624480 | 60% | 0% | 60% | 50% |  |  | #REF! | 3222720 | 751968 | 3974688 | 0 | 0 | 0 | 3974688
|  | Cable Cu/XLPE/PVC 3Cx1.5mm2 | 397 | 397 | m | 22980.09 | 5743.9305 | 28724.0205 | 9123095.73 | 2280340.4085 | 11403436.1385 | 60% | 0% | 60% | 50% |  |  | #REF! | 5473857.438 | 1368204.2451 | 6842061.6831 | 0 | 0 | 0 | 6842061.6831
|  | PVC conduit D20 | 81 | 81 | m | 8773.9726 | 14594.0164 | 23367.989 | 710691.7808 | 1182115.3294 | 1892807.1102 | 60% | 0% | 60% | 50% |  |  | #REF! | 426415.0685 | 709269.1976 | 1135684.2661 | 0 | 0 | 0 | 1135684.2661
|  | HDPE pipe D25/32 | 397 | 397 | m | 10550.2392 | 11445 | 21995.2392 | 4188444.9761 | 4543665 | 8732109.9761 | 60% | 0% | 60% | 50% |  |  | #REF! | 2513066.9856 | 2726199 | 5239265.9856 | 0 | 0 | 0 | 5239265.9856
|  | Camera Pole 15m | 3 | 3 | pcs | 10000000 | 450000 | 10450000 | 30000000 | 1350000 | 31350000 | 60% | 0% | 60% | 50% |  |  | #REF! | 18000000 | 810000 | 18810000 | 0 | 0 | 0 | 18810000
|  | Reforce cable for camera pole | 3 | 3 | lot | 550000 | 250000 | 800000 | 1650000 | 750000 | 2400000 | 60% | 0% | 60% | 50% |  |  | #REF! | 990000 | 450000 | 1440000 | 0 | 0 | 0 | 1440000
|  | Concrete plinth | 3 | 3 | lot | 1000000 | 500000 | 1500000 | 3000000 | 1500000 | 4500000 | 60% | 0% | 60% | 50% |  |  | #REF! | 1800000 | 900000 | 2700000 | 0 | 0 | 0 | 2700000
|  | Remove Pole + Camera | 3 | 3 | time | 0 | 1250000 | 1250000 | 0 | 3750000 | 3750000 | 60% | 0% | 60% | 50% |  |  | #REF! | 0 | 2250000 | 2250000 | 0 | 0 | 0 | 2250000
|  | Accessories | 1 | 1 | lot | 5404452.8133 | 1621335.844 | 7025788.6573 | 5404452.8133 | 1621335.844 | 7025788.6573 | 60% | 0% | 60% | 50% |  |  | #REF! | 3242671.688 | 972801.5064 | 4215473.1944 | 0 | 0 | 0 | 4215473.1944
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. |  | Production and Logistic building (Hall 3) | [6 empty] | 803801420.8294 | 119493877.9513 | 923295298.7807 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 132912088.5246 | 14259566.88 | 147171655.4046 | 147171655.4046
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
2.1. |  | Civil Engineering | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
2. 1. 10. |  | Calculations | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 20. |  | Rainwater and waste water sewer | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 30. |  | Earthworks | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 40. |  | Demolition, removal and dismantling works | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 50. |  | Foundation | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 60. |  | Building structure | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 70. |  | General concrete- / reinforced concrete works | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 80. |  | Fire protection | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 90. |  | Fire rated walls | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 100. |  | Cutting base slabs / ceilings / floors | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 110. |  | Cutting holes into existing facades, walls and roofs | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 120. |  | Exterior walls | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 130. |  | Exterior doors and windows | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 140. |  | Fire protection doors | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 150. |  | Internal doors | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 160. |  | Fire protection roller shutter door | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 170. |  | Fire protection bulkhead | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 180. |  | High speed roller shutter | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 190. |  | Fitting and metal work - general | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 200. |  | Railings and hand rails | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 210. |  | Steel stage for installations | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 220. |  | Collision protection | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 230. |  | canopies of exterior doors | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 240. |  | Concerete steps in front of the hall | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 250. |  | Painting and varnishing works | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 260. |  | Guidance systems | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 270. |  | Locking system | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 280. |  | Internal signage | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 290. |  | Adjustment ridge vent | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 300. |  | Roof reinforcment Option 1 | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 310. |  | Insert new ventilation louvers | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
2. 1. 320. |  | Metal louvers to cover mechanical units | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
2. 2. |  | Electrical Engineering | 1 | 1 | PSCH |  |  |  | 120237495.4217 | 36030743.1568 | 156268238.5785 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 2931049.1803 | 455112 | 3386161.1803 | 3386161.1803
2. 2. 10. |  | Adjustment of existing facilities, dismantling and disposal works | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
2. 2. 20. |  | Rennovation existing grounding system and lightning protection | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
2. 2. 30. |  | Rennovation existing grounding and equipotential bonding | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
2. 2. 40. |  | Power supply | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
2. 2. 50. |  | Energy measurement system | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
2. 2. 60. |  | Electrical installation in the production hall | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
2. 2. 70. |  | Electrical installation in the logistics hall | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
2. 2. 80. |  | Power supply of building utilities | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
2. 2. 90. |  | Three-arm Turnstile | 1 | 1 | PSCH |  |  |  | 120237495.4217 | 36030743.1568 | 156268238.5785 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 2931049.1803 | 455112 | 3386161.1803 | 3386161.1803
|  | INTUS ACM40e-NT as access control manager | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | INTUS ACM40e-NT (S3840-380) Intelligent access control manager (Supplier by Client) | 4 | 4 | set | 0 | 616000 | 616000 | 0 | 2464000 | 2464000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | INTUS ACM40e 2-4 reader-ext (V3841-202) Firmware extension from 2 to 4 access readers (Supplier by Client) | 4 | 4 | set | 0 | 616000 | 616000 | 0 | 2464000 | 2464000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Network configuration setup fee (3000-243) Set up of one IPv4 terminal basis configuration by PCS. Precondition: Excel- or CSV-file with following details: IPaddress and net mask terminal, IP-address gateway, TCPport. Host name. This information must be submitted with the order. (by Client) | 4 | 4 | set | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | INTUS 6xx/7xx as RFID reader for access control | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | NTUS 615/La ( S3850-670) INTUS 615 Legic advant r/w access reader for flush mounting. Reads/writes Legic prime and Legic advant cards/tags. PCS universal coding: VNA00- 000 (Supplier by Client) | 8 | 8 | set | 0 | 616000 | 616000 | 0 | 4928000 | 4928000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | INTUS 600/500/400 reader configuration fee (V3000-231) INTUS reader configuration price for customer specific car coding deviating from PCS standard coding. Also required for standalone parametrization. (by Client) | 8 | 8 | set | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | NTUS 600 spacer frame (S3850-607) INTUS 315ro/615/620 spacer frame, mandatory for mounting on metal wall or for surface mounting cable introduction (Supplier by Client) | 8 | 8 | set | 0 | 616000 | 616000 | 0 | 4928000 | 4928000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | NTUS 700-Panel/La (S3853-610) SM4200-M Legic advant r/w access reader for mounting in metal panels. Reads/writes Legic prime and Legic advant cards/tags. PCS universal coding: VNA00-000 (Supplier by Client) | 8 | 8 | set | 0 | 616000 | 616000 | 0 | 4928000 | 4928000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | INTUS 700 reader configuration fee (V3000-249) INTUS 700 reader configuration price for card coding, deviating from PCS standard coding. (by Client) | 8 | 8 | set | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5A, 12VDC Power supply adapter | 1 | 1 | set | 2220000 | 95200 | 2315200 | 2220000 | 95200 | 2315200 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Push button for releasing entrance & exit lock at reception area | 1 | 4 | pcs | 528000 | 61600 | 589600 | 2112000 | 246400 | 2358400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Emergency at the reception area | 1 | 4 | pcs | 528000 | 61600 | 589600 | 2112000 | 246400 | 2358400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cabinet box for controller located at reception | 1 | 1 | set | 3000000 | 280000 | 3280000 | 3000000 | 280000 | 3280000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Backup battery, 12VDC 7Ah | 4 | 4 | set | 540000 | 72800 | 612800 | 2160000 | 291200 | 2451200 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Tripod turnstile | 4 | 4 | set | 21600000 | 369600 | 21969600 | 86400000 | 1478400 | 87878400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Double Socket 16A/230V | 4 | 4 | pcs | 150480 | 54500 | 204980 | 601920 | 218000 | 819920 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Signal cable, AWG18 - 1Pair | 153 | 153 | m | 15000 | 3360 | 18360 | 2295000 | 514080 | 2809080 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cat6A | 327 | 301 | m | 21639.3443 | 3360 | 24999.3443 | 6513442.623 | 1011360 | 7524802.623 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 2931049.1803 | 455112 | 3386161.1803 | 3386161.1803
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 50 | 150 | m | 32518.74 | 7485.665 | 40004.405 | 4877811 | 1122849.75 | 6000660.75 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 369 | 360 | m | 8773.9726 | 14594.0164 | 23367.989 | 3158630.137 | 5253845.9082 | 8412476.0452 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cutting concrete background and backfill | 5 | 5 | m | 0 | 125000 | 125000 | 0 | 625000 | 625000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Labour cost for support DRX test funtion of Turnstile system | 1 | 1 | lot | 0 | 3500000 | 3500000 | 0 | 3500000 | 3500000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 4786691.6618 | 1436007.4985 | 6222699.1603 | 4786691.6618 | 1436007.4985 | 6222699.1603 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 2. 100. |  | Emergency lighting | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 2. 120. |  | Network infrastructure | 1 | 1 | PSCH |  |  | 0 | 307745509.2338 | 64282788.3235 | 372028297.5573 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 118840892.459 | 12250026 | 131090918.459 | 131090918.459
|  | Single Mode OS2 48 fibers SC- Duplex | 207 | 230 | m | 144000 | 28000 | 172000 | 33120000 | 6440000 | 39560000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 14904000 | 2898000 | 17802000 | 17802000
|  | 20 x 0,8 pair copper phone wire | 0 | 0 | m | 117360 | 13798.4 | 131158.4 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | IDF7 42U (0.8x1.0x2.0), Included PDU, 10 patch panel, Cable routing channel 1U | 1 | 1 | pcs | 68750000 | 1308000 | 70058000 | 68750000 | 1308000 | 70058000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 30937500 | 588600 | 31526100 | 31526100
|  | Patch panel 24 Port CAT6A | 8 |  | pcs | 5060000 | 654000 | 5714000 | 0 | 0 | 0 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Patch panel 24 Port cat 5e | 2 | 2 | pcs | 2195600 | 654000 | 2849600 | 4391200 | 1308000 | 5699200 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 1976040 | 588600 | 2564640 | 2564640
|  | Cat 6A Patch Cord, 3m | 77 | 77 | pcs | 600000 | 13440 | 613440 | 46200000 | 1034880 | 47234880 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 20790000 | 465696 | 21255696 | 21255696
|  | Cat 6A Patch Cord, 3m | 0 | 0 | pcs | 600000 | 13440 | 613440 | 0 | 0 | 0 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ODF F.O Singlemode, 48F | 2 | 2 | pcs | 6490000 | 490500 | 6980500 | 12980000 | 981000 | 13961000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 5841000 | 441450 | 6282450 | 6282450
|  | Socket strip (PDU) with 7 sockets | 2 | 2 | pcs | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 16A Turnlock socket | 2 | 2 | pcs | 150480 | 54500 | 204980 | 300960 | 109000 | 409960 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Patch panel 24 Port | 0 | 0 | pcs | 5060000 | 654000 | 5714000 | 0 | 0 | 0 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Double data outlet RJ45 | 26 | 26 | pcs | 480000 | 81750 | 561750 | 12480000 | 2125500 | 14605500 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 5616000 | 956475 | 6572475 | 6572475
|  | Wifi module (Wifi supply by Client) | 25 | 25 | pcs | 0 | 136250 | 136250 | 0 | 3406250 | 3406250 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FO Patch Cord, SC-SC Duplex, LSOH, SM,3m | 20 | 20 | pcs | 550000 | 10900 | 560900 | 11000000 | 218000 | 11218000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 4950000 | 98100 | 5048100 | 5048100
|  | FO Pigtail LC, SM, 1m for welding to optical fibre | 20 | 96 | pcs | 132000 | 65400 | 197400 | 12672000 | 6278400 | 18950400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cat 6A Patch Cord, 3m from Data outlet to Wifi | 25 | 25 | pcs | 198000 | 10900 | 208900 | 4950000 | 272500 | 5222500 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 2227500 | 122625 | 2350125 | 2350125
|  | Cable Cat6A | 3219 | 3245 | m | 21639.3443 | 3360 | 24999.3443 | 70219672.1311 | 10903200 | 81122872.1311 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 31598852.459 | 4906440 | 36505292.459 | 36505292.459
|  | PVC conduit D20 | 1610 | 1510 | m | 8773.9726 | 14594.0164 | 23367.989 | 13248698.6301 | 22036964.7818 | 35285663.4119 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Network cable test cost - Cat6A cable | 52 | 52 | nos | 0 | 50600 | 50600 | 0 | 2631200 | 2631200 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 0 | 1184040 | 1184040 | 1184040
|  | Accessories | 1 | 1 | lot | 17432978.4725 | 5229893.5417 | 22662872.0142 | 17432978.4725 | 5229893.5417 | 22662872.0142 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 2. 130. |  | Access control preparation | 1 | 1 | PSCH |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 2. 140. |  | CCTV System | 1 | 1 | PSCH |  |  | 0 | 375818416.1739 | 19180346.471 | 394998762.6449 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 11140146.8852 | 1554428.88 | 12694575.7652 | 12694575.7652
|  | Outside Camera CE-1-->12 | 12 | 12 | pcs | 19242720 | 198000 | 19440720 | 230912640 | 2376000 | 233288640 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Symphony Standard Edition - VMS Device License | 12 | 12 | pcs | 2704800 | 330000 | 3034800 | 32457600 | 3960000 | 36417600 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Telescopic parapet mount (T91D62) | 12 | 12 | pcs | 1803200 | 49500 | 1852700 | 21638400 | 594000 | 22232400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Overvoltage protection | 12 | 12 | pcs | 4494000 | 49050 | 4543050 | 53928000 | 588600 | 54516600 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Double data outlet RJ45 | 12 | 12 | pcs | 480000 | 81750 | 561750 | 5760000 | 981000 | 6741000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 2592000 | 441450 | 3033450 | 3033450
|  | Cat 6A Patch Cord, 3m | 36 | 24 | pcs | 198000 | 10900 | 208900 | 4752000 | 261600 | 5013600 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 2138400 | 117720 | 2256120 | 2256120
|  | Cable Cat6A | 686 | 658.24 | m | 21639.3443 | 3360 | 24999.3443 | 14243881.9672 | 2211686.4 | 16455568.3672 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 6409746.8852 | 995258.88 | 7405005.7652 | 7405005.7652
|  | PVC conduit D20 | 274 | 280.5 | m | 8773.9726 | 14594.0164 | 23367.989 | 2461099.3151 | 4093621.6035 | 6554720.9186 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Network cable test cost - Cat6A cable | 12 | 24 | nos | 0 | 50600 | 50600 | 0 | 1214400 | 1214400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 9664794.8916 | 2899438.4675 | 12564233.3591 | 9664794.8916 | 2899438.4675 | 12564233.3591 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 3. |  | Mechanical Engineering | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 3. 10. |  | Ventilation System Production | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 3. 20. |  | Fire Protection Engineering | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 3. 30. |  | Installation of In-Rack Sprinkler at Logistic | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 3. 40. |  | Compressed Air Network Production 1 | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 3. 50. |  | Compressed Air Network Production 2 | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. |  | Office, Social and Technical Areas (Hall 3) | [6 empty] | 1095015293.254 | 204033421.602 | 1299048714.856 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 376329124.918 | 42616218.6 | 418945343.518 | 418945343.518
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
3. 1. |  | Civil Engineering | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 10. |  | Rainwater and waste water sewer | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 20. |  | Foundations | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 30. |  | Steel columns | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 40. |  | Building structure | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 50. |  | Concrete works | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 60. |  | Reinforced concrete slabs 1st floor | 0 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 70. |  | Reinforced concrete stairs | 0 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 80. |  | Screed coat | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 90. |  | Metal works | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 100. |  | Exterior walls | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 110. |  | Masonry works | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 120. |  | plastering works | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 130. |  | Drywall works | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 140. |  | Ceiling for new built-ins | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 150. |  | Fire protection | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 160. |  | Fire rated walls | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 170. |  | Cutting holes into existing facades, walls and roofs | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 180. |  | Cuts in Floor/slab/wall | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 190. |  | Exterior doors and windows | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 200. |  | Canopies for exterior doors | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 210. |  | Covering existing windows with mirroring film | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 220. |  | Internal doors | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 230. |  | Fire protection doors | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 240. |  | Suspended ceiling | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 250. |  | Floor covering works | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 260. |  | Tiles | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 270. |  | Needle Felt | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 280. |  | Raised floor | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 290. |  | Drainage of new wet rooms | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 300. |  | Railing and handrail | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 310. |  | Collision protection | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 320. |  | Vertical blinds | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 330. |  | Kitchenette | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 340. |  | Painting and varnishing works | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 350. |  | internal signage | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 360. |  | Locking system | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. 1. 370. |  | Tightness Test Gas Extinguished Rooms | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
3. 2. |  | Electrical engineering | 1 | 1 | PSCH |  |  |  | 1095015293.254 | 204033421.602 | 1299048714.856 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 376329124.918 | 42616218.6 | 418945343.518 | 418945343.518
3. 2. 10. |  | Rennovation existing grounding system and lightning protection | 1 | 1 | psch | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 2. 20. |  | Rennovation existing grounding and equipotential bonding | 1 | 1 | psch | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 2. 30. |  | Main Power supply | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 2. 40. |  | Uninterrupted power supply (UPS) | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 2. 50. |  | Electrical Capacitor bank | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 2. 60. |  | Power supply of building utilities | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 2. 70. |  | Energy measurement system | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 2. 80. |  | Electrical installation in offices and meeting rooms | 1 |  | PSCH |  |  |  | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 2. 90. |  | Electrical installation in social rooms | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 2. 100. |  | Electrical installation in corridors and stairways | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 2. 110. |  | Electrical installation in technical areas | 1 |  | PSCH |  |  |  | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
3. 2. 120. |  | Electrical installation in kitchenette areas | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
3. 2. 130. |  | Electrical installation for Workshop/Formbrettbau | 1 |  | PSCH |  |  |  | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
3. 2. 140. |  | Electrical installation at the reception | 1 |  | PSCH |  |  |  | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
3. 2. 150. |  | Electrical installation in other rooms/secondary rooms | 1 |  | PSCH |  |  |  | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
3. 2. 160. |  | Emergency lighting | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
3. 2. 170. |  | Fire alarm system | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
3. 2. 180. |  | Network infrastructure | 1 | 1 | PSCH |  |  |  | 947613765.2926 | 174994605.0134 | 1122608370.3061 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 372418241.3115 | 41967003.6 | 414385244.9115 | 414385244.9115
|  | IDF4 42U (0.8x1.0x2.0), Included PDU, 10 patch panel, Cable routing channel 1U | 1 | 1 | pcs | 68750000 | 1308000 | 70058000 | 68750000 | 1308000 | 70058000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 30937500 | 588600 | 31526100 | 31526100
|  | IDF5 42U (0.8x1.0x2.0), Included PDU, 10 patch panel, Cable routing channel 1U | 1 | 1 | pcs | 68750000 | 1308000 | 70058000 | 68750000 | 1308000 | 70058000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 30937500 | 588600 | 31526100 | 31526100
|  | IDF6 42U (0.8x1.0x2.0), Included PDU, 10 patch panel, Cable routing channel 1U | 1 | 1 | pcs | 68750000 | 1308000 | 70058000 | 68750000 | 1308000 | 70058000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 30937500 | 588600 | 31526100 | 31526100
|  | Patch panel 24 Port CAT6A | 24 |  | pcs | 5060000 | 654000 | 5714000 | 0 | 0 | 0 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Patch panel 24 Port cat 5e | 6 | 6 | pcs | 2195600 | 654000 | 2849600 | 13173600 | 3924000 | 17097600 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 5928120 | 1765800 | 7693920 | 7693920
|  | Cat 6A Patch Cord, 3m | 423 | 452 | pcs | 198000 | 10900 | 208900 | 89496000 | 4926800 | 94422800 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 40273200 | 2217060 | 42490260 | 42490260
|  | Cat 6A Patch Cord, 3m | 0 | 0 | pcs | 198000 | 10900 | 208900 | 0 | 0 | 0 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ODF F.O Singlemode, 48F | 6 | 6 | pcs | 6490000 | 490500 | 6980500 | 38940000 | 2943000 | 41883000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 17523000 | 1324350 | 18847350 | 18847350
|  | Socket strip (PDU) with 7 sockets | 6 | 6 | pcs |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 16A Turnlock socket | 6 | 6 | pcs | 150480 | 54500 | 204980 | 902880 | 327000 | 1229880 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Double data outlet RJ45 | 197 | 226 | pcs | 480000 | 81750 | 561750 | 108480000 | 18475500 | 126955500 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 48816000 | 8313975 | 57129975 | 57129975
|  | Wifi module (Wifi supply by Client) | 29 | 29 | pcs | 0 | 136250 | 136250 | 0 | 3951250 | 3951250 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FO Patch Cord, SC-SC Duplex, LSOH, SM,3m | 60 | 60 | pcs | 550000 | 10900 | 560900 | 33000000 | 654000 | 33654000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 14850000 | 294300 | 15144300 | 15144300
|  | FO Pigtail LC, SM, 1m for welding to optical fibre | 60 | 144 | pcs | 132000 | 65400 | 197400 | 19008000 | 9417600 | 28425600 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 8553600 | 4237920 | 12791520 | 12791520
|  | Cat 6A Patch Cord, 3m from Data outlet to Wifi | 29 | 29 | pcs | 198000 | 10900 | 208900 | 5742000 | 316100 | 6058100 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 2583900 | 142245 | 2726145 | 2726145
|  | Cable Cat6A | 14691 | 14487.8 | m | 21639.3443 | 3360 | 24999.3443 | 313506491.8033 | 48679008 | 362185499.8033 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 141077921.3115 | 21905553.6 | 162983474.9115 | 162983474.9115
|  | PVC conduit D20 | 138 | 2800 | m | 8773.9726 | 14594.0164 | 23367.989 | 24567123.2877 | 40863245.9529 | 65430369.2406 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Network cable test cost - FO cable | 24 | 96 | nos | 0 | 50600 | 50600 | 0 | 4857600 | 4857600 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Network cable test cost - Cat6A cable | 197 | 452 | nos | 0 | 50600 | 50600 | 0 | 22871200 | 22871200 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 29547670.2017 | 8864301.0605 | 38411971.2622 | 29547670.2017 | 8864301.0605 | 38411971.2622 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Updated for data socket outlet on Dadoduct | 1 | 1 | lot | 65000000 |  | 65000000 | 65000000 | 0 | 65000000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 2. 190. |  | CCTV System for custom fence | 1 | 1 | PSCH |  |  |  | 93265409.772 | 9368475.5017 | 102633885.2737 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 639900 | 125077.5 | 764977.5 | 764977.5
|  | Camera fence CF-5,6 | 2 | 2 | pcs | 1264480 | 137500 | 1401980 | 2528960 | 275000 | 2803960 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Camera Inside CI-1, Dome | 1 | 1 | pcs | 20015520 | 198000 | 20213520 | 20015520 | 198000 | 20213520 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Symphony Standard Edition - VMS Device License | 1 | 1 | pcs | 2704800 | 330000 | 3034800 | 2704800 | 330000 | 3034800 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LCD 43" for CE, CI | 2 | 2 | pcs | 11990000 | 163500 | 12153500 | 23980000 | 327000 | 24307000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LCD 32" for CF | 2 | 2 | pcs | 11990000 | 163500 | 12153500 | 23980000 | 327000 | 24307000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | HDMI cable c/w socket, 15m | 2 | 3 | pcs | 979000 | 59950 | 1038950 | 2937000 | 179850 | 3116850 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single data outlet RJ45 | 3 | 3 | pcs | 276000 | 81750 | 357750 | 828000 | 245250 | 1073250 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 372600 | 110362.5 | 482962.5 | 482962.5
|  | Double Socket 16A/230V | 2 | 2 | pcs | 150480 | 54500 | 204980 | 300960 | 109000 | 409960 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cat 6A Patch Cord, 3m from Data outlet to camera | 3 | 3 | pcs | 198000 | 10900 | 208900 | 594000 | 32700 | 626700 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 267300 | 14715 | 282015 | 282015
|  | Cable Cat6 | 400 | 403 | m | 10032.7869 | 3360 | 13392.7869 | 4043213.1148 | 1354080 | 5397293.1148 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 124 | 124 | m | 32518.74 | 7485.665 | 40004.405 | 4032323.76 | 928222.46 | 4960546.22 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 210 | 210 | m | 8773.9726 | 14594.0164 | 23367.989 | 1842534.2466 | 3064743.4465 | 4907277.693 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Network cable test cost - Cat6A cable | 3 | 7 | nos | 0 | 50600 | 50600 | 0 | 354200 | 354200 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 5478098.6507 | 1643429.5952 | 7121528.2459 | 5478098.6507 | 1643429.5952 | 7121528.2459 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 2. 200. |  | Access control preparation | 1 | 1 | PSCH |  |  |  | 54136118.1893 | 19670341.0869 | 73806459.2762 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 3270983.6066 | 524137.5 | 3795121.1066 | 3795121.1066
|  | Exit Button | 5 | 5 | pcs | 528000 | 61600 | 589600 | 2640000 | 308000 | 2948000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Emergency Button | 5 | 5 | pcs | 528000 | 61600 | 589600 | 2640000 | 308000 | 2948000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Door sensor | 55 | 5 | pcs | 2116800 | 95200 | 2212000 | 10584000 | 476000 | 11060000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Access control card reader | 8 | 5 | set | 0 | 95200 | 95200 | 0 | 476000 | 476000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single Socket 16A/230V | 5 | 5 | pcs | 150480 | 54500 | 204980 | 752400 | 272500 | 1024900 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Data outlet RJ45 | 5 | 5 | pcs | 480000 | 81750 | 561750 | 2400000 | 408750 | 2808750 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 1080000 | 183937.5 | 1263937.5 | 1263937.5
|  | AC/DC converter | 5 | 5 | pcs | 2220000 | 95200 | 2315200 | 11100000 | 476000 | 11576000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conection box, SS304 | 5 | 5 | pcs | 180000 | 50400 | 230400 | 900000 | 252000 | 1152000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable cat6A | 357 | 225 | m | 21639.3443 | 3360 | 24999.3443 | 4868852.459 | 756000 | 5624852.459 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 2190983.6066 | 340200 | 2531183.6066 | 2531183.6066
|  | Cable telephone cat5e | 357 | 225 | m | 7475.4098 | 3360 | 10835.4098 | 1681967.2131 | 756000 | 2437967.2131 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 286 | 286 | m | 32518.74 | 7485.665 | 40004.405 | 9300359.64 | 2140900.19 | 11441259.83 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 643 | 586 | m | 8773.9726 | 14594.0164 | 23367.989 | 5141547.9452 | 8552093.6173 | 13693641.5625 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Labour cost for support DRX test funtion of Access control system | 1 | 1 | lot | 0 | 3850000 | 3850000 | 0 | 3850000 | 3850000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 2126990.932 | 638097.2796 | 2765088.2116 | 2126990.932 | 638097.2796 | 2765088.2116 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 3. |  | Mechanical Engineering | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 3. 10. |  | Waste Water System | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 3. 20. |  | Service Water System | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 3. 40. |  | Ventilation System | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 3. 50. |  | Ventilation System 1st Floor Offices Ventilation Units | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 3. 60. |  | Ventilation System 1st Floor Offices Ducting | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 3. 70. |  | Air Conditioning | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 3. 80. |  | Fire Protection Engineering Sprinkler | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 3. 90. |  | Fire Protection Engineering Temperature Controlled Storage | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 3. 100. |  | Fire Protection Engineering Extinguishing Systems | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 3. 110. |  | Door Fan Test for Gas Extinguishing System | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 3. 120. |  | Compressed Air Connections | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. |  | Machine hook-up (Hall 3) | [8 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. 1. |  | Electrical engineering | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. 1. 10. |  | Power cables and lines | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. 2. |  | Mechanical Engineering | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. 2. 10. |  | Machine hook-up | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Supply & Installation pipe & fittings: Drop Piping (D25), Considering all drop piping & fittings | 1 |  | lot | 0 | 0 |  |  |  |  | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger support & accessories | 1 |  | lot | 0 | 0 |  |  |  |  | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. |  | Scooter Garage | [8 empty] | 162238150.0078 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 3806415 | 3806415
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
5. 1. |  | Civil Engineering | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
5. 1. 10. |  | Adjustments on the existing scooter garage | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
5. 1. 20. |  | Expansion of Scooter Garage | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
5. 2. |  | Electrical Engineering | 1 | 1 | PSCH |  |  |  | 144640388.5392 | 17597761.4686 | 162238150.0078 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 3399300 | 407115 | 3806415 | 3806415
5. 2. 10. |  | Grounding and Lightining protection | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. 2. 20. |  | Power supply | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. 2. 30. |  | Power supply of building utilities | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. 2. 40. |  | Electrical installations | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. 2. 50. |  | Emergency lighting | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. 2. 60. |  | Fire alarms system | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. 2. 70. |  | CCTV System | 1 | 1 | PSCH |  |  |  | 144640388.5392 | 17597761.4686 | 162238150.0078 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 3399300 | 407115 | 3806415 | 3806415
|  | POWER surveillance cabinet | 2 | 2 | pcs | 1650000 | 136250 | 1786250 | 3300000 | 272500 | 3572500 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DATA surveillance cabinet | 2 | 2 | pcs | 1650000 | 136250 | 1786250 | 3300000 | 272500 | 3572500 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Terminal 4mm2 | 2 | 2 | pcs | 27500 | 10900 | 38400 | 55000 | 21800 | 76800 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MCB 1P-16A-230V | 2 | 2 | pcs | 90000 | 49050 | 139050 | 180000 | 98100 | 278100 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Power adapter (Mean Well SDR-240-48) | 2 | 2 | pcs | 2833600 | 114450 | 2948050 | 5667200 | 228900 | 5896100 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PoE Switch Planet IGS-10020HPT | 2 | 2 | pcs | 15180000 | 272500 | 15452500 | 30360000 | 545000 | 30905000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Outside Camera CF-7-->14 | 8 | 8 | pcs | 1264480 | 137500 | 1401980 | 10115840 | 1100000 | 11215840 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Telescopic parapet mount (T91D62) | 8 | 8 | pcs | 1803200 | 49500 | 1852700 | 14425600 | 396000 | 14821600 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Overvoltage protection | 8 | 8 | pcs | 4494000 | 49050 | 4543050 | 35952000 | 392400 | 36344400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single data outlet RJ45 | 8 | 8 | pcs | 276000 | 81750 | 357750 | 2208000 | 654000 | 2862000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 993600 | 294300 | 1287900 | 1287900
|  | Cat 6A Patch Cord, 3m from Data outlet to camera | 8 | 8 | pcs | 198000 | 10900 | 208900 | 1584000 | 87200 | 1671200 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 712800 | 39240 | 752040 | 752040
|  | Cable Cat6 | 343 | 264 | m | 10032.7869 | 3360 | 13392.7869 | 2648655.7377 | 887040 | 3535695.7377 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gigabit Ethernet LX Mini-GBIC SFP Transceiver | 2 | 2 | pcs | 4032000 | 272500 | 4304500 | 8064000 | 545000 | 8609000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | converter quang đồng (Connect from optic cable to Patch panel) | 2 | 2 | pcs | 935000 | 49050 | 984050 | 1870000 | 98100 | 1968100 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 841500 | 44145 | 885645 | 885645
|  | Cat 6A Patch Cord, 3m from Converter to patch panel | 4 | 4 | pcs | 198000 | 10900 | 208900 | 792000 | 43600 | 835600 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 356400 | 19620 | 376020 | 376020
|  | FO Patch Cord, SC-SC Duplex, LSOH, SM,3m | 2 | 2 | pcs | 550000 | 10900 | 560900 | 1100000 | 21800 | 1121800 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 495000 | 9810 | 504810 | 504810
|  | Fiber optical 8FO (SM-OS2 G9/125) | 190 | 190 | m | 54000 | 3360 | 57360 | 10260000 | 638400 | 10898400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 100 | 100 | m | 32518.74 | 7485.665 | 40004.405 | 3251874 | 748566.5 | 4000440.5 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 144 | 200 | m | 8773.9726 | 14594.0164 | 23367.989 | 1754794.5205 | 2918803.2824 | 4673597.8029 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | HDPE pipe D40/50 | 100 | 100 | m | 17049.1866 | 15805 | 32854.1866 | 1704918.6603 | 1580500 | 3285418.6603 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | The cost of cutting and refinishing the concrete path for the undergruond pipe | 8 | 8 | m | 0 | 175000 | 175000 | 0 | 1400000 | 1400000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Network cable test cost - FO cable | 2 | 48 | nos | 0 | 50600 | 50600 | 0 | 2428800 | 2428800 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Network cable test cost - Cat6A cable | 8 | 8 | nos | 0 | 50600 | 50600 | 0 | 404800 | 404800 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 6046505.6207 | 1813951.6862 | 7860457.3069 | 6046505.6207 | 1813951.6862 | 7860457.3069 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. 3. |  | Mechancial Engineering | [8 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. 3. 10. |  | Rainwater System | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. 3. 20. |  | Fire Protection System | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. |  | Canteen | [8 empty] | 274132627.4702 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 56260639.918 | 56260639.918
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
6. 1. |  | Civil Engineering | [8 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 10. |  | Demolition of existing canteen | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 20. |  | Building Structure | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 30. |  | Earthworks | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 40. |  | Rain water and waste water sewer | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 50. |  | Primary construction of reinforced concrete | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 60. |  | Foundations | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 70. |  | Concrete floor | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 80. |  | Concrete plinth | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 90. |  | Reinforced concrete columns | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 100. |  | Reinforced concrete beams | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 110. |  | Reinforced concrete 1st roof slab or structure | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 120. |  | Reinforced concrete stairs | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 130. |  | Concrete steps | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 140. |  | Screed coat | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 150. |  | Roof structure | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 160. |  | Metal facade | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 170. |  | Masonry works | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 180. |  | Exterior doors | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 190. |  | Fire protection | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 200. |  | Fire protection doors | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 210. |  | Interior doors | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 220. |  | Floor covering works | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 230. |  | Tiles | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 240. |  | Painting and finishing works | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 250. |  | Metal and railing works | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 260. |  | Elevator for goods | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 270. |  | Canpoy for the main entrance | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 280. |  | Exterior steel staircase | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 290. |  | Exterior sinks | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. 1. 300. |  | Locking system | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
6. 2. |  | Electrical Engineering | [6 empty] | 246947482.5691 | 27185144.9011 | 274132627.4702 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 52557904.918 | 3702735 | 56260639.918 | 56260639.918
|  | Notes Calculation Basis | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. 2. 10. |  | Grounding and Lightining protection | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. 2. 20. |  | Power supply | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. 2. 30. |  | Power supply of building utilities | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. 2. 40. |  | Electrical installations | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. 2. 50. |  | Emergency lighting | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. 2. 60. |  | Fire alarms system | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. 2. 70. |  | CCTV System For Custom fence | 1 | 1 | PSCH |  |  |  | 117565498.5134 | 6055261.4345 | 123620759.9479 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 1756150.8197 | 469170 | 2225320.8197 | 2225320.8197
|  | LCD 43" for CE, CI | 8 | 8 | pcs | 11990000 | 163500 | 12153500 | 95920000 | 1308000 | 97228000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | HDMI cable c/w socket, 15m | 8 | 8 | pcs | 979000 | 59950 | 1038950 | 7832000 | 479600 | 8311600 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Outside Camera CF-16-->18 | 4 | 4 | pcs | 1264480 | 137500 | 1401980 | 5057920 | 550000 | 5607920 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single data outlet RJ45 | 4 | 4 | pcs | 276000 | 81750 | 357750 | 1104000 | 327000 | 1431000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 496800 | 147150 | 643950 | 643950
|  | Cat 6A Patch Cord, 3m from Data outlet to camera | 4 | 4 | pcs | 198000 | 10900 | 208900 | 792000 | 43600 | 835600 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 356400 | 19620 | 376020 | 376020
|  | Cable Cat6 | 229 | 200 | m | 10032.7869 | 3360 | 13392.7869 | 2006557.377 | 672000 | 2678557.377 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 902950.8197 | 302400 | 1205350.8197 | 1205350.8197
|  | PVC conduit D20 | 91 | 85 | m | 8773.9726 | 14594.0164 | 23367.989 | 745787.6712 | 1240491.395 | 1986279.0662 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Network cable test cost - Cat6A cable | 4 | 4 | nos | 0 | 50600 | 50600 | 0 | 202400 | 202400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 4107233.4651 | 1232170.0395 | 5339403.5046 | 4107233.4651 | 1232170.0395 | 5339403.5046 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. 2. 80. |  | Network infrastructure | 1 | 1 | PSCH |  |  |  | 129381984.0557 | 21129883.4666 | 150511867.5223 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 50801754.0984 | 3233565 | 54035319.0984 | 54035319.0984
|  | IDF8 12U (0.8x1.0x2.0), Included PDU, 10 patch panel, Cable routing channel 1U | 1 | 1 | pcs | 68750000 | 1308000 | 70058000 | 68750000 | 1308000 | 70058000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 30937500 | 588600 | 31526100 | 31526100
|  | Patch panel 24 Port CAT6A | 2 |  | pcs | 5060000 | 654000 | 5714000 | 0 | 0 | 0 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cat 6A Patch Cord, 3m | 28 | 16 | pcs | 198000 | 10900 | 208900 | 3168000 | 174400 | 3342400 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 1425600 | 78480 | 1504080 | 1504080
|  | Cat 6A Patch Cord, 3m | 0 | 0 | pcs | 198000 | 10900 | 208900 | 0 | 0 | 0 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ODF F.O Singlemode, 48F | 1 | 1 | pcs | 6490000 | 490500 | 6980500 | 6490000 | 490500 | 6980500 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 2920500 | 220725 | 3141225 | 3141225
|  | Socket strip (PDU) with 7 sockets | 2 | 2 | pcs |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 16A Turnlock socket | 2 | 2 | pcs | 150480 | 54500 | 204980 | 300960 | 109000 | 409960 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Double data outlet RJ45 | 12 | 12 | pcs | 480000 | 81750 | 561750 | 5760000 | 981000 | 6741000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 2592000 | 441450 | 3033450 | 3033450
|  | Wifi module (Wifi supply by Client) | 4 | 4 | pcs | 0 | 136250 | 136250 | 0 | 545000 | 545000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FO Patch Cord, SC-SC Duplex, LSOH, SM,3m | 2 | 2 | pcs | 550000 | 10900 | 560900 | 1100000 | 21800 | 1121800 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 495000 | 9810 | 504810 | 504810
|  | FO Pigtail LC, SM, 1m for welding to optical fibre | 2 | 48 | pcs | 132000 | 65400 | 197400 | 6336000 | 3139200 | 9475200 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cat 6A Patch Cord, 3m from Data outlet to wifi | 4 | 4 | pcs | 198000 | 10900 | 208900 | 792000 | 43600 | 835600 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 356400 | 19620 | 376020 | 376020
|  | Cable Cat6A | 1257 | 1240 | m | 21639.3443 | 3360 | 24999.3443 | 26832786.8852 | 4166400 | 30999186.8852 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 12074754.0984 | 1874880 | 13949634.0984 | 13949634.0984
|  | PVC conduit D20 | 503 | 500 | m | 8773.9726 | 14594.0164 | 23367.989 | 4386986.3014 | 7297008.2059 | 11683994.5073 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Network cable test cost - Cat6A cable | 12 | 24 | nos | 0 | 50600 | 50600 | 0 | 1214400 | 1214400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 5465250.8691 | 1639575.2607 | 7104826.1298 | 5465250.8691 | 1639575.2607 | 7104826.1298 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. 3. |  | Mechancial Engineering | [8 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. 3. 10. |  | Rainwater System | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. 3. 20. |  | Waste Water System | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. 3. 30. |  | Service Water System | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. 3. 40. |  | Sanitary Furnishings | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. 3. 50. |  | Air Conditioning | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. 3. 60. |  | Ventilation System Overhead Fans | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. 3. 70. |  | Ventilation System | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. 3. 80. |  | Fire Protection System | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. |  | Exterior Area | [6 empty] | 509452988.9423 | 100342530.3589 | 609795519.3012 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 190954297.1803 | 30692835 | 221647132.1803 | 221647132.1803
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. 1. |  | Civil Engineering | [8 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. 1. 10. |  | Flag pole | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. 1. 20. |  | Fence | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. 1. 30. |  | Bollards and delineator panels | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. 1. 40. |  | New Septic Tanks | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. 1. 50. |  | Excavation | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. 1. 60. |  | Laying conduits, pipes, etc. | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. 1. 70. |  | Asphalt areas | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. 2. |  | Electrical Engineering | [6 empty] | 509452988.9423 | 100342530.3589 | 609795519.3012 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 190954297.1803 | 30692835 | 221647132.1803 | 221647132.1803
7. 2. 10. |  | Electrical Installations General | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. 2. 20. |  | Exterior Lighting | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. 2. 30. |  | Emergency Lighting | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. 2. 40. |  | Building service connections | 1 | 1 | PSCH |  |  |  | 449449440 | 94825780 | 544275220 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 187996248 | 30143601 | 218139849 | 218139849
|  | Single Mode OS2 48 fibers SC- Duplex | 1325 | 2141.26 | m | 144000 | 28000 | 172000 | 308341440 | 59955280 | 368296720 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 138753648 | 26979876 | 165733524 | 165733524
|  | 20 x 0,8 pair copper phone wire (20P cat3) | 0 |  | m | 117360 | 13798.4 | 131158.4 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ODF F.O Singlemode, 48F add to MDF at server rooms | 5 | 5 | pcs | 6490000 | 490500 | 6980500 | 32450000 | 2452500 | 34902500 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 14602500 | 1103625 | 15706125 | 15706125
|  | Patch panel 24 Port cat 5e | 5 | 5 | pcs | 2195600 | 654000 | 2849600 | 10978000 | 3270000 | 14248000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 4940100 | 1471500 | 6411600 | 6411600
|  | Cat 6A Patch Cord, 3m | 120 |  | pcs | 198000 | 10900 | 208900 | 0 | 0 | 0 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | FO Patch Cord, SC-SC Duplex, LSOH, SM,3m | 120 | 120 | pcs | 550000 | 10900 | 560900 | 66000000 | 1308000 | 67308000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 29700000 | 588600 | 30288600 | 30288600
|  | FO Pigtail LC, SM, 1m for welding to optical fibre | 120 | 240 | pcs | 132000 | 65400 | 197400 | 31680000 | 15696000 | 47376000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Network cable test cost - FO cable | 120 | 240 | nos | 0 | 50600 | 50600 | 0 | 12144000 | 12144000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Network cable test cost - Cat6A cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. 2. 50. |  | CCTV System | 1 | 1 | PSCH |  |  |  | 60003548.9423 | 5516750.3589 | 65520299.3012 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 2958049.1803 | 549234 | 3507283.1803 | 3507283.1803
|  | For Custom fence | [6 empty] | 60003548.9423 | 5516750.3589 | 65520299.3012 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 2958049.1803 | 549234 | 3507283.1803 | 3507283.1803
|  | NVR 32 Chanel | 1 | 1 | pcs | 19810560 | 385000 | 20195560 | 19810560 | 385000 | 20195560 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Outside Camera CF-1-->4 | 4 | 4 | pcs | 1264480 | 137500 | 1401980 | 5057920 | 550000 | 5607920 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Telescopic parapet mount (T91D62) | 4 | 4 | pcs | 1803200 | 49500 | 1852700 | 7212800 | 198000 | 7410800 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Overvoltage protection | 4 | 4 | pcs | 4494000 | 49050 | 4543050 | 17976000 | 196200 | 18172200 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Double data outlet RJ45 | 4 | 4 | pcs | 480000 | 81750 | 561750 | 1920000 | 327000 | 2247000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 864000 | 147150 | 1011150 | 1011150
|  | Cat 6A Patch Cord, 3m | 12 | 12 | pcs | 198000 | 10900 | 208900 | 2376000 | 130800 | 2506800 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 1069200 | 58860 | 1128060 | 1128060
|  | Cable Cat6 | 240 | 227 | m | 10032.7869 | 3360 | 13392.7869 | 2277442.623 | 762720 | 3040162.623 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 1024849.1803 | 343224 | 1368073.1803 | 1368073.1803
|  | PVC conduit D20 | 96 | 100 | m | 8773.9726 | 14594.0164 | 23367.989 | 877397.2603 | 1459401.6412 | 2336798.9015 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Network cable test cost - Cat6A cable | 4 | 15 | nos | 0 | 50600 | 50600 | 0 | 759000 | 759000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 2495429.0591 | 748628.7177 | 3244057.7768 | 2495429.0591 | 748628.7177 | 3244057.7768 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. 3. |  | Mechanical Engineering | [8 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. 3. 10. |  | Underground Compressed Air Connection | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 |  | 0 | 0
8. |  | Adjustments Hall 2 | [8 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. 1. |  | Roof Renovation | [8 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. 1. 10. |  | Roof Reinforcement Option 1 | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. 2. |  | Adjustment Ridge Vent | [8 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. 2. 10. |  | Adjustment Ridge Vent | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. 3. |  | Adjustment Overhead Fans | [8 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. 3. 10. |  | Adjustment Overhead Fans | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. 4. |  | Additonal In-Rack Sprinkler Logistic | [8 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. 4. 10. |  | Additonal In-Rack Sprinkler Logistic | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. 5. |  | Additional Compressed Air Equipment | [8 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. 5. 10. |  | Additional Compressed Air Equipment | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 |  | 0 | 0
8. 6. |  | Flag pole | [8 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. 6. 10. |  | Flag pole | 0 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
9. |  | As built documentation | [8 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
9. 1. |  | As built documentation all trades | [8 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
9. 1. 10. |  | As built documentation | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
10. |  | Service of Architects and Engineers | [8 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
10. 1. |  | Civil engineering | [8 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
10. 1. 10. |  | Design works | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
10. 1. 20. |  | Geotechnical survey | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
10. 1. 30. |  | Topographical survey | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
10. 1. 40. |  | Fire protection report | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
10. 1. 50. |  | Compactation report of earthworks | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
10. 1. 60. |  | Structure and welding quality report | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
10. 1. 70. |  | Adherence and width of paint quality control reports | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
10. 1. 80. |  | Material quality control reports | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
10. 1. 90. |  | Planning service Building construction | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
10. 1. 100. |  | Planning service Structural design | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
10. 1. 110. |  | Planning service Structural revision | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
10. 1. 120. |  | Surveying services Inventory registration | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
10. 1. 130. |  | Quality control laboratory for material testing (laboratory and field testing) | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
10. 1. 140. |  | Revision fire department and civil protection | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
10. 2. |  | Electrical engineering | [8 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
10. 2. 10. |  | Design & approval works | 1 |  | psch | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
10. 3. |  | Mechanical engineering | [8 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
10. 3. 10. |  | Design & approval works | 1 |  | psch | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | III. AIR COMPRESSOR | [8 empty] | 1143011058.0929 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 6333059.2 | 0 | 0 | 331236002.4232 | 337569061.6232
2. |  | Production and Logistic building (Hall 3) | [6 empty] | 585597305.9781 | 205702981.3661 | 791300287.3442 | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 258726771.7686 | 72509230.6546 | 331236002.4232 | 331236002.4232
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 3. |  | Mechanical Engineering | [6 empty] | 585597305.9781 | 205702981.3661 | 791300287.3442 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 258726771.7686 | 72509230.6546 | 331236002.4232 | 331236002.4232
2. 3. 40. |  | Compressed Air Network Production 1 | 1 |  | PSCH |  |  |  | 425312121.5169 | 147070051.5988 | 572382173.1157 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 186112897.681 | 51465563.2369 | 237578460.9179 | 237578460.9179
|  | BLUE ALUMINIUM PIPE, DN63 | 470 | 485 | m | 362322.6857 | 115320.5625 | 477643.2482 | 175726502.5676 | 55930472.8125 | 231656975.3801 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 87863251.2838 | 27965236.4062 | 115828487.6901 | 115828487.6901
|  | BLUE ALUMINIUM PIPE, DN40 | 0 | 30 | pcs | 190224.1656 | 70966.5 | 261190.6656 | 5706724.968 | 2128995 | 7835719.968 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 2853362.484 | 1064497.5 | 3917859.984 | 3917859.984
|  | BLUE ALUMINIUM PIPE, DN25 | 180 | 174 | m | 94950.6667 | 42579.9 | 137530.5667 | 16521416 | 7408902.6 | 23930318.6 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 8260708 | 3704451.3 | 11965159.3 | 11965159.3
|  | TUBE CLIP, DN63 (POLYMER) | 162 | 172 | pcs | 54295.4118 | 82376.8 | 136672.2118 | 9338810.8362 | 14168809.6 | 23507620.4362 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 4669405.4181 | 7084404.8 | 11753810.2181 | 11753810.2181
|  | TUBE CLIP, DN40 (POLYMER) | 76 | 10 | pcs | 32609.857 | 57608.1 | 90217.957 | 326098.5696 | 576081 | 902179.5696 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 163049.2848 | 288040.5 | 451089.7848 | 451089.7848
|  | PIPE TO PIPE JOINT, DN63 | 79 | 79 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 47234236.4616 | 6507767.2 | 53742003.6616 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 23617118.2308 | 3253883.6 | 26871001.8308 | 26871001.8308
|  | PIPE TO PIPE JOINT, DN63 | 50 | 50 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 29895086.3681 | 4118840 | 34013926.3681 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 14947543.184 | 2059420 | 17006963.184 | 17006963.184
|  | 90° ELBOW, DN63 | 6 | 8 | pcs | 326098.5696 | 82376.8 | 408475.3696 | 2608788.5568 | 659014.4 | 3267802.9568 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 1304394.2784 | 329507.2 | 1633901.4784 | 1633901.4784
|  | EQUAL TEE, DN63 | 3 | 5 | pcs | 543443.2662 | 82376.8 | 625820.0662 | 2717216.3312 | 411884 | 3129100.3312 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 1358608.1656 | 205942 | 1564550.1656 | 1564550.1656
|  | END CAP, DN63 | 1 | 1 | pcs | 380393.9814 | 82376.8 | 462770.7814 | 380393.9814 | 82376.8 | 462770.7814 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 190196.9907 | 41188.4 | 231385.3907 | 231385.3907
|  | REDUCING TEE, DN63-40 | 12 | 14 | pcs | 861389.3716 | 82376.8 | 943766.1716 | 12059451.2024 | 1153275.2 | 13212726.4024 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 6029725.6012 | 576637.6 | 6606363.2012 | 6606363.2012
|  | QUICK DROP, DN63-25 | 32 | 32 | pcs | 372241.5172 | 82376.8 | 454618.3172 | 11911728.5503 | 2636057.6 | 14547786.1503 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 5955864.2752 | 1318028.8 | 7273893.0752 | 7273893.0752
|  | PIPE TO PIPE JOINT, DN40 | 37 | 37 | pcs | 317946.1054 | 57608.1 | 375554.2054 | 11764005.8983 | 2131499.7 | 13895505.5983 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 5882002.9492 | 1065749.85 | 6947752.7992 | 6947752.7992
|  | LOCKABLE BRASS VALVE, DN25-1/2" FEMALE THREAD, WITH FIXING PLATE | 32 | 32 | pcs | 680241.6162 | 53385.955 | 733627.5712 | 21767731.7179 | 1708350.5613 | 23476082.2792 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 10883865.859 | 854175.2806 | 11738041.1396 | 11738041.1396
|  | TWO-WAYS PNEUMATIC CONNECTOR, FEMALE THREAD G1/2" | 0 |  | pcs | 206583.4438 | 53385.955 | 259969.3989 | 0 | 0 | 0 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | T-BOLT, M8, 6CM | 228 | 228 | pcs | 3260.9857 | 3850 | 7110.9857 | 743504.7387 | 877800 | 1621304.7387 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 371752.3693 | 438900 | 810652.3693 | 810652.3693
|  | THREADED ROD, M8, 3 METER | 50 | 50 | pcs | 48914.7854 | 11000 | 59914.7854 | 2445739.272 | 550000 | 2995739.272 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 1222869.636 | 275000 | 1497869.636 | 1497869.636
|  | WALL MOUNTED BRACKET, 50CM | 228 | 228 | pcs | 92448.9445 | 8250 | 100698.9445 | 21078359.3418 | 1881000 | 22959359.3418 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 10539179.6709 | 940500 | 11479679.6709 | 11479679.6709
|  | BEAM CLAMP, 2.5CM | 456 | 456 | pcs | 37990.4834 | 8250 | 46240.4834 | 17323660.4114 | 3762000 | 21085660.4114 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fire Stop | 1 | 1 | lot | 2500000 | 1000000 | 3500000 | 2500000 | 1000000 | 3500000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 33262665.7435 | 9978799.7231 | 43241465.4666 | 33262665.7435 | 9978799.7231 | 43241465.4666 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | T&C | 1 | 1 | lot | 0 | 29398125.4019 | 29398125.4019 | 0 | 29398125.4019 | 29398125.4019 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 3. 50. |  | Compressed Air Network Production 2 | 1 |  | PSCH |  |  |  | 160285184.4612 | 58632929.7673 | 218918114.2285 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 72613874.0876 | 21043667.4177 | 93657541.5053 | 93657541.5053
|  | PRODUCTION 2 | [6 empty] | 83418012.7013 | 26026366.1504 | 109444378.8517 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 41709006.3506 | 13013183.0752 | 54722189.4258 | 54722189.4258
|  | BLUE ALUMINIUM PIPE, DN40 | 109 | 210 | m | 190224.1656 | 70966.5 | 261190.6656 | 39947074.776 | 14902965 | 54850039.776 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 19973537.388 | 7451482.5 | 27425019.888 | 27425019.888
|  | BLUE ALUMINIUM PIPE, DN25 | 56 | 59 | m | 94950.6667 | 42579.9 | 137530.5667 | 5602089.3333 | 2512214.1 | 8114303.4333 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 2801044.6667 | 1256107.05 | 4057151.7167 | 4057151.7167
|  | PIPE TO PIPE JOINT, DN63 | 4 | 4 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 2391606.9094 | 329507.2 | 2721114.1094 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 1195803.4547 | 164753.6 | 1360557.0547 | 1360557.0547
|  | PIPE TO PIPE JOINT, DN40 | 19 | 19 | pcs | 317946.1054 | 57608.1 | 375554.2054 | 6040976.0018 | 1094553.9 | 7135529.9018 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 3020488.0009 | 547276.95 | 3567764.9509 | 3567764.9509
|  | REDUCING TEE, DN63-40 | 2 | 2 | pcs | 861389.3716 | 82376.8 | 943766.1716 | 1722778.7432 | 164753.6 | 1887532.3432 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 861389.3716 | 82376.8 | 943766.1716 | 943766.1716
|  | TUBE CLIP, DN40 (POLYMER) | 40 | 70 | pcs | 32609.857 | 57608.1 | 90217.957 | 2282689.9872 | 4032567 | 6315256.9872 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 1141344.9936 | 2016283.5 | 3157628.4936 | 3157628.4936
|  | 45° ELBOW, DN40 | 6 | 6 | pcs | 741874.2458 | 57608.1 | 799482.3458 | 4451245.475 | 345648.6 | 4796894.075 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 2225622.7375 | 172824.3 | 2398447.0375 | 2398447.0375
|  | QUICK DROP, DN40-25 | 10 | 10 | pcs | 318435.2532 | 57608.1 | 376043.3532 | 3184352.5321 | 576081 | 3760433.5321 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 1592176.2661 | 288040.5 | 1880216.7661 | 1880216.7661
|  | BRASS VALVE, DN40-DN40 | 2 | 2 | pcs | 1451138.6347 | 57608.1 | 1508746.7347 | 2902277.2694 | 115216.2 | 3017493.4694 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 1451138.6347 | 57608.1 | 1508746.7347 | 1508746.7347
|  | LOCKABLE BRASS VALVE, DN25-1/2" FEMALE THREAD, WITH FIXING PLATE | 10 | 10 | pcs | 680241.6162 | 53385.955 | 733627.5712 | 6802416.1619 | 533859.5504 | 7336275.7123 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 3401208.0809 | 266929.7752 | 3668137.8561 | 3668137.8561
|  | TWO-WAYS PNEUMATIC CONNECTOR, FEMALE THREAD G1/2" | 0 |  | pcs | 206583.4438 | 53385.955 | 259969.3989 | 0 | 0 | 0 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | T-BOLT, M8, 6CM | 40 | 40 | pcs | 3260.9857 | 3850 | 7110.9857 | 130439.4278 | 154000 | 284439.4278 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 65219.7139 | 77000 | 142219.7139 | 142219.7139
|  | THREADED ROD, M8, 3 METER | 25 | 25 | pcs | 48914.7854 | 11000 | 59914.7854 | 1222869.636 | 275000 | 1497869.636 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 611434.818 | 137500 | 748934.818 | 748934.818
|  | WALL MOUNTED BRACKET, 50CM | 40 | 40 | pcs | 92448.9445 | 8250 | 100698.9445 | 3697957.7793 | 330000 | 4027957.7793 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 1848978.8896 | 165000 | 2013978.8896 | 2013978.8896
|  | BEAM CLAMP, 2.5CM | 80 | 80 | pcs | 37990.4834 | 8250 | 46240.4834 | 3039238.6687 | 660000 | 3699238.6687 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 1519619.3343 | 330000 | 1849619.3343 | 1849619.3343
|  | LOGICSTIC | [6 empty] | 76867171.7599 | 32606563.6169 | 109473735.3768 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 30904867.7369 | 8030484.3425 | 38935352.0795 | 38935352.0795
|  | BLUE ALUMINIUM PIPE, DN63 | 0 | 30 | m | 362322.6857 | 115320.5625 | 477643.2482 | 10869680.5712 | 3459616.875 | 14329297.4462 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 5434840.2856 | 1729808.4375 | 7164648.7231 | 7164648.7231
|  | BLUE ALUMINIUM PIPE, DN40 | 69 | 72 | m | 190224.1656 | 70966.5 | 261190.6656 | 13696139.9232 | 5109588 | 18805727.9232 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 6848069.9616 | 2554794 | 9402863.9616 | 9402863.9616
|  | BLUE ALUMINIUM PIPE, DN25 | 17 | 21 | m | 94950.6667 | 42579.9 | 137530.5667 | 1993964 | 894177.9 | 2888141.9 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 996982 | 447088.95 | 1444070.95 | 1444070.95
|  | TUBE CLIP, DN63 (POLYMER) | 0 | 6 | pcs | 54295.4118 | 82376.8 | 136672.2118 | 325772.471 | 494260.8 | 820033.271 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 162886.2355 | 247130.4 | 410016.6355 | 410016.6355
|  | PIPE TO PIPE JOINT, DN63 | 0 | 8 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 4783213.8189 | 659014.4 | 5442228.2189 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 2391606.9094 | 329507.2 | 2721114.1094 | 2721114.1094
|  | PIPE TO PIPE JOINT, DN63 | 0 | 8 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 4783213.8189 | 659014.4 | 5442228.2189 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 2391606.9094 | 329507.2 | 2721114.1094 | 2721114.1094
|  | EQUAL TEE, DN63 | 0 | 6 | pcs | 543443.2662 | 82376.8 | 625820.0662 | 3260659.5974 | 494260.8 | 3754920.3974 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 1630329.7987 | 247130.4 | 1877460.1987 | 1877460.1987
|  | REDUCING TEE, DN63-40 | 2 | 2 | pcs | 861389.3716 | 82376.8 | 943766.1716 | 1722778.7432 | 164753.6 | 1887532.3432 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 861389.3716 | 82376.8 | 943766.1716 | 943766.1716
|  | END CAP, DN63 | 1 | 1 | pcs | 380393.9814 | 82376.8 | 462770.7814 | 380393.9814 | 82376.8 | 462770.7814 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 190196.9907 | 41188.4 | 231385.3907 | 231385.3907
|  | TUBE CLIP, DN40 (POLYMER) | 26 | 24 | pcs | 32609.857 | 57608.1 | 90217.957 | 782636.567 | 1382594.4 | 2165230.967 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 391318.2835 | 691297.2 | 1082615.4835 | 1082615.4835
|  | PIPE TO PIPE JOINT, DN40 | 12 | 12 | pcs | 317946.1054 | 57608.1 | 375554.2054 | 3815353.2643 | 691297.2 | 4506650.4643 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 1907676.6322 | 345648.6 | 2253325.2322 | 2253325.2322
|  | 90° ELBOW, DN40 | 1 | 1 | pcs | 706492.551 | 57608.1 | 764100.651 | 706492.551 | 57608.1 | 764100.651 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 353246.2755 | 28804.05 | 382050.3255 | 382050.3255
|  | EQUAL TEE, DN40 | 1 | 1 | pcs | 1066831.4704 | 57608.1 | 1124439.5704 | 1066831.4704 | 57608.1 | 1124439.5704 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 533415.7352 | 28804.05 | 562219.7852 | 562219.7852
|  | QUICK DROP, DN63-25 | 1 | 1 | pcs | 372241.5172 | 82376.8 | 454618.3172 | 372241.5172 | 82376.8 | 454618.3172 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 186120.7586 | 41188.4 | 227309.1586 | 227309.1586
|  | QUICK DROP, DN40-25 | 2 | 2 | pcs | 318435.2532 | 57608.1 | 376043.3532 | 636870.5064 | 115216.2 | 752086.7064 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 318435.2532 | 57608.1 | 376043.3532 | 376043.3532
|  | END CAP, DN40 | 2 | 2 | pcs | 529910.1756 | 57608.1 | 587518.2756 | 1059820.3512 | 115216.2 | 1175036.5512 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 529910.1756 | 57608.1 | 587518.2756 | 587518.2756
|  | BRASS VALVE, DN40-DN40 | 2 | 2 | pcs | 1451138.6347 | 57608.1 | 1508746.7347 | 2902277.2694 | 115216.2 | 3017493.4694 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 1451138.6347 | 57608.1 | 1508746.7347 | 1508746.7347
|  | BRASS VALVE, DN25-1/2" FEMALE THREAD, WITH FIXING PLATE | 2 | 2 | pcs | 617304.5923 | 53385.955 | 670690.5473 | 1234609.1845 | 106771.9101 | 1341381.0946 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 617304.5923 | 53385.955 | 670690.5473 | 670690.5473
|  | TWO-WAYS PNEUMATIC CONNECTOR, FEMALE THREAD G1/2" | 0 |  | pcs | 206583.4438 | 48702.5 | 255285.9438 | 0 | 0 | 0 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | T-BOLT, M8, 6CM | 40 | 40 | pcs | 3260.9857 | 3850 | 7110.9857 | 130439.4278 | 154000 | 284439.4278 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 65219.7139 | 77000 | 142219.7139 | 142219.7139
|  | THREADED ROD, M8, 3 METER | 25 | 25 | pcs | 48914.7854 | 11000 | 59914.7854 | 1222869.636 | 275000 | 1497869.636 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 611434.818 | 137500 | 748934.818 | 748934.818
|  | WALL MOUNTED BRACKET, 50CM | 36 | 36 | pcs | 92448.9445 | 8250 | 100698.9445 | 3328162.0013 | 297000 | 3625162.0013 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 1664081.0007 | 148500 | 1812581.0007 | 1812581.0007
|  | BEAM CLAMP, 2.5CM | 72 | 72 | pcs | 37990.4834 | 8250 | 46240.4834 | 2735314.8018 | 594000 | 3329314.8018 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 1367657.4009 | 297000 | 1664657.4009 | 1664657.4009
|  | Fire Stop | 1 | 1 | lot | 2500000 | 1000000 | 3500000 | 2500000 | 1000000 | 3500000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 12557436.286 | 3767230.8858 | 16324667.1718 | 12557436.286 | 3767230.8858 | 16324667.1718 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | T&C | 1 | 1 | lot | 0 | 11778364.046 | 11778364.046 | 0 | 11778364.046 | 11778364.046 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. |  | Office, Social and Technical Areas (Hall 3) | [6 empty] | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
3. 3. |  | Mechanical Engineering | [6 empty] | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 3. 120. |  | Compressed Air Connections | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. |  | Machine hook-up (Hall 3) | [6 empty] | 246537484.7813 | 58813621.1675 | 305351105.9487 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
4. 2. |  | Mechanical Engineering | [6 empty] | 246537484.7813 | 58813621.1675 | 305351105.9487 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. 2. 10. |  | Machine hook-up | 1 | 1 | PSCH |  |  |  | 246537484.7813 | 58813621.1675 | 305351105.9487 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | BLUE ALUMINIUM PIPE, DN63 | 16 | 18 | m | 362322.6857 | 115320.5625 | 477643.2482 | 6521808.3427 | 2075770.125 | 8597578.4677 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | BLUE ALUMINIUM PIPE, DN40 | 257 | 228 | m | 190224.1656 | 70966.5 | 261190.6656 | 43371109.7568 | 16180362 | 59551471.7568 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | BLUE ALUMINIUM PIPE, DN25 | 23 | 27 | m | 94950.6667 | 42579.9 | 137530.5667 | 2563668 | 1149657.3 | 3713325.3 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PIPE TO PIPE JOINT, DN63 | 1 | 1 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 597901.7274 | 82376.8 | 680278.5274 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | REDUCING PIPE TO PIPE JOINT, DN63-DN40 | 1 | 1 | pcs | 684154.799 | 82376.8 | 766531.599 | 684154.799 | 82376.8 | 766531.599 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | TUBE CLIP, DN40 (POLYMER) | 92 | 77 | pcs | 32609.857 | 57608.1 | 90217.957 | 2510958.9859 | 4435823.7 | 6946782.6859 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PIPE TO PIPE JOINT, DN40 | 45 | 45 | pcs | 317946.1054 | 57608.1 | 375554.2054 | 14307574.7412 | 2592364.5 | 16899939.2412 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | QUICK DROP, DN40-25 | 45 | 45 | pcs | 318435.2532 | 57608.1 | 376043.3532 | 14329586.3946 | 2592364.5 | 16921950.8946 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pressureless decouling | 96 | 96 | pcs | 387040 | 30056.4 | 417096.4 | 37155840 | 2885414.4 | 40041254.4 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | BRASS VALVE, DN63-DN63 | 1 | 1 | pcs | 2445739.272 | 82376.8 | 2528116.072 | 2445739.272 | 82376.8 | 2528116.072 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | BRASS VALVE, DN40-DN40 | 2 | 2 | pcs | 1451138.6347 | 57608.1 | 1508746.7347 | 2902277.2694 | 115216.2 | 3017493.4694 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LOCKABLE BRASS VALVE, DN25-1/2" FEMALE THREAD, WITH FIXING PLATE | 28 | 28 | pcs | 680241.6162 | 53385.955 | 733627.5712 | 19046765.2532 | 1494806.7411 | 20541571.9943 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | LOCKABLE BRASS VALVE, DN25-3/8" FEMALE THREAD, WITH FIXING PLATE | 68 | 68 | pcs | 680241.6162 | 53385.955 | 733627.5712 | 46256429.9006 | 3630244.9427 | 49886674.8433 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | BRASS VALVE, DN25-1/2" FEMALE THREAD, WITH FIXING PLATE | 6 | 6 | pcs | 617304.5923 | 53385.955 | 670690.5473 | 3703827.5535 | 320315.7302 | 4024143.2838 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | T-split 3 way outlet tap | 28 | 28 | pcs | 451350 | 27500 | 478850 | 12637800 | 770000 | 13407800 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | T-BOLT, M8, 6CM | 92 | 92 | pcs | 3260.9857 | 3850 | 7110.9857 | 300010.684 | 354200 | 654210.684 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | THREADED ROD, M8, 3 METER | 50 | 50 | pcs | 48914.7854 | 11000 | 59914.7854 | 2445739.272 | 550000 | 2995739.272 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | WALL MOUNTED BRACKET, 50CM | 92 | 92 | pcs | 92448.9445 | 8250 | 100698.9445 | 8505302.8923 | 759000 | 9264302.8923 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | BEAM CLAMP, 2.5CM | 184 | 184 | pcs | 37990.4834 | 8250 | 46240.4834 | 6990248.9379 | 1518000 | 8508248.9379 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 19260740.9985 | 5778222.2996 | 25038963.2981 | 19260740.9985 | 5778222.2996 | 25038963.2981 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | T&C | 1 | 1 | lot | 0 | 11364728.3288 | 11364728.3288 | 0 | 11364728.3288 | 11364728.3288 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. |  | Scooter Garage | [6 empty] | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
6. |  | Canteen | [6 empty] | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
7. |  | Exterior Area | [6 empty] | 28542816 | 17816848.8 | 46359664.8 | 0% | 0% | 0% | 0% |  |  | #REF! | 4122851.2 | 2210208 | 6333059.2 | 0 | 0 | 0 | 6333059.2
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
7. 3. |  | Mechanical Engineering | [6 empty] | 28542816 | 17816848.8 | 46359664.8 | 0% | 0% | 0% | 0% |  |  | #REF! | 4122851.2 | 2210208 | 6333059.2 | 0 | 0 | 0 | 6333059.2
7. 3. 10. |  | Underground Compressed Air Connection | 1 |  | PSCH |  |  |  | 28542816 | 17816848.8 | 46359664.8 | 0% | 0% | 0% | 0% |  |  | #REF! | 4122851.2 | 2210208 | 6333059.2 | 0 | 0 | 0 | 6333059.2
|  | HDPE Pipe DN100 | 115 | 115 | m | 179254.4 | 96096 | 275350.4 | 20614256 | 11051040 | 31665296 | 20% | 0% | 20% | 40% |  |  | #REF! | 4122851.2 | 2210208 | 6333059.2 | 0 | 0 | 0 | 6333059.2
|  | Fitting for connecting HDPE pipes with aluminum pipes | 1 | 1 | lot | 4757136 | 1427140.8 | 6184276.8 | 4757136 | 1427140.8 | 6184276.8 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger support & accessories | 1 | 1 | lot | 3171424 | 951427.2 | 4122851.2 | 3171424 | 951427.2 | 4122851.2 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | T&C | 1 | 1 | lot | 0 | 4387240.8 | 4387240.8 | 0 | 4387240.8 | 4387240.8 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. |  | Adjustments Hall 2 | [6 empty] | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
8. 5. |  | Additional Compressed Air Equipment | [6 empty] | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. 5. 10. |  | Additional Compressed Air Equipment | 1 |  | PSCH |  |  |  | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Main equipments | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Rotary screw air compressor | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Air dryer | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ball Valve D63 | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ball Valve D40 | 6 |  | Pcs |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Oil removal filter | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pressure maintainance system | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Condensate drain pipe D19 | 15 |  | m |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Condensate drain pipe D15.9 | 25 |  | m |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 |  | lot |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | T&C | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ventilation for Air compressor | [5 empty] | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Tole 0.95mm | 12 |  | m2 |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Motor fire damper 550x500x450 | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flexiable connection | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cat6A | 66 |  | m |  |  | 0 | 0 | 0 | 0 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable 1 pair 18AWG | 22 |  | m |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/PVC/PVC 2Cx1.5mm2 | 22 |  | m |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 39 |  | m |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | GI flexible conduct D20 | 42 |  | m |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable tray 50x50x1.0mm | 7 |  | m |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger support | 1 |  | lot |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 |  | lot |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Compressed air pipes and valves | [5 empty] | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Aluminium Air pipe D63 | 11 |  | m |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Aluminium Air pipe D40 | 8 |  | m |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fiiting for Aluminium pipe | 1 |  | lot |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger support + Accessories | 1 |  | lot |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | IV. 4.VENTILATION | [8 empty] | 3204713406.5221 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 189607500 |  |  | 157611605.1125 | 347219105.1125
2. |  | Production and Logistic building (Hall 3) | [6 empty] | 876156669.5216 | 245761873.2789 | 1121918542.8005 | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 3. |  | Mechanical Engineering | [6 empty] | 876156669.5216 | 245761873.2789 | 1121918542.8005 | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 3. 10. |  | Ventilation System Production | 1 | 1 | PSCH |  |  |  | 304034489.6043 | 189644193.2889 | 493678682.8931 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Logistics Area | [6 empty] | 32646354.8705 | 20550720.3964 | 53197075.267 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Overhead Propeller Fans | 2 | 2 | pcs | 0 | 6300000 | 6300000 | 0 | 12600000 | 12600000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Control panel for Overhead Fans | 1 | 1 | pcs | 19550000 | 385000 | 19935000 | 19550000 | 385000 | 19935000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/PVC/PVC 4Cx1.5mm2 | 160 | 163.8 | m | 25928.4 | 7485.665 | 33414.065 | 4247071.92 | 1226151.927 | 5473223.847 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/PVC/PVC 2Cx1.5mm2 | 165 | 163.8 | m | 15443.88 | 5031.18 | 20475.06 | 2529707.544 | 824107.284 | 3353814.828 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 243 | 300 | m | 8773.9726 | 14594.0164 | 23367.989 | 2632191.7808 | 4378204.9235 | 7010396.7044 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC flexible conduct D20 | 7 | 7.35 | m | 3554.7229 | 5289.7059 | 8844.4288 | 26127.2135 | 38879.3382 | 65006.5517 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 15 |  | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger, support | 1 | 1 | lot | 1220418.8041 | 366125.6412 | 1586544.4453 | 1220418.8041 | 366125.6412 | 1586544.4453 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 2440837.6082 | 732251.2824 | 3173088.8906 | 2440837.6082 | 732251.2824 | 3173088.8906 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | [7 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Production Hall 1 | 0 | 0 |  |  |  |  | 233479516.9276 | 145274230.7072 | 378753747.6348 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Overhead Propeller Fans | 14 | 14 | pcs | 0 | 6300000 | 6300000 | 0 | 88200000 | 88200000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Control panel for Overhead Fans | 7 | 7 | m | 19550000 | 385000 | 19935000 | 136850000 | 2695000 | 139545000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4Cx-1.5mm2 Cu/PVC/PVC | 1600 | 1556.5 | m | 25928.4 | 7485.665 | 33414.065 | 40357554.6 | 11651437.5725 | 52008992.1725 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2Cx-1.5mm2 Cu/PVC/PVC | 1050 | 1156.5 | m | 15443.88 | 5031.18 | 20475.06 | 17860847.22 | 5818559.67 | 23679406.89 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 2125 | 2100 | m | 8773.9726 | 14594.0164 | 23367.989 | 18425342.4658 | 30647434.4647 | 49072776.9305 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC flexible conduct D20 | 70 | 63 | m | 3554.7229 | 5289.7059 | 8844.4288 | 223947.544 | 333251.4706 | 557199.0145 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 150 |  | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger, support | 1 | 1 | lot | 8982647.7718 | 2694794.3315 | 11677442.1033 | 8982647.7718 | 2694794.3315 | 11677442.1033 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 10779177.3261 | 3233753.1978 | 14012930.524 | 10779177.3261 | 3233753.1978 | 14012930.524 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Production Hall 2 | 0 | 0 |  |  |  |  | 30503490.5753 | 19149107.5868 | 49652598.1621 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Overhead Propeller Fans | 2 | 2 | pcs | 0 | 6300000 | 6300000 | 0 | 12600000 | 12600000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Control panel for Overhead Fans | 1 | 1 | m | 19550000 | 385000 | 19935000 | 19550000 | 385000 | 19935000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4Cx-1.5mm2 Cu/PVC/PVC | 160 | 108.15 | m | 25928.4 | 7485.665 | 33414.065 | 2804156.46 | 809574.6698 | 3613731.1298 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2Cx-1.5mm2 Cu/PVC/PVC | 165 | 170 | m | 15443.88 | 5031.18 | 20475.06 | 2625459.6 | 855300.6 | 3480760.2 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 243 | 220 | m | 8773.9726 | 14594.0164 | 23367.989 | 1930273.9726 | 3210683.6106 | 5140957.5832 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC flexible conduct D20 | 7 | 7.35 | m | 3554.7229 | 5289.7059 | 8844.4288 | 26127.2135 | 38879.3382 | 65006.5517 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 15 | 15 | m | 8773.9726 | 14594.0164 | 23367.989 | 131609.589 | 218910.2462 | 350519.8352 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger, support | 1 | 1 | lot | 1145287.9134 | 343586.374 | 1488874.2874 | 1145287.9134 | 343586.374 | 1488874.2874 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 2290575.8268 | 687172.748 | 2977748.5748 | 2290575.8268 | 687172.748 | 2977748.5748 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Interface between fire alarm and fan system | 0 | 0 |  |  |  |  | 7405127.2308 | 4670134.5985 | 12075261.8293 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8 | Fire signal cable: (2x1.0)mm2 Dây tín hiệu báo cháy: (2x1.0)mm2 | 830 | 830 | M | 7457.49 | 3300 | 10757.49 | 6189716.7 | 2739000 | 8928716.7 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 | D16 PVC conduit & accessories Ống bảo vệ dây dẫn D16 và phụ kiện | 140 | 140 | M | 6646.8692 | 13183.4282 | 19830.2974 | 930561.6849 | 1845679.9447 | 2776241.6296 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 284848.8459 | 85454.6538 | 370303.4997 | 284848.8459 | 85454.6538 | 370303.4997 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. 3. 60. |  | SMOKE EXHAUST SYSTEM | [6 empty] | 572122179.9173 | 56117679.99 | 628239859.9073 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Equipment | [6 empty] | 474178458 | 32835793.1 | 507014251.1 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Roof smoke exhaust FAN - SEAF @26500m3/h, 100Pa, 3.0kW, 300oC in 2hrs | 6 | 6 | pcs | 43434300 | 2241801.1 | 45676101.1 | 260605800 | 13450806.6 | 274056606.6 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Roof smoke exhaust FAN - SEAF @8000m3/h, 100Pa, 0.5kW, 300oC in 2hrs | 4 | 4 | pcs | 17612370 | 923094.7 | 18535464.7 | 70449480 | 3692378.8 | 74141858.8 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Wall mounted smoke exhaust FAN - SEAF @26500m3/h, 100Pa, 3kW, 300oC in 2hrs | 3 | 3 | pcs | 25306446 | 2241801.1 | 27548247.1 | 75919338 | 6725403.3 | 82644741.3 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Wall mounted smoke exhaust FAN - SEAF @16000m3/h, 100Pa, 1.5kW, 300oC in 2hrs | 4 | 4 | pcs | 16800960 | 2241801.1 | 19042761.1 | 67203840 | 8967204.4 | 76171044.4 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power supply & conduit | [6 empty] | 97943721.9173 | 23281886.89 | 121225608.8073 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/Fr/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 1156 | 1281 | m | 60411.45 | 9350 | 69761.45 | 77387067.45 | 11977350 | 89364417.45 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D25 | 463 | 415 | m | 12762.0356 | 15805 | 28567.0356 | 5296244.7808 | 6559075 | 11855319.7808 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC flexible conduct D25 | 120 | 53.55 | m | 8113.63 | 5559 | 13672.63 | 434484.8865 | 297684.45 | 732169.3365 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 14825924.8 | 4447777.44 | 19273702.24 | 14825924.8 | 4447777.44 | 19273702.24 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. |  | Office, Social and Technical Areas (Hall 3) | [6 empty] | 1272946321.0445 | 134316312.1879 | 1407262633.2324 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 140519880 | 6325200 | 146845080 | 146845080
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
3. 3. |  | Mechanical Engineering | [6 empty] | 1272946321.0445 | 134316312.1879 | 1407262633.2324 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 140519880 | 6325200 | 146845080 | 146845080
3. 3. 40. |  | Ventilation System | 1 | 1 | PSCH |  |  |  | 915624507.9952 | 94236583.2039 | 1009861091.1991 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 67733712 | 4697280 | 72430992 | 72430992
|  | Ground floor - west side | [6 empty] | 259524148.7256 | 33244549.9752 | 292768698.7008 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 28081620 | 2136960 | 30218580 | 30218580
|  | Equipments | [6 empty] | 32262384 | 3815280.7 | 36077664.7 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Exhaust air fan in-line centrifugal type (Q = 1240/620 m3/h, 220 Pa) | 1 | 1 | pcs | 7426788 | 923094.7 | 8349882.7 | 7426788 | 923094.7 | 8349882.7 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Exhaust air fan in-line centrifugal type (Q = 460/230 m3/h, 200 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Exhaust air fan in-line centrifugal type (Q = 680/340 m3/h, 200 Pa) | 1 | 1 | pcs | 4734816 | 495000 | 5229816 | 4734816 | 495000 | 5229816 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Exhaust air fan in-line centrifugal type (Q = 550/275 m3/h, 180 Pa) | 2 | 2 | pcs | 4658448 | 495000 | 5153448 | 9316896 | 990000 | 10306896 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Exhaust air fan in-line centrifugal type (Q = 120 m3/h, 120 Pa) | 1 | 1 | pcs | 4734816 | 495000 | 5229816 | 4734816 | 495000 | 5229816 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger support & Sub materials | 1 | 1 | lot | 1390620 | 417186 | 1807806 | 1390620 | 417186 | 1807806 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Air grille, louver | [6 empty] | 167427120 | 9290400 | 176717520 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 28081620 | 2136960 | 30218580 | 30218580
|  | Poppet Valves D160 | 3 | 3 | pcs | 1079160 | 84000 | 1163160 | 3237480 | 252000 | 3489480 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Poppet Valves D100 | 43 | 43 | pcs | 921840 | 84000 | 1005840 | 39639120 | 3612000 | 43251120 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fresh air grille 500x200 | 18 | 18 | pcs | 1117800 | 140000 | 1257800 | 20120400 | 2520000 | 22640400 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 9054180 | 1134000 | 10188180 | 10188180
|  | Exhaust air grille 200x200 | 1 | 1 | pcs | 797640 | 117600 | 915240 | 797640 | 117600 | 915240 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Louver 200x200 + IS | 1 | 1 | pcs | 698280 | 117600 | 815880 | 698280 | 117600 | 815880 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 314226 | 52920 | 367146 | 367146
|  | Louver 400x200 + IS | 1 | 1 | pcs | 844560 | 117600 | 962160 | 844560 | 117600 | 962160 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 380052 | 52920 | 432972 | 432972
|  | Louver 400x250 + IS | 3 | 3 | pcs | 1073640 | 117600 | 1191240 | 3220920 | 352800 | 3573720 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 1449414 | 158760 | 1608174 | 1608174
|  | Louver 700x300 + IS | 1 | 1 | pcs | 2152800 | 140000 | 2292800 | 2152800 | 140000 | 2292800 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 968760 | 63000 | 1031760 | 1031760
|  | Volume control damper VCD D100 | 1 | 1 | pcs | 979800 | 84000 | 1063800 | 979800 | 84000 | 1063800 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 440910 | 37800 | 478710 | 478710
|  | Volume control damper VCD D160 | 6 | 6 | pcs | 1208880 | 84000 | 1292880 | 7253280 | 504000 | 7757280 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 3263976 | 226800 | 3490776 | 3490776
|  | Volume control damper VCD D200 | 1 | 1 | pcs | 1479360 | 84000 | 1563360 | 1479360 | 84000 | 1563360 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 665712 | 37800 | 703512 | 703512
|  | Volume control controller D160 | 1 | 1 | pcs | 2718600 | 84000 | 2802600 | 2718600 | 84000 | 2802600 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 1223370 | 37800 | 1261170 | 1261170
|  | Pressure release flap 345x400 | 2 | 2 | pcs | 30674640 | 280000 | 30954640 | 61349280 | 560000 | 61909280 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Silencer D120xL500 | 1 | 1 | pcs | 2368080 | 106400 | 2474480 | 2368080 | 106400 | 2474480 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 1065636 | 47880 | 1113516 | 1113516
|  | Silencer D190xL500 | 6 | 6 | pcs | 3427920 | 106400 | 3534320 | 20567520 | 638400 | 21205920 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 9255384 | 287280 | 9542664 | 9542664
|  | Ductwork sheet | [6 empty] | 59834644.7256 | 20138869.2752 | 79973514.0008 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Rigid duct Z8, thickness 0.58mm | 52 | 51.7 | m2 | 236291.3455 | 106400 | 342691.3455 | 12216262.56 | 5500880 | 17717142.56 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Insulation 6mmT | 57 | 55 | m2 | 104230.8 | 44800 | 149030.8 | 5732694 | 2464000 | 8196694 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Simili for fan | 12 | 12 | pcs | 90000 | 35000 | 125000 | 1080000 | 420000 | 1500000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger support & Sub materials | 1 | 1 | lot | 15556006.38 | 4666801.914 | 20222808.294 | 15556006.38 | 4666801.914 | 20222808.294 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power supply & conduit | [6 empty] | 25249681.7856 | 7087187.3612 | 32336869.1468 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Timer delay | 5 | 5 | pcs | 2875000 | 82500 | 2957500 | 14375000 | 412500 | 14787500 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switch 1way - 1gang 10A-220V | 1 | 1 | m | 46800 | 54500 | 101300 | 46800 | 54500 | 101300 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3C-1.5mm2 Cu/XLPE/PVC | 330 | 308 | m | 22980.09 | 5743.9305 | 28724.0205 | 7077867.72 | 1769130.594 | 8846998.314 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC flexible conduct D20 | 9 | 9.9 | m | 3554.7229 | 5289.7059 | 8844.4288 | 35191.7569 | 52368.0882 | 87559.8451 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 333 | 308 | m | 8773.9726 | 14594.0164 | 23367.989 | 2702383.5616 | 4494957.0548 | 7197340.6165 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 1012438.7471 | 303731.6241 | 1316170.3712 | 1012438.7471 | 303731.6241 | 1316170.3712 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ground floor - east side | [6 empty] | 540527596.8724 | 42856692.0376 | 583384288.91 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 24447528 | 1779120 | 26226648 | 26226648
|  | Equipments | [6 empty] | 41276280 | 4988745 | 46265025 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Exhaust air fan in-line centrifugal type (Q = 800/400 m3/h, 200 Pa) | 1 | 1 | pcs | 4734816 | 495000 | 5229816 | 4734816 | 495000 | 5229816 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Exhaust air fan in-line centrifugal type (Q = 600/300 m3/h, 220 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Exhaust air fan in-line centrifugal type (Q = 550/275 m3/h, 180 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Exhaust air fan in-line centrifugal type (Q = 500 m3/h, 200 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Exhaust air fan wall type (Q = 120 m3/h, 50 Pa) | 1 | 1 | pcs | 2324562 | 495000 | 2819562 | 2324562 | 495000 | 2819562 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Exhaust air fan wall type (Q = 1210 m3/h, 50 Pa) | 4 | 4 | pcs | 4615602 | 495000 | 5110602 | 18462408 | 1980000 | 20442408 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger support & Sub materials | 1 | 1 | lot | 1779150 | 533745 | 2312895 | 1779150 | 533745 | 2312895 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Air grille, louver | [6 empty] | 429116520 | 10169600 | 439286120 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 24447528 | 1779120 | 26226648 | 26226648
|  | Poppet Valves D160 | 1 | 1 | pcs | 1079160 | 84000 | 1163160 | 1079160 | 84000 | 1163160 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Poppet Valves D100 | 23 | 23 | pcs | 921840 | 84000 | 1005840 | 21202320 | 1932000 | 23134320 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fresh air grille 500x200 | 18 | 18 | pcs | 1117800 | 140000 | 1257800 | 20120400 | 2520000 | 22640400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Exhaust air grille 200x200 | 1 | 1 | pcs | 797640 | 117600 | 915240 | 797640 | 117600 | 915240 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 358938 | 52920 | 411858 | 411858
|  | Exhaust air grille 500x200 + OBD | 13 | 13 | pcs | 1349640 | 140000 | 1489640 | 17545320 | 1820000 | 19365320 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 7895394 | 819000 | 8714394 | 8714394
|  | Louver 200x200 + IS | 1 | 1 | pcs | 698280 | 117600 | 815880 | 698280 | 117600 | 815880 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 314226 | 52920 | 367146 | 367146
|  | Louver 400x250 + IS | 3 | 3 | pcs | 1073640 | 117600 | 1191240 | 3220920 | 352800 | 3573720 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 1449414 | 158760 | 1608174 | 1608174
|  | Louver 500x500 + IS | 4 | 4 | pcs | 2484000 | 140000 | 2624000 | 9936000 | 560000 | 10496000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 4471200 | 252000 | 4723200 | 4723200
|  | Louver 700x250 + IS | 1 | 1 | pcs | 2152800 | 140000 | 2292800 | 2152800 | 140000 | 2292800 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 968760 | 63000 | 1031760 | 1031760
|  | Volume control damper VCD D100 | 1 | 1 | pcs | 979800 | 84000 | 1063800 | 979800 | 84000 | 1063800 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 440910 | 37800 | 478710 | 478710
|  | Volume control damper VCD D160 | 3 | 3 | pcs | 1208880 | 84000 | 1292880 | 3626640 | 252000 | 3878640 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 1631988 | 113400 | 1745388 | 1745388
|  | Volume control controller D160 | 1 | 1 | pcs | 2718600 | 84000 | 2802600 | 2718600 | 84000 | 2802600 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 1223370 | 37800 | 1261170 | 1261170
|  | Pressure release flap 345x400 | 2 | 2 | pcs | 30674640 | 280000 | 30954640 | 61349280 | 560000 | 61909280 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fire damper D250 | 2 | 2 | pcs | 21834360 | 140000 | 21974360 | 43668720 | 280000 | 43948720 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Overflow air via fire protection flaps 400x250 | 3 | 3 | pcs | 75789600 | 280000 | 76069600 | 227368800 | 840000 | 228208800 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Silencer D120xL500 | 1 | 1 | pcs | 2368080 | 106400 | 2474480 | 2368080 | 106400 | 2474480 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 1065636 | 47880 | 1113516 | 1113516
|  | Silencer D190xL500 | 3 | 3 | pcs | 3427920 | 106400 | 3534320 | 10283760 | 319200 | 10602960 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 4627692 | 143640 | 4771332 | 4771332
|  | Ductwork sheet | [6 empty] | 42937395.394 | 15270557.0262 | 58207952.4202 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Rigid duct Z8, thickness 0.58mm | 44 | 46.2 | m2 | 236291.3455 | 106400 | 342691.3455 | 10916660.16 | 4915680 | 15832340.16 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Insulation 6mmT | 50 | 50.6 | m2 | 104230.8 | 44800 | 149030.8 | 5274078.48 | 2266880 | 7540958.48 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Simili for fan | 8 | 8 | pcs | 90000 | 35000 | 125000 | 720000 | 280000 | 1000000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger support & Sub materials | 1 | 1 | lot | 26026656.754 | 7807997.0262 | 33834653.7802 | 26026656.754 | 7807997.0262 | 33834653.7802 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power supply & conduit | [6 empty] | 27197401.4784 | 12427790.0114 | 39625191.4898 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Timer delay | 2 | 2 | pcs | 2875000 | 82500 | 2957500 | 5750000 | 165000 | 5915000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switch 1way - 1gang 10A-220V | 1 | 1 | m | 46800 | 54500 | 101300 | 46800 | 54500 | 101300 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contactor + Box | 3 | 3 | m | 900000 | 163500 | 1063500 | 2700000 | 490500 | 3190500 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3C-1.5mm2 Cu/XLPE/PVC | 495 | 495 | m | 22980.09 | 5743.9305 | 28724.0205 | 11375144.55 | 2843245.5975 | 14218390.1475 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2C-1.5mm2 Cu/PVC/PVC | 90 | 90 | m | 15443.88 | 5031.18 | 20475.06 | 1389949.2 | 452806.2 | 1842755.4 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC flexible conduct D20 | 14 | 14.7 | m | 3554.7229 | 5289.7059 | 8844.4288 | 52254.4269 | 77758.6765 | 130013.1034 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D16 | 495 |  | m | 6646.8692 | 13183.4282 | 19830.2974 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 498 | 550 | m | 8773.9726 | 14594.0164 | 23367.989 | 4825684.9315 | 8026709.0265 | 12852393.958 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 1057568.3699 | 317270.511 | 1374838.8809 | 1057568.3699 | 317270.511 | 1374838.8809 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fist floor - west side | [6 empty] | 95572762.3972 | 15135341.1911 | 110708103.5883 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 15204564 | 781200 | 15985764 | 15985764
|  | Equipments | [6 empty] | 19632768 | 2233872 | 21866640 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Exhaust air fan in-line centrifugal type (Q = 830/415 m3/h, 150 Pa) | 2 | 2 | pcs | 4734816 | 495000 | 5229816 | 9469632 | 990000 | 10459632 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Exhaust air fan in-line centrifugal type (Q = 480/240 m3/h, 150 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Exhaust air fan in-line centrifugal type (Q = 420/210 m3/h, 150 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger support & Sub materials | 1 | 1 | lot | 846240 | 253872 | 1100112 | 846240 | 253872 | 1100112 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Air grille, louver | [6 empty] | 47615520 | 2996000 | 50611520 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 15204564 | 781200 | 15985764 | 15985764
|  | Poppet Valves D100 | 15 | 15 | pcs | 921840 | 84000 | 1005840 | 13827600 | 1260000 | 15087600 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Louver 700x250 + IS | 2 | 2 | pcs | 2152800 | 140000 | 2292800 | 4305600 | 280000 | 4585600 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 1937520 | 126000 | 2063520 | 2063520
|  | Louver 400x200 + IS | 2 | 2 | pcs | 844560 | 117600 | 962160 | 1689120 | 235200 | 1924320 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 760104 | 105840 | 865944 | 865944
|  | Exhaust air grille EAG-600x600 | 2 | 2 | pcs | 3960600 | 140000 | 4100600 | 7921200 | 280000 | 8201200 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 3564540 | 126000 | 3690540 | 3690540
|  | Supply air grille EAG-300x300 | 8 | 8 | pcs | 2484000 | 117600 | 2601600 | 19872000 | 940800 | 20812800 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 8942400 | 423360 | 9365760 | 9365760
|  | Ductwork sheet | [6 empty] | 12042039.2045 | 4956818.7105 | 16998857.915 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Rigid duct Z8, thickness 0.58mm | 25 | 25 | m2 | 236291.3455 | 106400 | 342691.3455 | 5907283.6364 | 2660000 | 8567283.6364 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Insulation 6mmT | 29 | 29 | m2 | 104230.8 | 44800 | 149030.8 | 3022693.2 | 1299200 | 4321893.2 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Simili for fan | 8 | 8 | pcs | 90000 | 35000 | 125000 | 720000 | 280000 | 1000000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger support & Sub materials | 1 | 1 | lot | 2392062.3682 | 717618.7105 | 3109681.0786 | 2392062.3682 | 717618.7105 | 3109681.0786 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power supply & conduit | [6 empty] | 16282435.1926 | 4948650.4806 | 21231085.6733 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Timer delay | 3 | 3 | pcs | 2875000 | 82500 | 2957500 | 8625000 | 247500 | 8872500 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3C-1.5mm2 Cu/XLPE/PVC | 220 | 220 | m | 22980.09 | 5743.9305 | 28724.0205 | 5055619.8 | 1263664.71 | 6319284.51 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 220 | 220 | m | 8773.9726 | 14594.0164 | 23367.989 | 1930273.9726 | 3210683.6106 | 5140957.5832 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC flexible conduct D20 | 6 | 6 | m | 3554.7229 | 5289.7059 | 8844.4288 | 21328.3375 | 31738.2353 | 53066.5728 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 650213.0825 | 195063.9248 | 845277.0073 | 650213.0825 | 195063.9248 | 845277.0073 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fist floor - esat side | [6 empty] | 20000000 | 3000000 | 23000000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Equipments | [6 empty] | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Exhaust air fan in-line centrifugal type (Q = 440/220m3/h, 150 Pa) | 3 |  | pcs | 4658448 | 495000 | 5153448 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger support & Sub materials | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Air grille, louver | [6 empty] | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Poppet Valves D220 | 4 |  | pcs | 1484880 | 84000 | 1568880 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Poppet Valves D100 | 19 |  | pcs | 921840 | 84000 | 1005840 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Louver 400x200 + IS | 3 |  | pcs | 844560 | 117600 | 962160 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Volume control damper VCD D100 | 1 |  | pcs | 979800 | 84000 | 1063800 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Volume control damper VCD D160 | 2 |  | pcs | 1208880 | 84000 | 1292880 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Supply air grille EAG-300x300 | 4 |  | pcs | 2484000 | 117600 | 2601600 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Silencer D120xL500 | 1 |  | pcs | 2368080 | 106400 | 2474480 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Silencer D190xL500 | 2 |  | pcs | 3427920 | 106400 | 3534320 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ductwork sheet | [6 empty] | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Rigid duct Z8, thickness 0.58mm | 18 |  | m2 | 236291.3455 | 106400 | 342691.3455 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Insulation 6mmT | 22 |  | m2 | 104230.8 | 44800 | 149030.8 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Simili for fan | 6 |  | pcs | 90000 | 35000 | 125000 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger support & Sub materials | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power supply & conduit | [6 empty] | 20000000 | 3000000 | 23000000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Timer delay | 2 |  | pcs | 2875000 | 82500 | 2957500 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3C-1.5mm2 Cu/XLPE/PVC | 165 |  | m | 22980.09 | 5743.9305 | 28724.0205 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 165 |  | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC flexible conduct D20 | 6 |  | m | 3554.7229 | 5289.7059 | 8844.4288 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fire stop | 3 | 1 | lot | 20000000 | 3000000 | 23000000 | 20000000 | 3000000 | 23000000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 |  | lot | 1000000 | 300000 | 1300000 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 3. 50. |  | Ventilation System 1st Floor Offices Ventilation Units | 1 | 1 | PSCH |  |  |  | 84938287.2586 | 5889562.8377 | 90827850.0963 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | west side | 0 | 0 |  |  |  | 0 | 84938287.2586 | 5889562.8377 | 90827850.0963 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Equipments | [6 empty] | 80634445.35 | 3616553.635 | 84250998.985 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Heat Recovery Ventilation 390 m3/h | 1 | 1 | pcs | 19802999.7 | 1064000 | 20866999.7 | 19802999.7 | 1064000 | 20866999.7 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Heat Recovery Ventilation 2000 m3/h | 1 | 1 | pcs | 54096000.2 | 1400000 | 55496000.2 | 54096000.2 | 1400000 | 55496000.2 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remote wirring for ERV | 2 | 2 | pcs | 1614800 | 50400 | 1665200 | 3229600 | 100800 | 3330400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger support & Accessories | 1 | 1 | lot | 3505845.45 | 1051753.635 | 4557599.085 | 3505845.45 | 1051753.635 | 4557599.085 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power supply & conduit | [6 empty] | 4303841.9086 | 2273009.2027 | 6576851.1113 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3C-2.5mm2 Cu/XLPE/PVC | 100 | 100 | m | 32518.74 | 7485.665 | 40004.405 | 3251874 | 748566.5 | 4000440.5 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 100 | 100 | m | 8773.9726 | 14594.0164 | 23367.989 | 877397.2603 | 1459401.6412 | 2336798.9015 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC flexible conduct D20 | 3 | 3 | m | 3554.7229 | 5289.7059 | 8844.4288 | 10664.1688 | 15869.1176 | 26533.2864 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 3 |  | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 163906.4796 | 49171.9439 | 213078.4235 | 163906.4796 | 49171.9439 | 213078.4235 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 3. 60. |  | Ventilation System 1st Floor Offices Ducting | 1 | 1 | PSCH |  |  |  | 272383525.7906 | 34190166.1463 | 306573691.937 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 72786168 | 1627920 | 74414088 | 74414088
|  | west side | 0 | 0 |  |  |  | 0 | 272383525.7906 | 34190166.1463 | 306573691.937 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 72786168 | 1627920 | 74414088 | 74414088
|  | Equipments | [6 empty] | 262643773.8955 | 29033956.5687 | 291677730.4642 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 72786168 | 1627920 | 74414088 | 74414088
|  | Exhaust air fan in-line centrifugal type (Q = 2000m3/h, 300 Pa) | 2 | 2 | pcs | 7379058 | 923094.7 | 8302152.7 | 14758116 | 1846189.4 | 16604305.4 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Duct smoke detector | 4 | 4 | pcs | 4140000 | 128800 | 4268800 | 16560000 | 515200 | 17075200 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Rigid duct Z8, thickness 0.58mm | 132 | 132 | m2 | 236291.3455 | 106400 | 342691.3455 | 31190457.6 | 14044800 | 45235257.6 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Insulation 16mmT | 142 | 143 | m2 | 207754.8 | 44800 | 252554.8 | 29708936.4 | 6406400 | 36115336.4 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Supply air grill 300x300 | 6 | 6 | pcs | 2484000 | 117600 | 2601600 | 14904000 | 705600 | 15609600 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 6706800 | 317520 | 7024320 | 7024320
|  | Supply air grill 600x600 | 3 | 3 | pcs | 3960600 | 140000 | 4100600 | 11881800 | 420000 | 12301800 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 5346810 | 189000 | 5535810 | 5535810
|  | Exhaust air grill 600x600 | 5 | 5 | pcs | 3960600 | 140000 | 4100600 | 19803000 | 700000 | 20503000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 8911350 | 315000 | 9226350 | 9226350
|  | Louver 400x200 + IS | 2 | 2 | pcs | 844560 | 117600 | 962160 | 1689120 | 235200 | 1924320 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 760104 | 105840 | 865944 | 865944
|  | Louver 900x400 + IS | 2 | 2 | pcs | 3759120 | 140000 | 3899120 | 7518240 | 280000 | 7798240 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 3383208 | 126000 | 3509208 | 3509208
|  | Siliencer D240xL1000 | 2 | 2 | pcs | 6668160 | 106400 | 6774560 | 13336320 | 212800 | 13549120 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 6001344 | 95760 | 6097104 | 6097104
|  | Siliencer D300xL800 | 6 | 6 | pcs | 7998480 | 106400 | 8104880 | 47990880 | 638400 | 48629280 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 21595896 | 287280 | 21883176 | 21883176
|  | Siliencer D420XL1000 | 4 | 4 | pcs | 11155920 | 106400 | 11262320 | 44623680 | 425600 | 45049280 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 20080656 | 191520 | 20272176 | 20272176
|  | Hanger support & Accessories | 1 | 1 | lot | 8679223.8955 | 2603767.1687 | 11282991.0642 | 8679223.8955 | 2603767.1687 | 11282991.0642 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power supply & conduit | [6 empty] | 9739751.8951 | 5156209.5777 | 14895961.4728 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Switch 1way - 2gang 10A-220V | 1 | 1 | m | 46800 | 54500 | 101300 | 46800 | 54500 | 101300 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Contactor + Box | 4 | 4 | m | 900000 | 163500 | 1063500 | 3600000 | 654000 | 4254000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3C-2.5mm2 Cu/XLPE/PVC | 80 | 79.2 | m | 32518.74 | 7485.665 | 40004.405 | 2575484.208 | 592864.668 | 3168348.876 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2C-1.5mm2 Cu/PVC/PVC | 80 | 79.2 | m | 15443.88 | 5031.18 | 20475.06 | 1223155.296 | 398469.456 | 1621624.752 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 76 | 160 | m | 8773.9726 | 14594.0164 | 23367.989 | 1403835.6164 | 2335042.6259 | 3738878.2423 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC flexible conduct D20 | 3 | 3 | m | 3554.7229 | 5289.7059 | 8844.4288 | 10664.1688 | 15869.1176 | 26533.2864 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 3 | 3 | m | 8773.9726 | 14594.0164 | 23367.989 | 26321.9178 | 43782.0492 | 70103.967 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D16 | 72 | 72 | m | 6646.8692 | 13183.4282 | 19830.2974 | 478574.5808 | 949206.8287 | 1427781.4095 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 374916.1073 | 112474.8322 | 487390.9395 | 374916.1073 | 112474.8322 | 487390.9395 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 3. 130. |  | SMOKE EXHAUST SYSTEM | [6 empty] | 143640024.0078 | 24229831.2332 | 167869855.241 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | WEST SIDE | [6 empty] | 32042422.6672 | 2927603.7911 | 34970026.4583 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Equipment | [6 empty] | 26144496 | 990000 | 27134496 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Wall mounted smoke exhaust FAN - SEAF @11550m3/h, 100Pa, 1.5kW, 300oC in 2hrs | 2 | 2 | pcs | 13072248 | 495000 | 13567248 | 26144496 | 990000 | 27134496 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power supply & conduit | [6 empty] | 5897926.6672 | 1937603.7911 | 7835530.4583 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/Fr/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 70 | 66 | m | 60411.45 | 9350 | 69761.45 | 3987155.7 | 617100 | 4604255.7 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 63 | 60 | m | 8773.9726 | 14594.0164 | 23367.989 | 526438.3562 | 875640.9847 | 1402079.3409 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC flexible conduct D20 | 7 | 7 | m | 3554.7229 | 5289.7059 | 8844.4288 | 24883.0604 | 37027.9412 | 61911.0016 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 1359449.5506 | 407834.8652 | 1767284.4158 | 1359449.5506 | 407834.8652 | 1767284.4158 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | EAST SIDE | [6 empty] | 111597601.3406 | 21302227.4421 | 132899828.7827 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Equipment | [6 empty] | 23339970 | 2769284.1 | 26109254.1 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | AXIAL Smoke exhaust FAN - SEAF @7320m3/h, 180Pa, 1.25kW, 300oC in 2hrs | 3 | 3 | pcs | 7779990 | 923094.7 | 8703084.7 | 23339970 | 2769284.1 | 26109254.1 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger support & Sub materials | 1 | 1 | lot | 1051350 | 315405 | 1366755 | 1051350 | 315405 | 1366755 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Air grille, louver | [6 empty] | 23084640 | 840000 | 23924640 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Smoke Exhaust grille 1200x600 + OBD | 3 | 3 | pcs | 3281640 | 140000 | 3421640 | 9844920 | 420000 | 10264920 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Louver 1000x400 + IS | 3 | 3 | pcs | 4413240 | 140000 | 4553240 | 13239720 | 420000 | 13659720 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ductwork sheet | [6 empty] | 48893376.2182 | 12696041.9127 | 61589418.1309 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Rigid duct Z8, thickness 0.58mm | 47 | 42 | m2 | 236291.3455 | 106400 | 342691.3455 | 9924236.5091 | 4468800 | 14393036.5091 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Rockwool 50mmT | 36 | 36 | m2 | 408250 | 61600 | 469850 | 14697000 | 2217600 | 16914600 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fireproof paint for smoke duct | 33 | 33 | m2 | 432000 | 89600 | 521600 | 14256000 | 2956800 | 17212800 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Simili for fan | 6 | 6 | pcs | 90000 | 35000 | 125000 | 540000 | 210000 | 750000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger support & Sub materials | 1 | 1 | lot | 9476139.7091 | 2842841.9127 | 12318981.6218 | 9476139.7091 | 2842841.9127 | 12318981.6218 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power supply & conduit | [6 empty] | 15228265.1224 | 4681496.4294 | 19909761.5518 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/Fr/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 195 | 195 | m | 60411.45 | 9350 | 69761.45 | 11780232.75 | 1823250 | 13603482.75 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 176 | 150 | m | 8773.9726 | 14594.0164 | 23367.989 | 1316095.8904 | 2189102.4618 | 3505198.3522 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC flexible conduct D20 | 7 | 7 | m | 3554.7229 | 5289.7059 | 8844.4288 | 24883.0604 | 37027.9412 | 61911.0016 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 2107053.4216 | 632116.0265 | 2739169.448 | 2107053.4216 | 632116.0265 | 2739169.448 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. |  | Machine hook-up (Hall 3) | [6 empty] | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
5. |  | Scooter Garage | [6 empty] | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
6. |  | Canteen | [6 empty] | 435189667.08 | 72472708.1683 | 507662375.2483 | 0% | 0% | 0% | 0% |  |  | #REF! | 167332500 | 22275000 | 189607500 | 8704474.65 | 2062050.4625 | 10766525.1125 | 200374025.1125
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
6. 3. 60. |  | Ventilation System Overhead Fans | 1 | 1 | PSCH |  |  |  | 413174538.3791 | 66328606.8362 | 479503145.2154 | 0% | 0% | 0% | 0% |  |  | #REF! | 167332500 | 22275000 | 189607500 | 6686224.65 | 1797450.4625 | 8483675.1125 | 198091175.1125
|  | Overhead Propeller Fans, D=3m | 10 | 10 | pcs | 37185000 | 4950000 | 42135000 | 371850000 | 49500000 | 421350000 | 45% | 0% | 45% | 90% |  |  | #REF! | 167332500 | 22275000 | 189607500 | 0 | 0 | 0 | 189607500
|  | 3C-2.5mm2 Cu/XLPE/PVC | 250 | 245 | m | 32518.74 | 7485.665 | 40004.405 | 7967091.3 | 1833987.925 | 9801079.225 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 3983545.65 | 916993.9625 | 4900539.6125 | 4900539.6125
|  | Control Cable Cu/PVC 2cx1.5mm2 | 450 | 350 | m | 15443.88 | 5031.18 | 20475.06 | 5405358 | 1760913 | 7166271 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 2702679 | 880456.5 | 3583135.5 | 3583135.5
|  | PVC conduit D20 | 515 | 400 | m | 8773.9726 | 14594.0164 | 23367.989 | 3509589.0411 | 5837606.5647 | 9347195.6058 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC flexible conduct D20 | 20 | 15 | m | 3554.7229 | 5289.7059 | 8844.4288 | 53320.8438 | 79345.5882 | 132666.432 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger, support | 1 | 1 | lot | 10452505.369 | 3135751.6107 | 13588256.9797 | 10452505.369 | 3135751.6107 | 13588256.9797 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 13936673.8253 | 4181002.1476 | 18117675.9729 | 13936673.8253 | 4181002.1476 | 18117675.9729 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. 3. 70. |  | Ventilation System | 1 | 1 | PSCH |  |  |  | 22015128.7008 | 6144101.3321 | 28159230.0329 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 2018250 | 264600 | 2282850 | 2282850
|  | Exhaust air fan Q=100m3/h, 50Pa, type wall | 2 | 2 | pcs | 2324562 | 495000 | 2819562 | 4649124 | 990000 | 5639124 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Exhaust air fan Q=140m3/h, 50Pa, type wall | 1 | 1 | pcs | 2324562 | 495000 | 2819562 | 2324562 | 495000 | 2819562 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Exhaust air fan Q=180m3/h, 50Pa, type wall | 1 | 1 | pcs | 2324562 | 495000 | 2819562 | 2324562 | 495000 | 2819562 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Exhaust air fan Q=300m3/h, 50Pa, type wall | 1 | 1 | pcs | 2735040 | 495000 | 3230040 | 2735040 | 495000 | 3230040 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Louver 250x250 + IS | 5 | 5 | pcs | 897000 | 117600 | 1014600 | 4485000 | 588000 | 5073000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 2018250 | 264600 | 2282850 | 2282850
|  | Switch 1way - 1gang 10A-250V | 5 | 5 | pcs | 46800 | 54500 | 101300 | 234000 | 272500 | 506500 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3C-1.5mm2 Cu/XLPE/PVC | 111 | 109.25 | m | 22980.09 | 5743.9305 | 28724.0205 | 2510574.8325 | 627524.4071 | 3138099.2396 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC flexible conduct D20 | 8 | 11.5 | m | 3554.7229 | 5289.7059 | 8844.4288 | 40879.3136 | 60831.6176 | 101710.9312 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 119 | 109.25 | m | 8773.9726 | 14594.0164 | 23367.989 | 958556.5068 | 1594396.293 | 2552952.7998 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger, support, Accessories | 1 | 1 | lot | 1752830.0479 | 525849.0144 | 2278679.0623 | 1752830.0479 | 525849.0144 | 2278679.0623 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | V. AC SYSTEM | [8 empty] | 2228147077.7132 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 776027676.168 | 776027676.168
3. |  | Office, Social and Technical Areas (Hall 3) | [6 empty] | 1992902350.6879 | 211748078.3635 | 2204650429.0514 | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 735250252.5 | 32793465.168 | 768043717.668 | 768043717.668
3. 3. 70. |  | Air Conditioning | 1 | 1 | PSCH |  |  |  | 1992902350.6879 | 211748078.3635 | 2204650429.0514 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 735250252.5 | 32793465.168 | 768043717.668 | 768043717.668
|  | west side | [6 empty] | 1284913905.8615 | 131256535.4444 | 1416170441.3058 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 475358287.5 | 19563105.168 | 494921392.668 | 494921392.668
|  | Equipments | [6 empty] | 1094815450 | 55012677.04 | 1149828127.04 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 475358287.5 | 19563105.168 | 494921392.668 | 494921392.668
|  | Outdoor unit 56KW | 1 | 1 | pcs | 109143100 | 4434383.52 | 113577483.52 | 109143100 | 4434383.52 | 113577483.52 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 49114395 | 1995472.584 | 51109867.584 | 51109867.584
|  | Outdoor unit 50.4KW | 1 | 1 | pcs | 102932500 | 4434383.52 | 107366883.52 | 102932500 | 4434383.52 | 107366883.52 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 46319625 | 1995472.584 | 48315097.584 | 48315097.584
|  | Outdoor unit 40KW | 1 | 1 | pcs | 72590100 | 3920000 | 76510100 | 72590100 | 3920000 | 76510100 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 32665545 | 1764000 | 34429545 | 34429545
|  | Outdoor unit 33.6KW | 1 | 1 | pcs | 62381000 | 3920000 | 66301000 | 62381000 | 3920000 | 66301000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 28071450 | 1764000 | 29835450 | 29835450
|  | Outdoor unit 14KW | 1 | 1 | pcs | 30222170 | 840000 | 31062170 | 30222170 | 840000 | 31062170 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 13599976.5 | 378000 | 13977976.5 | 13977976.5
|  | Indoor unit cassette type, 9.0kW | 6 | 6 | pcs | 9845660 | 537600 | 10383260 | 59073960 | 3225600 | 62299560 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 26583282 | 1451520 | 28034802 | 28034802
|  | Indoor unit cassette type, 7.1kW | 11 | 11 | pcs | 9569780 | 537600 | 10107380 | 105267580 | 5913600 | 111181180 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 47370411 | 2661120 | 50031531 | 50031531
|  | Indoor unit cassette type, 6kW | 7 | 7 | pcs | 8741260 | 504000 | 9245260 | 61188820 | 3528000 | 64716820 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 27534969 | 1587600 | 29122569 | 29122569
|  | Indoor unit cassette type, 5.6kW | 4 | 4 | pcs | 8464170 | 504000 | 8968170 | 33856680 | 2016000 | 35872680 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 15235506 | 907200 | 16142706 | 16142706
|  | Indoor unit cassette type, 3.6kW | 1 | 1 | pcs | 7911200 | 504000 | 8415200 | 7911200 | 504000 | 8415200 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 3560040 | 226800 | 3786840 | 3786840
|  | Split Air conditioner, indoor unit wall type, cooling capacity 4.5kW | 4 | 4 | pcs | 12599730 | 621600 | 13221330 | 50398920 | 2486400 | 52885320 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 22679514 | 1118880 | 23798394 | 23798394
|  | Split Air conditioner, indoor unit wall type, cooling capacity 6.3kW | 2 | 2 | pcs | 16773020 | 733600 | 17506620 | 33546040 | 1467200 | 35013240 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 15095718 | 660240 | 15755958 | 15755958
|  | Split Air conditioner, indoor unit wall type, cooling capacity 7.1kW | 1 | 1 | pcs | 31227680 | 733600 | 31961280 | 31227680 | 733600 | 31961280 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 14052456 | 330120 | 14382576 | 14382576
|  | Dehumidifiers 1200m3/h | 6 | 6 | pcs | 19690000 | 168000 | 19858000 | 118140000 | 1008000 | 119148000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 53163000 | 453600 | 53616600 | 53616600
|  | Controller center for AC | 1 | 1 | pcs | 11532400 | 168000 | 11700400 | 11532400 | 168000 | 11700400 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 5189580 | 75600 | 5265180 | 5265180
|  | Remote wirring for AC | 36 | 36 | pcs | 1614800 | 50400 | 1665200 | 58132800 | 1814400 | 59947200 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 26159760 | 816480 | 26976240 | 26976240
|  | Controller for AC Split (IT Room, UPS room) | 2 | 2 | pcs | 873400 | 140000 | 1013400 | 1746800 | 280000 | 2026800 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 786060 | 126000 | 912060 | 912060
|  | DB controller | 1 | 1 | pcs | 13200000 | 280000 | 13480000 | 13200000 | 280000 | 13480000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 5940000 | 126000 | 6066000 | 6066000
|  | Gas splitter | 16 | 44 | pcs | 1815000 | 0 | 1815000 | 79860000 | 0 | 79860000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 35937000 | 0 | 35937000 | 35937000
|  | Concrete base for outdoor unit | 5 | 5 | pcs | 1300000 | 500000 | 1800000 | 6500000 | 2500000 | 9000000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 2925000 | 1125000 | 4050000 | 4050000
|  | Extra refrigerant charge R410a or R32 | 1 | 1 | lot | 7500000 | 0 | 7500000 | 7500000 | 0 | 7500000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 3375000 | 0 | 3375000 | 3375000
|  | Hanger support & Sub materials | 1 | 1 | lot | 38463700 | 11539110 | 50002810 | 38463700 | 11539110 | 50002810 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Copper pipe | [6 empty] | 67284685.7759 | 24357916.6293 | 91642602.4052 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø6.4mm-0.81mmT | 78 | 112.7 | m | 38160 | 22400 | 60560 | 4300632 | 2524480 | 6825112 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø9.5mm-0.81mmT | 249 | 203.55 | m | 60000 | 23520 | 83520 | 12213000 | 4787496 | 17000496 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø12.7mm-0.81mmT | 90 | 119.6 | m | 81840 | 28000 | 109840 | 9788064 | 3348800 | 13136864 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø15.9mm-0.81mmT | 262 | 210.45 | m | 103760 | 38808 | 142568 | 21836292 | 8167143.6 | 30003435.6 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø19.1mm-0.81mmT | 0 | 0 | m | 129600 | 42560 | 172160 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø22.2mm-0.81mmT | 18 | 27.6 | m | 147310.3448 | 49392 | 196702.3448 | 4065765.5172 | 1363219.2 | 5428984.7172 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø28.6mm-1.0mmT | 54 | 52.9 | m | 234206.8966 | 63504 | 297710.8966 | 12389544.8276 | 3359361.6 | 15748906.4276 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger support & Accessories | 1 | 1 | lot | 2691387.431 | 807416.2293 | 3498803.6603 | 2691387.431 | 807416.2293 | 3498803.6603 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Insulation copper pipe | [6 empty] | 14380586.125 | 5959615.4335 | 20340201.5585 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø6.4mm-15mmT | 78 | 112.7 | m | 15358.8 | 5600 | 20958.8 | 1730936.76 | 631120 | 2362056.76 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø9.5mm-15mmT | 249 | 203.55 | m | 16754.4 | 5644.8 | 22399.2 | 3410358.12 | 1148999.04 | 4559357.16 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø12.7mm-15mmT | 90 | 119.6 | m | 17871.6 | 7728 | 25599.6 | 2137443.36 | 924268.8 | 3061712.16 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø15.9mm-15mmT | 262 | 210.45 | m | 20664 | 9172.8 | 29836.8 | 4348738.8 | 1930415.76 | 6279154.56 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø19.1mm-15mmT | 0 | 0 | m | 23176.8 | 101595.2 | 124772 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø22.2mm-15mmT | 18 | 27.6 | m | 24852 | 11995.2 | 36847.2 | 685915.2 | 331067.52 | 1016982.72 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø28.6mm-15mmT | 54 | 52.9 | m | 28203.6 | 15523.2 | 43726.8 | 1491970.44 | 821177.28 | 2313147.72 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 575223.445 | 172567.0335 | 747790.4785 | 575223.445 | 172567.0335 | 747790.4785 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Condensate pipe | [6 empty] | 3756725.28 | 3113650.848 | 6870376.128 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | uPVC-Ø27mm-PN12 | 124 | 127.6 | m | 8236.8 | 11743.2 | 19980 | 1051015.68 | 1498432.32 | 2549448 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | uPVC-Ø34mm-PN12 | 59 | 72.6 | m | 16286.4 | 12639.2 | 28925.6 | 1182392.64 | 917605.92 | 2099998.56 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | uPVC-Ø42mm-PN12 | 33 | 29.7 | m | 21528 | 14560 | 36088 | 639381.6 | 432432 | 1071813.6 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fitting for UpVC | 1 | 1 | lot | 662951.52 | 198885.456 | 861836.976 | 662951.52 | 198885.456 | 861836.976 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger support & Accessories | 1 | 1 | lot | 220983.84 | 66295.152 | 287278.992 | 220983.84 | 66295.152 | 287278.992 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Insulation condensate pipe | 0 | 0 |  |  |  |  | 3118303.375 | 3148490.6805 | 6266794.0555 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø27mm-10mmT | 124 | 127.6 | m | 11169.6 | 11743.2 | 22912.8 | 1425240.96 | 1498432.32 | 2923673.28 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø34mm-10mmT | 59 | 72.6 | m | 14520 | 15523.2 | 30043.2 | 1054152 | 1126984.32 | 2181136.32 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø42mm-10mmT | 33 | 29.7 | m | 17312.4 | 16352 | 33664.4 | 514178.28 | 485654.4 | 999832.68 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 124732.135 | 37419.6405 | 162151.7755 | 124732.135 | 37419.6405 | 162151.7755 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power supply & conduit | [6 empty] | 101558155.3056 | 39664184.8131 | 141222340.1186 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Double socket 1P-16A-250V | 6 | 6 | pcs | 150480 | 54500 | 204980 | 902880 | 327000 | 1229880 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 4x1Cx4mm2+E4mm2 | 200 | 174.9 | m | 72299.4 | 17189.865 | 89489.265 | 12645165.06 | 3006507.3885 | 15651672.4485 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3Cx-2.5mm2Cu/XLPE/PVC | 260 | 177.1 | m | 32518.74 | 7485.665 | 40004.405 | 5759068.854 | 1325711.2715 | 7084780.1255 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3Cx-1.5mm2Cu/XLPE/PVC | 450 | 338.8 | m | 22980.09 | 5743.9305 | 28724.0205 | 7785654.492 | 1946043.6534 | 9731698.1454 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4Cx-1.5mm2Cu/PVC/PVC | 105 | 111.1 | m | 25928.4 | 7485.665 | 33414.065 | 2880645.24 | 831657.3815 | 3712302.6215 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2Cx-1.5mm2Cu/PVC/PVC | 495 | 332.2 | m | 15443.88 | 5031.18 | 20475.06 | 5130456.936 | 1671357.996 | 6801814.932 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 18 core AWG 1 pair | 540 | 607.2 | m | 21976.8 | 3920 | 25896.8 | 13344312.96 | 2380224 | 15724536.96 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 104 | 660 | m | 8773.9726 | 14594.0164 | 23367.989 | 5790821.9178 | 9632050.8318 | 15422872.7496 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D16 | 378 | 935 | m | 6646.8692 | 13183.4282 | 19830.2974 | 6214822.6815 | 12326505.345 | 18541328.0265 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D16 | 891 | 0 | m | 6646.8692 | 13183.4282 | 19830.2974 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 143 | 0 | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D25 | 140 | 154 | m | 12762.0356 | 15805 | 28567.0356 | 1965353.4849 | 2433970 | 4399323.4849 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC flexible conduit D20 | 39 | 55 | m | 3554.7229 | 5289.7059 | 8844.4288 | 195509.7606 | 290933.8235 | 486443.5841 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC flexible conduit D20 | 22 | 0 | m | 3554.7229 | 5289.7059 | 8844.4288 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable tray 200x100x2.0mm | 42 | 45 | m | 776880 | 51045.8655 | 827925.8655 | 34959600 | 2297063.9462 | 37256663.9462 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 3983863.9187 | 1195159.1756 | 5179023.0944 | 3983863.9187 | 1195159.1756 | 5179023.0944 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | East side | [6 empty] | 707988444.8264 | 80491542.9191 | 788479987.7455 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 259891965 | 13230360 | 273122325 | 273122325
|  | Equipments | [6 empty] | 606357980 | 35796884 | 642154864 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 259891965 | 13230360 | 273122325 | 273122325
|  | Outdoor unit 33.6KW | 2 | 2 | pcs | 62381000 | 3920000 | 66301000 | 124762000 | 7840000 | 132602000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 56142900 | 3528000 | 59670900 | 59670900
|  | Outdoor unit 22.4KW | 1 | 1 | pcs | 48310460 | 3304000 | 51614460 | 48310460 | 3304000 | 51614460 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 21739707 | 1486800 | 23226507 | 23226507
|  | Outdoor unit 14KW | 1 | 1 | pcs | 30222170 | 840000 | 31062170 | 30222170 | 840000 | 31062170 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 13599976.5 | 378000 | 13977976.5 | 13977976.5
|  | Indoor unit cassette type, 9.0kW | 6 | 6 | pcs | 9845660 | 537600 | 10383260 | 59073960 | 3225600 | 62299560 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 26583282 | 1451520 | 28034802 | 28034802
|  | Indoor unit cassette type, 7.1kW | 7 | 7 | pcs | 9569780 | 537600 | 10107380 | 66988460 | 3763200 | 70751660 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 30144807 | 1693440 | 31838247 | 31838247
|  | Indoor unit cassette type, 6kW | 1 | 1 | pcs | 8741260 | 504000 | 9245260 | 8741260 | 504000 | 9245260 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 3933567 | 226800 | 4160367 | 4160367
|  | Split Air conditioner, indoor unit wall type, cooling capacity 4.5kW | 2 | 2 | pcs | 12599730 | 621600 | 13221330 | 25199460 | 1243200 | 26442660 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 11339757 | 559440 | 11899197 | 11899197
|  | Split Air conditioner, indoor unit wall type, cooling capacity 7.1kW | 2 | 2 | pcs | 31227680 | 733600 | 31961280 | 62455360 | 1467200 | 63922560 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 28104912 | 660240 | 28765152 | 28765152
|  | Split Air conditioner, indoor unit cassette type, cooling capacity 5.2kW | 1 | 1 | pcs | 21620170 | 733600 | 22353770 | 21620170 | 733600 | 22353770 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 9729076.5 | 330120 | 10059196.5 | 10059196.5
|  | Dehumidifiers 1500m3/h | 3 | 3 | pcs | 19690000 | 168000 | 19858000 | 59070000 | 504000 | 59574000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 26581500 | 226800 | 26808300 | 26808300
|  | Remote wirring for AC | 19 | 19 | pcs | 1614800 | 168000 | 1782800 | 30681200 | 3192000 | 33873200 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 13806540 | 1436400 | 15242940 | 15242940
|  | Controller for AC | 2 | 10 | pcs | 873400 | 50400 | 923800 | 8734000 | 504000 | 9238000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 3930300 | 226800 | 4157100 | 4157100
|  | DB controller | 1 | 1 | pcs | 13200000 | 280000 | 13480000 | 13200000 | 280000 | 13480000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 5940000 | 126000 | 6066000 | 6066000
|  | Gas splitter | 5 | 8 | pcs | 1659900 | 0 | 1659900 | 13279200 | 0 | 13279200 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 5975640 | 0 | 5975640 | 5975640
|  | Concrete base for outdoor unit | 4 | 4 | pcs | 1300000 | 500000 | 1800000 | 5200000 | 2000000 | 7200000 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 2340000 | 900000 | 3240000 | 3240000
|  | Extra refrigerant charge R410a or R32 | 1 | 1 | lot | 7500000 | 0 | 7500000 | 7500000 | 0 | 7500000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger support & Sub materials | 1 | 1 | lot | 21320280 | 6396084 | 27716364 | 21320280 | 6396084 | 27716364 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Copper pipe | 0 | 0 |  |  |  |  | 28355645.2586 | 9993875.3431 | 38349520.6017 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø6.4mm-0.81mmT | 18 | 19.95 | m | 38160 | 22400 | 60560 | 761292 | 446880 | 1208172 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø9.5mm-0.81mmT | 86 | 94.5 | m | 60000 | 23520 | 83520 | 5670000 | 2222640 | 7892640 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø12.7mm-0.81mmT | 28 | 30.45 | m | 81840 | 28000 | 109840 | 2492028 | 852600 | 3344628 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø15.9mm-0.81mmT | 92 | 101.85 | m | 103760 | 38808 | 142568 | 10567956 | 3952594.8 | 14520550.8 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø19.1mm-0.81mmT | 3 | 3.15 | m | 129600 | 42560 | 172160 | 408240 | 134064 | 542304 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø22.2mm-0.81mmT | 6 | 6.3 | m | 147310.3448 | 49392 | 196702.3448 | 928055.1724 | 311169.6 | 1239224.7724 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø28.6mm-1.0mmT | 25 | 27.3 | m | 234206.8966 | 63504 | 297710.8966 | 6393848.2759 | 1733659.2 | 8127507.4759 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger support & Sub materials | 1 | 1 | lot | 1134225.8103 | 340267.7431 | 1474493.5534 | 1134225.8103 | 340267.7431 | 1474493.5534 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Insulation copper pipe | 0 | 0 |  |  |  |  | 5768802.375 | 2703324.5085 | 8472126.8835 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø6.4mm-15mmT | 18 | 19.95 | m | 15358.8 | 5600 | 20958.8 | 306408.06 | 111720 | 418128.06 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø9.5mm-15mmT | 86 | 94.5 | m | 16754.4 | 5644.8 | 22399.2 | 1583290.8 | 533433.6 | 2116724.4 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø12.7mm-15mmT | 28 | 30.45 | m | 17871.6 | 7728 | 25599.6 | 544190.22 | 235317.6 | 779507.82 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø15.9mm-15mmT | 92 | 101.85 | m | 20664 | 9172.8 | 29836.8 | 2104628.4 | 934249.68 | 3038878.08 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø19.1mm-15mmT | 3 | 3.15 | m | 23176.8 | 101595.2 | 124772 | 73006.92 | 320024.88 | 393031.8 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø22.2mm-15mmT | 6 | 6.3 | m | 24852 | 11995.2 | 36847.2 | 156567.6 | 75569.76 | 232137.36 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø28.6mm-15mmT | 25 | 27.3 | m | 28203.6 | 15523.2 | 43726.8 | 769958.28 | 423783.36 | 1193741.64 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 230752.095 | 69225.6285 | 299977.7235 | 230752.095 | 69225.6285 | 299977.7235 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Condensate pipe | 0 | 0 |  |  |  |  | 4058656.35 | 2146658.409 | 6205314.759 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | uPVC-Ø27mm-PN12 | 46 | 50.4 | m | 8236.8 | 11743.2 | 19980 | 415134.72 | 591857.28 | 1006992 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | uPVC-Ø34mm-PN12 | 38 | 42 | m | 16286.4 | 12639.2 | 28925.6 | 684028.8 | 530846.4 | 1214875.2 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | uPVC-Ø42mm-PN12 | 15 | 16.8 | m | 21528 | 14560 | 36088 | 361670.4 | 244608 | 606278.4 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fitting for UpVC | 1 | 1 | lot | 1953259.56 | 585977.868 | 2539237.428 | 1953259.56 | 585977.868 | 2539237.428 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger support & Sub materials | 1 | 1 | lot | 644562.87 | 193368.861 | 837931.731 | 644562.87 | 193368.861 | 837931.731 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Insulation condensate pipe | 0 | 0 |  |  |  |  | 1524621 | 1536840.732 | 3061461.732 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø27mm-10mmT | 46 | 50.4 | m | 11169.6 | 11743.2 | 22912.8 | 562947.84 | 591857.28 | 1154805.12 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø34mm-10mmT | 38 | 42 | m | 14520 | 15523.2 | 30043.2 | 609840 | 651974.4 | 1261814.4 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø42mm-10mmT | 15 | 16.8 | m | 17312.4 | 16352 | 33664.4 | 290848.32 | 274713.6 | 565561.92 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 60984.84 | 18295.452 | 79280.292 | 60984.84 | 18295.452 | 79280.292 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power supply & conduit | 0 | 0 |  |  |  |  | 61922739.8428 | 28313959.9265 | 90236699.7693 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Double socket 1P-16A-250V | 3 | 3 | pcs | 150480 | 54500 | 204980 | 451440 | 163500 | 614940 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 4x1Cx4mm2+E4mm2 | 135 | 168 | m | 72299.4 | 17189.865 | 89489.265 | 12146299.2 | 2887897.32 | 15034196.52 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3Cx-2.5mm2Cu/XLPE/PVC | 155 | 43.05 | m | 32518.74 | 7485.665 | 40004.405 | 1399931.757 | 322257.8783 | 1722189.6353 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3Cx-1.5mm2Cu/XLPE/PVC | 219 | 260.4 | m | 22980.09 | 5743.9305 | 28724.0205 | 5984015.436 | 1495719.5022 | 7479734.9382 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4Cx-1.5mm2 Cu/PVC/PVC | 75 | 70.35 | m | 25928.4 | 7485.665 | 33414.065 | 1824062.94 | 526616.5328 | 2350679.4728 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2Cx-1.5mm2 Cu/PVC/PVC | 546 | 176.4 | m | 15443.88 | 5031.18 | 20475.06 | 2724300.432 | 887500.152 | 3611800.584 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 18 core AWG 1 pair | 253 | 396.9 | m | 21976.8 | 3920 | 25896.8 | 8722591.92 | 1555848 | 10278439.92 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 62 | 336 | m | 8773.9726 | 14594.0164 | 23367.989 | 2948054.7945 | 4903589.5144 | 7851644.3089 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D16 | 327 | 840 | m | 6646.8692 | 13183.4282 | 19830.2974 | 5583370.1096 | 11074079.6682 | 16657449.7778 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D16 | 1023 | 0 | m | 6646.8692 | 13183.4282 | 19830.2974 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 86 | 0 | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D25 | 99 | 160 | m | 12762.0356 | 15805 | 28567.0356 | 2041925.6986 | 2528800 | 4570725.6986 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC flexible conduit D20 | 21 | 31.5 | m | 3554.7229 | 5289.7059 | 8844.4288 | 111973.772 | 166625.7353 | 278599.5073 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC flexible conduit D20 | 11 | 11 | m | 3554.7229 | 5289.7059 | 8844.4288 | 39101.9521 | 58186.7647 | 97288.7168 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable tray 200x100x2.0mm | 19 | 20 | m | 776880 | 51045.8655 | 827925.8655 | 15537600 | 1020917.3094 | 16558517.3094 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 2408071.831 | 722421.5493 | 3130493.3802 | 2408071.831 | 722421.5493 | 3130493.3802 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. |  | Machine hook-up (Hall 3) | [8 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
5. |  | Scooter Garage | [8 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
6. |  | Canteen | [6 empty] | 21057187.7199 | 2439460.942 | 23496648.6619 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 7681558.5 | 302400 | 7983958.5 | 7983958.5
6. 3. 50. |  | Air Conditioning | 1 | 1 | PSCH |  |  |  | 21057187.7199 | 2439460.942 | 23496648.6619 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 7681558.5 | 302400 | 7983958.5 | 7983958.5
|  | Split Air conditioner, indoor unit wall type, cooling capacity 2.5kW | 1 | 1 | pcs | 15455330 | 621600 | 16076930 | 15455330 | 621600 | 16076930 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 6954898.5 | 279720 | 7234618.5 | 7234618.5
|  | Remote wirring for AC | 1 | 1 | pcs | 1614800 | 50400 | 1665200 | 1614800 | 50400 | 1665200 | 0% | 45% | 45% | 90% |  |  | #REF! | 0 | 0 | 0 | 726660 | 22680 | 749340 | 749340
|  | Hanger support & Sub materials | 1 | 1 | lot | 775915 | 232774.5 | 1008689.5 | 775915 | 232774.5 | 1008689.5 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Copper pipe | 0 | 0 |  |  |  |  | 1022500 | 471470 | 1493970 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø6.4mm-0.81mmT | 10 | 10 | m | 38160 | 22400 | 60560 | 381600 | 224000 | 605600 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø9.5mm-0.81mmT | 10 | 10 | m | 60000 | 23520 | 83520 | 600000 | 235200 | 835200 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger support & Sub materials | 1 | 1 | lot | 40900 | 12270 | 53170 | 40900 | 12270 | 53170 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Insulation copper pipe | 0 | 0 |  |  |  |  | 334512.5 | 116462.15 | 450974.65 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø6.4mm-15mmT | 10 | 10 | m | 15358.8 | 5600 | 20958.8 | 153588 | 56000 | 209588 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø9.5mm-15mmT | 10 | 10 | m | 16754.4 | 5644.8 | 22399.2 | 167544 | 56448 | 223992 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 13380.5 | 4014.15 | 17394.65 | 13380.5 | 4014.15 | 17394.65 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Condensate pipe | 0 | 0 |  |  |  |  | 107712 | 125035.2 | 232747.2 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | uPVC-Ø27mm-PN12 | 10 | 10 | m | 8236.8 | 11743.2 | 19980 | 82368 | 117432 | 199800 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fitting for UpVC | 1 | 1 | lot | 19008 | 5702.4 | 24710.4 | 19008 | 5702.4 | 24710.4 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger support & Sub materials | 1 | 1 | lot | 6336 | 1900.8 | 8236.8 | 6336 | 1900.8 | 8236.8 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Insulation condensate pipe | 0 | 0 |  |  |  |  | 116350 | 118828.2 | 235178.2 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Ø27mm-10mmT | 10 | 10 | m | 11169.6 | 11743.2 | 22912.8 | 111696 | 117432 | 229128 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 4654 | 1396.2 | 6050.2 | 4654 | 1396.2 | 6050.2 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable power supply & conduit | 0 | 0 |  |  |  |  | 1630068.2199 | 702890.892 | 2332959.1119 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3Cx-2.5mm2Cu/XLPE/PVC | 15 | 15 | m | 32518.74 | 7485.665 | 40004.405 | 487781.1 | 112284.975 | 600066.075 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3Cx-1.5mm2Cu/XLPE/PVC | 15 | 15 | m | 22980.09 | 5743.9305 | 28724.0205 | 344701.35 | 86158.9575 | 430860.3075 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4Cx-1.5mm2 Cu/PVC/PVC | 10 | 10 | m | 25928.4 | 7485.665 | 33414.065 | 259284 | 74856.65 | 334140.65 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 18 core AWG 1 pair | 10 | 10 | m | 26400 | 3360 | 29760 | 264000 | 33600 | 297600 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 15 | 15 | m | 8773.9726 | 14594.0164 | 23367.989 | 131609.589 | 218910.2462 | 350519.8352 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D16 | 12 | 12 | m | 6646.8692 | 13183.4282 | 19830.2974 | 79762.4301 | 158201.1381 | 237963.5683 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 62929.7507 | 18878.9252 | 81808.6759 | 62929.7507 | 18878.9252 | 81808.6759 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | VI. PLUMBING | [8 empty] | 2878365804.8714 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 49864427.5067 |  |  | 113063871.4337 | 162928298.9405
3. |  | Office, Social and Technical Areas (Hall 3) | [6 empty] | 2135112119.4552 | 210437879.8945 | 2345549999.3497 | 0 | 0% | 0% | 0% |  |  | #REF! | 27780455.3129 | 22083972.1939 | 49864427.5067 | 67444795.5364 | 12105298.6329 | 79550094.1694 | 129414521.6761
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
3. 3. |  | Mechanical Engineering | [6 empty] | 2135112119.4552 | 210437879.8945 | 2345549999.3497 | 0% | 0% | 0% | 0% |  |  | #REF! | 27780455.3129 | 22083972.1939 | 49864427.5067 | 67444795.5364 | 12105298.6329 | 79550094.1694 | 129414521.6761
3. 3. 10. |  | Waste Water System | 1 | 1 | PSCH |  |  |  | 195924697.8575 | 71484007.4162 | 267408705.2737 | 0% | 0% | 0% | 0% |  |  | #REF! | 27780455.3129 | 22083972.1939 | 49864427.5067 | 16494815.0564 | 8813298.3129 | 25308113.3694 | 75172540.8761
|  | West side | 0 | 0 | m | 0 | 0 | 0 | 79936135.2 | 44199519.52 | 124135654.72 | 0% | 0% | 0% | 0% |  |  | #REF! | 18290810.88 | 13583367.656 | 31874178.536 | 11755314 | 5964396.044 | 17719710.044 | 49593888.58
|  | uPVC pipe D200 - PN6 | 35 | 40 | m | 356616 | 71941.408 | 428557.408 | 14264640 | 2877656.32 | 17142296.32 | 0% | 15% | 15% |  |  |  | #REF! | 0 | 0 | 0 | 2139696 | 431648.448 | 2571344.448 | 2571344.448
|  | uPVC pipe D168 - PN6 | 40 | 65 | m | 179337.6 | 57600.928 | 236938.528 | 11656944 | 3744060.32 | 15401004.32 | 30% | 15% | 45% |  |  |  | #REF! | 3497083.2 | 1123218.096 | 4620301.296 | 1748541.6 | 561609.048 | 2310150.648 | 6930451.944
|  | uPVC pipe D114 - PN6 | 115 | 156 | m | 93225.6 | 42504 | 135729.6 | 14543193.6 | 6630624 | 21173817.6 | 30% | 15% | 45% |  |  |  | #REF! | 4362958.08 | 1989187.2 | 6352145.28 | 2181479.04 | 994593.6 | 3176072.64 | 9528217.92
|  | uPVC pipe D90 - PN6 | 185 | 209 | m | 65145.6 | 36064 | 101209.6 | 13615430.4 | 7537376 | 21152806.4 | 30% | 15% | 45% |  |  |  | #REF! | 4084629.12 | 2261212.8 | 6345841.92 | 2042314.56 | 1130606.4 | 3172920.96 | 9518762.88
|  | uPVC pipe D60 - PN6 | 153 | 187 | m | 29858.4 | 24884.16 | 54742.56 | 5583520.8 | 4653337.92 | 10236858.72 | 30% | 15% | 45% |  |  |  | #REF! | 1675056.24 | 1396001.376 | 3071057.616 | 837528.12 | 698000.688 | 1535528.808 | 4606586.424
|  | uPVC pipe D42 - PN6 | 65 | 68 | m | 21528 | 17851.68 | 39379.68 | 1463904 | 1213914.24 | 2677818.24 | 30% | 15% | 45% |  |  |  | #REF! | 439171.2 | 364174.272 | 803345.472 | 219585.6 | 182087.136 | 401672.736 | 1205018.208
|  | uPVC Fitting | 1 | 1 | lot | 14106376.8 | 4231913.04 | 18338289.84 | 14106376.8 | 4231913.04 | 18338289.84 | 30% | 15% | 45% |  |  |  | #REF! | 4231913.04 | 1269573.912 | 5501486.952 | 2115956.52 | 634786.956 | 2750743.476 | 8252230.428
|  | Excavation & backfill | 37 | 37 | m3 | 0 | 200000 | 200000 | 0 | 7400000 | 7400000 | 70% | 10% | 80% |  |  |  | #REF! | 0 | 5180000 | 5180000 | 0 | 740000 | 740000 | 5920000
|  | Connect to existing manhole | 1 | 1 | lot | 0 | 3000000 | 3000000 | 0 | 3000000 | 3000000 | 0% | 10% | 10% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 300000 | 300000 | 300000
|  | Connect to existing pipe | 1 | 1 | lot | 0 | 1500000 | 1500000 | 0 | 1500000 | 1500000 | 0% | 10% | 10% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 150000 | 150000 | 150000
|  | Accessories | 1 | 1 | lot | 4702125.6 | 1410637.68 | 6112763.28 | 4702125.6 | 1410637.68 | 6112763.28 | 0% | 10% | 10% |  |  |  | #REF! | 0 | 0 | 0 | 470212.56 | 141063.768 | 611276.328 | 611276.328
|  | East side | 0 |  | m |  |  |  | 115988562.6575 | 27284487.8962 | 143273050.5537 | 0% | 0% | 0% |  |  |  | #REF! | 9489644.4329 | 8500604.5379 | 17990248.9707 | 4739501.0564 | 2848902.2689 | 7588403.3254 | 25578652.2961
|  | Submersible Pump Q=5M3/H, H=8MH20 | 2 | 2 | pcs | 19613000 | 616000 | 20229000 | 39226000 | 1232000 | 40458000 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Auto coupling Rp2' | 2 | 2 | pcs | 4488000 | 0 | 4488000 | 8976000 | 0 | 8976000 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Slider + chain | 2 | 2 | pcs | 3850000 | 0 | 3850000 | 7700000 | 0 | 7700000 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Float for submersible pump | 2 | 2 | pcs | 3850000 | 168000 | 4018000 | 7700000 | 336000 | 8036000 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Electrical control panel for submeriable pump | 1 | 1 | pcs | 13420000 | 840000 | 14260000 | 13420000 | 840000 | 14260000 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Check valve DN50 | 1 | 1 | pcs | 174200 | 61600 | 235800 | 174200 | 61600 | 235800 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gate valve DN50 | 1 | 1 | pcs | 128700 | 61600 | 190300 | 128700 | 61600 | 190300 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 30 | 30 | m | 40467 | 9350 | 49817 | 1214010 | 280500 | 1494510 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 30 | 30 | m | 8773.9726 | 14594.0164 | 23367.989 | 263219.1781 | 437820.4924 | 701039.6704 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | uPVC pipe D168 - PN6 | 29 | 35 | m | 179337.6 | 57600.928 | 236938.528 | 6276816 | 2016032.48 | 8292848.48 | 30% | 15% | 45% |  |  |  | #REF! | 1883044.8 | 604809.744 | 2487854.544 | 941522.4 | 302404.872 | 1243927.272 | 3731781.816
|  | uPVC pipe D114 - PN6 | 39 | 45 | m | 93225.6 | 42504 | 135729.6 | 4195152 | 1912680 | 6107832 | 30% | 15% | 45% |  |  |  | #REF! | 1258545.6 | 573804 | 1832349.6 | 629272.8 | 286902 | 916174.8 | 2748524.4
|  | uPVC pipe D90 - PN6 | 149 | 167 | m | 65145.6 | 36064 | 101209.6 | 10879315.2 | 6022688 | 16902003.2 | 30% | 15% | 45% |  |  |  | #REF! | 3263794.56 | 1806806.4 | 5070600.96 | 1631897.28 | 903403.2 | 2535300.48 | 7605901.44
|  | uPVC pipe D60 - PN6 | 101 | 124 | m | 29858.4 | 24884.16 | 54742.56 | 3702441.6 | 3085635.84 | 6788077.44 | 30% | 15% | 45% |  |  |  | #REF! | 1110732.48 | 925690.752 | 2036423.232 | 555366.24 | 462845.376 | 1018211.616 | 3054634.848
|  | uPVC pipe D42 - PN6 | 18 | 23 | m | 21528 | 17851.68 | 39379.68 | 495144 | 410588.64 | 905732.64 | 30% | 15% | 45% |  |  |  | #REF! | 148543.2 | 123176.592 | 271719.792 | 74271.6 | 61588.296 | 135859.896 | 407579.688
|  | Pipe clean out D60 | 1 | 1 | pcs | 106423.2 | 28000 | 134423.2 | 106423.2 | 28000 | 134423.2 | 30% | 10% | 40% |  |  |  | #REF! | 31926.96 | 8400 | 40326.96 | 10642.32 | 2800 | 13442.32 | 53769.28
|  | uPVC Fitting | 1 | 1 | lot | 5976856.1096 | 1793056.8329 | 7769912.9425 | 5976856.1096 | 1793056.8329 | 7769912.9425 | 30% | 15% | 45% |  |  |  | #REF! | 1793056.8329 | 537917.0499 | 2330973.8827 | 896528.4164 | 268958.5249 | 1165486.9414 | 3496460.8241
|  | Excavation & backfill | 21 | 28 | m3 | 0 | 200000 | 200000 | 0 | 5600000 | 5600000 | 70% | 10% | 80% |  |  |  | #REF! | 0 | 3920000 | 3920000 | 0 | 560000 | 560000 | 4480000
|  | Connect to existing manhole | 1 | 1 | lot | 0 | 1500000 | 1500000 | 0 | 1500000 | 1500000 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 5554285.3699 | 1666285.611 | 7220570.9808 | 5554285.3699 | 1666285.611 | 7220570.9808 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 3. 20. |  | Service Water System | 1 | 1 | PSCH |  |  |  | 350026408.4568 | 59395813.3191 | 409422221.7759 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 50949980.48 | 3292000.32 | 54241980.8 | 54241980.8
|  | West side | [6 empty] | 205749865.9577 | 34591531.4404 | 240341397.398 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 32768188.48 | 2093299.52 | 34861488 | 34861488
|  | Pump room | [6 empty] | 149717065.9577 | 8068928.1916 | 157785994.1492 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 30745000 | 728000 | 31473000 | 31473000
|  | Booster pump Q=9.3 m3, H=30m | 2 | 2 | set | 30745000 | 728000 | 31473000 | 61490000 | 1456000 | 62946000 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 30745000 | 728000 | 31473000 | 31473000
|  | Electrical control panel for booster pump | 1 | 1 | set | 44440000 | 1400000 | 45840000 | 44440000 | 1400000 | 45840000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pressure tank 100l | 1 | 1 | pcs | 7915200 | 168000 | 8083200 | 7915200 | 168000 | 8083200 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Storage tank 3m3 | 1 | 1 | pcs | 9970909.0909 | 322000 | 10292909.0909 | 9970909.0909 | 322000 | 10292909.0909 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Filter | 1 | 1 | set | 10800000 | 225400 | 11025400 | 10800000 | 225400 | 11025400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Water metter DN40 | 1 | 1 | pcs | 2154000 | 75152 | 2229152 | 2154000 | 75152 | 2229152 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/PVC/PVC 2Cx1.5mm2 | 20 | 25 | m | 15443.88 | 5031.18 | 20475.06 | 386097 | 125779.5 | 511876.5 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 20 | 25 | m | 40467 | 9350 | 49817 | 1011675 | 233750 | 1245425 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 40 | 50 | m | 8773.9726 | 14594.0164 | 23367.989 | 438698.6301 | 729700.8206 | 1168399.4507 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger + Support | 1 | 1 | lot | 6172492.3537 | 1851747.7061 | 8024240.0598 | 6172492.3537 | 1851747.7061 | 8024240.0598 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 4937993.8829 | 1481398.1649 | 6419392.0478 | 4937993.8829 | 1481398.1649 | 6419392.0478 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Valve | [6 empty] | 31053568.8 | 3110074.6696 | 34163643.4696 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pressure Gauges | 1 | 1 | pcs | 1008000 | 49588 | 1057588 | 1008000 | 49588 | 1057588 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flexible DN40 | 4 | 4 | pcs | 825600 | 75152 | 900752 | 3302400 | 300608 | 3603008 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Float level indicator | 1 | 1 | pcs | 4200000 | 168000 | 4368000 | 4200000 | 168000 | 4368000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Float valve DN40 | 1 | 1 | pcs | 2809200 | 75152 | 2884352 | 2809200 | 75152 | 2884352 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Y-Strainer DN40 | 2 | 2 | pcs | 726000 | 75152 | 801152 | 1452000 | 150304 | 1602304 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Safety valve DN40 | 3 | 3 | pcs | 3133200 | 75152 | 3208352 | 9399600 | 225456 | 9625056 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Check valve DN40 | 3 | 3 | pcs | 867600 | 75152 | 942752 | 2602800 | 225456 | 2828256 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gate valve DN40 | 4 | 4 | pcs | 726000 | 75152 | 801152 | 2904000 | 300608 | 3204608 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gate valve DN25 | 1 | 1 | pcs | 322800 | 50880.368 | 373680.368 | 322800 | 50880.368 | 373680.368 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gate valve DN32 PPR | 5 | 7 | pcs | 99122.4 | 58877.3007 | 157999.7007 | 693856.8 | 412141.105 | 1105997.905 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gate valve DN25 PPR | 3 | 2 | pcs | 85924.8 | 49415.0989 | 135339.8989 | 171849.6 | 98830.1978 | 270679.7978 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gate valve DN20 PPR | 10 | 15 | pcs | 63367.2 | 45472.3119 | 108839.5119 | 950508 | 682084.6788 | 1632592.6788 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 1236554.4 | 370966.32 | 1607520.72 | 1236554.4 | 370966.32 | 1607520.72 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cold water pipe | [6 empty] | 21159921.6 | 22158696.668 | 43318618.268 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 2023188.48 | 1365299.52 | 3388488 | 3388488
|  | PPR pipe D75 - PN10 | 10 | 11 | m | 99964.8 | 39200 | 139164.8 | 1099612.8 | 431200 | 1530812.8 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PPR pipe D63 - PN10 | 23 | 25 | m | 71884.8 | 34720 | 106604.8 | 1797120 | 868000 | 2665120 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PPR pipe D50 - PN10 | 21 | 26 | m | 45208.8 | 28000 | 73208.8 | 1175428.8 | 728000 | 1903428.8 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PPR pipe D40 - PN10 | 29 | 31 | m | 30841.2 | 25388.1544 | 56229.3544 | 956077.2 | 787032.7864 | 1743109.9864 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PPR pipe D32 - PN10 | 47 | 72 | m | 22978.8 | 22306.7432 | 45285.5432 | 1654473.6 | 1606085.5104 | 3260559.1104 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PPR pipe D25 - PN10 | 68 | 87 | m | 17737.2 | 18258.8168 | 35996.0168 | 1543136.4 | 1588517.0616 | 3131653.4616 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PPR pipe D20 - PN10 | 272 | 297 | m | 9921.6 | 15682.8168 | 25604.4168 | 2946715.2 | 4657796.5896 | 7604511.7896 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PPR Fitting | 1 | 1 | lot | 2578284 | 773485.2 | 3351769.2 | 2578284 | 773485.2 | 3351769.2 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | uPVC pipe D60 - PN10 | 54 | 62 | m | 35287.2 | 24884.16 | 60171.36 | 2187806.4 | 1542817.92 | 3730624.32 | 0% | 40% | 40% |  |  |  | #REF! | 0 | 0 | 0 | 875122.56 | 617127.168 | 1492249.728 | 1492249.728
|  | uPVC pipe D34 - PN10 | 104 | 118 | m | 16286.4 | 13440 | 29726.4 | 1921795.2 | 1585920 | 3507715.2 | 0% | 40% | 40% |  |  |  | #REF! | 0 | 0 | 0 | 768718.08 | 634368 | 1403086.08 | 1403086.08
|  | uPVC Fitting | 1 | 1 | lot | 948369.6 | 284510.88 | 1232880.48 | 948369.6 | 284510.88 | 1232880.48 | 0% | 40% | 40% |  |  |  | #REF! | 0 | 0 | 0 | 379347.84 | 113804.352 | 493152.192 | 493152.192
|  | Connect to existing pipe | 1 | 1 | lot | 0 | 1000000 | 1000000 | 0 | 1000000 | 1000000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Excavation & backfill | 14 | 28 | m3 | 0 | 200000 | 200000 | 0 | 5600000 | 5600000 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories + Support | 1 | 1 | lot | 2351102.4 | 705330.72 | 3056433.12 | 2351102.4 | 705330.72 | 3056433.12 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hot water pipe | [6 empty] | 3819309.6 | 1253831.9112 | 5073141.5112 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PPR pipe D20 - PN20 | 7 | 9 | m | 12261.6 | 15682.8168 | 27944.4168 | 110354.4 | 141145.3512 | 251499.7512 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PPR Fitting | 1 | 1 | lot | 25466.4 | 7639.92 | 33106.32 | 25466.4 | 7639.92 | 33106.32 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fire stop | 1 | 1 | lot | 3500000 | 1050000 | 4550000 | 3500000 | 1050000 | 4550000 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories + Support | 1 | 1 | lot | 183488.8 | 55046.64 | 238535.44 | 183488.8 | 55046.64 | 238535.44 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | East side | [6 empty] | 144276542.4991 | 24804281.8787 | 169080824.3779 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 18181792 | 1198700.8 | 19380492.8 | 19380492.8
|  | Pump room | [6 empty] | 121538562.8991 | 7728105.642 | 129266668.5411 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 17380000 | 616000 | 17996000 | 17996000
|  | Booster pump Q=9.3 m3, H=30m | 2 | 2 | set | 17380000 | 616000 | 17996000 | 34760000 | 1232000 | 35992000 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 17380000 | 616000 | 17996000 | 17996000
|  | Electrical control panel for booster pump | 1 | 1 | set | 44440000 | 1400000 | 45840000 | 44440000 | 1400000 | 45840000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pressure tank 100l | 1 | 1 | pcs | 7915200 | 168000 | 8083200 | 7915200 | 168000 | 8083200 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Storage tank 3m3 | 1 | 1 | pcs | 9970909.0909 | 322000 | 10292909.0909 | 9970909.0909 | 322000 | 10292909.0909 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Filter | 1 | 1 | set | 10800000 | 225400 | 11025400 | 10800000 | 225400 | 11025400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Water metter DN25 | 1 | 1 | pcs | 1014000 | 50880.368 | 1064880.368 | 1014000 | 50880.368 | 1064880.368 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/PVC/PVC 2Cx1.5mm2 | 20 | 25 | m | 15443.88 | 5031.18 | 20475.06 | 386097 | 125779.5 | 511876.5 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 20 | 25 | m | 40467 | 9350 | 49817 | 1011675 | 233750 | 1245425 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 40 | 50 | m | 8773.9726 | 14594.0164 | 23367.989 | 438698.6301 | 729700.8206 | 1168399.4507 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger + Support | 1 | 1 | lot | 4909992.3537 | 1472997.7061 | 6382990.0598 | 4909992.3537 | 1472997.7061 | 6382990.0598 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 5891990.8244 | 1767597.2473 | 7659588.0717 | 5891990.8244 | 1767597.2473 | 7659588.0717 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Valve | [6 empty] | 15191076.4 | 2017377.4463 | 17208453.8463 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pressure Gauges | 1 | 1 | pcs | 1008000 | 49588 | 1057588 | 1008000 | 49588 | 1057588 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flexible DN25 | 4 | 4 | pcs | 568800 | 50880.368 | 619680.368 | 2275200 | 203521.472 | 2478721.472 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Float level indicator | 1 | 1 | pcs | 4200000 | 168000 | 4368000 | 4200000 | 168000 | 4368000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Float valve DN25 | 1 | 1 | pcs | 770400 | 50880.368 | 821280.368 | 770400 | 50880.368 | 821280.368 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Y-Strainer DN25 | 2 | 2 | pcs | 322800 | 50880.368 | 373680.368 | 645600 | 101760.736 | 747360.736 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Safety valve DN25 | 1 | 1 | pcs | 1376400 | 50880.368 | 1427280.368 | 1376400 | 50880.368 | 1427280.368 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Check valve DN25 | 3 | 3 | pcs | 480000 | 50880.368 | 530880.368 | 1440000 | 152641.104 | 1592641.104 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gate valve DN25 | 5 | 5 | pcs | 322800 | 50880.368 | 373680.368 | 1614000 | 254401.84 | 1868401.84 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gate valve DN25 PPR | 8 | 8 | pcs | 85924.8 | 49415.0989 | 135339.8989 | 687398.4 | 395320.791 | 1082719.191 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gate valve DN20 PPR | 9 | 9 | pcs | 63367.2 | 45472.3119 | 108839.5119 | 570304.8 | 409250.8073 | 979555.6073 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 603773.2 | 181131.96 | 784905.16 | 603773.2 | 181131.96 | 784905.16 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cold water pipe | [6 empty] | 7418628 | 14924281.536 | 22342909.536 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 801792 | 582700.8 | 1384492.8 | 1384492.8
|  | PPR pipe D63 - PN10 | 10 | 12 | m | 71884.8 | 34720 | 106604.8 | 862617.6 | 416640 | 1279257.6 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PPR pipe D40 - PN10 | 5 | 7 | m | 30841.2 | 25388.1544 | 56229.3544 | 215888.4 | 177717.0808 | 393605.4808 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PPR pipe D32 - PN10 | 29 | 32 | m | 22978.8 | 22306.7432 | 45285.5432 | 735321.6 | 713815.7824 | 1449137.3824 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PPR pipe D25 - PN10 | 21 | 28 | m | 17737.2 | 18258.8168 | 35996.0168 | 496641.6 | 511246.8704 | 1007888.4704 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PPR pipe D20 - PN10 | 130 | 143 | m | 9921.6 | 15682.8168 | 25604.4168 | 1418788.8 | 2242642.8024 | 3661431.6024 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PPR Fitting | 1 | 1 | lot | 860598 | 258179.4 | 1118777.4 | 860598 | 258179.4 | 1118777.4 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | uPVC pipe D34 - PN10 | 104 | 100 | m | 16286.4 | 13440 | 29726.4 | 1628640 | 1344000 | 2972640 | 0% | 40% | 40% |  |  |  | #REF! | 0 | 0 | 0 | 651456 | 537600 | 1189056 | 1189056
|  | uPVC Fitting | 1 | 1 | lot | 375840 | 112752 | 488592 | 375840 | 112752 | 488592 | 0% | 40% | 40% |  |  |  | #REF! | 0 | 0 | 0 | 150336 | 45100.8 | 195436.8 | 195436.8
|  | Connect to existing pipe | 1 | 1 | lot | 0 | 1000000 | 1000000 | 0 | 1000000 | 1000000 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Excavation & backfill | 10 | 20 | m3 | 0 | 200000 | 200000 | 0 | 4000000 | 4000000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cut wall and backfill | 91 | 130 | m | 0 | 30000 | 30000 | 0 | 3900000 | 3900000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories + Support | 1 | 1 | lot | 824292 | 247287.6 | 1071579.6 | 824292 | 247287.6 | 1071579.6 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hot water pipe | [6 empty] | 128275.2 | 134517.2544 | 262792.4544 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PPR pipe D20 - PN20 | 7 | 8 | m | 12261.6 | 15682.8168 | 27944.4168 | 98092.8 | 125462.5344 | 223555.3344 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PPR Fitting | 1 | 1 | lot | 22636.8 | 6791.04 | 29427.84 | 22636.8 | 6791.04 | 29427.84 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories + Support | 1 | 1 | lot | 7545.6 | 2263.68 | 9809.28 | 7545.6 | 2263.68 | 9809.28 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 3. 30. |  | Sanitary Furnishings | 1 | 1 | PSCH |  |  |  | 1589161013.1409 | 79558059.1592 | 1668719072.3001 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | West side | 0 |  | m |  |  |  |  | 50588775.2524 | 1032592350.3478 | 0% | 0% | 0% | 0% |  |  | #REF! |  | 0 | 0 |  | 0 | 0 | 0
|  | Santinary | [6 empty] | 982003575.0955 | 50588775.2524 | 1032592350.3478 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Water closet one block, included stop valve | 37 | 37 | pcs | 14750000 | 413200.4464 | 15163200.4464 | 545750000 | 15288416.5168 | 561038416.5168 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Water closet spray | 37 | 37 | pcs | 638000 | 50232 | 688232 | 23606000 | 1858584 | 25464584 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Paper holder | 37 | 37 | pcs | 653000 | 50232 | 703232 | 24161000 | 1858584 | 26019584 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lavatory under-mounted type | 43 | 43 | pcs | 1443000 | 300710.7768 | 1743710.7768 | 62049000 | 12930563.4024 | 74979563.4024 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Water tap for lavatory (cold) | 43 | 43 | pcs | 953000 | 50232 | 1003232 | 40979000 | 2159976 | 43138976 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mirror (H=1m, L according to the lavabo table) | 33 | 33 | m2 | 768883.5 | 123200 | 892083.5 | 25373155.5 | 4065600 | 29438755.5 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hand Dryer | 8 | 8 | pcs | 5018000 | 61600 | 5079600 | 40144000 | 492800 | 40636800 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Uniral included flush valve | 15 | 15 | pcs | 11003000 | 280000 | 11283000 | 165045000 | 4200000 | 169245000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Floor drain DN80 | 16 | 16 | pcs | 855000 | 88480 | 943480 | 13680000 | 1415680 | 15095680 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Floor drain W100xL5100 | 1 | 1 | pcs | 5417500 | 476000 | 5893500 | 5417500 | 476000 | 5893500 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Floor drain W100xL3800 | 1 | 1 | pcs | 4334000 | 380800 | 4714800 | 4334000 | 380800 | 4714800 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Floor drain W100xL3000 | 1 | 1 | pcs | 3250500 | 285600 | 3536100 | 3250500 | 285600 | 3536100 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shower | 1 | 1 | pcs | 7305000 | 196000 | 7501000 | 7305000 | 196000 | 7501000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Heat Water 5L for kitchen | 2 | 2 | pcs | 1628727.2727 | 168000 | 1796727.2727 | 3257454.5455 | 336000 | 3593454.5455 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Heat Water 50L for shower | 1 | 1 | pcs | 3104727.2727 | 280000 | 3384727.2727 | 3104727.2727 | 280000 | 3384727.2727 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Waterproof for neck pipe | 114 | 114 | nos | 50000 | 15000 | 65000 | 5700000 | 1710000 | 7410000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 8847237.7773 | 2654171.3332 | 11501409.1105 | 8847237.7773 | 2654171.3332 | 11501409.1105 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | East side | [6 empty] | 607157438.0455 | 28969283.9068 | 636126721.9523 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Santinary | [6 empty] | 607157438.0455 | 28969283.9068 | 636126721.9523 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Water closet one block, included stop valve | 24 | 24 | pcs | 14750000 | 413200.4464 | 15163200.4464 | 354000000 | 9916810.7136 | 363916810.7136 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Water closet spray | 24 | 24 | pcs | 638000 | 50232 | 688232 | 15312000 | 1205568 | 16517568 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Paper holder | 24 | 24 | pcs | 653000 | 50232 | 703232 | 15672000 | 1205568 | 16877568 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lavatory under-mounted type | 12 | 24 | pcs | 1443000 | 300710.7768 | 1743710.7768 | 34632000 | 7217058.6432 | 41849058.6432 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Water tap for lavatory (cold) | 12 | 12 | pcs | 953000 | 50232 | 1003232 | 11436000 | 602784 | 12038784 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mirror (H=1m, L according to the lavabo table) | 10 | 10 | m2 | 768883.5 | 123200 | 892083.5 | 7688835 | 1232000 | 8920835 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hand Dryer | 4 | 4 | pcs | 5018000 | 61600 | 5079600 | 20072000 | 246400 | 20318400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Uniral included flush valve | 11 | 11 | pcs | 11003000 | 280000 | 11283000 | 121033000 | 3080000 | 124113000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Floor drain DN80 | 10 | 10 | pcs | 855000 | 88480 | 943480 | 8550000 | 884800 | 9434800 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Floor drain W100xL4400 | 1 | 1 | pcs | 4334000 | 380800 | 4714800 | 4334000 | 380800 | 4714800 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Floor drain W100xL3200 | 1 | 1 | pcs | 3250500 | 285600 | 3536100 | 3250500 | 285600 | 3536100 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Heat Water 5L for kitchen | 2 | 2 | pcs | 1628727.2727 | 168000 | 1796727.2727 | 3257454.5455 | 336000 | 3593454.5455 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Waterproof for neck pipe | 49 | 49 | nos | 50000 | 15000 | 65000 | 2450000 | 735000 | 3185000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 5469648.5 | 1640894.55 | 7110543.05 | 5469648.5 | 1640894.55 | 7110543.05 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. |  | Machine hook-up (Hall 3) | [8 empty] | 0 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
5. |  | Scooter Garage | [6 empty] | 36457255.9273 | 16528783.2582 | 52986039.1855 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 5603179.2218 | 1789020.9305 | 7392200.1524 | 7392200.1524
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. 3. |  | Mechancial Engineering | [6 empty] | 36457255.9273 | 16528783.2582 | 52986039.1855 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 5603179.2218 | 1789020.9305 | 7392200.1524 | 7392200.1524
5. 3. 10. |  | Rainwater System | 1 | 1 | PSCH |  |  |  | 36457255.9273 | 16528783.2582 | 52986039.1855 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 5603179.2218 | 1789020.9305 | 7392200.1524 | 7392200.1524
|  | uPVC pipe D220-PN6 | 12 | 15 | m | 356616 | 71941.408 | 428557.408 | 5349240 | 1079121.12 | 6428361.12 | 0% | 50% | 50% |  |  |  | #REF! | 0 | 0 | 0 | 2674620 | 539560.56 | 3214180.56 | 3214180.56
|  | uPVC pipe D110-PN6 | 92 | 112 | m | 93225.6 | 42504 | 135729.6 | 10441267.2 | 4760448 | 15201715.2 | 0% | 15% | 15% |  |  |  | #REF! | 0 | 0 | 0 | 1566190.08 | 714067.2 | 2280257.28 | 2280257.28
|  | uPVC pipe D60-PN6 | 59 | 55 | m | 29858.4 | 24884.16 | 54742.56 | 1642212 | 1368628.8 | 3010840.8 | 0% | 15% | 15% |  |  |  | #REF! | 0 | 0 | 0 | 246331.8 | 205294.32 | 451626.12 | 451626.12
|  | uPVC Cleanout DN100 | 8 | 8 | pcs | 106423.2 | 28000 | 134423.2 | 851385.6 | 224000 | 1075385.6 | 0% | 15% | 15% |  |  |  | #REF! | 0 | 0 | 0 | 127707.84 | 33600 | 161307.84 | 161307.84
|  | Leaf gaurd DN100 | 8 | 8 | pcs | 231000 | 50400 | 281400 | 1848000 | 403200 | 2251200 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Floor Drain DN50 | 8 | 8 | pcs | 855000 | 88480 | 943480 | 6840000 | 707840 | 7547840 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fitting for uPVC piping | 8 | 1 | lot | 6588863.3455 | 1976659.0036 | 8565522.3491 | 6588863.3455 | 1976659.0036 | 8565522.3491 | 0% | 15% | 15% | 30% |  |  | #REF! | 0 | 0 | 0 | 988329.5018 | 296498.8505 | 1284828.3524 | 1284828.3524
|  | Excavation and backfill | 15 | 18 | m3 | 0 | 200000 | 200000 | 0 | 3600000 | 3600000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger/ support and Accessories | 1 | 1 | lot | 2196287.7818 | 658886.3345 | 2855174.1164 | 2196287.7818 | 658886.3345 | 2855174.1164 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Conection existing drain stormwater | 1 | 1 | lot | 700000 | 1750000 | 2450000 | 700000 | 1750000 | 2450000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. |  | Canteen | [6 empty] | 420920023.6422 | 58959472.3741 | 479879496.0162 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 22298652.64 | 3822924.472 | 26121577.112 | 26121577.112
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
6. 3. |  | Mechancial Engineering | [6 empty] | 420920023.6422 | 58959472.3741 | 479879496.0162 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 22298652.64 | 3822924.472 | 26121577.112 | 26121577.112
6. 3. 10. |  | Rainwater System | 1 | 1 | PSCH |  |  |  | 16378977.6 | 11954799.36 | 28333776.96 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 2248946.64 | 1747859.904 | 3996806.544 | 3996806.544
|  | uPVC pipe D110-PN6 | 93 | 112 | m | 93225.6 | 42504 | 135729.6 | 10441267.2 | 4760448 | 15201715.2 | 0% | 15% | 15% | 30% |  |  | #REF! | 0 | 0 | 0 | 1566190.08 | 714067.2 | 2280257.28 | 2280257.28
|  | Leaf gaurd DN100 | 6 | 6 | pcs | 231000 | 50400 | 281400 | 1386000 | 302400 | 1688400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | uPVC Cleanout DN100 | 6 | 6 | pcs | 106423.2 | 28000 | 134423.2 | 638539.2 | 168000 | 806539.2 | 0% | 15% | 15% | 30% |  |  | #REF! | 0 | 0 | 0 | 95780.88 | 25200 | 120980.88 | 120980.88
|  | Fitting for uPVC piping | 1 | 1 | lot | 2934878.4 | 880463.52 | 3815341.92 | 2934878.4 | 880463.52 | 3815341.92 | 0% | 15% | 15% | 30% |  |  | #REF! | 0 | 0 | 0 | 440231.76 | 132069.528 | 572301.288 | 572301.288
|  | Excavation and backfill | 13 | 19 | m3 | 0 | 200000 | 200000 | 0 | 3800000 | 3800000 | 0% | 15% | 15% | 30% |  |  | #REF! | 0 | 0 | 0 | 0 | 570000 | 570000 | 570000
|  | Hanger/ support and Accessories | 1 | 1 | lot | 978292.8 | 293487.84 | 1271780.64 | 978292.8 | 293487.84 | 1271780.64 | 0% | 15% | 15% | 30% |  |  | #REF! | 0 | 0 | 0 | 146743.92 | 44023.176 | 190767.096 | 190767.096
|  | Conection existing drain stormwater | 1 | 1 | lot | 0 | 1750000 | 1750000 | 0 | 1750000 | 1750000 | 0% | 15% | 15% | 30% |  |  | #REF! | 0 | 0 | 0 | 0 | 262500 | 262500 | 262500
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. 3. 20. |  | Waste Water System | 1 | 1 | PSCH |  |  |  | 20651731.2 | 14688997.44 | 35340728.64 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 2480282.64 | 1321401.504 | 3801684.144 | 3801684.144
|  | Piping for Bain maries | [9 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | uPVC pipe DN80 | 43 | 50 | m | 65145.6 | 36064 | 101209.6 | 3257280 | 1803200 | 5060480 | 0% | 15% | 15% | 30% |  |  | #REF! | 0 | 0 | 0 | 488592 | 270480 | 759072 | 759072
|  | Water pipe heating system | 1 | 1 | lot |  |  |  |  | 0 | 0 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fitting for uPVC piping | 1 | 1 | lot | 751680 | 225504 | 977184 | 751680 | 225504 | 977184 | 0% | 15% | 15% | 30% |  |  | #REF! | 0 | 0 | 0 | 112752 | 33825.6 | 146577.6 | 146577.6
|  | Hanger/ support and Accessories | 1 | 1 | lot | 250560 | 75168 | 325728 | 250560 | 75168 | 325728 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Piping | [6 empty] | 16392211.2 | 12585125.44 | 28977336.64 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 1878938.64 | 1017095.904 | 2896034.544 | 2896034.544
|  | uPVC pipe DN100 - PN6 | 7 | 9 | m | 93225.6 | 42504 | 135729.6 | 839030.4 | 382536 | 1221566.4 | 0% | 15% | 15% |  |  |  | #REF! | 0 | 0 | 0 | 125854.56 | 57380.4 | 183234.96 | 183234.96
|  | uPVC pipe DN80 - PN6 | 89 | 96 | m | 65145.6 | 36064 | 101209.6 | 6253977.6 | 3462144 | 9716121.6 | 0% | 15% | 15% |  |  |  | #REF! | 0 | 0 | 0 | 938096.64 | 519321.6 | 1457418.24 | 1457418.24
|  | uPVC pipe DN50 - PN6 | 75 | 82 | m | 29858.4 | 24884.16 | 54742.56 | 2448388.8 | 2040501.12 | 4488889.92 | 0% | 15% | 15% |  |  |  | #REF! | 0 | 0 | 0 | 367258.32 | 306075.168 | 673333.488 | 673333.488
|  | Clean Out DN50 | 1 | 1 | m | 297000 | 84000 | 381000 | 297000 | 84000 | 381000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Clean Out DN80 | 7 | 7 | m | 319000 | 84000 | 403000 | 2233000 | 588000 | 2821000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Clean Out DN100 | 1 | 1 | m | 341000 | 84000 | 425000 | 341000 | 84000 | 425000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fitting for uPVC piping | 1 | 1 | lot | 2984860.8 | 895458.24 | 3880319.04 | 2984860.8 | 895458.24 | 3880319.04 | 0% | 15% | 15% | 30% |  |  | #REF! | 0 | 0 | 0 | 447729.12 | 134318.736 | 582047.856 | 582047.856
|  | Connect pipes to existing manhole | 1 | 1 | lot | 0 | 1750000 | 1750000 | 0 | 1750000 | 1750000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Excavation and backfill | 8 | 15 | m3 | 0 | 200000 | 200000 | 0 | 3000000 | 3000000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger/ support and Accessories | 1 | 1 | lot | 994953.6 | 298486.08 | 1293439.68 | 994953.6 | 298486.08 | 1293439.68 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. 3. 30. |  | Service Water System | 1 | 1 | PSCH |  |  |  | 10371428 | 9116560.5373 | 19487988.5373 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 189423.36 | 137663.064 | 327086.424 | 327086.424
|  | Valve | [6 empty] | 2328612.8 | 1693755.9317 | 4022368.7317 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gate valve DN25 | 1 | 1 | pcs | 322800 | 50880.368 | 373680.368 | 322800 | 50880.368 | 373680.368 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gate valve DN25 PPR | 7 | 7 | pcs | 85924.8 | 49415.0989 | 135339.8989 | 601473.6 | 345905.6922 | 947379.2922 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gate valve DN20 PPR | 6 | 6 | pcs | 63367.2 | 45472.3119 | 108839.5119 | 380203.2 | 272833.8715 | 653037.0715 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 1024136 | 1024136 | 2048272 | 1024136 | 1024136 | 2048272 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cold water pipe | [6 empty] | 4239540 | 3735787.3512 | 7975327.3512 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 189423.36 | 137663.064 | 327086.424 | 327086.424
|  | PPR pipe DN40 - PN10 | 12 | 8 | m | 45208.8 | 28000 | 73208.8 | 361670.4 | 224000 | 585670.4 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PPR pipe DN32 - PN10 | 5 | 6 | m | 30841.2 | 25388.1544 | 56229.3544 | 185047.2 | 152328.9264 | 337376.1264 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PPR pipe DN25 - PN10 | 7 | 10 | m | 22978.8 | 22306.7432 | 45285.5432 | 229788 | 223067.432 | 452855.432 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PPR pipe DN20 - PN10 | 61 | 71 | m | 17737.2 | 18258.8168 | 35996.0168 | 1259341.2 | 1296375.9928 | 2555717.1928 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PPR Fitting | 1 | 1 | lot | 469810.8 | 140943.24 | 610754.04 | 469810.8 | 140943.24 | 610754.04 | 0% | 0% | 0% |  |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | uPVC pipe D34 - PN10 | 60 | 63 | m | 16286.4 | 13440 | 29726.4 | 1026043.2 | 846720 | 1872763.2 | 0% | 15% | 15% |  |  |  | #REF! | 0 | 0 | 0 | 153906.48 | 127008 | 280914.48 | 280914.48
|  | Fitting for uPVC piping | 1 | 1 | lot | 236779.2 | 71033.76 | 307812.96 | 236779.2 | 71033.76 | 307812.96 | 0% | 15% | 15% | 30% |  |  | #REF! | 0 | 0 | 0 | 35516.88 | 10655.064 | 46171.944 | 46171.944
|  | Excavation and backfill | 2 | 3.2 | m3 | 0 | 200000 | 200000 | 0 | 640000 | 640000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories + Support | 1 | 1 | lot | 471060 | 141318 | 612378 | 471060 | 141318 | 612378 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | hot water pipe | [6 empty] | 3803275.2 | 3687017.2544 | 7490292.4544 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PPR pipe DN15 - PN20 | 10 | 8 | m | 12261.6 | 15682.8168 | 27944.4168 | 98092.8 | 125462.5344 | 223555.3344 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PPR Fitting | 1 | 1 | lot | 22636.8 | 6791.04 | 29427.84 | 22636.8 | 6791.04 | 29427.84 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Fire stop | 1 | 1 | lot | 3500000 | 3500000 | 7000000 | 3500000 | 3500000 | 7000000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories + Support | 1 | 1 | lot | 182545.6 | 54763.68 | 237309.28 | 182545.6 | 54763.68 | 237309.28 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. 3. 40. |  | Sanitary Furnishings | 1 | 1 | PSCH |  |  |  | 240793394.3675 | 15204292.8421 | 255997687.2095 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lavatory under-mounted type | 2 | 2 | pcs | 1443000 | 300710.7768 | 1743710.7768 | 2886000 | 601421.5536 | 3487421.5536 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Lavatory wall mounted type | 1 | 1 | pcs | 1253000 | 300710.7768 | 1553710.7768 | 1253000 | 300710.7768 | 1553710.7768 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Water tap for lavatory (hot and cold) | 2 | 2 | pcs | 1320000 | 50232 | 1370232 | 2640000 | 100464 | 2740464 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Water tap for lavatory (cold) | 1 | 1 | pcs | 953000 | 50232 | 1003232 | 953000 | 50232 | 1003232 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Mirror 700x500x6mm | 3 | 3 | pcs | 2896300 | 61600 | 2957900 | 8688900 | 184800 | 8873700 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Water closet one block, included stop valve | 2 | 2 | set | 14750000 | 413200.4464 | 15163200.4464 | 29500000 | 826400.8928 | 30326400.8928 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Water closet spray | 2 | 2 | pcs | 638000 | 50232 | 688232 | 1276000 | 100464 | 1376464 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Paper holder | 2 | 2 | pcs | 653000 | 50232 | 703232 | 1306000 | 100464 | 1406464 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hand Dryer | 1 | 1 | pcs | 5018000 | 61600 | 5079600 | 5018000 | 61600 | 5079600 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Floor Drain DN50 | 1 | 1 | m | 855000 | 88480 | 943480 | 855000 | 88480 | 943480 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Floor Drain DN80 | 12 | 12 | m | 855000 | 88480 | 943480 | 10260000 | 1061760 | 11321760 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Stainless steel hand washing channel: L10000xH170xD500 | 1 | 1 | pcs | 44000000 | 2240000 | 46240000 | 44000000 | 2240000 | 46240000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Taps for hand washing (Cold) | 14 | 14 | pcs | 7755000 | 50400 | 7805400 | 108570000 | 705600 | 109275600 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Heat Water 5l | 2 | 2 | pcs | 1628727.2727 | 168000 | 1796727.2727 | 3257454.5455 | 336000 | 3593454.5455 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Double Socket 16A/230V | 3 | 3 | pcs | 150480 | 54500 | 204980 | 451440 | 163500 | 614940 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single Socket 16A/230V | 14 | 14 | pcs | 124560 | 54500 | 179060 | 1743840 | 763000 | 2506840 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3C-2.5mm2 Cu/XLPE/PVC | 105 | 112 | m | 32518.74 | 7485.665 | 40004.405 | 3642098.88 | 838394.48 | 4480493.36 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3C-1.5mm2 Cu/XLPE/PVC | 84 | 95 | m | 22980.09 | 5743.9305 | 28724.0205 | 2183108.55 | 545673.3975 | 2728781.9475 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 105 | 110 | m | 8773.9726 | 14594.0164 | 23367.989 | 965136.9863 | 1605341.8053 | 2570478.7916 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 8 | 10 | m | 8773.9726 | 14594.0164 | 23367.989 | 87739.726 | 145940.1641 | 233679.8901 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D16 | 84 | 90 | m | 6646.8692 | 13183.4282 | 19830.2974 | 598218.226 | 1186508.5359 | 1784726.7619 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Waterproof for neck pipe | 5 | 5 | nos | 50000 | 15000 | 65000 | 250000 | 75000 | 325000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 10408457.4536 | 3122537.2361 | 13530994.6897 | 10408457.4536 | 3122537.2361 | 13530994.6897 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. 3. 90. |  | Booster pump assembly | 1 |  | PSCH |  |  |  | 132724492.4747 | 7994822.1947 | 140719314.6694 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 17380000 | 616000 | 17996000 | 17996000
|  | PUMP ROOM | [6 empty] | 119059072.0747 | 5427258.3947 | 125718330.4694 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 17380000 | 0 | 17996000 | 17996000
|  | Booster pump Q=11.7 m3, H=30m | 2 | 2 | set | 17380000 | 616000 | 17996000 | 34760000 | 1232000 | 35992000 | 0% | 50% | 50% | 100% |  |  | #REF! | 0 | 0 | 0 | 17380000 | 616000 | 17996000 | 17996000
|  | Electrical control panel for booster pump | 1 | 1 | set | 44440000 | 1400000 | 45840000 | 44440000 | 1400000 | 45840000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pressure tank 100l | 1 | 1 | pcs | 7915200 | 168000 | 8083200 | 7915200 | 168000 | 8083200 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Storage tank 3m3 | 1 | 1 | pcs | 9970909.0909 | 322000 | 10292909.0909 | 9970909.0909 | 322000 | 10292909.0909 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Filter | 1 | 1 | set | 10800000 | 225400 | 11025400 | 10800000 | 225400 | 11025400 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Water metter DN25 | 1 | 1 | pcs | 1014000 | 50880.368 | 1064880.368 | 1014000 | 50880.368 | 1064880.368 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/PVC/PVC 2Cx1.5mm2 | 20 | 25 | m | 15443.88 | 5031.18 | 20475.06 | 386097 | 125779.5 | 511876.5 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 20 | 25 | m | 40467 | 9350 | 49817 | 1011675 | 233750 | 1245425 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 40 | 50 | m | 8773.9726 | 14594.0164 | 23367.989 | 438698.6301 | 729700.8206 | 1168399.4507 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Concrete base for pump | 1 | 1 | lot | 2500000 | 450000 | 2950000 | 2500000 | 450000 | 2950000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cover for pump | 1 | 1 | lot | 750000 | 200000 | 950000 | 750000 | 200000 | 950000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hanger + Support | 1 | 1 | lot | 3043495.4122 | 913048.6237 | 3956544.0359 | 3043495.4122 | 913048.6237 | 3956544.0359 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 2028996.9415 | 608699.0824 | 2637696.0239 | 2028996.9415 | 608699.0824 | 2637696.0239 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Valve | [6 empty] | 13303750 | 1140438.52 | 14444188.52 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Pressure Gauges | 1 | 1 | pcs | 1008000 | 49588 | 1057588 | 1008000 | 49588 | 1057588 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Flexible DN25 | 4 | 4 | pcs | 568800 | 50880.368 | 619680.368 | 2275200 | 203521.472 | 2478721.472 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Float level indicator | 1 | 1 | pcs | 4200000 | 168000 | 4368000 | 4200000 | 168000 | 4368000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Float valve DN25 | 1 | 1 | pcs | 770400 | 50880.368 | 821280.368 | 770400 | 50880.368 | 821280.368 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Y-Strainer DN25 | 2 | 2 | pcs | 322800 | 50880.368 | 373680.368 | 645600 | 101760.736 | 747360.736 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Safety valve DN25 | 1 | 1 | pcs | 1376400 | 50880.368 | 1427280.368 | 1376400 | 50880.368 | 1427280.368 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Check valve DN25 | 3 | 3 | pcs | 480000 | 50880.368 | 530880.368 | 1440000 | 152641.104 | 1592641.104 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Gate valve DN25 | 4 | 4 | pcs | 264000 | 50880.368 | 314880.368 | 1056000 | 203521.472 | 1259521.472 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 532150 | 159645 | 691795 | 532150 | 159645 | 691795 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cold water pipe | [6 empty] | 361670.4 | 195125.28 | 556795.68 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PPR pipe DN50 - PN10 | 5 | 6 | m | 45208.8 | 28000 | 73208.8 | 271252.8 | 168000 | 439252.8 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | PPR Fitting | 1 | 1 | lot | 52164 | 15649.2 | 67813.2 | 52164 | 15649.2 | 67813.2 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories + Support | 1 | 1 | lot | 38253.6 | 11476.08 | 49729.68 | 38253.6 | 11476.08 | 49729.68 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | VII.CIVIL | [8 empty] | 337968025 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 41316450 |  |  | 192012100 | 233328550
7. |  | Exterior Area | [6 empty] | 187529525 | 150438500 | 337968025 | 0 | 0% | 0% | 0% |  |  | #REF! | 28841400 | 12475050 | 41316450 | 99180200 | 92831900 | 192012100 | 233328550
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF!
7. 1. |  | Civil Engineering | [6 empty] | 187529525 | 150438500 | 337968025 | 0% | 0% | 0% | 0% |  |  | #REF! | 28841400 | 12475050 | 41316450 | 99180200 | 92831900 | 192012100 | 233328550
7. 1. 50. |  | Excavation | 1 | 1 | PSCH |  |  |  | 86750000 | 108855000 | 195605000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 60725000 | 76198500 | 136923500 | 136923500
|  | LV | [6 empty] | 58500000 | 54800000 | 115800000 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 40950000 | 38360000 | 81060000 | 81060000
|  | Manhole 1000x1000x1000 | 5 | 5 | m | 4500000 | 2000000 | 6500000 | 22500000 | 10000000 | 32500000 | 0% | 70% | 70% | 140% |  |  | #REF! | 0 | 0 | 0 | 15750000 | 7000000 | 22750000 | 22750000
|  | Excavation and backfilling | 164 | 164 | m3 | 0 | 200000 | 200000 | 0 | 32800000 | 32800000 | 0% | 70% | 70% | 140% |  |  | #REF! | 0 | 0 | 0 | 0 | 22960000 | 22960000 | 22960000
|  | Concrete crossroads protection | 190 | 120 | m | 300000 | 100000 | 400000 | 36000000 | 12000000 | 48000000 | 0% | 70% | 70% | 140% |  |  | #REF! | 0 | 0 | 0 | 25200000 | 8400000 | 33600000 | 33600000
|  | Labor (Remove old cable) | 1 | 1 | m | 0 | 2500000 | 2500000 | 0 | 2500000 | 2500000 | 0% | 70% | 70% | 140% |  |  | #REF! | 0 | 0 | 0 | 0 | 1750000 | 1750000 | 1750000
|  | AIR COMPRESSOR | [6 empty] | 1250000 | 4515000 | 5765000 | 0% | 70% | 70% | 140% |  |  | #REF! | 0 | 0 | 0 | 875000 | 3160500 | 4035500 | 4035500
|  | Excavation and backfill | 31 | 20.7 | m3 | 0 | 200000 | 200000 | 0 | 4140000 | 4140000 | 0% | 70% | 70% | 140% |  |  | #REF! | 0 | 0 | 0 | 0 | 2898000 | 2898000 | 2898000
|  | The cost of cutting and refinishing the concrete path for the undergruond pipe | 15 | 10 | m | 125000 | 37500 | 162500 | 1250000 | 375000 | 1625000 | 0% | 70% | 70% | 140% |  |  | #REF! | 0 | 0 | 0 | 875000 | 262500 | 1137500 | 1137500
|  | ELV |  | 11 |  |  |  |  | 27000000 | 47040000 | 74040000 | 0% | 70% | 70% | 140% |  |  | #REF! | 0 | 0 | 0 | 18900000 | 32928000 | 51828000 | 51828000
|  | Khoan đường đi ống | 52 | 52 | m | 0 | 300000 | 300000 | 0 | 15600000 | 15600000 | 0% | 70% | 70% | 140% |  |  | #REF! | 0 | 0 | 0 | 0 | 10920000 | 10920000 | 10920000
|  | Manhole 1200x1200x1200 | 4 | 6 | pcs | 4500000 | 2000000 | 6500000 | 27000000 | 12000000 | 39000000 | 0% | 70% | 70% | 140% |  |  | #REF! | 0 | 0 | 0 | 18900000 | 8400000 | 27300000 | 27300000
|  | Spare fee for Move and reinstall lighting pole if can't excavation pavement | 6 | 6 | pcs | 0 | 1200000 | 1200000 | 0 | 7200000 | 7200000 | 0% | 70% | 70% | 140% |  |  | #REF! | 0 | 0 | 0 | 0 | 5040000 | 5040000 | 5040000
|  | Excavation and backfill | 100 | 61.2 | m3 | 0 | 200000 | 200000 | 0 | 12240000 | 12240000 | 0% | 70% | 70% | 140% |  |  | #REF! | 0 | 0 | 0 | 0 | 8568000 | 8568000 | 8568000
[12 empty] | 0% | 70% | 70% | 140% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. 1. 60. |  | Laying conduits, pipes, etc. | 1 |  | PSCH |  |  |  | 100779525 | 41583500 | 142363025 | 0% | 0% | 0% | 0% |  |  | #REF! | 28841400 | 12475050 | 41316450 | 38455200 | 16633400 | 55088600 | 96405050
|  | LV | [6 empty] | 41773725 | 16061150 | 57834875 | 0% | 0% | 0% | 0% |  |  | #REF! | 11139660 | 4818345 | 15958005 | 14852880 | 6424460 | 21277340 | 37235345
|  | HDPE pipe D160/125 | 340 | 421 | m | 88200 | 38150 | 126350 | 37132200 | 16061150 | 53193350 | 30% | 40% | 70% | 140% |  |  | #REF! | 11139660 | 4818345 | 15958005 | 14852880 | 6424460 | 21277340 | 37235345
|  | Accessories | 1 | 1 | lot | 4641525 | 0 | 4641525 | 4641525 | 0 | 4641525 | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | ELV | [6 empty] | 59005800 | 25522350 | 84528150 | 0% | 0% | 0% | 0% |  |  | #REF! | 17701740 | 7656705 | 25358445 | 23602320 | 10208940 | 33811260 | 59169705
|  | HDPE pipe D160/125 | 848 | 669 | m | 88200 | 38150 | 126350 | 59005800 | 25522350 | 84528150 | 30% | 40% | 70% | 140% |  |  | #REF! | 17701740 | 7656705 | 25358445 | 23602320 | 10208940 | 33811260 | 59169705
[12 empty] | 0% | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | VIII.EQUIPMENT KITCHEN | [8 empty] | 229689172.3178 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
3. |  | Office, Social and Technical Areas (Hall 3) | [6 empty] | 225500372.3178 | 4188800 | 229689172.3178 | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 3. |  | Mechanical Engineering | [6 empty] | 225500372.3178 | 4188800 | 229689172.3178 | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. 3. 30. |  | Sanitary Furnishings | 1 | 1 | PSCH |  |  |  | 225500372.3178 | 4188800 | 229689172.3178 | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | West side | 0 | 0 | m |  |  | 0 | 107848004.152 | 2094400 | 109942404.152 | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Equiment kitchen | [6 empty] | 107848004.152 | 2094400 | 109942404.152 | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hafele refrigerator (1-wing refrigerator) | 2 | 2 | pcs | 20093299.732 | 224000 | 20317299.732 | 40186599.464 | 448000 | 40634599.464 | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single sink for kitchen included faucet waster pop up, flexiable, stop valve | 2 | 2 | pcs | 3486000.21 | 280000 | 3766000.21 | 6972000.42 | 560000 | 7532000.42 | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hafele semi-sonic dishwasher | 2 | 2 | pcs | 15336300.067 | 168000 | 15504300.067 | 30672600.134 | 336000 | 31008600.134 | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hafele standalone microwave oven | 2 | 2 | pcs | 2807300.067 | 95200 | 2902500.067 | 5614600.134 | 190400 | 5805000.134 | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Domino's Induction Cooker | 4 | 4 | pcs | 6100551 | 140000 | 6240551 | 24402204 | 560000 | 24962204 | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 4902182.0069 | 0 | 4902182.0069 | 4902182.0069 | 0 | 4902182.0069 | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | East side | [6 empty] | 112750186.1589 | 2094400 | 114844586.1589 | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Equiment kitchen | [6 empty] | 107848004.152 | 2094400 | 109942404.152 | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hafele refrigerator (1-wing refrigerator) | 2 | 2 | pcs | 20093299.732 | 224000 | 20317299.732 | 40186599.464 | 448000 | 40634599.464 | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Single sink for kitchen included faucet waster pop up, flexiable, stop valve | 2 | 2 | pcs | 3486000.21 | 280000 | 3766000.21 | 6972000.42 | 560000 | 7532000.42 | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hafele semi-sonic dishwasher | 2 | 2 | pcs | 15336300.067 | 168000 | 15504300.067 | 30672600.134 | 336000 | 31008600.134 | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hafele standalone microwave oven | 2 | 2 | pcs | 2807300.067 | 95200 | 2902500.067 | 5614600.134 | 190400 | 5805000.134 | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Domino's Induction Cooker | 4 | 4 | pcs | 6100551 | 140000 | 6240551 | 24402204 | 560000 | 24962204 | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 4902182.0069 | 0 | 4902182.0069 | 4902182.0069 | 0 | 4902182.0069 | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | IX.ELEVATOR | [8 empty] | 280000000 | 0% | 0% | 0% | 0% |  |  | #REF! |  |  | 0 |  |  | 0 | 0
6. |  | Canteen | [6 empty] | 280000000 | 0 | 280000000 | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. 1. |  | Civil Engineering | [6 empty] | 280000000 | 0 | 280000000 | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. 1. 260. |  | Elevator for goods | [6 empty] | 280000000 | 0 | 280000000 | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Food elevator without person, no loading machine room weight 200kg/02stop/30m/min | 1 | 1 | lot | 280000000 | 0 | 280000000 | 280000000 | 0 | 280000000 | 0 | 0% | 0% | 0% |  |  | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0
IV |  | CHI PHÍ QUẢN LÝ | [7 empty] | 1090000000 | 1090000000 | 0% | 0% | 0% | [6 empty] | 246700000 |  |  | 213400000 | 460100000
|  | Chi phí thuê xe nâng | 1 | 1 | Lot |  |  |  |  | 250000000 | 250000000 | 26% | 22% | 48% |  |  |  | #REF! | 0 |  | 65000000 | 0 |  | 55000000 | 120000000
|  | Chi phí kho bãi, văn phòng, điện nước tạm | 1 | 1 | Lot |  |  |  |  | 70000000 | 70000000 | 26% | 22% | 48% |  |  |  | #REF! | 0 |  | 18200000 | 0 |  | 15400000 | 33600000
|  | Chi phí quản lý | 1 | 1 | Lot |  |  |  |  | 600000000 | 600000000 | 26% | 22% | 48% |  |  |  | #REF! | 0 |  | 156000000 | 0 |  | 132000000 | 288000000
|  | In ấn,submit bản vẽ thi công,hoàn công,hồ sơ nghiệm thu… | 1 | 1 | Lot |  |  |  |  | 50000000 | 50000000 | 15% | 22% | 37% |  |  |  | #REF! | 0 |  | 7500000 | 0 |  | 11000000 | 18500000
|  | Kiểm định PCCC van gió | 1 | 1 | lot |  |  |  |  | 120000000 | 120000000 | 0% | 0% | 0% |  |  |  | #REF! | 0 |  | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0% | 0% | [6 empty] | 0 |  |  | 0 | 0
| TOTAL (BEFORE VAT) | [9 empty] | 33142000000 | [9 empty] | 2546776761 |  |  | 4675596437 | 7222373198
| TAX VAT (8%): | [19 empty] | 203742141 |  |  | 374047715 | 577789856
| GRAND TOTAL (AFTER VAT) | [19 empty] | 2750518902 |  |  | 5049644152 | 7800163054
NHÀ THẦU CHÍNH: CÔNG TY CỔ PHẦN CƠ ĐIỆN DITECHCO | [9 empty] | NHÀ THẦU PHỤ: CÔNG TY CỔ PHẦN HMEP
CHỈ HUY TRƯỞNG |  | GIÁM SÁT | CHỈ HUY PHÓ ME | [6 empty] | GIÁM ĐỐC DỰ ÁN CHỈ HUY TRƯỞNG
CAO XUÂN TRƯỜNG |  | ĐỖ PHẠM THANH HỒNG | CAO XUÂN TRƯỜNG | [6 empty] | VÕ HOÀNG KHẮC PHỤC NGUYỄN MINH HẢI
7222373198.7952
577789855.9036
[21 empty] | 2750518902.3545 |  | 7800163054.6988
5049644152.3443
7800163054.6988
Note on C223: PC: Cho group A
Note on C226: PC: cho group A

## SUMMARY (hidden)
Project: VN-RENTAL BUILDING HALL 3 ELECTRIC
Location: Lô D1, Khu công nghiệp Tam Thăng, Huyện Tam Thăng, thành Phố Tam Kỳ, Tỉnh quản Nam, Việt Nam
Client: Draexlmaier Automotive Vietnam Company Limited
Package: Cơ - Điện
Item: Summary sheet
Date: 27/02/2022
Contractor name: HMEP
No. | DESCRIPTION | Q.TY | UNIT | UNIT RATE (VND) | AMOUNT (VND) | Giá trị thực hiện đợt 1 | REMARK
1 | Electrical system | 1 | PSCH | #REF! | #REF! | 168260426.4674 |  |  | Làm tròn vào ô 133-G sheet "1. ELEC" | 18536127645.6357 | #REF!
2 | ELV System | 1 | PSCH | 3412928080.1667 | 3412928080.1667 | 129975992.7758 |  |  |  | 3347928080.1667 | 65000000
3 | Air compressor system | 1 | PSCH | 1143011058.0929 | 1143011058.0929 | 16491404.8 |  |  |  | 1143011058.0929 | 0
4 | Ventilation system | 1 | PSCH | 3204713406.5221 | 3204713406.5221 | 73055118.3127 |  |  |  | 3204713406.5221 | 0
5 | AC system | 1 | PSCH | 2228147077.7132 | 2228147077.7132 | 20593863.5681 |  |  |  | 2228147077.7132 | 0
6 | Plumping system | 1 | PSCH | 2878415534.5514 | 2878415534.5514 | 114633635.2767 |  |  |  | 2878415534.5514 | 0
7 | Fire fighting system | 1 | PSCH |  | 0 |  |  |  |  | 0 | 0
8 | Civil (Excavation, pipe…) | 1 | PSCH | 337968025 | 337968025 | 110177200 |  |  |  | 337968025 | 0
9 | Equipment kitchen | 1 | PSCH | 229689172.3178 | 229689172.3178 | 0 |  |  |  | 229689172.3178 | 0
10 | Elevator | 1 | PSCH | 280000000 | 280000000 | 0 |  |  |  | 280000000 | 0
0
11 | CHI PHÍ QUẢN LÝ |  |  |  | 1090000000 | 175000000 |  |  |  | 1090000000 | 0
| Chi phí thuê xe nâng | 1 | Lot | 250000000 | 250000000 | 30000000 |  |  |  | 250000000 | 0
| Chi phí kho bãi, văn phòng, điện nước tạm | 1 | Lot | 70000000 | 70000000 | 40000000 |  |  |  | 70000000 | 0
| Chi phí quản lý | 1 | Lot | 600000000 | 600000000 | 100000000 |  |  |  | 600000000 | 0
| In ấn,submit bản vẽ thi công,hoàn công,hồ sơ nghiệm thu… | 1 | Lot | 50000000 | 50000000 | 5000000 |  |  |  | 50000000 | 0
| Kiểm định PCCC van gió | 1 | lot | 120000000 | 120000000 |  |  |  |  | 120000000 | 0
0
| TOTAL AMOUNT (Not included VAT) |  |  |  | #REF! | 808187641.2008 |  |  | 33077739080 | 33276000000 | #REF!
| NHÀ THẦU PHỤ: CÔNG TY CỔ PHẦN HMEP | NHÀ THẦU CHÍNH: CÔNG TY CỔ PHẦN KỸ THUẬT XÂY DỰNG DINCO
| GIÁM ĐỐC |  | GIÁM ĐỐC |  |  | CHỈ HUY TRƯỞNG
CHỈ HUY TRƯỞNG

## KL TTHT CV DOT 2
BẢNG KHỐI LƯỢNG HOÀN THÀNH THANH TOÁN ĐỢT 2
- Tên/số hợp đồng xây dựng :0310/2022/HĐKT-DRX2/DITECHCO-HMEP
- Bên giao thầu :CÔNG TY CỔ PHẦN CƠ ĐIỆN DITECHCO
- Bên nhận thầu : CÔNG TY CỔ PHẦN HMEP
- Hạng mục :Hệ thống Cơ điện
- Dự án: VN-RENTAL BUILDING HALL 3 ELECTRIC
- Giai đoạn :Thanh toán đợt 2
Contractor name: HMEP
Position |  | Headline | Quantity | Quantity By contractor | Unit | Material Unit | Labor Unit | Unit rate | Material Amount | Labor Amount | Amount (VND) |  |  |  | % Công việc hoàn thành |  | % Công việc hoàn thành đến cuối kỳ này
[12 empty] | Đợt 2 | Đợt 3 | % KL hoàn thành lũy kế | Đợt 1 | Đợt 2 |  | Đợt 2 | Đợt 3 | % KL hoàn thành lũy kế
|  | I. ELEC | [8 empty] | 18337127645.6357
1. |  | Construction site facilities | [8 empty] | 0
[14 empty] | #REF! | [5 empty] | 0%
1. 1. |  | Construction site facilities | 1 |  | psch | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
1. 2. |  | Construction site cameras | 1 |  | psch | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
[14 empty] | #REF! | [5 empty] | 0%
2. |  | Production and Logistic building (Hall 3) | [6 empty] | 4384819997.1499 | 819871975.3259 | 5204691972.4758 |  |  | #REF! | [5 empty] | 0%
[14 empty] | #REF! | [5 empty] | 0%
2.1. |  | Civil Engineering | 1 |  | PSCH | [8 empty] | #REF! | [5 empty] | 0%
2. 1. 10. |  | Calculations | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 20. |  | Rainwater and waste water sewer | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 30. |  | Earthworks | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 40. |  | Demolition, removal and dismantling works | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 50. |  | Foundation | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 60. |  | Building structure | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 70. |  | General concrete- / reinforced concrete works | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 80. |  | Fire protection | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 90. |  | Fire rated walls | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 100. |  | Cutting base slabs / ceilings / floors | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 110. |  | Cutting holes into existing facades, walls and roofs | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 120. |  | Exterior walls | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 130. |  | Exterior doors and windows | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 140. |  | Fire protection doors | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 150. |  | Internal doors | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 160. |  | Fire protection roller shutter door | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 170. |  | Fire protection bulkhead | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 180. |  | High speed roller shutter | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 190. |  | Fitting and metal work - general | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 200. |  | Railings and hand rails | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 210. |  | Steel stage for installations | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 220. |  | Collision protection | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 230. |  | canopies of exterior doors | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 240. |  | Concerete steps in front of the hall | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 250. |  | Painting and varnishing works | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 260. |  | Guidance systems | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 270. |  | Locking system | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 280. |  | Internal signage | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 290. |  | Adjustment ridge vent | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 300. |  | Roof reinforcment Option 1 | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 310. |  | Insert new ventilation louvers | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
2. 1. 320. |  | Metal louvers to cover mechanical units | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! | [5 empty] | 0%
[14 empty] | #REF! | [5 empty] | 0%
2. 2. |  | Electrical Engineering | 1 |  | PSCH |  |  |  | 4384819997.1499 | 819871975.3259 | 5204691972.4758 |  |  | #REF! | [5 empty] | 0%
2. 2. 10. |  | Adjustment of existing facilities, dismantling and disposal works | 1 | 1 | PSCH |  |  |  | 0 | 24400000 | 24400000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | The cost of dismantling electrical distribution board, trunking & ladder and lighting system existing system | 1 | 1 | lot | 0 | 14000000 | 14000000 | 0 | 14000000 | 14000000 |  |  | #REF! |  | 80% | 80% |  |  | 0%
|  | Opening (inluded supports & waterproof) for wall through ductwork fee | 1 | 1 | lot | 0 | 10400000 | 10400000 | 0 | 10400000 | 10400000 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
2. 2. 20. |  | Rennovation existing grounding system and lightning protection | 1 | 1 | PSCH | 0 | 5000000 | 5000000 | 0 | 5000000 | 5000000 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
2. 2. 30. |  | Rennovation existing grounding and equipotential bonding | 1 | 1 | PSCH | 0 | 2500000 | 2500000 | 0 | 2500000 | 2500000 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
2. 2. 40. |  | Power supply | 1 | 1 | PSCH |  |  |  | 1266144274.1142 | 405876628.1459 | 1672020902.2601 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | From DB SYN-TR1 Panel to Building 3_BMDP | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 6x(4x1Cx300mm2)+E240mm2 | 67 | 64.9 | m | 2672599.35 | 818400 | 3490999.35 | 173451697.815 | 53114160 | 226565857.815 |  |  | #REF! | 36% | 39% | 75% |  |  | 0%
| Option1 | From DB SYN-TR1 Panel to Building 3_BMDP | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 5x(4x1Cx240mm2)+E240mm2 | 67 | 67 | m | 15029239.743 | 686400 | [6 empty] | #REF! |  |  | 0% |  |  | 0%
|  | From Building 3_BMDP Panel to Building 3_PDP 1.0 | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 4x1Cx300mm2+E150mm2 | 15 | 14 | m | 481493.34 | 158400 | 639893.34 | 6740906.76 | 2217600 | 8958506.76 |  |  | #REF! | 36% | 39% | 75% |  |  | 0%
|  | From Building 3_BMDP Panel to Building 3_PDP 1.1 | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 2x(4x1Cx185mm2)+E185mm2 | 116 | 106 | m | 618512.88 | 176000 | 794512.88 | 65562365.28 | 18656000 | 84218365.28 |  |  | #REF! | 36% | 39% | 75% |  |  | 0%
|  | From Building 3_BMDP Panel to Building 3_PDP 2.0 | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 3x(3x1Cx240mm2)+N1Cx240mm2+E120mm2 | 182 | 203.5 | m | 909229.53 | 304700 | 1213929.53 | 185028209.355 | 62006450 | 247034659.355 |  |  | #REF! | 36% | 39% | 75% |  |  | 0%
|  | From Building 3_BMDP Panel to Building 3_PDP 1.2 | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 3x(3x1Cx240mm2)+N2x1Cx240mm2+E185mm2 | 135 | 143 | m | 1018095.6 | 304700 | 1322795.6 | 145587670.8 | 43572100 | 189159770.8 |  |  | #REF! | 36% | 39% | 75% |  |  | 0%
|  | From Building 3_BMDP Panel to Building 3_PDP 2.1 | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 3x(3x1Cx240mm2)+N2x1Cx240mm2+E185mm2 | 136 | 137 | m | 1018095.6 | 304700 | 1322795.6 | 139479097.2 | 41743900 | 181222997.2 |  |  | #REF! | 36% | 39% | 75% |  |  | 0%
|  | From Building 3_BMDP Panel to Building 3_BDP 1.0 | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 4x1Cx150mm2+E70mm2 | 70 | 16.5 | m | 247104.54 | 116765.3025 | 363869.8425 | 4077224.91 | 1926627.4913 | 6003852.4013 |  |  | #REF! | 36% | 39% | 75% |  |  | 0%
|  | From Building 3_BMDP Panel to Building 3_BDP 1.1 | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 2x(4x1Cx150mm2)+E150mm2 | 15 | 99 | m | 497079.9 | 138600 | 635679.9 | 49210910.1 | 13721400 | 62932310.1 |  |  | #REF! | 36% | 39% | 75% |  |  | 0%
|  | From Building 3_BMDP Panel to Building 3_BDP 2.0 | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 3x(3x1Cx240mm2)+N2x1Cx185mm2+E185mm2 | 116 | 191.1 | m | 1018095.6 | 304700 | 1322795.6 | 194558069.16 | 58228170 | 252786239.16 |  |  | #REF! | 36% | 39% | 75% |  |  | 0%
|  | From Building 3_BMDP Panel to Scooter garage BDP 1.0 | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 4x1Cx35mm2+E16mm2 | 131 | 86 | m | 70862.76 | 46119.15 | 116981.91 | 6094197.36 | 3966246.9 | 10060444.26 |  |  | #REF! | 36% | 0% | 36% |  |  | 0%
|  | From Building 3_BMDP Panel to Canteen BDP 1.0 | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 3x1Cx120mm2+N1Cx25mm2+E16mm2 | 174 | 181 | m | 165603.51 | 101462.13 | 267065.64 | 29974235.31 | 18364645.53 | 48338880.84 |  |  | #REF! | 36% | 0% | 36% |  |  | 0%
|  | From Building 3_BDP 1.1 Panel to Building 3_UPS1-100 kVA | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 4x1Cx70mm2+E35mm2 | 106 | 121 | m | 128659.23 | 83182.176 | 211841.406 | 15567766.83 | 10065043.296 | 25632810.126 |  |  | #REF! | 36% | 0% | 36% |  |  | 0%
|  | From Building 3 UPS1-MDP Panel to Building 3_UPS 1 DP 1.3 35kVA | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 4x1Cx70mm2+E35mm2 | 20 | 18.7 | m | 128659.23 | 83182.176 | 211841.406 | 2405927.601 | 1555506.6912 | 3961434.2922 |  |  | #REF! | 36% | 0% | 36% |  |  | 0%
|  | From Building 3_BDP 2.0 Panel to Building 3_UPS2-100 kVA | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 4x1Cx70mm2+E35mm2 | 18 | 27.5 | m | 128659.23 | 83182.176 | 211841.406 | 3538128.825 | 2287509.84 | 5825638.665 |  |  | #REF! | 36% | 0% | 36% |  |  | 0%
|  | From Building 3 UPS1-MDP Panel to Building 3_UPS 2 DP 1.3 35kVA | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 4x1Cx70mm2+E35mm2 | 25 | 27.5 | m | 128659.23 | 83182.176 | 211841.406 | 3538128.825 | 2287509.84 | 5825638.665 |  |  | #REF! | 36% | 0% | 36% |  |  | 0%
|  | From Building 3 UPS1-MDP Panel to Building 3 UPS 2-DP1.2 | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx10mm2 | 185 | 184.8 | m | 102150.27 | 17818.7625 | 119969.0325 | 18877369.896 | 3292907.31 | 22170277.206 |  |  | #REF! | 36% | 0% | 36% |  |  | 0%
|  | From Building 3 UPS1-MDP Panel to Building 3 UPS 2-DP1.3 | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx6mm2 | 115 | 105 | m | 65470.44 | 17189.865 | 82660.305 | 6874396.2 | 1804935.825 | 8679332.025 |  |  | #REF! | 36% | 0% | 36% |  |  | 0%
|  | From Building 3 UPS1-MDP Panel to Building 3_UPS 1 DP 1.3 35kVA | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 4x1Cx50mm2+E10mm2 | 115 | 90 | m | 166514.94 | 52580 | 219094.94 | 14986344.6 | 4732200 | 19718544.6 |  |  | #REF! | 36% | 0% | 36% |  |  | 0%
|  | From Building 3 UPS1-MDP Panel to PDU | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 590 | 480 | m | 32518.74 | 7485.665 | 40004.405 | 15608995.2 | 3593119.2 | 19202114.4 |  |  | #REF! | 36% | 0% | 36% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | From Building 3_BDP 2.0 Panel to Building 3_UPS2-100 kVA | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 4x1Cx35mm2+E16mm2 | 18 | 27.5 | m | 448964.76 | 46119.15 | 495083.91 | 12346530.9 | 1268276.625 | 13614807.525 |  |  | #REF! | 36% | 0% | 36% |  |  | 0%
|  | From Building 3 UPS2-MDP Panel to Building 3 UPS 2-DP1.2 | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx4mm2 | 25 | 20 | m | 46999.53 | 9969.2395 | 56968.7695 | 939990.6 | 199384.79 | 1139375.39 |  |  | #REF! | 36% | 0% | 36% |  |  | 0%
|  | From Building 3 UPS1-MDP Panel to Building 3 UPS 2-DP1.2 | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx10mm2 | 180 | 193.6 | m | 102150.27 | 17818.7625 | 119969.0325 | 19776292.272 | 3449712.42 | 23226004.692 |  |  | #REF! | 36% | 0% | 36% |  |  | 0%
|  | From Building 3 UPS1-MDP Panel to Building 3 UPS 2-DP1.2 | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx6mm2 | 115 | 187 | m | 65470.44 | 14173.4395 | 79643.8795 | 12242972.28 | 2650433.1865 | 14893405.4665 |  |  | #REF! | 36% | 0% | 36% |  |  | 0%
|  | From Building 3 UPS1-MDP Panel to Building 3_UPS 2 DP 1.3 35kVA | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 4x1Cx50mm2+E10mm2 | 115 | 117.7 | m | 166514.94 | 52580 | 219094.94 | 19598808.438 | 6188666 | 25787474.438 |  |  | #REF! | 36% | 0% | 36% |  |  | 0%
|  | From Building 3 UPS2-MDP Panel to PDU | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 590 | 480 | m | 32518.74 | 7485.665 | 40004.405 | 15608995.2 | 3593119.2 | 19202114.4 |  |  | #REF! | 36% | 0% | 36% |  |  | 0%
|  | From DB PDP 1.2 Panel to Cetral feeding unit 1 | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 4x1Cx150mm2+E70mm2 | 24 | 26.4 | m | 247104.54 | 116765.3025 | 363869.8425 | 6523559.856 | 3082603.986 | 9606163.842 |  |  | #REF! | 36% | 39% | 75% |  |  | 0%
|  | From DB PDP 1.2 Panel to Cetral feeding unit 2 | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 4x1Cx150mm2+E70mm2 | 16 | 17.6 | m | 247104.54 | 116765.3025 | 363869.8425 | 4349039.904 | 2055069.324 | 6404109.228 |  |  | #REF! | 36% | 39% | 75% |  |  | 0%
|  | From DB PDP 1.2 Panel to Cetral feeding unit 3 | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 4x1Cx150mm2+E70mm2 | 57 | 68.2 | m | 247104.54 | 116765.3025 | 363869.8425 | 16852529.628 | 7963393.6305 | 24815923.2585 |  |  | #REF! | 36% | 39% | 75% |  |  | 0%
|  | From DB PDP 2.1 Panel to Cetral feeding unit 1 | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 4x1Cx150mm2+E70mm2 | 24 | 26.4 | m | 247104.54 | 116765.3025 | 363869.8425 | 6523559.856 | 3082603.986 | 9606163.842 |  |  | #REF! | 36% | 39% | 75% |  |  | 0%
|  | From DB PDP 2.1 Panel to Cetral feeding unit 2 | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 4x1Cx150mm2+E70mm2 | 16 | 17.6 | m | 247104.54 | 116765.3025 | 363869.8425 | 4349039.904 | 2055069.324 | 6404109.228 |  |  | #REF! | 36% | 39% | 75% |  |  | 0%
|  | From DB PDP 2.1 Panel to Cetral feeding unit 3 | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 4x1Cx150mm2+E70mm2 | 57 | 68.2 | m | 247104.54 | 116765.3025 | 363869.8425 | 16852529.628 | 7963393.6305 | 24815923.2585 |  |  | #REF! | 36% | 39% | 75% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 49018783.6212 | 15188870.1199 | 64207653.7411 | 49018783.6212 | 15188870.1199 | 64207653.7411 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
2. 2. 50. |  | Energy measurement system | 1 | 1 | PSCH |  |  |  | 315804122.0768 | 12524296.2357 | 328328418.3125 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | SOFTWARE PRODUCTS | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Pre-parameterization per device | 11 | 11 | pcs | 343200 | 0 | 343200 | 3775200 | 0 | 3775200 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | visual energy ZP5 | 3 | 3 | pcs | 6063200 | 0 | 6063200 | 18189600 | 0 | 18189600 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hourly rate for remote services, Costs per hour / co-worker | 11 | 11 | pcs | 3832400 | 0 | 3832400 | 42156400 | 0 | 42156400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Freight charges | 1 | 1 | lot | 5291000 | 0 | 5291000 | 5291000 | 0 | 5291000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 3344406 | 1003321.8 | 4347727.8 | 3344406 | 1003321.8 | 4347727.8 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | MULTI METERS | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Multimess F144 | 11 | 11 | pcs | 21251230 | 275000 | 21526230 | 233763530 | 3025000 | 236788530 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | ELV cable | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cat6A | 330 | 330 | m | 21639.3443 | 3360 | 24999.3443 | 7140983.6066 | 1108800 | 8249783.6066 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 150 | 150 | m | 8773.9726 | 14594.0164 | 23367.989 | 1316095.8904 | 2189102.4618 | 3505198.3522 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 826906.5798 | 248071.974 | 1074978.5538 | 826906.5798 | 248071.974 | 1074978.5538 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | ENGINEERING SERVICES | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Labour cost for support DRX test funtion of Access control system | 1 | 1 | lot | 0 | 4950000 | 4950000 | 0 | 4950000 | 4950000 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
2. 2. 60. |  | Electrical installation in the production hall | 1 | 1 | PSCH |  |  |  | 2359220157.2575 | 298880144.662 | 2658100301.9195 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable trays_Hot dip-Galvanized Steel | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Production hall 01 | [6 empty] | 1059238180 | 131854511.8676 | 1191092691.8676 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable tray 500x100x2.0mm | 0 | 0 | m | 1443780 | 81001.3848 | 1524781.3848 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable tray 300x100x2.0mm | 0 | 129.8 | m | 1009710 | 61078.452 | 1070788.452 | 131060358 | 7927983.0721 | 138988341.0721 |  |  | #REF! | 30% | 45% | 75% | 25% | 25% | 25%
|  | Cable tray 200x100x2.0mm | 13 | 129.8 | m | 776880 | 51045.8655 | 827925.8655 | 100839024 | 6625753.3383 | 107464777.3383 |  |  | #REF! | 30% | 45% | 75% | 25% | 25% | 25%
|  | Cable tray 500x100 with separating bar, c/w cover | 185 | 215.6 | m | 1525680 | 81001.3848 | 1606681.3848 | 328936608 | 17463898.5532 | 346400506.5532 |  |  | #REF! | 30% | 45% | 75% | 25% | 25% | 25%
|  | Cable tray 400x100 with separating bar, c/w cover | 232 | 269.5 | m | 826020 | 68320 | 894340 | 222612390 | 18412240 | 241024630 |  |  | #REF! | 30% | 45% | 75% | 25% | 25% | 25%
|  | Cable tray 300x100 with separating bar, c/w cover | 112 | 0 | m | 1091610 | 61078.452 | 1152688.452 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable tray 200x100 with separating bar, c/w cover | 112 | 0 | m | 858780 | 51045.8655 | 909825.8655 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable tray 200x50 with separating bar, c/w cover | 187 | 0 | m | 669240 | 51045.8655 | 720285.8655 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable ladder 600x100x2.0mm, c/w cover | 9 | 0 | m | 1199250 | 91952 | 1291202 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable ladder 500x100x2.0mm, c/w cover | 0 | 0 | m | 1067040 | 81001.3848 | 1148041.3848 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable ladder 400x100x2.0mm, c/w cover | 5 | 5 | m | 933660 | 68320 | 1001980 | 4668300 | 341600 | 5009900 |  |  | #REF! | 30% | 45% | 75% | 25% | 25% | 25%
|  | Cable ladder 300x100x1.5mm, c/w cover | 2 | 2 | m | 625950 | 61078.452 | 687028.452 | 1251900 | 122156.904 | 1374056.904 |  |  | #REF! | 30% | 45% | 75% | 25% | 25% | 25%
|  | Fitting and accessories | 1 | 1 | lot | 269869600 | 80960880 | 350830480 | 269869600 | 80960880 | 350830480 |  |  | #REF! | 30% | 45% | 75% | 25% | 25% | 25%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Production hall 02 | [6 empty] | 205951658 | 26469471.7777 | 232421129.7777 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable tray 500x100x2.0mm | 0 |  | m | 1443780 | 81001.3848 | 1524781.3848 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable tray 300x100x2.0mm | 0 |  | m | 1009710 | 61078.452 | 1070788.452 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable tray 200x100x2.0mm | 10 |  | m | 776880 | 51045.8655 | 827925.8655 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable tray 500x100 with separating bar, c/w cover | 0 |  | m | 1525680 | 81001.3848 | 1606681.3848 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable tray 400x100 with separating bar, c/w cover | 64 | 73.7 | m | 826020 | 68320 | 894340 | 60877674 | 5035184 | 65912858 |  |  | #REF! | 30% | 45% | 75% | 25% | 25% | 25%
|  | Cable tray 300x100 with separating bar, c/w cover | 0 | 0 | m | 1091610 | 61078.452 | 1152688.452 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable tray 200x100 with separating bar, c/w cover | 82 | 94.6 | m | 858780 | 51045.8655 | 909825.8655 | 81240588 | 4828938.8737 | 86069526.8737 |  |  | #REF! | 30% | 45% | 75% | 25% | 25% | 25%
|  | Cable tray 200x50 with separating bar, c/w cover | 66 | 0 | m | 669240 | 51045.8655 | 720285.8655 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable ladder 600x100x2.0mm, c/w cover | 0 | 0 | m | 1199250 | 91952 | 1291202 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable ladder 500x100x2.0mm, c/w cover | 0 | 0 | m | 1067040 | 81001.3848 | 1148041.3848 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable ladder 400x100x2.0mm, c/w cover | 11 | 11 | m | 933660 | 68320 | 1001980 | 10270260 | 751520 | 11021780 |  |  | #REF! | 30% | 45% | 75% | 25% | 25% | 25%
|  | Cable ladder 300x100x1.5mm, c/w cover | 0 | 0 | m | 625950 | 61078.452 | 687028.452 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable ladder 200x100x1.5mm, c/w cover | 2 | 2.2 | m | 496080 | 51045.8655 | 547125.8655 | 1091376 | 112300.904 | 1203676.904 |  |  | #REF! | 30% | 45% | 75% | 25% | 25% | 25%
|  | Fitting and accessories | 1 | 1 | lot | 52471760 | 15741528 | 68213288 | 52471760 | 15741528 | 68213288 |  |  | #REF! | 30% | 45% | 75% | 25% | 25% | 25%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Electrical installation | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Production hall 01 | [6 empty] | 4068960 | 2081884 | 6150844 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 1-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 2-Way switch, 1 gang for lighting control panel | 0 | 0 | pcs | 0 | 54500 | 54500 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single Socket NEMA5 | 10 | 10 | pcs | 124560 | 54500 | 179060 | 1245600 | 545000 | 1790600 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Double Socket NEMA5 | 0 | 0 | pcs | 249120 | 54500 | 303620 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single Socket 16A/230V, Lighting outlet general (wall) + Plug | 18 | 18 | pcs | 124560 | 54500 | 179060 | 2242080 | 981000 | 3223080 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Socket combination type 1 | 1 | 1 | pcs | 0 | 381500 | 381500 | 0 | 381500 | 381500 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 581280 | 174384 | 755664 | 581280 | 174384 | 755664 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Production hall 02 | [6 empty] | 1017240 | 425096 | 1442336 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 1-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 2-Way switch, 1 gang for lighting control panel | 0 | 0 | pcs | 0 | 54500 | 54500 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single Socket NEMA5 | 2 | 2 | pcs | 124560 | 54500 | 179060 | 249120 | 109000 | 358120 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Double Socket NEMA5 | 0 | 0 | pcs | 249120 | 54500 | 303620 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single Socket 16A/230V, Lighting outlet general (wall) + Plug | 5 | 5 | pcs | 124560 | 54500 | 179060 | 622800 | 272500 | 895300 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 145320 | 43596 | 188916 | 145320 | 43596 | 188916 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Lighting | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Production hall 01 | [6 empty] | 891792936.3239 | 117504814.1732 | 1009297750.4972 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Led Highbay light 115W, Type CI | 154 | 154 | pcs | 4081000 | 196000 | 4277000 | 628474000 | 30184000 | 658658000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Frame Lamp 1x46W, Type BII | 2 | 2 | pcs | 1607100 | 63504 | 1670604 | 3214200 | 127008 | 3341208 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Wall mounted Light 1x15W, Type E | 18 | 18 | pcs | 585200 | 63504 | 648704 | 10533600 | 1143072 | 11676672 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 19140000 | 3828000 | 22968000 | 19140000 | 3828000 | 22968000 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable for lighting system (Hall 01) | [6 empty] | 230431136.3239 | 82222734.1732 | 312653870.4972 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE//PVC 3Cx4.0mm2 | 565 | 800 | m | 46999.53 | 8250 | 55249.53 | 37599624 | 6600000 | 44199624 |  |  | #REF! | 36% | 39% | 75% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 2404 | 2550 | m | 32518.74 | 7485.665 | 40004.405 | 82922787 | 19088445.75 | 102011232.75 |  |  | #REF! | 36% | 39% | 75% |  |  | 0%
|  | Cable Cu/XLPE//PVC 3Cx1.5mm2 | 359 | 889 | m | 22980.09 | 5743.9305 | 28724.0205 | 20429300.01 | 5106354.2145 | 25535654.2245 |  |  | #REF! | 36% | 39% | 75% |  |  | 0%
|  | PVC conduit D20 | 1061 | 1850 | m | 8773.9726 | 14594.0164 | 23367.989 | 16231849.3151 | 26998930.3618 | 43230779.6768 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D32(cho PA đổi cáp 3x6mm group A) |  | 749 | m | 19428.0822 | 20044.0164 | 39472.0986 | 14551633.5616 | 15012968.2924 | 29564601.8541 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 220 | 220 | m | 3554.7229 | 5289.7059 | 8844.4288 | 782039.0424 | 1163735.2941 | 1945774.3365 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 5485667.5348 | 1645700.2604 | 7131367.7953 | 5485667.5348 | 1645700.2604 | 7131367.7953 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE//PVC 3Cx6.0mm2 |  | 800.8 | m | 65469.825 | 8250 | 73719.825 | 52428235.86 | 6606600 | 59034835.86 |  |  | #REF! | 36% | 39% | 75% |  |  | 0%
|  | Production hall 02 | [6 empty] | 171116000 | 9147520 | 180263520 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Led Highbay light 115W, Type CI | 40 | 40 | pcs | 4081000 | 196000 | 4277000 | 163240000 | 7840000 | 171080000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Frame Lamp 1x46W, Type BII | 0 | 0 | pcs | 1607100 | 63504 | 1670604 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Wall mounted Light 1x15W, Type E | 5 | 5 | pcs | 585200 | 63504 | 648704 | 2926000 | 317520 | 3243520 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 4950000 | 990000 | 5940000 | 4950000 | 990000 | 5940000 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable for lighting system (Hall 02) | [6 empty] | 26035182.9336 | 11396846.8435 | 37432029.777 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 536 | 560 | m | 32518.74 | 7485.665 | 40004.405 | 18210494.4 | 4191972.4 | 22402466.8 |  |  | #REF! | 36% | 39% | 75% |  |  | 0%
|  | Cable Cu/XLPE//PVC 3Cx1.5mm2 | 96 | 120 | m | 22980.09 | 5743.9305 | 28724.0205 | 2757610.8 | 689271.66 | 3446882.46 |  |  | #REF! | 36% | 39% | 75% |  |  | 0%
|  | PVC conduit D20 | 277 | 398.2 | m | 8773.9726 | 14594.0164 | 23367.989 | 3493795.8904 | 5811337.3352 | 9305133.2256 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 88 | 0 | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 57 | 55 | m | 3554.7229 | 5289.7059 | 8844.4288 | 195509.7606 | 290933.8235 | 486443.5841 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 1377772.0826 | 413331.6248 | 1791103.7073 | 1377772.0826 | 413331.6248 | 1791103.7073 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
2. 2. 70. |  | Electrical installation in the logistics hall | 1 | 1 | PSCH |  |  |  | 365728225.5911 | 45073708.1139 | 410801933.705 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable trays_Hot dip-Galvanized Steel | [6 empty] | 184238087 | 23645406.8737 | 207883493.8737 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable tray 500x100x2.0mm | 0 | 0 | m | 1443780 | 81001.3848 | 1524781.3848 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable tray 300x100x2.0mm | 0 | 0 | m | 1009710 | 61078.452 | 1070788.452 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable tray 200x100x2.0mm | 10 |  | m | 776880 | 51045.8655 | 827925.8655 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable tray 500x100 with separating bar | 9 |  | m | 1525680 | 81001.3848 | 1606681.3848 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable tray 400x100 with separating bar | 56 | 66 | m | 826020 | 68320 | 894340 | 54517320 | 4509120 | 59026440 |  |  | #REF! | 30% | 45% | 75% | 25% | 25% | 25%
|  | Cable tray 300x100 with separating bar | 0 | 0 | m | 1091610 | 61078.452 | 1152688.452 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable tray 200x100 with separating bar | 83 | 94.6 | m | 858780 | 51045.8655 | 909825.8655 | 81240588 | 4828938.8737 | 86069526.8737 |  |  | #REF! | 30% | 45% | 75% | 25% | 25% | 25%
|  | Cable tray 200x50 with separating bar | 66 | 0 | m | 669240 | 51045.8655 | 720285.8655 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable ladder 600x100x2.0mm | 0 | 0 | m | 1199250 | 91952 | 1291202 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable ladder 500x100x2.0mm | 0 | 0 | m | 1067040 | 81001.3848 | 1148041.3848 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable ladder 400x100x2.0mm | 3 | 3.3 | m | 466830 | 68320 | 535150 | 1540539 | 225456 | 1765995 |  |  | #REF! | 30% | 45% | 75% | 25% | 25% | 25%
|  | Cable ladder 300x100x1.5mm | 0 | 0 | m | 625950 | 61078.452 | 687028.452 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable ladder 200x100x1.5mm | 0 | 0 | m | 496080 | 51045.8655 | 547125.8655 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Fitting and accessories | 1 | 1 | lot | 46939640 | 14081892 | 61021532 | 46939640 | 14081892 | 61021532 |  |  | #REF! | 30% | 45% | 75% | 25% | 25% | 25%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Electrical installation | [6 empty] | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 1-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 2-Way switch, 1 gang for lighting control panel | 0 | 0 | pcs | 0 | 54500 | 54500 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single Socket NEMA5 | 0 | 0 | pcs | 124560 | 54500 | 179060 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Double Socket NEMA5 | 0 | 0 | pcs | 249120 | 54500 | 303620 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Lighting | [6 empty] | 147378000 | 7630000 | 155008000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Led Highbay light 115W, Type CII | 35 | 35 | pcs | 4100800 | 196000 | 4296800 | 143528000 | 6860000 | 150388000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Frame Lamp 1x46W, Type BII | 0 | 0 | pcs | 1607100 | 63504 | 1670604 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 63504 | 648704 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 3850000 | 770000 | 4620000 | 3850000 | 770000 | 4620000 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable for lighting system | [6 empty] | 34112138.5911 | 13798301.2403 | 47910439.8314 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 693 | 805 | m | 32518.74 | 7485.665 | 40004.405 | 26177585.7 | 6025960.325 | 32203546.025 |  |  | #REF! | 36% | 39% | 75% |  |  | 0%
|  | Cable Cu/XLPE//PVC 3Cx1.5mm2 | 96 | 90 | m | 22980.09 | 5743.9305 | 28724.0205 | 2068208.1 | 516953.745 | 2585161.845 |  |  | #REF! | 36% | 39% | 75% |  |  | 0%
|  | PVC conduit D20 | 277 | 440 | m | 8773.9726 | 14594.0164 | 23367.989 | 3860547.9452 | 6421367.2212 | 10281915.1664 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 88 | 0 | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 33 | 55 | m | 3554.7229 | 5289.7059 | 8844.4288 | 195509.7606 | 290933.8235 | 486443.5841 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 1810287.0853 | 543086.1256 | 2353373.2109 | 1810287.0853 | 543086.1256 | 2353373.2109 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
2. 2. 80. |  | Power supply of building utilities | 1 | 1 | PSCH |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
2. 2. 90. |  | Three-arm Turnstile | 1 | 1 | PSCH |  |  |  | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
2. 2. 100. |  | Emergency lighting | 1 | 1 | PSCH |  |  |  | 77923218.1103 | 25617198.1684 | 103540416.2786 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Production hall 01 | [6 empty] | 18834457.2 | 3323337.16 | 22157794.36 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Emergency light | 13 | 13 | pcs | 516120 | 63504 | 579624 | 6709560 | 825552 | 7535112 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exit light | 13 | 13 | pcs | 566280 | 63504 | 629784 | 7361640 | 825552 | 8187192 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single Socket 16A/230V | 26 | 26 | pcs | 150480 | 54500 | 204980 | 3912480 | 1417000 | 5329480 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | pcs | 850777.2 | 255233.16 | 1106010.36 | 850777.2 | 255233.16 | 1106010.36 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable power supply | [6 empty] | 22294958.4377 | 8918664.6672 | 31213623.1048 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE//PVC 3Cx2.5mm2 | 619 | 569 | m | 32518.74 | 7485.665 | 40004.405 | 18503163.06 | 4259343.385 | 22762506.445 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | PVC conduit D20 | 371 | 275 | m | 8773.9726 | 14594.0164 | 23367.989 | 2412842.4658 | 4013354.5132 | 6426196.979 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 74 | 55 | m | 3554.7229 | 5289.7059 | 8844.4288 | 195509.7606 | 290933.8235 | 486443.5841 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 1183443.1513 | 355032.9454 | 1538476.0967 | 1183443.1513 | 355032.9454 | 1538476.0967 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Production hall 02 | [6 empty] | 8540160 | 1464048 | 10004208 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Emergency light | 6 | 6 | pcs | 516120 | 63504 | 579624 | 3096720 | 381024 | 3477744 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exit light | 6 | 6 | pcs | 566280 | 63504 | 629784 | 3397680 | 381024 | 3778704 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single Socket 16A/230V | 12 | 12 | pcs | 150480 | 54500 | 204980 | 1805760 | 654000 | 2459760 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | pcs | 240000 | 48000 | 288000 | 240000 | 48000 | 288000 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable power supply | [6 empty] | 10420834.2021 | 4757933.0991 | 15178767.3011 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE//PVC 3Cx2.5mm2 | 286 | 253 | m | 32518.74 | 7485.665 | 40004.405 | 8227241.22 | 1893873.245 | 10121114.465 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | PVC conduit D20 | 171 | 165 | m | 8773.9726 | 14594.0164 | 23367.989 | 1447705.4795 | 2408012.7079 | 3855718.1874 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 34 | 55 | m | 3554.7229 | 5289.7059 | 8844.4288 | 195509.7606 | 290933.8235 | 486443.5841 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 550377.742 | 165113.3226 | 715491.0646 | 550377.742 | 165113.3226 | 715491.0646 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Logistics area | [6 empty] | 7116800 | 1220040 | 8336840 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Emergency light | 5 | 5 | pcs | 516120 | 63504 | 579624 | 2580600 | 317520 | 2898120 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exit light | 5 | 5 | pcs | 566280 | 63504 | 629784 | 2831400 | 317520 | 3148920 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single Socket 16A/230V | 10 | 10 | pcs | 150480 | 54500 | 204980 | 1504800 | 545000 | 2049800 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | pcs | 200000 | 40000 | 240000 | 200000 | 40000 | 240000 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable power supply | [6 empty] | 10716008.2705 | 5933175.2421 | 16649183.5127 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE//PVC 3Cx2.5mm2 | 238 | 238 | m | 32518.74 | 7485.665 | 40004.405 | 7739460.12 | 1781588.27 | 9521048.39 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | PVC conduit D20 | 143 | 253 | m | 8773.9726 | 14594.0164 | 23367.989 | 2219815.0685 | 3692286.1522 | 5912101.2207 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 29 | 55 | m | 3554.7229 | 5289.7059 | 8844.4288 | 195509.7606 | 290933.8235 | 486443.5841 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 561223.3215 | 168366.9964 | 729590.3179 | 561223.3215 | 168366.9964 | 729590.3179 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
2. 2. 110. |  | Fire alarm system | 1 | 1 | PSCH |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 2. 120. |  | Network infrastructure | 1 | 1 | PSCH |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 2. 130. |  | Access control preparation | 1 | 1 | PSCH |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 2. 140. |  | CCTV System | 1 | 1 | PSCH |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. |  | Office, Social and Technical Areas (Hall 3) | [6 empty] | 8556494945.4536 | 444494571.6059 | 9000989517.0595 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. |  | Electrical engineering | 1 | 1 | PSCH |  |  |  | 8556494945.4536 | 444494571.6059 | 9000989517.0595 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 2. 10. |  | Rennovation existing grounding system and lightning protection | 1 | 1 | psch | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 2. 20. |  | Rennovation existing grounding and equipotential bonding | 1 | 1 | psch | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 2. 30. |  | Main Power supply | 1 | 1 | PSCH |  |  |  | 4272504384.025 | 197907035.9748 | 4470411419.9998 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Electrical panel | [6 empty] | 2486429270 | 40937031 | 2527366301 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Modify SYN - TR1, Add ACB 4P 2250A, 85ka, fixed type | 1 | 1 | pcs | 243347500 | 1400000 | 244747500 | 243347500 | 1400000 | 244747500 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Building3_BMDP min 1500kVA | 1 | 1 | pcs | 581849400 | 3920000 | 585769400 | 581849400 | 3920000 | 585769400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Building 3_PDP 1.0 | 1 | 1 | pcs | 137478000 | 1400000 | 138878000 | 137478000 | 1400000 | 138878000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Building 3_PDP 1.1 | 1 | 1 | pcs | 124835700 | 1400000 | 126235700 | 124835700 | 1400000 | 126235700 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Building 3_PDP 2.0 | 1 | 1 | pcs | 137478000 | 1400000 | 138878000 | 137478000 | 1400000 | 138878000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Building 3_PDP 1.2 | 1 | 1 | pcs | 160848600 | 1400000 | 162248600 | 160848600 | 1400000 | 162248600 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Building 3_PDP 2.1 | 1 | 1 | pcs | 162050900 | 1400000 | 163450900 | 162050900 | 1400000 | 163450900 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Building 3_BDP 1.0 | 1 | 1 | pcs | 113520000 | 1400000 | 114920000 | 113520000 | 1400000 | 114920000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Building 3_BDP 1.1 | 1 | 1 | pcs | 232601600 | 1400000 | 234001600 | 232601600 | 1400000 | 234001600 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Building 3_BDP 2.0 | 1 | 1 | pcs | 246041400 | 1400000 | 247441400 | 246041400 | 1400000 | 247441400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Scooter garage__BDP 1.0 | 1 | 1 | pcs | 15643100 | 840000 | 16483100 | 15643100 | 840000 | 16483100 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Canteen__BDP 1.0 | 1 | 1 | pcs | 47347300 | 1400000 | 48747300 | 47347300 | 1400000 | 48747300 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Building 3_DB SEF 1 | 1 | 1 | pcs | 28968500 | 840000 | 29808500 | 28968500 | 840000 | 29808500 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Building 3_DB SEF 2 | 1 | 1 | pcs | 24835800 | 840000 | 25675800 | 24835800 | 840000 | 25675800 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Building 3_UPS1-MDP | 1 | 1 | pcs | 91081100 | 1400000 | 92481100 | 91081100 | 1400000 | 92481100 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Building UPS1-DP1.2 | 1 | 1 | pcs | 79290200 | 1400000 | 80690200 | 79290200 | 1400000 | 80690200 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Building 3_UPS 1-DP 1.2 | 1 | 1 | pcs | 10457700 | 840000 | 11297700 | 10457700 | 840000 | 11297700 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Building 3_UPS 1 DP 1.3 | 1 | 1 | pcs | 8309400 | 840000 | 9149400 | 8309400 | 840000 | 9149400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Building 3_UPS 1 DP 1.3 35kVA | 1 | 1 | pcs | 70643100 | 1400000 | 72043100 | 70643100 | 1400000 | 72043100 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Building 3 UPS2-MD | 1 | 1 | pcs | 79290200 | 1400000 | 80690200 | 79290200 | 1400000 | 80690200 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Building UPS2-DP1.2 | 1 | 1 | pcs | 10457700 | 840000 | 11297700 | 10457700 | 840000 | 11297700 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Building 3_UPS 2-DP1.2 | 1 | 1 | pcs | 8309400 | 840000 | 9149400 | 8309400 | 840000 | 9149400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Building 3_UPS 2 DP 1.3 | 1 | 1 | pcs | 8309400 | 840000 | 9149400 | 8309400 | 840000 | 9149400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Building 3_UPS 2 DP 1.3 35kVA | 1 | 1 | pcs | 71126000 | 1400000 | 72526000 | 71126000 | 1400000 | 72526000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Building 3_DP PUMP 1 | 1 |  | pcs | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Building 3_DP PUMP 2 | 1 |  | pcs | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Fitting and accessories | 1 | 1 | lot | 35656770 | 10697031 | 46353801 | 35656770 | 10697031 | 46353801 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable trays_Hot dip-Galvanized Steel | [6 empty] | 982315957 | 122770928.7283 | 1105086885.7283 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable tray 500x100x2.0mm | 0 | 0 | m | 1443780 | 81001.3848 | 1524781.3848 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable tray 300x100x2.0mm | 0 | 0 | m | 1009710 | 61078.452 | 1070788.452 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable tray 200x100x2.0mm | 0 | 0 | m | 776880 | 51045.8655 | 827925.8655 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable tray 500x100 with separating bar, c/w cover | 0 | 93 | m | 1525680 | 81001.3848 | 1606681.3848 | 141888240 | 7533128.7822 | 149421368.7822 |  |  | #REF! | 25% | 20% | 45% |  |  | 25%
|  | Cable tray 400x100 with separating bar, c/w cover | 0 | 0 | m | 826020 | 68320 | 894340 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable tray 300x100 with separating bar, c/w cover | 0 | 0 | m | 1091610 | 61078.452 | 1152688.452 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable tray 200x100 with separating bar, c/w cover | 0 | 0 | m | 858780 | 51045.8655 | 909825.8655 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable tray 600x50 with separating bar, c/w cover | 26 | 28.6 | m | 1568970 | 87472 | 1656442 | 44872542 | 2501699.2 | 47374241.2 |  |  | #REF! | 25% | 20% | 45% |  |  | 25%
|  | Cable tray 500x50 with separating bar, c/w cover | 6 | 6.6 | m | 1334970 | 81001.3848 | 1415971.3848 | 8810802 | 534609.1394 | 9345411.1394 |  |  | #REF! | 25% | 20% | 45% |  |  | 25%
|  | Cable tray 400x50 with separating bar, c/w cover | 165 | 183.7 | m | 1136070 | 68320 | 1204390 | 208696059 | 12550384 | 221246443 |  |  | #REF! | 25% | 20% | 45% |  |  | 25%
|  | Cable tray 200x50 with separating bar, c/w cover | 303 | 453.2 | m | 669240 | 51045.8655 | 720285.8655 | 303299568 | 23133986.2319 | 326433554.2319 |  |  | #REF! | 25% | 20% | 45% |  |  | 25%
|  | Cable tray 100x50 with separating bar, c/w cover | 14 | 15.4 | m | 469170 | 51045.8655 | 520215.8655 | 7225218 | 786106.3283 | 8011324.3283 |  |  | #REF! | 25% | 20% | 45% |  |  | 25%
|  | Cable ladder 600x100x2.0mm, c/w cover | 0 | 0 | m | 1199250 | 91952 | 1291202 | 0 | 0 | 0 |  |  | #REF! | 25% | 20% | 45% |  |  | 25%
|  | Cable ladder 500x100x2.0mm, c/w cover | 2 | 2.2 | m | 1067040 | 81001.3848 | 1148041.3848 | 2347488 | 178203.0465 | 2525691.0465 |  |  | #REF! | 25% | 20% | 45% |  |  | 25%
|  | Cable ladder 400x100x2.0mm, c/w cover | 0 | 0 | m | 933660 | 68320 | 1001980 | 0 | 0 | 0 |  |  | #REF! | 25% | 20% | 45% |  |  | 25%
|  | Cable ladder 300x100x1.5mm, c/w cover | 0 | 0 | m | 625950 | 61078.452 | 687028.452 | 0 | 0 | 0 |  |  | #REF! | 25% | 20% | 45% |  |  | 25%
|  | Cable ladder 200x100x1.5mm, c/w cover | 0 | 0 | m | 496080 | 51045.8655 | 547125.8655 | 0 | 0 | 0 |  |  | #REF! | 25% | 20% | 45% |  |  | 25%
|  | Fitting and accessories | 1 | 1 | lot | 245176040 | 73552812 | 318728852 | 245176040 | 73552812 | 318728852 |  |  | #REF! | 25% | 20% | 45% |  |  | 25%
|  | Fire stop | 1 | 1 | set | 20000000 | 2000000 | 22000000 | 20000000 | 2000000 | 22000000 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Lighting control panel | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | BDP 1.0 | [6 empty] | 97882510.475 | 7025037.0385 | 104907547.5135 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 8P smart key, white plastic surface material | 1 | 1 | pcs | 17060781.92 | 137500 | 17198281.92 | 17060781.92 | 137500 | 17198281.92 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 4P smart key, white plastic surface material | 2 | 2 | pcs | 13652800 | 137500 | 13790300 | 27305600 | 275000 | 27580600 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Smart light control device for 8 independent load groups - 16A/ K | 1 | 1 | pcs | 19992667.52 | 49500 | 20042167.52 | 19992667.52 | 49500 | 20042167.52 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Smart light control device for 4 independent load groups - 16A/ K | 1 | 1 | pcs | 14090720 | 49500 | 14140220 | 14090720 | 49500 | 14140220 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Power supply for control signals, 24VDC | 2 | 2 | pcs | 8376816 | 49500 | 8426316 | 16753632 | 99000 | 16852632 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Base for smart keys | 3 | 3 | pcs | 41884.08 | 49500 | 91384.08 | 125652.24 | 148500 | 274152.24 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 2553456.795 | 766037.0385 | 3319493.8335 | 2553456.795 | 766037.0385 | 3319493.8335 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | T&C | 1 | 1 | lot | 0 | 5500000 | 5500000 | 0 | 5500000 | 5500000 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | BDP 1.1 | [6 empty] | 162133437.125 | 10750870.3775 | 172884307.5025 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 8P smart key, white plastic surface material | 3 | 3 | pcs | 17060781.92 | 137500 | 17198281.92 | 51182345.76 | 412500 | 51594845.76 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 4P smart key, white plastic surface material | 2 | 2 | pcs | 13652800 | 137500 | 13790300 | 27305600 | 275000 | 27580600 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Smart light control device for 8 independent load groups - 16A/ K | 2 | 2 | pcs | 19992667.52 | 49500 | 20042167.52 | 39985335.04 | 99000 | 40084335.04 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Smart light control device for 4 independent load groups - 16A/ K | 1 | 1 | pcs | 14090720 | 49500 | 14140220 | 14090720 | 49500 | 14140220 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Power supply for control signals, 24VDC | 3 | 3 | pcs | 8376816 | 49500 | 8426316 | 25130448 | 148500 | 25278948 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Base for smart keys | 5 | 5 | pcs | 41884.08 | 49500 | 91384.08 | 209420.4 | 247500 | 456920.4 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 4229567.925 | 1268870.3775 | 5498438.3025 | 4229567.925 | 1268870.3775 | 5498438.3025 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | T&C | 1 | 1 | lot | 0 | 8250000 | 8250000 | 0 | 8250000 | 8250000 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | BDP 2.0 | [6 empty] | 290635290.425 | 12702537.0555 | 303337827.4805 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 8P smart key, white plastic surface material | 7 | 7 | pcs | 17060781.92 | 137500 | 17198281.92 | 119425473.44 | 962500 | 120387973.44 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 4P smart key, white plastic surface material | 2 | 2 | pcs | 13652800 | 137500 | 13790300 | 27305600 | 275000 | 27580600 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Smart light control device for 8 independent load groups - 16A/ K | 4 | 4 | pcs | 19992667.52 | 49500 | 20042167.52 | 79970670.08 | 198000 | 80168670.08 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Smart light control device for 4 independent load groups - 16A/ K | 1 | 1 | pcs | 14090720 | 49500 | 14140220 | 14090720 | 49500 | 14140220 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Power supply for control signals, 24VDC | 5 | 5 | pcs | 8376816 | 49500 | 8426316 | 41884080 | 247500 | 42131580 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Base for smart keys | 9 | 9 | pcs | 41884.08 | 49500 | 91384.08 | 376956.72 | 445500 | 822456.72 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 7581790.185 | 2274537.0555 | 9856327.2405 | 7581790.185 | 2274537.0555 | 9856327.2405 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | T&C | 1 | 1 | lot | 0 | 8250000 | 8250000 | 0 | 8250000 | 8250000 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable power supply | [6 empty] | 9760419 | 2320631.775 | 12081050.775 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | From Building 3_BDP 1.1 Panel to DB-PUMP1 | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 4x1Cx4mm2+E4mm2 | 71 | 64 | m | 72299.4 | 17189.865 | 89489.265 | 4627161.6 | 1100151.36 | 5727312.96 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | From Building 3_BDP 2.0 Panel to DB-PUMP2 | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 4x1Cx4mm2+E4mm2 | 71 | 71 | m | 72299.4 | 17189.865 | 89489.265 | 5133257.4 | 1220480.415 | 6353737.815 |  |  | #REF! | 36% |  | 36% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. 40. |  | Uninterrupted power supply (UPS) | 1 | 1 | PSCH |  |  |  | 2008718012.8938 | 15050660.8087 | 2023768673.7025 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | UPS 93PR 60kW*100%load, backup 15 Minutes, frame 125kw | 2 | 2 | set | 967016600 | 3300000 | 970316600 | 1934033200 | 6600000 | 1940633200 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 93PR 125kW Frame to contain up to max. 6 Power Modules, Back-Feed, MBS & 1 x internal PDU | 0 | 0 |  | 310491720 | 0 | 310491720 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 93PR Power Module of 25KW capacity (Rev B) | 0 | 0 |  | 101372040 | 0 | 101372040 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Industrial Gateway Card | 0 | 0 |  | 9882180 | 0 | 9882180 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Eaton battery backup 15 mins @ 75kW | 0 | 0 |  | 6021400 | 0 | 6021400 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Battery cabinet, MCB, cable to connect Battery to UPS and accesoriess. | 0 | 0 |  | 99429000 | 0 | 99429000 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 10000000 | 2000000 | 12000000 | 10000000 | 2000000 | 12000000 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | water leak warning system | 2 | 2 | lot |  |  |  | 64684812.8938 | 6450660.8087 | 71135473.7025 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Water leak detector | 4 | 4 | pcs | 1587000 | 49500 | 1636500 | 6348000 | 198000 | 6546000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cabinet for Water leak detector | 4 | 4 | pcs | 1725000 | 220000 | 1945000 | 6900000 | 880000 | 7780000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Power supply | 4 | 4 | pcs | 862500 | 165000 | 1027500 | 3450000 | 660000 | 4110000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | water leak cable | 140 | 120 | m | 317400 | 22000 | 339400 | 38088000 | 2640000 | 40728000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Connection conductor A-LLW58; wire holder permanent | 4 | 4 | pcs | 1269600 | 49500 | 1319100 | 5078400 | 198000 | 5276400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single Socket 1P-16A-250V | 4 | 4 | pcs | 124560 | 54500 | 179060 | 498240 | 218000 | 716240 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 60 | 51 | m | 22980.09 | 5743.9305 | 28724.0205 | 1171984.59 | 292940.4555 | 1464925.0455 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | PVC conduit D20 | 58 | 35 | m | 8773.9726 | 14594.0164 | 23367.989 | 307089.0411 | 510790.5744 | 817879.6155 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 2843099.2627 | 852929.7788 | 3696029.0415 | 2843099.2627 | 852929.7788 | 3696029.0415 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. 50. |  | Electrical Capacitor bank | 1 | 1 | PSCH |  |  |  | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Electrical Capacitor bank Building3_BMDP min 1500kVA | 1 |  | pcs | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. 60. |  | Power supply of building utilities | 1 | 1 | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. 70. |  | Energy measurement system | 1 | 1 | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. 80. |  | Electrical installation in offices and meeting rooms | 1 | 1 | PSCH |  |  |  | 1229075412.0457 | 66404103.9782 | 1295479516.0239 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Switch & Socket | [6 empty] | 221333361.2618 | 14243567.4985 | 235576928.7604 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 1-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Push-button - (switch) | 37 | 37 | pcs | 223200 | 54500 | 277700 | 8258400 | 2016500 | 10274900 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single Socket NEMA5 | 15 | 15 | pcs | 124560 | 54500 | 179060 | 1868400 | 817500 | 2685900 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Double Socket NEMA5 | 15 | 15 | pcs | 249120 | 54500 | 303620 | 3736800 | 817500 | 4554300 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Dimmer Switch | 6 | 6 | pcs | 254400 | 54500 | 308900 | 1526400 | 327000 | 1853400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cord outlet socket with 2m cable reserve with connection terminals, E1 | 6 | 6 | pcs | 507247.2 | 54500 | 561747.2 | 3043483.2 | 327000 | 3370483.2 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cord outlet socket with 4m cable reserve with connection terminals, E2 | 0 | 0 | pcs | 507247.2 | 54500 | 561747.2 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cord outlet socket with 6m cable reserve with connection terminals, E3 | 33 | 33 | pcs | 507247.2 | 54500 | 561747.2 | 16739157.6 | 1798500 | 18537657.6 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Floor box, recessed (3xDouble Socket NEMA5, 2xIT - Double socket) | 3 | 3 | pcs | 8885676 | 272500 | 9158176 | 26657028 | 817500 | 27474528 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Floor box, recessed (4xDouble Socket NEMA5, 2xIT - Double socket) | 1 | 1 | pcs | 9467332.8 | 272500 | 9739832.8 | 9467332.8 | 272500 | 9739832.8 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Floor box, recessed (1xDouble Socket NEMA5, 1xIT - Double socket,1x HDMI connection to the projector) | 3 | 3 | pcs | 9216914.4 | 272500 | 9489414.4 | 27650743.2 | 817500 | 28468243.2 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Floor box, recessed (2xDouble Socket NEMA5, 2xIT - Double socket, 1x HDMI connection to the projector) | 1 | 1 | pcs | 10490947.2 | 272500 | 10763447.2 | 10490947.2 | 272500 | 10763447.2 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Floor box, recessed (3xDouble Socket NEMA5, 2xIT - Double socket, 1x HDMI connection to the projector) | 0 | 0 | pcs | 11072604 | 272500 | 11345104 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Floor box, recessed (4xDouble Socket NEMA5, 2xIT - Double socket, 1x HDMI connection to the projector) | 2 | 2 | pcs | 11654260.8 | 272500 | 11926760.8 | 23308521.6 | 545000 | 23853521.6 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Projector + Accessories | 3 | 3 | pcs | 18650000 | 381500 | 19031500 | 55950000 | 1144500 | 57094500 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Motion sensor | 19 | 19 | pcs | 1150224 | 54500 | 1204724 | 21854256 | 1035500 | 22889756 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 10781891.6618 | 3234567.4985 | 14016459.1604 | 10781891.6618 | 3234567.4985 | 14016459.1604 |  |  | #REF! |  |  | 0% |  |  | 0%
|  |  | 0 | 0 | [9 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Lighting | 0 | 0 |  |  |  |  | 643593600 | 11842000 | 655435600 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Panel 36W, Type AI | 168 | 168 | pcs | 3339600 | 56000 | 3395600 | 561052800 | 9408000 | 570460800 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Panel 36W, Type AI - Dali Dim | 23 | 23 | pcs | 3339600 | 56000 | 3395600 | 76810800 | 1288000 | 78098800 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Frame Lamp 1x46W, Type BII | 0 | 0 | pcs | 1607100 | 56000 | 1663100 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 56000 | 641200 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 5730000 | 1146000 | 6876000 | 5730000 | 1146000 | 6876000 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable power | [6 empty] | 364148450.7839 | 40318536.4797 | 404466987.2635 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 1142 | 1002 | m | 22980.09 | 5743.9305 | 28724.0205 | 23026050.18 | 5755418.361 | 28781468.541 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | 3C-2.5mm2 Cu/XLPE/PVC | 630 | 570 | m | 32518.74 | 7485.665 | 40004.405 | 18535681.8 | 4266829.05 | 22802510.85 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | 3C-2.5mm2 Cu/XLPE/PVC for E1, E2, E3 | 303 | 303 | m | 32518.74 | 7485.665 | 40004.405 | 9853178.22 | 2268156.495 | 12121334.715 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 0 | 0 | m | 72299.4 | 17189.865 | 89489.265 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 0 | 0 | m | 102372.9 | 18573.4395 | 120946.3395 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Dado duct 50x130mm | 296 | 296 | m | 985945.6609 | 53025 | 1038970.6609 | 291839915.6313 | 15695400 | 307535315.6313 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 507 | 507 | m | 8773.9726 | 14594.0164 | 23367.989 | 4448404.1096 | 7399166.3208 | 11847570.4304 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 16445220.843 | 4933566.2529 | 21378787.0959 | 16445220.843 | 4933566.2529 | 21378787.0959 |  |  | #REF! |  |  | 0% |  |  | 0%
|  |  | 0 | 0 | [9 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. 90. |  | Electrical installation in social rooms | 1 | 1 | PSCH |  |  |  | 258752977.5651 | 35385729.898 | 294138707.4631 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Switch & Socket | [6 empty] | 10372584.6 | 3183623.38 | 13556207.98 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 1-Way switch, 1 gang | 2 | 2 | pcs | 46800 | 54500 | 101300 | 93600 | 109000 | 202600 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single Socket NEMA5 | 29 | 29 | pcs | 124560 | 54500 | 179060 | 3612240 | 1580500 | 5192740 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Double Socket NEMA5 | 25 | 25 | pcs | 249120 | 54500 | 303620 | 6228000 | 1362500 | 7590500 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Power outlet general, 3p/4W, grounded | 0 | 0 | pcs | 150480 | 54500 | 204980 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 438744.6 | 131623.38 | 570367.98 | 438744.6 | 131623.38 | 570367.98 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Lighting | [6 empty] | 180626800 | 8680000 | 189306800 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Panel 36W, Type AI | 0 | 0 | pcs | 3339600 | 56000 | 3395600 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Frame Lamp 1x30W, Type BI | 56 | 56 | pcs | 1346400 | 56000 | 1402400 | 75398400 | 3136000 | 78534400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Frame Lamp 1x46W, Type BII | 4 | 4 | pcs | 1607100 | 56000 | 1663100 | 6428400 | 224000 | 6652400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 56000 | 641200 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Ceiling mounted Light 1x19W, Type D | 80 | 80 | pcs | 1182500 | 56000 | 1238500 | 94600000 | 4480000 | 99080000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 4200000 | 840000 | 5040000 | 4200000 | 840000 | 5040000 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable power | [6 empty] | 67753592.9651 | 23522106.518 | 91275699.4831 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 1187 | 1492.7 | m | 22980.09 | 5743.9305 | 28724.0205 | 34302380.343 | 8573965.0574 | 42876345.4004 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | 3C-2.5mm2 Cu/XLPE/PVC | 690 | 792 | m | 32518.74 | 7485.665 | 40004.405 | 25754842.08 | 5928646.68 | 31683488.76 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 0 | 0 | m | 72299.4 | 17189.865 | 89489.265 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 0 | 0 | m | 102372.9 | 18573.4395 | 120946.3395 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Dado duct 50x130mm | 0 | 0 | m | 985945.6609 | 53025 | 1038970.6609 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 703 | 561 | m | 8773.9726 | 14594.0164 | 23367.989 | 4922198.6301 | 8187243.207 | 13109441.8371 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 2774171.912 | 832251.5736 | 3606423.4856 | 2774171.912 | 832251.5736 | 3606423.4856 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. 100. |  | Electrical installation in corridors and stairways | 1 | 1 | PSCH |  |  |  | 74974338.2247 | 17389802.6953 | 92364140.92 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Switch & Socket | [6 empty] | 13582018.8 | 4641349.64 | 18223368.44 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 1-Way switch, 1 gang | 6 | 6 | pcs | 46800 | 54500 | 101300 | 280800 | 327000 | 607800 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Push-button switch | 32 | 32 | pcs | 223200 | 54500 | 277700 | 7142400 | 1744000 | 8886400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single Socket NEMA5 | 12 | 12 | pcs | 124560 | 54500 | 179060 | 1494720 | 654000 | 2148720 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Double Socket NEMA5 | 0 | 0 | pcs | 249120 | 54500 | 303620 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Power outlet general, 1p/2W, grounded | 4 | 4 | pcs | 150480 | 54500 | 204980 | 601920 | 218000 | 819920 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Power outlet general, 3p/4W, grounded | 0 | 0 | pcs | 150480 | 54500 | 204980 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single Socket 16A/230V, Lighting outlet general (wall) + Plug | 28 | 28 | pcs | 124560 | 54500 | 179060 | 3487680 | 1526000 | 5013680 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 574498.8 | 172349.64 | 746848.44 | 574498.8 | 172349.64 | 746848.44 |  |  | #REF! |  |  | 0% |  |  | 0%
|  |  | 0 | 0 | [9 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Lighting | 0 | 0 |  |  |  |  | 40385700 | 2790000 | 43175700 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Panel 36W, Type AI | 0 | 0 | pcs | 3339600 | 56000 | 3395600 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Frame Lamp 1x30W, Type BI | 0 | 0 | pcs | 1346400 | 56000 | 1402400 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Frame Lamp 1x46W, Type BII for Canopy | 6 | 6 | pcs | 1607100 | 56000 | 1663100 | 9642600 | 336000 | 9978600 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Wall mounted Light 1x15W, Type E | 28 | 28 | pcs | 585200 | 56000 | 641200 | 16385600 | 1568000 | 17953600 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Ceiling mounted Light 1x19W, Type D | 16 | 11 | pcs | 1182500 | 56000 | 1238500 | 13007500 | 616000 | 13623500 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 0 | 1 | lot | 1350000 | 270000 | 1620000 | 1350000 | 270000 | 1620000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  |  | 0 | 0 | [9 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable power | 0 | 0 |  |  |  |  | 21006619.4247 | 9958453.0553 | 30965072.48 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 478 | 450 | m | 22980.09 | 5743.9305 | 28724.0205 | 10341040.5 | 2584768.725 | 12925809.225 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | 3C-2.5mm2 Cu/XLPE/PVC | 217 | 190 | m | 32518.74 | 7485.665 | 40004.405 | 6178560.6 | 1422276.35 | 7600836.95 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 0 | 0 | m | 72299.4 | 17189.865 | 89489.265 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 0 | 0 | m | 102372.9 | 18573.4395 | 120946.3395 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Dado duct 50x130mm | 0 | 0 | m | 985945.6609 | 53025 | 1038970.6609 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 384 | 385 | m | 8773.9726 | 14594.0164 | 23367.989 | 3377979.4521 | 5618696.3185 | 8996675.7706 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 1109038.8726 | 332711.6618 | 1441750.5344 | 1109038.8726 | 332711.6618 | 1441750.5344 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. 110. |  | Electrical installation in technical areas | 1 | 1 | PSCH |  |  |  | 86058509.2699 | 9713896.6252 | 95772405.895 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Switch & Socket | [6 empty] | 2553112.8 | 2375897.84 | 4929010.64 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 1-Way switch, 1 gang | 7 | 7 | pcs | 46800 | 54500 | 101300 | 327600 | 381500 | 709100 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single Socket NEMA5 | 13 | 13 | pcs | 124560 | 54500 | 179060 | 1619280 | 708500 | 2327780 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Double Socket NEMA5 | 2 | 2 | pcs | 249120 | 54500 | 303620 | 498240 | 109000 | 607240 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Power outlet general, 3p/4W, grounded | 0 | 0 | pcs | 150480 | 54500 | 204980 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single Socket 16A/230V, Lighting outlet general (wall) + Plug | 0 | 0 | pcs | 124560 | 54500 | 179060 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Socket combination type 1 | 3 | 3 | pcs | 0 | 381500 | 381500 | 0 | 1144500 | 1144500 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 107992.8 | 32397.84 | 140390.64 | 107992.8 | 32397.84 | 140390.64 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Lighting | [6 empty] | 68830900 | 2170000 | 71000900 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Panel 36W, Type AI | 0 | 0 | pcs | 3339600 | 56000 | 3395600 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Frame Lamp 1x30W, Type BI | 0 | 0 | pcs | 1346400 | 56000 | 1402400 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Frame Lamp 1x46W, Type BII | 28 | 28 | pcs | 1607100 | 56000 | 1663100 | 44998800 | 1568000 | 46566800 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 56000 | 641200 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Ceiling mounted Light 1x19W, Type D | 0 | 0 | pcs | 1182500 | 56000 | 1238500 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Battery-operated hand lamp | 7 | 7 | pcs | 3254585.7143 | 56000 | 3310585.7143 | 22782100 | 392000 | 23174100 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 1050000 | 210000 | 1260000 | 1050000 | 210000 | 1260000 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable power | [6 empty] | 14674496.4699 | 5167998.7852 | 19842495.255 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 167 | 150 | m | 22980.09 | 5743.9305 | 28724.0205 | 3447013.5 | 861589.575 | 4308603.075 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | 3C-2.5mm2 Cu/XLPE/PVC | 100 | 110 | m | 32518.74 | 7485.665 | 40004.405 | 3577061.4 | 823423.15 | 4400484.55 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 0 | 0 | m | 72299.4 | 17189.865 | 89489.265 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 43 | 53.9 | m | 102372.9 | 18573.4395 | 120946.3395 | 5517899.31 | 1001108.3891 | 6519007.6991 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | Dado duct 50x130mm | 0 | 0 | m | 985945.6609 | 53025 | 1038970.6609 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 150 | 154 | m | 8773.9726 | 14594.0164 | 23367.989 | 1351191.7808 | 2247478.5274 | 3598670.3082 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 781330.479 | 234399.1437 | 1015729.6228 | 781330.479 | 234399.1437 | 1015729.6228 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. 120. |  | Electrical installation in kitchenette areas | 1 | 1 | PSCH |  |  |  | 92827708.5941 | 16840279.0483 | 109667987.6424 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Switch & Socket | [6 empty] | 9916993.8 | 3613842.14 | 13530835.94 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 1-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single Socket NEMA5 | 47 | 47 | pcs | 124560 | 54500 | 179060 | 5854320 | 2561500 | 8415820 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Double Socket NEMA5 | 11 | 11 | pcs | 249120 | 54500 | 303620 | 2740320 | 599500 | 3339820 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Power outlet general, 3p/4W, grounded | 6 | 6 | pcs | 150480 | 54500 | 204980 | 902880 | 327000 | 1229880 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 419473.8 | 125842.14 | 545315.94 | 419473.8 | 125842.14 | 545315.94 |  |  | #REF! |  |  | 0% |  |  | 0%
|  |  | 0 | 0 | [9 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Lighting | 0 | 0 |  |  |  |  | 40075200 | 672000 | 40747200 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Panel 36W, Type AI | 12 | 12 | pcs | 3339600 | 56000 | 3395600 | 40075200 | 672000 | 40747200 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Frame Lamp 1x46W, Type BII | 0 | 0 | pcs | 1607100 | 56000 | 1663100 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 56000 | 641200 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 0 | 0 | lot | 240000 | 48000 | 288000 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  |  | 0 | 0 | [9 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable power | 0 | 0 |  |  |  |  | 42835514.7941 | 12554436.9083 | 55389951.7024 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 196 | 210 | m | 22980.09 | 5743.9305 | 28724.0205 | 4825818.9 | 1206225.405 | 6032044.305 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 501 | 480 | m | 72299.4 | 17189.865 | 89489.265 | 34703712 | 8251135.2 | 42954847.2 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | Dado duct 50x130mm | 0 | 0 | m | 985945.6609 | 53025 | 1038970.6609 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 120 | 176 | m | 8773.9726 | 14594.0164 | 23367.989 | 1544219.1781 | 2568546.8885 | 4112766.0666 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 1761764.716 | 528529.4148 | 2290294.1308 | 1761764.716 | 528529.4148 | 2290294.1308 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. 130. |  | Electrical installation for Workshop/Formbrettbau | 1 | 1 | PSCH |  |  |  | 90067954.1041 | 12614941.0865 | 102682895.1906 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Switch & Socket | [6 empty] | 596177.4 | 1315565.22 | 1911742.62 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 1-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Push-button switch | 2 | 2 | pcs | 223200 | 54500 | 277700 | 446400 | 109000 | 555400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single Socket NEMA5 | 1 | 1 | pcs | 124560 | 54500 | 179060 | 124560 | 54500 | 179060 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Double Socket NEMA5 | 0 | 0 | pcs | 249120 | 54500 | 303620 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Power outlet general, 3p/4W, grounded | 0 | 0 | pcs | 150480 | 54500 | 204980 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Socket combination type 2 | 3 | 3 | pcs | 0 | 381500 | 381500 | 0 | 1144500 | 1144500 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 25217.4 | 7565.22 | 32782.62 | 25217.4 | 7565.22 | 32782.62 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Lighting | [6 empty] | 52067200 | 1920000 | 53987200 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Panel 36W, Type AI | 0 | 0 | pcs | 3339600 | 56000 | 3395600 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Frame Lamp 1x46W, Type BII | 32 | 32 | pcs | 1607100 | 56000 | 1663100 | 51427200 | 1792000 | 53219200 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 56000 | 641200 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 640000 | 128000 | 768000 | 640000 | 128000 | 768000 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable power | [6 empty] | 37404576.7041 | 9379375.8665 | 46783952.5706 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 222 | 234 | m | 22980.09 | 5743.9305 | 28724.0205 | 5377341.06 | 1344079.737 | 6721420.797 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 94 | 80 | m | 72299.4 | 17189.865 | 89489.265 | 5783952 | 1375189.2 | 7159141.2 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 248 | 230 | m | 102372.9 | 18573.4395 | 120946.3395 | 23545767 | 4271891.085 | 27817658.085 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | Dado duct 50x130mm | 0 | 0 | m | 985945.6609 | 53025 | 1038970.6609 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 115 | 132 | m | 8773.9726 | 14594.0164 | 23367.989 | 1158164.3836 | 1926410.1664 | 3084574.5499 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 1539352.2605 | 461805.6782 | 2001157.9387 | 1539352.2605 | 461805.6782 | 2001157.9387 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. 140. |  | Electrical installation at the reception | 1 | 1 | PSCH |  |  |  | 41960735.3385 | 4068070.8188 | 46028806.1573 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Switch & Socket | [6 empty] | 1915601.436 | 405808.1108 | 2321409.5468 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 1-Way switch, 1 gang | 1 | 1 | pcs | 46800 | 54500 | 101300 | 46800 | 54500 | 101300 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single Socket NEMA5 | 1 | 1 | pcs | 124560 | 54500 | 179060 | 124560 | 54500 | 179060 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Double Socket NEMA5 | 2 | 2 | pcs | 249120 | 54500 | 303620 | 498240 | 109000 | 607240 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Power outlet general, 1p/2W, grounded | 1 | 1 | pcs | 150480 | 54500 | 204980 | 150480 | 54500 | 204980 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Power outlet general, 3p/4W, grounded | 0 | 0 | pcs | 150480 | 54500 | 204980 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cord outlet socket with 2m cable reserve with connection terminals, E1 | 2 | 2 | pcs | 507247.2 | 54500 | 561747.2 | 1014494.4 | 109000 | 1123494.4 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cord outlet socket with 4m cable reserve with connection terminals, E2 | 0 | 0 | pcs | 507247.2 | 54500 | 561747.2 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cord outlet socket with 6m cable reserve with connection terminals, E3 | 0 | 0 | pcs | 507247.2 | 54500 | 561747.2 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 81027.036 | 24308.1108 | 105335.1468 | 81027.036 | 24308.1108 | 105335.1468 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Lighting | [6 empty] | 13438400 | 240000 | 13678400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Panel 36W, Type AI | 4 | 4 | pcs | 3339600 | 56000 | 3395600 | 13358400 | 224000 | 13582400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Frame Lamp 1x46W, Type BII | 0 | 0 | pcs | 1607100 | 56000 | 1663100 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 56000 | 641200 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 80000 | 16000 | 96000 | 80000 | 16000 | 96000 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable power | [6 empty] | 26606733.9025 | 3422262.708 | 30028996.6105 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 60 | 55 | m | 22980.09 | 5743.9305 | 28724.0205 | 1263904.95 | 315916.1775 | 1579821.1275 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 80 | 74.8 | m | 72299.4 | 17189.865 | 89489.265 | 5407995.12 | 1285801.902 | 6693797.022 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 3 | 4.4 | m | 102372.9 | 18573.4395 | 120946.3395 | 450440.76 | 81723.1338 | 532163.8938 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | Dado duct 50x130mm | 18 | 18 | m | 985945.6609 | 53025 | 1038970.6609 | 17747021.8965 | 954450 | 18701471.8965 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 26 | 22 | m | 8773.9726 | 14594.0164 | 23367.989 | 193027.3973 | 321068.3611 | 514095.7583 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 1544343.7787 | 463303.1336 | 2007646.9124 | 1544343.7787 | 463303.1336 | 2007646.9124 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. 150. |  | Electrical installation in other rooms/secondary rooms | 1 | 1 | PSCH |  |  |  | 275591719.5806 | 31538420.0323 | 307130139.6129 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Switch & Socket | [6 empty] | 15705304.986 | 4668293.1758 | 20373598.1618 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 1-Way switch, 1 gang | 7 | 7 | pcs | 46800 | 54500 | 101300 | 327600 | 381500 | 709100 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Push-button switch | 9 | 9 | pcs | 223200 | 54500 | 277700 | 2008800 | 490500 | 2499300 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single Socket NEMA5 | 10 | 10 | pcs | 124560 | 54500 | 179060 | 1245600 | 545000 | 1790600 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Double Socket NEMA5 | 9 | 9 | pcs | 249120 | 54500 | 303620 | 2242080 | 490500 | 2732580 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Power outlet general, 1p/2W, grounded | 0 | 0 | pcs | 150480 | 54500 | 204980 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Power outlet general, 3p/4W, grounded | 0 | 0 | pcs | 150480 | 54500 | 204980 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Socket combination type 1 | 4 | 4 | pcs | 0 | 381500 | 381500 | 0 | 1526000 | 1526000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Socket combination type 2 | 2 | 2 | pcs | 0 | 381500 | 381500 | 0 | 763000 | 763000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cord outlet socket with 2m cable reserve with connection terminals, E1 | 0 | 0 | pcs | 507247.2 | 54500 | 561747.2 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cord outlet socket with 4m cable reserve with connection terminals, E2 | 0 | 0 | pcs | 507247.2 | 54500 | 561747.2 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cord outlet socket with 6m cable reserve with connection terminals, E3 | 0 | 0 | pcs | 507247.2 | 54500 | 561747.2 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Floor box, recessed (1xDouble Socket NEMA5, 1xIT - Double socket,1x HDMI connection to the projector) | 1 | 1 | pcs | 9216914.4 | 272500 | 9489414.4 | 9216914.4 | 272500 | 9489414.4 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 664310.586 | 199293.1758 | 863603.7618 | 664310.586 | 199293.1758 | 863603.7618 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Lighting | [6 empty] | 135827400 | 4650000 | 140477400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Panel 36W, Type AI | 9 | 9 | pcs | 3339600 | 56000 | 3395600 | 30056400 | 504000 | 30560400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Frame Lamp 1x46W, Type BII | 58 | 60 | pcs | 1607100 | 56000 | 1663100 | 96426000 | 3360000 | 99786000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 56000 | 641200 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Ceiling mounted Light 1x19W, Type D | 6 | 6 | pcs | 1182500 | 56000 | 1238500 | 7095000 | 336000 | 7431000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 2250000 | 450000 | 2700000 | 2250000 | 450000 | 2700000 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable power | [6 empty] | 124059014.5946 | 22220126.8565 | 146279141.4511 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 693 | 684.5455 | m | 22980.09 | 5743.9305 | 28724.0205 | 15730916.1545 | 3931981.515 | 19662897.6695 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | 3C-2.5mm2 Cu/XLPE/PVC | 442 | 464 | m | 32518.74 | 7485.665 | 40004.405 | 15088695.36 | 3473348.56 | 18562043.92 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 0 | 0 | m | 72299.4 | 17189.865 | 89489.265 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 317 | 280 | m | 102372.9 | 18573.4395 | 120946.3395 | 28664412 | 5200563.06 | 33864975.06 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | Dado duct 50x130mm | 57 | 57 | m | 985945.6609 | 53025 | 1038970.6609 | 56198902.6722 | 3022425 | 59221327.6722 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 278 | 341 | m | 8773.9726 | 14594.0164 | 23367.989 | 2991924.6575 | 4976559.5964 | 7968484.2539 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 5384163.7503 | 1615249.1251 | 6999412.8754 | 5384163.7503 | 1615249.1251 | 6999412.8754 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. 160. |  | Emergency lighting | 1 | 1 | PSCH |  |  |  | 125963193.8122 | 37581630.6399 | 163544824.4521 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Switch & Socket | [6 empty] | 73296840 | 12022500 | 85319340 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Emergency light | 81 | 81 | pcs | 516120 | 56000 | 572120 | 41805720 | 4536000 | 46341720 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exit light | 24 | 24 | pcs | 566280 | 56000 | 622280 | 13590720 | 1344000 | 14934720 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single Socket 16A/230V | 105 | 105 | pcs | 150480 | 54500 | 204980 | 15800400 | 5722500 | 21522900 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | pcs | 2100000 | 420000 | 2520000 | 2100000 | 420000 | 2520000 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable power supply | [6 empty] | 52666353.8122 | 25559130.6399 | 78225484.4521 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 1575 | 1265 | m | 32518.74 | 7485.665 | 40004.405 | 41136206.1 | 9469366.225 | 50605572.325 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | PVC conduit D20 | 882 | 950 | m | 8773.9726 | 14594.0164 | 23367.989 | 8335273.9726 | 13864315.5912 | 22199589.5638 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 315 | 300 | m | 3554.7229 | 5289.7059 | 8844.4288 | 1066416.876 | 1586911.7647 | 2653328.6407 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 2128456.8636 | 638537.0591 | 2766993.9226 | 2128456.8636 | 638537.0591 | 2766993.9226 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
4. |  | Machine hook-up (Hall 3) | [6 empty] | 3164184545.4338 | 446703070.7456 | 3610887616.1794 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
4. 1. |  | Electrical engineering | 1 | 1 | PSCH |  |  |  | 3164184545.4338 | 446703070.7456 | 3610887616.1794 |  |  | #REF! |  |  | 0% |  |  | 0%
4. 1. 10. |  | Machine hook-up | 1 | 1 | PSCH |  |  |  | 3164184545.4338 | 446703070.7456 | 3610887616.1794 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable trays_Hot dip-Galvanized Steel | [6 empty] | 538685840 | 65789758.3358 | 604475598.3358 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable tray 400x100x2.0mm | 122 | 122 | m | 776880 | 68320 | 845200 | 94779360 | 8335040 | 103114400 |  |  | #REF! | 30% | 40% | 70% |  |  | 30%
|  | Cable tray 500x100 with separating bar | 195 | 201 | m | 1525680 | 81001.3848 | 1606681.3848 | 306661680 | 16281278.3358 | 322942958.3358 |  |  | #REF! | 30% | 40% | 70% |  |  | 30%
|  | Fitting and accessories | 1 | 1 | lot | 137244800 | 41173440 | 178418240 | 137244800 | 41173440 | 178418240 |  |  | #REF! | 30% | 40% | 70% |  |  | 30%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Busway Canalis KSA 250A 3L+N+PE 10kA/s, IP54 | [6 empty] | 2002937565.0909 | 225436964.9679 | 2228374530.0588 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 250A Feeder,3L+N+PE | 190 | 194 | m | 7268140 | 553706.5149 | 7821846.5149 | 1410019160 | 107419063.8906 | 1517438223.8906 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 250A Cable Tap Box - End | 6 | 6 | pcs | 5043610 | 497400.75 | 5541010.75 | 30261660 | 2984404.5 | 33246064.5 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 100-250A End Cover | 6 | 6 | pcs | 551650 | 27500 | 579150 | 3309900 | 165000 | 3474900 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Joint Cover | 70 | 70 | pcs | 813560 | 27500 | 841060 | 56949200 | 1925000 | 58874200 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PIO Cover | 282 | 651 | pcs | 90090 | 27500 | 117590 | 58648590 | 17902500 | 76551090 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Fixing Bracket | 70 | 70 | pcs | 109450 | 220200.75 | 329650.75 | 7661500 | 15414052.5 | 23075552.5 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Screw-on plate for blanking of unused openings | 138 | 138 | pcs | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Tap-off Unit included: - 1x Busbar tap-off unit with 16A/230V 3pin Industrial Socket CEE - 1x MCB 2P 16A | 82 | 69 | pcs | 2882070 | 497400.75 | 3379470.75 | 198862830 | 34320651.75 | 233183481.75 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Tap-off Unit included: - 1x Busbar tap-off unit with 16A/400V 5pin Industrial Socket CEE - 1x MCB 3P 16A | 56 | 56 | pcs | 3041460 | 497400.75 | 3538860.75 | 170321760 | 27854442 | 198176202 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Industrial plug 16A-230V for Industrial socket 16A-230V | 82 | 69 | pcs | 226176 | 54500 | 280676 | 15606144 | 3760500 | 19366644 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Industrial plug 16A-400V for Industrial socket 16A-400V | 56 | 56 | pcs | 282720 | 54500 | 337220 | 15832320 | 3052000 | 18884320 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 35464501.0909 | 10639350.3273 | 46103851.4182 | 35464501.0909 | 10639350.3273 | 46103851.4182 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Electrical installation Production | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Schuko-socket 16A/230V | 0 | 0 | pcs | 0 | 54500 | 54500 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 16A/230V 3pin Industrial Socket CEE | 41 | 41 | pcs | 381600 | 54500 | 436100 | 15645600 | 2234500 | 17880100 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Socket combination type 1 | 21 | 21 | pcs | 0 | 381500 | 381500 | 0 | 8011500 | 8011500 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Socket combination type 2 | 10 | 10 | pcs | 0 | 381500 | 381500 | 0 | 3815000 | 3815000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 691014 | 207304.2 | 898318.2 | 691014 | 207304.2 | 898318.2 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable power | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | From Building 3_UPS 1 DP 1.3 35kVA Panel to16A/230V Socket (19 set) | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | 3C-2.5mm2 Cu/XLPE/PVC | 892 | 737 | m | 32518.74 | 7485.665 | 40004.405 | 23966311.38 | 5516935.105 | 29483246.485 |  |  | #REF! | 36% | 34% | 70% |  |  | 0%
|  | From Building 3_UPS 2 DP 1.3 35kVA Panel to16A/230V Socket (22 set) | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | 3C-2.5mm2 Cu/XLPE/PVC | 1107 | 1033 | m | 32518.74 | 7485.665 | 40004.405 | 33591858.42 | 7732691.945 | 41324550.365 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | From PDP 1.0 Panel to Combine socket (9 set) | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 587 | 519 | m | 72299.4 | 17189.865 | 89489.265 | 37523388.6 | 8921539.935 | 46444928.535 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | From PDP 1.1 Panel to Combine socket (3 set) | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 197 | 110 | m | 72299.4 | 17189.865 | 89489.265 | 7952934 | 1890885.15 | 9843819.15 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | From PDP 1.2 Panel to Combine socket (4 set) | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 182 | 205 | m | 72299.4 | 17189.865 | 89489.265 | 14821377 | 3523922.325 | 18345299.325 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | From PDP 2.0 Panel to Combine socket (9 set) | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 830 | 811 | m | 72299.4 | 17189.865 | 89489.265 | 58634813.4 | 13940980.515 | 72575793.915 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | From PDP 2.1 Panel to Combine socket (6 set) | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 440 | 445 | m | 72299.4 | 17189.865 | 89489.265 | 32173233 | 7649489.925 | 39822722.925 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | PVC conduit D20 | 246 | 250 | m | 8773.9726 | 14594.0164 | 23367.989 | 2193493.1507 | 3648504.1029 | 5841997.2536 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 9074248.7636 | 2722274.6291 | 11796523.3926 | 9074248.7636 | 2722274.6291 | 11796523.3926 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Tel-Data system | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Double data outlet RJ45 | 179 | 191 | pcs | 480000 | 81750 | 561750 | 91680000 | 15614250 | 107294250 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Cable Cat6A | 12618 | 12970 | m | 21639.3443 | 3360 | 24999.3443 | 280662295.082 | 43579200 | 324241495.082 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | PVC conduit D20 | 160 | 170.7263 | m | 8773.9726 | 14594.0164 | 23367.989 | 1497947.5013 | 2491581.7963 | 3989529.2977 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Network cable test cost - FO cable |  |  | nos | 0 | 50600 | 50600 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Network cable test cost - Cat6A cable | 376 | 400 | nos | 0 | 50600 | 50600 | 0 | 20240000 | 20240000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 12452626.0453 | 3735787.8136 | 16188413.8589 | 12452626.0453 | 3735787.8136 | 16188413.8589 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
5. |  | Scooter Garage | [6 empty] | 108075385.8789 | 16341158.0259 | 124416543.9048 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
5. 2. |  | Electrical Engineering | 1 | 1 | PSCH |  |  |  | 108075385.8789 | 16341158.0259 | 124416543.9048 |  |  | #REF! |  |  | 0% |  |  | 0%
5. 2. 10. |  | Grounding and Lightining protection | 1 |  | PSCH |  |  |  | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Classic lightning rod Ø16, l = 1,000mm | 9 |  | m | 312500 | 120872.0782 | 433372.0783 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Claded copper - steel grounding rod Ø 16, L = 2.4m | 9 |  | m | 210227.2727 | 120872.0782 | 331099.351 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exothermic welding connection | 19 |  | m | 119318.1818 | 56925 | 176243.1818 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Grounding Test Link box | 1 |  | m | 562500 | 56925 | 619425 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Bare Copper wire 50sqmm | 322 |  | m | 135322.14 | 22106.7 | 157428.84 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 54 |  | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | T&C | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
5. 2. 20. |  | Power supply | 1 | 1 | PSCH |  |  |  | 48996560 | 6144115.6772 | 55140675.6772 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable trays | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable tray 200x100x2.0mm, c/w cover | 47 | 47 | m | 776880 | 51045.8655 | 827925.8655 | 36513360 | 2399155.6772 | 38912515.6772 |  |  | #REF! | 30% |  | 30% |  |  | 30%
|  | Fitting and accessories | 1 | 1 | lot | 12483200 | 3744960 | 16228160 | 12483200 | 3744960 | 16228160 |  |  | #REF! | 30% |  | 30% |  |  | 30%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
5. 2. 30. |  | Power supply of building utilities | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
5. 2. 40. |  | Electrical installations | 1 | 1 | PSCH |  |  |  | 44249283.3619 | 5904426.8866 | 50153710.2486 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Switch & Socket | [6 empty] | 11703872.04 | 857016.812 | 12560888.852 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 1-Way switch, 1 gang | 2 | 2 | pcs | 46800 | 54500 | 101300 | 93600 | 109000 | 202600 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 16A/230V 3pin Industrial Socket CEE | 2 | 2 | pcs | 381600 | 54500 | 436100 | 763200 | 109000 | 872200 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Motion sensor | 9 | 9 | pcs | 1150224 | 54500 | 1204724 | 10352016 | 490500 | 10842516 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 495056.04 | 148516.812 | 643572.852 | 495056.04 | 148516.812 | 643572.852 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Lighting | [6 empty] | 25171700 | 992000 | 26163700 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Frame Lamp 1x46W, Type BII | 15 | 15 | pcs | 1607100 | 56000 | 1663100 | 24106500 | 840000 | 24946500 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Wall mounted Light 1x15W, Type E | 1 | 1 | pcs | 585200 | 56000 | 641200 | 585200 | 56000 | 641200 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 480000 | 96000 | 576000 | 480000 | 96000 | 576000 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable power | [6 empty] | 7373711.3219 | 4055410.0746 | 11429121.3966 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 164 | 149 | m | 22980.09 | 5743.9305 | 28724.0205 | 3424033.41 | 855845.6445 | 4279879.0545 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | 3C-2.5mm2 Cu/XLPE/PVC | 68 | 61 | m | 32518.74 | 7485.665 | 40004.405 | 1983643.14 | 456625.565 | 2440268.705 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | PVC conduit D20 | 12 | 180 | m | 8773.9726 | 14594.0164 | 23367.989 | 1579315.0685 | 2626922.9541 | 4206238.0226 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 386719.7034 | 116015.911 | 502735.6145 | 386719.7034 | 116015.911 | 502735.6145 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
5. 2. 50. |  | Emergency lighting | 1 | 1 | PSCH |  |  |  | 14829542.5169 | 4292615.4621 | 19122157.979 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Emergency light | 6 | 12 | pcs | 516120 | 56000 | 572120 | 6193440 | 672000 | 6865440 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exit light | 1 | 2 | pcs | 566280 | 56000 | 622280 | 1132560 | 112000 | 1244560 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single Socket 16A/230V | 8 | 8 | pcs | 124560 | 54500 | 179060 | 996480 | 436000 | 1432480 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | pcs | 440000 | 88000 | 528000 | 440000 | 88000 | 528000 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable power supply | [6 empty] | 6067062.5169 | 2984615.4621 | 9051677.979 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx1.5mm2 | 120 | 205 | m | 22980.09 | 5743.9305 | 28724.0205 | 4710918.45 | 1177505.7525 | 5888424.2025 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | PVC conduit D20 | 68 | 110 | m | 8773.9726 | 14594.0164 | 23367.989 | 965136.9863 | 1605341.8053 | 2570478.7916 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 24 | 20 | m | 3554.7229 | 5289.7059 | 8844.4288 | 71094.4584 | 105794.1176 | 176888.576 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 319912.6222 | 95973.7867 | 415886.4089 | 319912.6222 | 95973.7867 | 415886.4089 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
6. |  | Canteen | [6 empty] | 350267145.0631 | 45874850.9531 | 396141996.0162 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
6. 2. |  | Electrical Engineering | 1 | 1 | PSCH |  |  |  | 350267145.0631 | 45874850.9531 | 396141996.0162 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Notes Calculation Basis | [11 empty] | #REF! |  |  | 0% |  |  | 0%
6. 2. 10. |  | Grounding and Lightining protection | 1 | 1 | PSCH |  |  |  | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Classic lightning rod Ø16, l = 1,000mm | 6 |  | m | 312500 | 120872.0782 | 433372.0783 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Claded copper - steel grounding rod Ø 16, L = 2.4m | 6 |  | m | 210227.2727 | 120872.0782 | 331099.351 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exothermic welding connection | 21 |  | m | 119318.1818 | 56925 | 176243.1818 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Grounding Test Link box | 2 |  | m | 562500 | 56925 | 619425 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Bare Copper wire 50sqmm | 259 |  | m | 135322.14 | 22106.7 | 157428.84 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 36 |  | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | T&C | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
6. 2. 20. |  | Power supply | 1 | 1 | PSCH |  |  |  | 106191661.9795 | 12858262.8895 | 119049924.8689 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable trays_Hot dip-Galvanized Steel | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable tray 200x50 with separating bar | 149 | 149 | m | 669240 | 56000 | 725240 | 99716760 | 8344000 | 108060760 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 215 | 215 | m | 8773.9726 | 14594.0164 | 23367.989 | 1886404.1096 | 3137713.5285 | 5024117.6381 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Fitting and accessories | 1 | 1 | lot | 4588497.8699 | 1376549.361 | 5965047.2308 | 4588497.8699 | 1376549.361 | 5965047.2308 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
6. 2. 30. |  | Power supply of building utilities | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 2. 40. |  | Electrical installations | 1 | 1 | PSCH |  |  |  | 220631937.3221 | 25881817.2569 | 246513754.579 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Switch & Socket | [6 empty] | 27779110.24 | 5475504.272 | 33254614.512 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 1-Way switch, 1 gang | 5 | 5 | pcs | 46800 | 54500 | 101300 | 234000 | 272500 | 506500 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single Socket NEMA5 | 24 | 24 | pcs | 124560 | 54500 | 179060 | 2989440 | 1308000 | 4297440 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 16A/230V 3pin Industrial Socket CEE | 4 | 4 | pcs | 381600 | 54500 | 436100 | 1526400 | 218000 | 1744400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Socket combination type 1 | 6 | 6 | pcs | 0 | 381500 | 381500 | 0 | 2289000 | 2289000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Motion sensor | 19 | 19 | pcs | 1150224 | 54500 | 1204724 | 21854256 | 1035500 | 22889756 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 1175014.24 | 352504.272 | 1527518.512 | 1175014.24 | 352504.272 | 1527518.512 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Lighting | [6 empty] | 141953700 | 6649872 | 148603572 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Frame Lamp 1x46W, Type BII | 5 | 5 | pcs | 1607100 | 63504 | 1670604 | 8035500 | 317520 | 8353020 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Frame Lamp 1x46W, Type J | 70 | 70 | pcs | 1607100 | 63504 | 1670604 | 112497000 | 4445280 | 116942280 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Wall mounted Light 1x15W, Type E | 6 | 6 | pcs | 585200 | 63504 | 648704 | 3511200 | 381024 | 3892224 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LED Ceiling mounted Light 1x19W, Type D | 12 | 12 | pcs | 1182500 | 63504 | 1246004 | 14190000 | 762048 | 14952048 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 3720000 | 744000 | 4464000 | 3720000 | 744000 | 4464000 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable power | [6 empty] | 50899127.0821 | 13756440.9849 | 64655568.067 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 697 | 572 | m | 22980.09 | 5743.9305 | 28724.0205 | 13144611.48 | 3285528.246 | 16430139.726 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | 3C-2.5mm2 Cu/XLPE/PVC | 496 | 464 | m | 32518.74 | 7485.665 | 40004.405 | 15088695.36 | 3473348.56 | 18562043.92 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 242 | 226 | m | 72299.4 | 17189.865 | 89489.265 | 16339664.4 | 3884909.49 | 20224573.89 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 30 | 30 | m | 102372.9 | 18573.4395 | 120946.3395 | 3071187 | 557203.185 | 3628390.185 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | PVC conduit D20 | 117 | 132 | m | 8773.9726 | 14594.0164 | 23367.989 | 1158164.3836 | 1926410.1664 | 3084574.5499 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 2096804.4585 | 629041.3376 | 2725845.7961 | 2096804.4585 | 629041.3376 | 2725845.7961 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
6. 2. 50. |  | Emergency lighting | 1 | 1 | PSCH |  |  |  | 23443545.7616 | 7134770.8067 | 30578316.5683 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Emergency light | 14 | 15 | pcs | 516120 | 63504 | 579624 | 7741800 | 952560 | 8694360 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exit light | 7 | 7 | pcs | 566280 | 63504 | 629784 | 3963960 | 444528 | 4408488 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single Socket 16A/230V | 9 | 15 | pcs | 124560 | 54500 | 179060 | 1868400 | 817500 | 2685900 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | pcs | 440000 | 88000 | 528000 | 440000 | 88000 | 528000 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable power supply | [6 empty] | 9429385.7616 | 4832182.8067 | 14261568.5683 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 315 | 221 | m | 32518.74 | 7485.665 | 40004.405 | 7186641.54 | 1654331.965 | 8840973.505 |  |  | #REF! | 36% |  | 36% |  |  | 0%
|  | PVC conduit D20 | 177 | 190 | m | 8773.9726 | 14594.0164 | 23367.989 | 1667054.7945 | 2772863.1182 | 4439917.9128 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 63 | 55 | m | 3554.7229 | 5289.7059 | 8844.4288 | 195509.7606 | 290933.8235 | 486443.5841 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 380179.6664 | 114053.8999 | 494233.5664 | 380179.6664 | 114053.8999 | 494233.5664 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | II. ELV | [8 empty] | 3412928080.1667 |  |  | #REF! |  |  | 0% |  |  | 0%
1. |  | Construction site facilities | [6 empty] | 124241733.1691 | 20176036.5818 | 144417769.7509 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
1. 1. |  | Construction site facilities | 1 | 1 | psch | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
1. 2. |  | Construction site cameras | 1 | 1 | psch |  |  |  | 124241733.1691 | 20176036.5818 | 144417769.7509 |  |  | #REF! | 60% |  | 60% | 0.5 | 0.5 | 50%
|  | Rack for NVR+Swtich | 1 | 1 | pcs | 1848000 | 165000 | 2013000 | 1848000 | 165000 | 2013000 |  |  | #REF! | 60% |  | 60% | 0.5 | 0.5 | 50%
|  | Camera bullet 360' + base, Resolution: 4K | 3 | 3 | pcs | 9067520 | 198000 | 9265520 | 27202560 | 594000 | 27796560 |  |  | #REF! | 60% |  | 60% | 0.5 | 0.5 | 50%
|  | NVR 8 chanel | 1 | 1 | pcs | 9431520 | 165000 | 9596520 | 9431520 | 165000 | 9596520 |  |  | #REF! | 60% |  | 60% | 0.5 | 0.5 | 50%
|  | 1KVA UPS | 1 | 1 | pcs | 2529000 | 137500 | 2666500 | 2529000 | 137500 | 2666500 |  |  | #REF! | 60% |  | 60% | 0.5 | 0.5 | 50%
|  | Switch PoE 4P | 1 | 1 | pcs | 1155000 | 81750 | 1236750 | 1155000 | 81750 | 1236750 |  |  | #REF! | 60% |  | 60% | 0.5 | 0.5 | 50%
|  | LCD 32" | 1 | 1 | pcs | 8360000 | 163500 | 8523500 | 8360000 | 163500 | 8523500 |  |  | #REF! | 60% |  | 60% | 0.5 | 0.5 | 50%
|  | Double Socket 16A/230V | 3 | 3 | pcs | 150480 | 54500 | 204980 | 451440 | 163500 | 614940 |  |  | #REF! | 60% |  | 60% | 0.5 | 0.5 | 50%
|  | PVC box for socket, conver at camera | 3 | 3 | pcs | 36000 | 16350 | 52350 | 108000 | 49050 | 157050 |  |  | #REF! | 60% |  | 60% | 0.5 | 0.5 | 50%
|  | surge protection | 2 | 2 | pcs | 4494000 | 49050 | 4543050 | 8988000 | 98100 | 9086100 |  |  | #REF! | 60% |  | 60% | 0.5 | 0.5 | 50%
|  | Cable Cat6 | 10 | 10 | m | 10032.7869 | 3360 | 13392.7869 | 100327.8689 | 33600 | 133927.8689 |  |  | #REF! | 60% |  | 60% | 0.5 | 0.5 | 50%
|  | converter quang đồng | 6 | 6 | pcs | 770000 | 49050 | 819050 | 4620000 | 294300 | 4914300 |  |  | #REF! | 60% |  | 60% | 0.5 | 0.5 | 50%
|  | Fiber optical 2FO | 373 | 373 | m | 14400 | 3360 | 17760 | 5371200 | 1253280 | 6624480 |  |  | #REF! | 60% |  | 60% | 0.5 | 0.5 | 50%
|  | Cable Cu/XLPE/PVC 3Cx1.5mm2 | 397 | 397 | m | 22980.09 | 5743.9305 | 28724.0205 | 9123095.73 | 2280340.4085 | 11403436.1385 |  |  | #REF! | 60% |  | 60% | 0.5 | 0.5 | 50%
|  | PVC conduit D20 | 81 | 81 | m | 8773.9726 | 14594.0164 | 23367.989 | 710691.7808 | 1182115.3294 | 1892807.1102 |  |  | #REF! | 60% |  | 60% | 0.5 | 0.5 | 50%
|  | HDPE pipe D25/32 | 397 | 397 | m | 10550.2392 | 11445 | 21995.2392 | 4188444.9761 | 4543665 | 8732109.9761 |  |  | #REF! | 60% |  | 60% | 0.5 | 0.5 | 50%
|  | Camera Pole 15m | 3 | 3 | pcs | 10000000 | 450000 | 10450000 | 30000000 | 1350000 | 31350000 |  |  | #REF! | 60% |  | 60% | 0.5 | 0.5 | 50%
|  | Reforce cable for camera pole | 3 | 3 | lot | 550000 | 250000 | 800000 | 1650000 | 750000 | 2400000 |  |  | #REF! | 60% |  | 60% | 0.5 | 0.5 | 50%
|  | Concrete plinth | 3 | 3 | lot | 1000000 | 500000 | 1500000 | 3000000 | 1500000 | 4500000 |  |  | #REF! | 60% |  | 60% | 0.5 | 0.5 | 50%
|  | Remove Pole + Camera | 3 | 3 | time | 0 | 1250000 | 1250000 | 0 | 3750000 | 3750000 |  |  | #REF! | 60% |  | 60% | 0.5 | 0.5 | 50%
|  | Accessories | 1 | 1 | lot | 5404452.8133 | 1621335.844 | 7025788.6573 | 5404452.8133 | 1621335.844 | 7025788.6573 |  |  | #REF! | 60% |  | 60% | 0.5 | 0.5 | 50%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
2. |  | Production and Logistic building (Hall 3) | [6 empty] | 803801420.8294 | 119493877.9513 | 923295298.7807 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
2.1. |  | Civil Engineering | 1 | 1 | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
2. 1. 10. |  | Calculations | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 20. |  | Rainwater and waste water sewer | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 30. |  | Earthworks | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 40. |  | Demolition, removal and dismantling works | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 50. |  | Foundation | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 60. |  | Building structure | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 70. |  | General concrete- / reinforced concrete works | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 80. |  | Fire protection | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 90. |  | Fire rated walls | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 100. |  | Cutting base slabs / ceilings / floors | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 110. |  | Cutting holes into existing facades, walls and roofs | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 120. |  | Exterior walls | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 130. |  | Exterior doors and windows | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 140. |  | Fire protection doors | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 150. |  | Internal doors | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 160. |  | Fire protection roller shutter door | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 170. |  | Fire protection bulkhead | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 180. |  | High speed roller shutter | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 190. |  | Fitting and metal work - general | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 200. |  | Railings and hand rails | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 210. |  | Steel stage for installations | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 220. |  | Collision protection | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 230. |  | canopies of exterior doors | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 240. |  | Concerete steps in front of the hall | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 250. |  | Painting and varnishing works | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 260. |  | Guidance systems | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 270. |  | Locking system | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 280. |  | Internal signage | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 290. |  | Adjustment ridge vent | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 300. |  | Roof reinforcment Option 1 | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 310. |  | Insert new ventilation louvers | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 1. 320. |  | Metal louvers to cover mechanical units | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
2. 2. |  | Electrical Engineering | 1 | 1 | PSCH |  |  |  | 120237495.4217 | 36030743.1568 | 156268238.5785 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 2. 10. |  | Adjustment of existing facilities, dismantling and disposal works | 1 | 1 | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
2. 2. 20. |  | Rennovation existing grounding system and lightning protection | 1 | 1 | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
2. 2. 30. |  | Rennovation existing grounding and equipotential bonding | 1 | 1 | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
2. 2. 40. |  | Power supply | 1 | 1 | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
2. 2. 50. |  | Energy measurement system | 1 | 1 | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
2. 2. 60. |  | Electrical installation in the production hall | 1 | 1 | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
2. 2. 70. |  | Electrical installation in the logistics hall | 1 | 1 | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
2. 2. 80. |  | Power supply of building utilities | 1 | 1 | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
2. 2. 90. |  | Three-arm Turnstile | 1 | 1 | PSCH |  |  |  | 120237495.4217 | 36030743.1568 | 156268238.5785 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | INTUS ACM40e-NT as access control manager | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | INTUS ACM40e-NT (S3840-380) Intelligent access control manager (Supplier by Client) | 4 | 4 | set | 0 | 616000 | 616000 | 0 | 2464000 | 2464000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | INTUS ACM40e 2-4 reader-ext (V3841-202) Firmware extension from 2 to 4 access readers (Supplier by Client) | 4 | 4 | set | 0 | 616000 | 616000 | 0 | 2464000 | 2464000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Network configuration setup fee (3000-243) Set up of one IPv4 terminal basis configuration by PCS. Precondition: Excel- or CSV-file with following details: IPaddress and net mask terminal, IP-address gateway, TCPport. Host name. This information must be submitted with the order. (by Client) | 4 | 4 | set | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | INTUS 6xx/7xx as RFID reader for access control | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | NTUS 615/La ( S3850-670) INTUS 615 Legic advant r/w access reader for flush mounting. Reads/writes Legic prime and Legic advant cards/tags. PCS universal coding: VNA00- 000 (Supplier by Client) | 8 | 8 | set | 0 | 616000 | 616000 | 0 | 4928000 | 4928000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | INTUS 600/500/400 reader configuration fee (V3000-231) INTUS reader configuration price for customer specific car coding deviating from PCS standard coding. Also required for standalone parametrization. (by Client) | 8 | 8 | set | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | NTUS 600 spacer frame (S3850-607) INTUS 315ro/615/620 spacer frame, mandatory for mounting on metal wall or for surface mounting cable introduction (Supplier by Client) | 8 | 8 | set | 0 | 616000 | 616000 | 0 | 4928000 | 4928000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | NTUS 700-Panel/La (S3853-610) SM4200-M Legic advant r/w access reader for mounting in metal panels. Reads/writes Legic prime and Legic advant cards/tags. PCS universal coding: VNA00-000 (Supplier by Client) | 8 | 8 | set | 0 | 616000 | 616000 | 0 | 4928000 | 4928000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | INTUS 700 reader configuration fee (V3000-249) INTUS 700 reader configuration price for card coding, deviating from PCS standard coding. (by Client) | 8 | 8 | set | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 5A, 12VDC Power supply adapter | 1 | 1 | set | 2220000 | 95200 | 2315200 | 2220000 | 95200 | 2315200 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Push button for releasing entrance & exit lock at reception area | 1 | 4 | pcs | 528000 | 61600 | 589600 | 2112000 | 246400 | 2358400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Emergency at the reception area | 1 | 4 | pcs | 528000 | 61600 | 589600 | 2112000 | 246400 | 2358400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cabinet box for controller located at reception | 1 | 1 | set | 3000000 | 280000 | 3280000 | 3000000 | 280000 | 3280000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Backup battery, 12VDC 7Ah | 4 | 4 | set | 540000 | 72800 | 612800 | 2160000 | 291200 | 2451200 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Tripod turnstile | 4 | 4 | set | 21600000 | 369600 | 21969600 | 86400000 | 1478400 | 87878400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Double Socket 16A/230V | 4 | 4 | pcs | 150480 | 54500 | 204980 | 601920 | 218000 | 819920 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Signal cable, AWG18 - 1Pair | 153 | 153 | m | 15000 | 3360 | 18360 | 2295000 | 514080 | 2809080 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cat6A | 327 | 301 | m | 21639.3443 | 3360 | 24999.3443 | 6513442.623 | 1011360 | 7524802.623 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 50 | 150 | m | 32518.74 | 7485.665 | 40004.405 | 4877811 | 1122849.75 | 6000660.75 |  |  | #REF! |  | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 369 | 360 | m | 8773.9726 | 14594.0164 | 23367.989 | 3158630.137 | 5253845.9082 | 8412476.0452 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cutting concrete background and backfill | 5 | 5 | m | 0 | 125000 | 125000 | 0 | 625000 | 625000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Labour cost for support DRX test funtion of Turnstile system | 1 | 1 | lot | 0 | 3500000 | 3500000 | 0 | 3500000 | 3500000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 4786691.6618 | 1436007.4985 | 6222699.1603 | 4786691.6618 | 1436007.4985 | 6222699.1603 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
2. 2. 100. |  | Emergency lighting | 1 | 1 | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
2. 2. 120. |  | Network infrastructure | 1 | 1 | PSCH |  |  | 0 | 307745509.2338 | 64282788.3235 | 372028297.5573 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single Mode OS2 48 fibers SC- Duplex | 207 | 230 | m | 144000 | 28000 | 172000 | 33120000 | 6440000 | 39560000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | 20 x 0,8 pair copper phone wire | 0 | 0 | m | 117360 | 13798.4 | 131158.4 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | IDF7 42U (0.8x1.0x2.0), Included PDU, 10 patch panel, Cable routing channel 1U | 1 | 1 | pcs | 68750000 | 1308000 | 70058000 | 68750000 | 1308000 | 70058000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Patch panel 24 Port CAT6A | 8 |  | pcs | 5060000 | 654000 | 5714000 | 0 | 0 | 0 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Patch panel 24 Port cat 5e | 2 | 2 | pcs | 2195600 | 654000 | 2849600 | 4391200 | 1308000 | 5699200 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Cat 6A Patch Cord, 3m | 77 | 77 | pcs | 600000 | 13440 | 613440 | 46200000 | 1034880 | 47234880 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Cat 6A Patch Cord, 3m | 0 | 0 | pcs | 600000 | 13440 | 613440 | 0 | 0 | 0 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | ODF F.O Singlemode, 48F | 2 | 2 | pcs | 6490000 | 490500 | 6980500 | 12980000 | 981000 | 13961000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Socket strip (PDU) with 7 sockets | 2 | 2 | pcs | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 16A Turnlock socket | 2 | 2 | pcs | 150480 | 54500 | 204980 | 300960 | 109000 | 409960 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Patch panel 24 Port | 0 | 0 | pcs | 5060000 | 654000 | 5714000 | 0 | 0 | 0 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Double data outlet RJ45 | 26 | 26 | pcs | 480000 | 81750 | 561750 | 12480000 | 2125500 | 14605500 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Wifi module (Wifi supply by Client) | 25 | 25 | pcs | 0 | 136250 | 136250 | 0 | 3406250 | 3406250 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | FO Patch Cord, SC-SC Duplex, LSOH, SM,3m | 20 | 20 | pcs | 550000 | 10900 | 560900 | 11000000 | 218000 | 11218000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | FO Pigtail LC, SM, 1m for welding to optical fibre | 20 | 96 | pcs | 132000 | 65400 | 197400 | 12672000 | 6278400 | 18950400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cat 6A Patch Cord, 3m from Data outlet to Wifi | 25 | 25 | pcs | 198000 | 10900 | 208900 | 4950000 | 272500 | 5222500 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Cable Cat6A | 3219 | 3245 | m | 21639.3443 | 3360 | 24999.3443 | 70219672.1311 | 10903200 | 81122872.1311 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | PVC conduit D20 | 1610 | 1510 | m | 8773.9726 | 14594.0164 | 23367.989 | 13248698.6301 | 22036964.7818 | 35285663.4119 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Network cable test cost - Cat6A cable | 52 | 52 | nos | 0 | 50600 | 50600 | 0 | 2631200 | 2631200 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 17432978.4725 | 5229893.5417 | 22662872.0142 | 17432978.4725 | 5229893.5417 | 22662872.0142 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
2. 2. 130. |  | Access control preparation | 1 | 1 | PSCH |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 2. 140. |  | CCTV System | 1 | 1 | PSCH |  |  | 0 | 375818416.1739 | 19180346.471 | 394998762.6449 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Outside Camera CE-1-->12 | 12 | 12 | pcs | 19242720 | 198000 | 19440720 | 230912640 | 2376000 | 233288640 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Symphony Standard Edition - VMS Device License | 12 | 12 | pcs | 2704800 | 330000 | 3034800 | 32457600 | 3960000 | 36417600 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Telescopic parapet mount (T91D62) | 12 | 12 | pcs | 1803200 | 49500 | 1852700 | 21638400 | 594000 | 22232400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Overvoltage protection | 12 | 12 | pcs | 4494000 | 49050 | 4543050 | 53928000 | 588600 | 54516600 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Double data outlet RJ45 | 12 | 12 | pcs | 480000 | 81750 | 561750 | 5760000 | 981000 | 6741000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Cat 6A Patch Cord, 3m | 36 | 24 | pcs | 198000 | 10900 | 208900 | 4752000 | 261600 | 5013600 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Cable Cat6A | 686 | 658.24 | m | 21639.3443 | 3360 | 24999.3443 | 14243881.9672 | 2211686.4 | 16455568.3672 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | PVC conduit D20 | 274 | 280.5 | m | 8773.9726 | 14594.0164 | 23367.989 | 2461099.3151 | 4093621.6035 | 6554720.9186 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Network cable test cost - Cat6A cable | 12 | 24 | nos | 0 | 50600 | 50600 | 0 | 1214400 | 1214400 |  |  | #REF! |  | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 9664794.8916 | 2899438.4675 | 12564233.3591 | 9664794.8916 | 2899438.4675 | 12564233.3591 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
2. 3. |  | Mechanical Engineering | 1 | 1 | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 3. 10. |  | Ventilation System Production | 1 | 1 | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
2. 3. 20. |  | Fire Protection Engineering | 1 | 1 | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
2. 3. 30. |  | Installation of In-Rack Sprinkler at Logistic | 1 | 1 | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
2. 3. 40. |  | Compressed Air Network Production 1 | 1 | 1 | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
2. 3. 50. |  | Compressed Air Network Production 2 | 1 | 1 | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. |  | Office, Social and Technical Areas (Hall 3) | [6 empty] | 1095015293.254 | 204033421.602 | 1299048714.856 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 1. |  | Civil Engineering | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 10. |  | Rainwater and waste water sewer | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 20. |  | Foundations | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 30. |  | Steel columns | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 40. |  | Building structure | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 50. |  | Concrete works | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 60. |  | Reinforced concrete slabs 1st floor | 0 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 70. |  | Reinforced concrete stairs | 0 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 80. |  | Screed coat | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 90. |  | Metal works | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 100. |  | Exterior walls | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 110. |  | Masonry works | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 120. |  | plastering works | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 130. |  | Drywall works | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 140. |  | Ceiling for new built-ins | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 150. |  | Fire protection | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 160. |  | Fire rated walls | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 170. |  | Cutting holes into existing facades, walls and roofs | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 180. |  | Cuts in Floor/slab/wall | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 190. |  | Exterior doors and windows | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 200. |  | Canopies for exterior doors | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 210. |  | Covering existing windows with mirroring film | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 220. |  | Internal doors | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 230. |  | Fire protection doors | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 240. |  | Suspended ceiling | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 250. |  | Floor covering works | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 260. |  | Tiles | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 270. |  | Needle Felt | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 280. |  | Raised floor | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 290. |  | Drainage of new wet rooms | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 300. |  | Railing and handrail | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 310. |  | Collision protection | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 320. |  | Vertical blinds | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 330. |  | Kitchenette | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 340. |  | Painting and varnishing works | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 350. |  | internal signage | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 360. |  | Locking system | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 1. 370. |  | Tightness Test Gas Extinguished Rooms | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. |  | Electrical engineering | 1 | 1 | PSCH |  |  |  | 1095015293.254 | 204033421.602 | 1299048714.856 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 2. 10. |  | Rennovation existing grounding system and lightning protection | 1 | 1 | psch | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 2. 20. |  | Rennovation existing grounding and equipotential bonding | 1 | 1 | psch | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 2. 30. |  | Main Power supply | 1 |  | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. 40. |  | Uninterrupted power supply (UPS) | 1 |  | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. 50. |  | Electrical Capacitor bank | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 2. 60. |  | Power supply of building utilities | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. 70. |  | Energy measurement system | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. 80. |  | Electrical installation in offices and meeting rooms | 1 |  | PSCH |  |  |  | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. 90. |  | Electrical installation in social rooms | 1 |  | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. 100. |  | Electrical installation in corridors and stairways | 1 |  | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. 110. |  | Electrical installation in technical areas | 1 |  | PSCH |  |  |  | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. 120. |  | Electrical installation in kitchenette areas | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. 130. |  | Electrical installation for Workshop/Formbrettbau | 1 |  | PSCH |  |  |  | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. 140. |  | Electrical installation at the reception | 1 |  | PSCH |  |  |  | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. 150. |  | Electrical installation in other rooms/secondary rooms | 1 |  | PSCH |  |  |  | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. 160. |  | Emergency lighting | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. 170. |  | Fire alarm system | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. 180. |  | Network infrastructure | 1 | 1 | PSCH |  |  |  | 947613765.2926 | 174994605.0134 | 1122608370.3061 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | IDF4 42U (0.8x1.0x2.0), Included PDU, 10 patch panel, Cable routing channel 1U | 1 | 1 | pcs | 68750000 | 1308000 | 70058000 | 68750000 | 1308000 | 70058000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | IDF5 42U (0.8x1.0x2.0), Included PDU, 10 patch panel, Cable routing channel 1U | 1 | 1 | pcs | 68750000 | 1308000 | 70058000 | 68750000 | 1308000 | 70058000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | IDF6 42U (0.8x1.0x2.0), Included PDU, 10 patch panel, Cable routing channel 1U | 1 | 1 | pcs | 68750000 | 1308000 | 70058000 | 68750000 | 1308000 | 70058000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Patch panel 24 Port CAT6A | 24 |  | pcs | 5060000 | 654000 | 5714000 | 0 | 0 | 0 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Patch panel 24 Port cat 5e | 6 | 6 | pcs | 2195600 | 654000 | 2849600 | 13173600 | 3924000 | 17097600 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Cat 6A Patch Cord, 3m | 423 | 452 | pcs | 198000 | 10900 | 208900 | 89496000 | 4926800 | 94422800 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Cat 6A Patch Cord, 3m | 0 | 0 | pcs | 198000 | 10900 | 208900 | 0 | 0 | 0 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | ODF F.O Singlemode, 48F | 6 | 6 | pcs | 6490000 | 490500 | 6980500 | 38940000 | 2943000 | 41883000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Socket strip (PDU) with 7 sockets | 6 | 6 | pcs |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 16A Turnlock socket | 6 | 6 | pcs | 150480 | 54500 | 204980 | 902880 | 327000 | 1229880 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Double data outlet RJ45 | 197 | 226 | pcs | 480000 | 81750 | 561750 | 108480000 | 18475500 | 126955500 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Wifi module (Wifi supply by Client) | 29 | 29 | pcs | 0 | 136250 | 136250 | 0 | 3951250 | 3951250 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | FO Patch Cord, SC-SC Duplex, LSOH, SM,3m | 60 | 60 | pcs | 550000 | 10900 | 560900 | 33000000 | 654000 | 33654000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | FO Pigtail LC, SM, 1m for welding to optical fibre | 60 | 144 | pcs | 132000 | 65400 | 197400 | 19008000 | 9417600 | 28425600 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Cat 6A Patch Cord, 3m from Data outlet to Wifi | 29 | 29 | pcs | 198000 | 10900 | 208900 | 5742000 | 316100 | 6058100 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Cable Cat6A | 14691 | 14487.8 | m | 21639.3443 | 3360 | 24999.3443 | 313506491.8033 | 48679008 | 362185499.8033 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | PVC conduit D20 | 138 | 2800 | m | 8773.9726 | 14594.0164 | 23367.989 | 24567123.2877 | 40863245.9529 | 65430369.2406 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Network cable test cost - FO cable | 24 | 96 | nos | 0 | 50600 | 50600 | 0 | 4857600 | 4857600 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Network cable test cost - Cat6A cable | 197 | 452 | nos | 0 | 50600 | 50600 | 0 | 22871200 | 22871200 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 29547670.2017 | 8864301.0605 | 38411971.2622 | 29547670.2017 | 8864301.0605 | 38411971.2622 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Updated for data socket outlet on Dadoduct | 1 | 1 | lot | 65000000 |  | 65000000 | 65000000 | 0 | 65000000 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. 190. |  | CCTV System for custom fence | 1 | 1 | PSCH |  |  |  | 93265409.772 | 9368475.5017 | 102633885.2737 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Camera fence CF-5,6 | 2 | 2 | pcs | 1264480 | 137500 | 1401980 | 2528960 | 275000 | 2803960 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Camera Inside CI-1, Dome | 1 | 1 | pcs | 20015520 | 198000 | 20213520 | 20015520 | 198000 | 20213520 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Symphony Standard Edition - VMS Device License | 1 | 1 | pcs | 2704800 | 330000 | 3034800 | 2704800 | 330000 | 3034800 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LCD 43" for CE, CI | 2 | 2 | pcs | 11990000 | 163500 | 12153500 | 23980000 | 327000 | 24307000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LCD 32" for CF | 2 | 2 | pcs | 11990000 | 163500 | 12153500 | 23980000 | 327000 | 24307000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | HDMI cable c/w socket, 15m | 2 | 3 | pcs | 979000 | 59950 | 1038950 | 2937000 | 179850 | 3116850 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single data outlet RJ45 | 3 | 3 | pcs | 276000 | 81750 | 357750 | 828000 | 245250 | 1073250 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Double Socket 16A/230V | 2 | 2 | pcs | 150480 | 54500 | 204980 | 300960 | 109000 | 409960 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cat 6A Patch Cord, 3m from Data outlet to camera | 3 | 3 | pcs | 198000 | 10900 | 208900 | 594000 | 32700 | 626700 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Cable Cat6 | 400 | 403 | m | 10032.7869 | 3360 | 13392.7869 | 4043213.1148 | 1354080 | 5397293.1148 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 124 | 124 | m | 32518.74 | 7485.665 | 40004.405 | 4032323.76 | 928222.46 | 4960546.22 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 210 | 210 | m | 8773.9726 | 14594.0164 | 23367.989 | 1842534.2466 | 3064743.4465 | 4907277.693 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Network cable test cost - Cat6A cable | 3 | 7 | nos | 0 | 50600 | 50600 | 0 | 354200 | 354200 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 5478098.6507 | 1643429.5952 | 7121528.2459 | 5478098.6507 | 1643429.5952 | 7121528.2459 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 2. 200. |  | Access control preparation | 1 | 1 | PSCH |  |  |  | 54136118.1893 | 19670341.0869 | 73806459.2762 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exit Button | 5 | 5 | pcs | 528000 | 61600 | 589600 | 2640000 | 308000 | 2948000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Emergency Button | 5 | 5 | pcs | 528000 | 61600 | 589600 | 2640000 | 308000 | 2948000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Door sensor | 55 | 5 | pcs | 2116800 | 95200 | 2212000 | 10584000 | 476000 | 11060000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Access control card reader | 8 | 5 | set | 0 | 95200 | 95200 | 0 | 476000 | 476000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single Socket 16A/230V | 5 | 5 | pcs | 150480 | 54500 | 204980 | 752400 | 272500 | 1024900 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Data outlet RJ45 | 5 | 5 | pcs | 480000 | 81750 | 561750 | 2400000 | 408750 | 2808750 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | AC/DC converter | 5 | 5 | pcs | 2220000 | 95200 | 2315200 | 11100000 | 476000 | 11576000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Conection box, SS304 | 5 | 5 | pcs | 180000 | 50400 | 230400 | 900000 | 252000 | 1152000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable cat6A | 357 | 225 | m | 21639.3443 | 3360 | 24999.3443 | 4868852.459 | 756000 | 5624852.459 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Cable telephone cat5e | 357 | 225 | m | 7475.4098 | 3360 | 10835.4098 | 1681967.2131 | 756000 | 2437967.2131 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 286 | 286 | m | 32518.74 | 7485.665 | 40004.405 | 9300359.64 | 2140900.19 | 11441259.83 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 643 | 586 | m | 8773.9726 | 14594.0164 | 23367.989 | 5141547.9452 | 8552093.6173 | 13693641.5625 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Labour cost for support DRX test funtion of Access control system | 1 | 1 | lot | 0 | 3850000 | 3850000 | 0 | 3850000 | 3850000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 2126990.932 | 638097.2796 | 2765088.2116 | 2126990.932 | 638097.2796 | 2765088.2116 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 3. |  | Mechanical Engineering | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 3. 10. |  | Waste Water System | 1 |  | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
3. 3. 20. |  | Service Water System | 1 |  | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
3. 3. 40. |  | Ventilation System | 1 |  | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
3. 3. 50. |  | Ventilation System 1st Floor Offices Ventilation Units | 1 |  | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
3. 3. 60. |  | Ventilation System 1st Floor Offices Ducting | 1 |  | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
3. 3. 70. |  | Air Conditioning | 1 |  | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
3. 3. 80. |  | Fire Protection Engineering Sprinkler | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 3. 90. |  | Fire Protection Engineering Temperature Controlled Storage | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 3. 100. |  | Fire Protection Engineering Extinguishing Systems | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 3. 110. |  | Door Fan Test for Gas Extinguishing System | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 3. 120. |  | Compressed Air Connections | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
4. |  | Machine hook-up (Hall 3) | [8 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
4. 1. |  | Electrical engineering | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
4. 1. 10. |  | Power cables and lines | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
4. 2. |  | Mechanical Engineering | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
4. 2. 10. |  | Machine hook-up | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Supply & Installation pipe & fittings: Drop Piping (D25), Considering all drop piping & fittings | 1 |  | lot | 0 | 0 | [6 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Hanger support & accessories | 1 |  | lot | 0 | 0 | [6 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
5. |  | Scooter Garage | [8 empty] | 162238150.0078 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
5. 1. |  | Civil Engineering | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
5. 1. 10. |  | Adjustments on the existing scooter garage | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
5. 1. 20. |  | Expansion of Scooter Garage | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
5. 2. |  | Electrical Engineering | 1 | 1 | PSCH |  |  |  | 144640388.5392 | 17597761.4686 | 162238150.0078 |  |  | #REF! |  |  | 0% |  |  | 0%
5. 2. 10. |  | Grounding and Lightining protection | 1 |  | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
5. 2. 20. |  | Power supply | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
5. 2. 30. |  | Power supply of building utilities | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
5. 2. 40. |  | Electrical installations | 1 |  | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
5. 2. 50. |  | Emergency lighting | 1 |  | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
5. 2. 60. |  | Fire alarms system | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
5. 2. 70. |  | CCTV System | 1 | 1 | PSCH |  |  |  | 144640388.5392 | 17597761.4686 | 162238150.0078 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | POWER surveillance cabinet | 2 | 2 | pcs | 1650000 | 136250 | 1786250 | 3300000 | 272500 | 3572500 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | DATA surveillance cabinet | 2 | 2 | pcs | 1650000 | 136250 | 1786250 | 3300000 | 272500 | 3572500 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Terminal 4mm2 | 2 | 2 | pcs | 27500 | 10900 | 38400 | 55000 | 21800 | 76800 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | MCB 1P-16A-230V | 2 | 2 | pcs | 90000 | 49050 | 139050 | 180000 | 98100 | 278100 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Power adapter (Mean Well SDR-240-48) | 2 | 2 | pcs | 2833600 | 114450 | 2948050 | 5667200 | 228900 | 5896100 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PoE Switch Planet IGS-10020HPT | 2 | 2 | pcs | 15180000 | 272500 | 15452500 | 30360000 | 545000 | 30905000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Outside Camera CF-7-->14 | 8 | 8 | pcs | 1264480 | 137500 | 1401980 | 10115840 | 1100000 | 11215840 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Telescopic parapet mount (T91D62) | 8 | 8 | pcs | 1803200 | 49500 | 1852700 | 14425600 | 396000 | 14821600 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Overvoltage protection | 8 | 8 | pcs | 4494000 | 49050 | 4543050 | 35952000 | 392400 | 36344400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single data outlet RJ45 | 8 | 8 | pcs | 276000 | 81750 | 357750 | 2208000 | 654000 | 2862000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Cat 6A Patch Cord, 3m from Data outlet to camera | 8 | 8 | pcs | 198000 | 10900 | 208900 | 1584000 | 87200 | 1671200 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Cable Cat6 | 343 | 264 | m | 10032.7869 | 3360 | 13392.7869 | 2648655.7377 | 887040 | 3535695.7377 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Gigabit Ethernet LX Mini-GBIC SFP Transceiver | 2 | 2 | pcs | 4032000 | 272500 | 4304500 | 8064000 | 545000 | 8609000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | converter quang đồng (Connect from optic cable to Patch panel) | 2 | 2 | pcs | 935000 | 49050 | 984050 | 1870000 | 98100 | 1968100 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Cat 6A Patch Cord, 3m from Converter to patch panel | 4 | 4 | pcs | 198000 | 10900 | 208900 | 792000 | 43600 | 835600 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | FO Patch Cord, SC-SC Duplex, LSOH, SM,3m | 2 | 2 | pcs | 550000 | 10900 | 560900 | 1100000 | 21800 | 1121800 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Fiber optical 8FO (SM-OS2 G9/125) | 190 | 190 | m | 54000 | 3360 | 57360 | 10260000 | 638400 | 10898400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 100 | 100 | m | 32518.74 | 7485.665 | 40004.405 | 3251874 | 748566.5 | 4000440.5 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 144 | 200 | m | 8773.9726 | 14594.0164 | 23367.989 | 1754794.5205 | 2918803.2824 | 4673597.8029 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | HDPE pipe D40/50 | 100 | 100 | m | 17049.1866 | 15805 | 32854.1866 | 1704918.6603 | 1580500 | 3285418.6603 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | The cost of cutting and refinishing the concrete path for the undergruond pipe | 8 | 8 | m | 0 | 175000 | 175000 | 0 | 1400000 | 1400000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Network cable test cost - FO cable | 2 | 48 | nos | 0 | 50600 | 50600 | 0 | 2428800 | 2428800 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Network cable test cost - Cat6A cable | 8 | 8 | nos | 0 | 50600 | 50600 | 0 | 404800 | 404800 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 6046505.6207 | 1813951.6862 | 7860457.3069 | 6046505.6207 | 1813951.6862 | 7860457.3069 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
5. 3. |  | Mechancial Engineering | [8 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
5. 3. 10. |  | Rainwater System | 1 |  | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
5. 3. 20. |  | Fire Protection System | 1 |  | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
6. |  | Canteen | [8 empty] | 274132627.4702 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
6. 1. |  | Civil Engineering | [8 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 10. |  | Demolition of existing canteen | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 20. |  | Building Structure | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 30. |  | Earthworks | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 40. |  | Rain water and waste water sewer | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 50. |  | Primary construction of reinforced concrete | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 60. |  | Foundations | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 70. |  | Concrete floor | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 80. |  | Concrete plinth | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 90. |  | Reinforced concrete columns | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 100. |  | Reinforced concrete beams | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 110. |  | Reinforced concrete 1st roof slab or structure | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 120. |  | Reinforced concrete stairs | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 130. |  | Concrete steps | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 140. |  | Screed coat | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 150. |  | Roof structure | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 160. |  | Metal facade | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 170. |  | Masonry works | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 180. |  | Exterior doors | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 190. |  | Fire protection | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 200. |  | Fire protection doors | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 210. |  | Interior doors | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 220. |  | Floor covering works | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 230. |  | Tiles | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 240. |  | Painting and finishing works | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 250. |  | Metal and railing works | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 260. |  | Elevator for goods | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 270. |  | Canpoy for the main entrance | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 280. |  | Exterior steel staircase | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 290. |  | Exterior sinks | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 1. 300. |  | Locking system | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
6. 2. |  | Electrical Engineering | [6 empty] | 246947482.5691 | 27185144.9011 | 274132627.4702 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Notes Calculation Basis | [11 empty] | #REF! |  |  | 0% |  |  | 0%
6. 2. 10. |  | Grounding and Lightining protection | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 2. 20. |  | Power supply | 1 |  | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
6. 2. 30. |  | Power supply of building utilities | 1 |  | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
6. 2. 40. |  | Electrical installations | 1 |  | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
6. 2. 50. |  | Emergency lighting | 1 |  | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
6. 2. 60. |  | Fire alarms system | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 2. 70. |  | CCTV System For Custom fence | 1 | 1 | PSCH |  |  |  | 117565498.5134 | 6055261.4345 | 123620759.9479 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LCD 43" for CE, CI | 8 | 8 | pcs | 11990000 | 163500 | 12153500 | 95920000 | 1308000 | 97228000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | HDMI cable c/w socket, 15m | 8 | 8 | pcs | 979000 | 59950 | 1038950 | 7832000 | 479600 | 8311600 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Outside Camera CF-16-->18 | 4 | 4 | pcs | 1264480 | 137500 | 1401980 | 5057920 | 550000 | 5607920 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single data outlet RJ45 | 4 | 4 | pcs | 276000 | 81750 | 357750 | 1104000 | 327000 | 1431000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Cat 6A Patch Cord, 3m from Data outlet to camera | 4 | 4 | pcs | 198000 | 10900 | 208900 | 792000 | 43600 | 835600 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Cable Cat6 | 229 | 200 | m | 10032.7869 | 3360 | 13392.7869 | 2006557.377 | 672000 | 2678557.377 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | PVC conduit D20 | 91 | 85 | m | 8773.9726 | 14594.0164 | 23367.989 | 745787.6712 | 1240491.395 | 1986279.0662 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Network cable test cost - Cat6A cable | 4 | 4 | nos | 0 | 50600 | 50600 | 0 | 202400 | 202400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 4107233.4651 | 1232170.0395 | 5339403.5046 | 4107233.4651 | 1232170.0395 | 5339403.5046 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
6. 2. 80. |  | Network infrastructure | 1 | 1 | PSCH |  |  |  | 129381984.0557 | 21129883.4666 | 150511867.5223 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | IDF8 12U (0.8x1.0x2.0), Included PDU, 10 patch panel, Cable routing channel 1U | 1 | 1 | pcs | 68750000 | 1308000 | 70058000 | 68750000 | 1308000 | 70058000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Patch panel 24 Port CAT6A | 2 |  | pcs | 5060000 | 654000 | 5714000 | 0 | 0 | 0 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Cat 6A Patch Cord, 3m | 28 | 16 | pcs | 198000 | 10900 | 208900 | 3168000 | 174400 | 3342400 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Cat 6A Patch Cord, 3m | 0 | 0 | pcs | 198000 | 10900 | 208900 | 0 | 0 | 0 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | ODF F.O Singlemode, 48F | 1 | 1 | pcs | 6490000 | 490500 | 6980500 | 6490000 | 490500 | 6980500 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Socket strip (PDU) with 7 sockets | 2 | 2 | pcs |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 16A Turnlock socket | 2 | 2 | pcs | 150480 | 54500 | 204980 | 300960 | 109000 | 409960 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Double data outlet RJ45 | 12 | 12 | pcs | 480000 | 81750 | 561750 | 5760000 | 981000 | 6741000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Wifi module (Wifi supply by Client) | 4 | 4 | pcs | 0 | 136250 | 136250 | 0 | 545000 | 545000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | FO Patch Cord, SC-SC Duplex, LSOH, SM,3m | 2 | 2 | pcs | 550000 | 10900 | 560900 | 1100000 | 21800 | 1121800 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | FO Pigtail LC, SM, 1m for welding to optical fibre | 2 | 48 | pcs | 132000 | 65400 | 197400 | 6336000 | 3139200 | 9475200 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cat 6A Patch Cord, 3m from Data outlet to wifi | 4 | 4 | pcs | 198000 | 10900 | 208900 | 792000 | 43600 | 835600 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Cable Cat6A | 1257 | 1240 | m | 21639.3443 | 3360 | 24999.3443 | 26832786.8852 | 4166400 | 30999186.8852 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | PVC conduit D20 | 503 | 500 | m | 8773.9726 | 14594.0164 | 23367.989 | 4386986.3014 | 7297008.2059 | 11683994.5073 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Network cable test cost - Cat6A cable | 12 | 24 | nos | 0 | 50600 | 50600 | 0 | 1214400 | 1214400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 5465250.8691 | 1639575.2607 | 7104826.1298 | 5465250.8691 | 1639575.2607 | 7104826.1298 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
6. 3. |  | Mechancial Engineering | [8 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 3. 10. |  | Rainwater System | 1 |  | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
6. 3. 20. |  | Waste Water System | 1 |  | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
6. 3. 30. |  | Service Water System | 1 |  | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
6. 3. 40. |  | Sanitary Furnishings | 1 |  | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
6. 3. 50. |  | Air Conditioning | 1 |  | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
6. 3. 60. |  | Ventilation System Overhead Fans | 1 |  | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
6. 3. 70. |  | Ventilation System | 1 |  | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
6. 3. 80. |  | Fire Protection System | 1 |  | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
7. |  | Exterior Area | [6 empty] | 509452988.9423 | 100342530.3589 | 609795519.3012 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
7. 1. |  | Civil Engineering | [8 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
7. 1. 10. |  | Flag pole | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
7. 1. 20. |  | Fence | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
7. 1. 30. |  | Bollards and delineator panels | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
7. 1. 40. |  | New Septic Tanks | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
7. 1. 50. |  | Excavation | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
7. 1. 60. |  | Laying conduits, pipes, etc. | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
7. 1. 70. |  | Asphalt areas | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
7. 2. |  | Electrical Engineering | [6 empty] | 509452988.9423 | 100342530.3589 | 609795519.3012 |  |  | #REF! |  |  | 0% |  |  | 0%
7. 2. 10. |  | Electrical Installations General | 1 |  | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
7. 2. 20. |  | Exterior Lighting | 1 |  | PSCH | [8 empty] | #REF! |  |  | 0% |  |  | 0%
7. 2. 30. |  | Emergency Lighting | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
7. 2. 40. |  | Building service connections | 1 | 1 | PSCH |  |  |  | 449449440 | 94825780 | 544275220 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single Mode OS2 48 fibers SC- Duplex | 1325 | 2141.26 | m | 144000 | 28000 | 172000 | 308341440 | 59955280 | 368296720 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | 20 x 0,8 pair copper phone wire (20P cat3) | 0 |  | m | 117360 | 13798.4 | 131158.4 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | ODF F.O Singlemode, 48F add to MDF at server rooms | 5 | 5 | pcs | 6490000 | 490500 | 6980500 | 32450000 | 2452500 | 34902500 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Patch panel 24 Port cat 5e | 5 | 5 | pcs | 2195600 | 654000 | 2849600 | 10978000 | 3270000 | 14248000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Cat 6A Patch Cord, 3m | 120 |  | pcs | 198000 | 10900 | 208900 | 0 | 0 | 0 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | FO Patch Cord, SC-SC Duplex, LSOH, SM,3m | 120 | 120 | pcs | 550000 | 10900 | 560900 | 66000000 | 1308000 | 67308000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | FO Pigtail LC, SM, 1m for welding to optical fibre | 120 | 240 | pcs | 132000 | 65400 | 197400 | 31680000 | 15696000 | 47376000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Network cable test cost - FO cable | 120 | 240 | nos | 0 | 50600 | 50600 | 0 | 12144000 | 12144000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Network cable test cost - Cat6A cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
7. 2. 50. |  | CCTV System | 1 | 1 | PSCH |  |  |  | 60003548.9423 | 5516750.3589 | 65520299.3012 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | For Custom fence | [6 empty] | 60003548.9423 | 5516750.3589 | 65520299.3012 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | NVR 32 Chanel | 1 | 1 | pcs | 19810560 | 385000 | 20195560 | 19810560 | 385000 | 20195560 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Outside Camera CF-1-->4 | 4 | 4 | pcs | 1264480 | 137500 | 1401980 | 5057920 | 550000 | 5607920 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Telescopic parapet mount (T91D62) | 4 | 4 | pcs | 1803200 | 49500 | 1852700 | 7212800 | 198000 | 7410800 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Overvoltage protection | 4 | 4 | pcs | 4494000 | 49050 | 4543050 | 17976000 | 196200 | 18172200 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Double data outlet RJ45 | 4 | 4 | pcs | 480000 | 81750 | 561750 | 1920000 | 327000 | 2247000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Cat 6A Patch Cord, 3m | 12 | 12 | pcs | 198000 | 10900 | 208900 | 2376000 | 130800 | 2506800 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Cable Cat6 | 240 | 227 | m | 10032.7869 | 3360 | 13392.7869 | 2277442.623 | 762720 | 3040162.623 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | PVC conduit D20 | 96 | 100 | m | 8773.9726 | 14594.0164 | 23367.989 | 877397.2603 | 1459401.6412 | 2336798.9015 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Network cable test cost - Cat6A cable | 4 | 15 | nos | 0 | 50600 | 50600 | 0 | 759000 | 759000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 2495429.0591 | 748628.7177 | 3244057.7768 | 2495429.0591 | 748628.7177 | 3244057.7768 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
7. 3. |  | Mechanical Engineering | [8 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
7. 3. 10. |  | Underground Compressed Air Connection | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
8. |  | Adjustments Hall 2 | [8 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
8. 1. |  | Roof Renovation | [8 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
8. 1. 10. |  | Roof Reinforcement Option 1 | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
8. 2. |  | Adjustment Ridge Vent | [8 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
8. 2. 10. |  | Adjustment Ridge Vent | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
8. 3. |  | Adjustment Overhead Fans | [8 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
8. 3. 10. |  | Adjustment Overhead Fans | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
8. 4. |  | Additonal In-Rack Sprinkler Logistic | [8 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
8. 4. 10. |  | Additonal In-Rack Sprinkler Logistic | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
8. 5. |  | Additional Compressed Air Equipment | [8 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
8. 5. 10. |  | Additional Compressed Air Equipment | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
8. 6. |  | Flag pole | [8 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
8. 6. 10. |  | Flag pole | 0 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
9. |  | As built documentation | [8 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
9. 1. |  | As built documentation all trades | [8 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
9. 1. 10. |  | As built documentation | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
10. |  | Service of Architects and Engineers | [8 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
10. 1. |  | Civil engineering | [8 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
10. 1. 10. |  | Design works | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
10. 1. 20. |  | Geotechnical survey | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
10. 1. 30. |  | Topographical survey | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
10. 1. 40. |  | Fire protection report | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
10. 1. 50. |  | Compactation report of earthworks | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
10. 1. 60. |  | Structure and welding quality report | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
10. 1. 70. |  | Adherence and width of paint quality control reports | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
10. 1. 80. |  | Material quality control reports | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
10. 1. 90. |  | Planning service Building construction | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
10. 1. 100. |  | Planning service Structural design | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
10. 1. 110. |  | Planning service Structural revision | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
10. 1. 120. |  | Surveying services Inventory registration | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
10. 1. 130. |  | Quality control laboratory for material testing (laboratory and field testing) | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
10. 1. 140. |  | Revision fire department and civil protection | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
10. 2. |  | Electrical engineering | [8 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
10. 2. 10. |  | Design & approval works | 1 |  | psch | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
10. 3. |  | Mechanical engineering | [8 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
10. 3. 10. |  | Design & approval works | 1 |  | psch | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | III. AIR COMPRESSOR | [8 empty] | 1143011058.0929 |  |  | #REF! |  |  | 0% |  |  | 0%
2. |  | Production and Logistic building (Hall 3) | [6 empty] | 585597305.9781 | 205702981.3661 | 791300287.3442 |  |  | #REF! |  |  | 0 |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
2. 3. |  | Mechanical Engineering | [6 empty] | 585597305.9781 | 205702981.3661 | 791300287.3442 |  |  | #REF! |  |  | 0% |  |  | 0%
2. 3. 40. |  | Compressed Air Network Production 1 | 1 |  | PSCH |  |  |  | 425312121.5169 | 147070051.5988 | 572382173.1157 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | BLUE ALUMINIUM PIPE, DN63 | 470 | 485 | m | 362322.6857 | 115320.5625 | 477643.2482 | 175726502.5676 | 55930472.8125 | 231656975.3801 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | BLUE ALUMINIUM PIPE, DN40 | 0 | 30 | pcs | 190224.1656 | 70966.5 | 261190.6656 | 5706724.968 | 2128995 | 7835719.968 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | BLUE ALUMINIUM PIPE, DN25 | 180 | 174 | m | 94950.6667 | 42579.9 | 137530.5667 | 16521416 | 7408902.6 | 23930318.6 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | TUBE CLIP, DN63 (POLYMER) | 162 | 172 | pcs | 54295.4118 | 82376.8 | 136672.2118 | 9338810.8362 | 14168809.6 | 23507620.4362 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | TUBE CLIP, DN40 (POLYMER) | 76 | 10 | pcs | 32609.857 | 57608.1 | 90217.957 | 326098.5696 | 576081 | 902179.5696 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | PIPE TO PIPE JOINT, DN63 | 79 | 79 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 47234236.4616 | 6507767.2 | 53742003.6616 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | PIPE TO PIPE JOINT, DN63 | 50 | 50 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 29895086.3681 | 4118840 | 34013926.3681 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | 90° ELBOW, DN63 | 6 | 8 | pcs | 326098.5696 | 82376.8 | 408475.3696 | 2608788.5568 | 659014.4 | 3267802.9568 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | EQUAL TEE, DN63 | 3 | 5 | pcs | 543443.2662 | 82376.8 | 625820.0662 | 2717216.3312 | 411884 | 3129100.3312 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | END CAP, DN63 | 1 | 1 | pcs | 380393.9814 | 82376.8 | 462770.7814 | 380393.9814 | 82376.8 | 462770.7814 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | REDUCING TEE, DN63-40 | 12 | 14 | pcs | 861389.3716 | 82376.8 | 943766.1716 | 12059451.2024 | 1153275.2 | 13212726.4024 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | QUICK DROP, DN63-25 | 32 | 32 | pcs | 372241.5172 | 82376.8 | 454618.3172 | 11911728.5503 | 2636057.6 | 14547786.1503 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | PIPE TO PIPE JOINT, DN40 | 37 | 37 | pcs | 317946.1054 | 57608.1 | 375554.2054 | 11764005.8983 | 2131499.7 | 13895505.5983 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | LOCKABLE BRASS VALVE, DN25-1/2" FEMALE THREAD, WITH FIXING PLATE | 32 | 32 | pcs | 680241.6162 | 53385.955 | 733627.5712 | 21767731.7179 | 1708350.5613 | 23476082.2792 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | TWO-WAYS PNEUMATIC CONNECTOR, FEMALE THREAD G1/2" | 0 |  | pcs | 206583.4438 | 53385.955 | 259969.3989 | 0 | 0 | 0 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | T-BOLT, M8, 6CM | 228 | 228 | pcs | 3260.9857 | 3850 | 7110.9857 | 743504.7387 | 877800 | 1621304.7387 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | THREADED ROD, M8, 3 METER | 50 | 50 | pcs | 48914.7854 | 11000 | 59914.7854 | 2445739.272 | 550000 | 2995739.272 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | WALL MOUNTED BRACKET, 50CM | 228 | 228 | pcs | 92448.9445 | 8250 | 100698.9445 | 21078359.3418 | 1881000 | 22959359.3418 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | BEAM CLAMP, 2.5CM | 456 | 456 | pcs | 37990.4834 | 8250 | 46240.4834 | 17323660.4114 | 3762000 | 21085660.4114 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Fire Stop | 1 | 1 | lot | 2500000 | 1000000 | 3500000 | 2500000 | 1000000 | 3500000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 33262665.7435 | 9978799.7231 | 43241465.4666 | 33262665.7435 | 9978799.7231 | 43241465.4666 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | T&C | 1 | 1 | lot | 0 | 29398125.4019 | 29398125.4019 | 0 | 29398125.4019 | 29398125.4019 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
2. 3. 50. |  | Compressed Air Network Production 2 | 1 |  | PSCH |  |  |  | 160285184.4612 | 58632929.7673 | 218918114.2285 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PRODUCTION 2 | [6 empty] | 83418012.7013 | 26026366.1504 | 109444378.8517 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | BLUE ALUMINIUM PIPE, DN40 | 109 | 210 | m | 190224.1656 | 70966.5 | 261190.6656 | 39947074.776 | 14902965 | 54850039.776 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | BLUE ALUMINIUM PIPE, DN25 | 56 | 59 | m | 94950.6667 | 42579.9 | 137530.5667 | 5602089.3333 | 2512214.1 | 8114303.4333 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | PIPE TO PIPE JOINT, DN63 | 4 | 4 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 2391606.9094 | 329507.2 | 2721114.1094 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | PIPE TO PIPE JOINT, DN40 | 19 | 19 | pcs | 317946.1054 | 57608.1 | 375554.2054 | 6040976.0018 | 1094553.9 | 7135529.9018 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | REDUCING TEE, DN63-40 | 2 | 2 | pcs | 861389.3716 | 82376.8 | 943766.1716 | 1722778.7432 | 164753.6 | 1887532.3432 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | TUBE CLIP, DN40 (POLYMER) | 40 | 70 | pcs | 32609.857 | 57608.1 | 90217.957 | 2282689.9872 | 4032567 | 6315256.9872 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | 45° ELBOW, DN40 | 6 | 6 | pcs | 741874.2458 | 57608.1 | 799482.3458 | 4451245.475 | 345648.6 | 4796894.075 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | QUICK DROP, DN40-25 | 10 | 10 | pcs | 318435.2532 | 57608.1 | 376043.3532 | 3184352.5321 | 576081 | 3760433.5321 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | BRASS VALVE, DN40-DN40 | 2 | 2 | pcs | 1451138.6347 | 57608.1 | 1508746.7347 | 2902277.2694 | 115216.2 | 3017493.4694 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | LOCKABLE BRASS VALVE, DN25-1/2" FEMALE THREAD, WITH FIXING PLATE | 10 | 10 | pcs | 680241.6162 | 53385.955 | 733627.5712 | 6802416.1619 | 533859.5504 | 7336275.7123 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | TWO-WAYS PNEUMATIC CONNECTOR, FEMALE THREAD G1/2" | 0 |  | pcs | 206583.4438 | 53385.955 | 259969.3989 | 0 | 0 | 0 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | T-BOLT, M8, 6CM | 40 | 40 | pcs | 3260.9857 | 3850 | 7110.9857 | 130439.4278 | 154000 | 284439.4278 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | THREADED ROD, M8, 3 METER | 25 | 25 | pcs | 48914.7854 | 11000 | 59914.7854 | 1222869.636 | 275000 | 1497869.636 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | WALL MOUNTED BRACKET, 50CM | 40 | 40 | pcs | 92448.9445 | 8250 | 100698.9445 | 3697957.7793 | 330000 | 4027957.7793 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | BEAM CLAMP, 2.5CM | 80 | 80 | pcs | 37990.4834 | 8250 | 46240.4834 | 3039238.6687 | 660000 | 3699238.6687 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | LOGICSTIC | [6 empty] | 76867171.7599 | 32606563.6169 | 109473735.3768 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | BLUE ALUMINIUM PIPE, DN63 | 0 | 30 | m | 362322.6857 | 115320.5625 | 477643.2482 | 10869680.5712 | 3459616.875 | 14329297.4462 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | BLUE ALUMINIUM PIPE, DN40 | 69 | 72 | m | 190224.1656 | 70966.5 | 261190.6656 | 13696139.9232 | 5109588 | 18805727.9232 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | BLUE ALUMINIUM PIPE, DN25 | 17 | 21 | m | 94950.6667 | 42579.9 | 137530.5667 | 1993964 | 894177.9 | 2888141.9 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | TUBE CLIP, DN63 (POLYMER) | 0 | 6 | pcs | 54295.4118 | 82376.8 | 136672.2118 | 325772.471 | 494260.8 | 820033.271 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | PIPE TO PIPE JOINT, DN63 | 0 | 8 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 4783213.8189 | 659014.4 | 5442228.2189 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | PIPE TO PIPE JOINT, DN63 | 0 | 8 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 4783213.8189 | 659014.4 | 5442228.2189 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | EQUAL TEE, DN63 | 0 | 6 | pcs | 543443.2662 | 82376.8 | 625820.0662 | 3260659.5974 | 494260.8 | 3754920.3974 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | REDUCING TEE, DN63-40 | 2 | 2 | pcs | 861389.3716 | 82376.8 | 943766.1716 | 1722778.7432 | 164753.6 | 1887532.3432 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | END CAP, DN63 | 1 | 1 | pcs | 380393.9814 | 82376.8 | 462770.7814 | 380393.9814 | 82376.8 | 462770.7814 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | TUBE CLIP, DN40 (POLYMER) | 26 | 24 | pcs | 32609.857 | 57608.1 | 90217.957 | 782636.567 | 1382594.4 | 2165230.967 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | PIPE TO PIPE JOINT, DN40 | 12 | 12 | pcs | 317946.1054 | 57608.1 | 375554.2054 | 3815353.2643 | 691297.2 | 4506650.4643 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | 90° ELBOW, DN40 | 1 | 1 | pcs | 706492.551 | 57608.1 | 764100.651 | 706492.551 | 57608.1 | 764100.651 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | EQUAL TEE, DN40 | 1 | 1 | pcs | 1066831.4704 | 57608.1 | 1124439.5704 | 1066831.4704 | 57608.1 | 1124439.5704 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | QUICK DROP, DN63-25 | 1 | 1 | pcs | 372241.5172 | 82376.8 | 454618.3172 | 372241.5172 | 82376.8 | 454618.3172 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | QUICK DROP, DN40-25 | 2 | 2 | pcs | 318435.2532 | 57608.1 | 376043.3532 | 636870.5064 | 115216.2 | 752086.7064 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | END CAP, DN40 | 2 | 2 | pcs | 529910.1756 | 57608.1 | 587518.2756 | 1059820.3512 | 115216.2 | 1175036.5512 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | BRASS VALVE, DN40-DN40 | 2 | 2 | pcs | 1451138.6347 | 57608.1 | 1508746.7347 | 2902277.2694 | 115216.2 | 3017493.4694 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | BRASS VALVE, DN25-1/2" FEMALE THREAD, WITH FIXING PLATE | 2 | 2 | pcs | 617304.5923 | 53385.955 | 670690.5473 | 1234609.1845 | 106771.9101 | 1341381.0946 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | TWO-WAYS PNEUMATIC CONNECTOR, FEMALE THREAD G1/2" | 0 |  | pcs | 206583.4438 | 48702.5 | 255285.9438 | 0 | 0 | 0 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | T-BOLT, M8, 6CM | 40 | 40 | pcs | 3260.9857 | 3850 | 7110.9857 | 130439.4278 | 154000 | 284439.4278 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | THREADED ROD, M8, 3 METER | 25 | 25 | pcs | 48914.7854 | 11000 | 59914.7854 | 1222869.636 | 275000 | 1497869.636 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | WALL MOUNTED BRACKET, 50CM | 36 | 36 | pcs | 92448.9445 | 8250 | 100698.9445 | 3328162.0013 | 297000 | 3625162.0013 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | BEAM CLAMP, 2.5CM | 72 | 72 | pcs | 37990.4834 | 8250 | 46240.4834 | 2735314.8018 | 594000 | 3329314.8018 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | Fire Stop | 1 | 1 | lot | 2500000 | 1000000 | 3500000 | 2500000 | 1000000 | 3500000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 12557436.286 | 3767230.8858 | 16324667.1718 | 12557436.286 | 3767230.8858 | 16324667.1718 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | T&C | 1 | 1 | lot | 0 | 11778364.046 | 11778364.046 | 0 | 11778364.046 | 11778364.046 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. |  | Office, Social and Technical Areas (Hall 3) | [6 empty] | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 3. |  | Mechanical Engineering | [6 empty] | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 3. 120. |  | Compressed Air Connections | 1 |  | PSCH | [5 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
4. |  | Machine hook-up (Hall 3) | [6 empty] | 246537484.7813 | 58813621.1675 | 305351105.9487 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
4. 2. |  | Mechanical Engineering | [6 empty] | 246537484.7813 | 58813621.1675 | 305351105.9487 |  |  | #REF! |  |  | 0% |  |  | 0%
4. 2. 10. |  | Machine hook-up | 1 | 1 | PSCH |  |  |  | 246537484.7813 | 58813621.1675 | 305351105.9487 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | BLUE ALUMINIUM PIPE, DN63 | 16 | 18 | m | 362322.6857 | 115320.5625 | 477643.2482 | 6521808.3427 | 2075770.125 | 8597578.4677 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | BLUE ALUMINIUM PIPE, DN40 | 257 | 228 | m | 190224.1656 | 70966.5 | 261190.6656 | 43371109.7568 | 16180362 | 59551471.7568 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | BLUE ALUMINIUM PIPE, DN25 | 23 | 27 | m | 94950.6667 | 42579.9 | 137530.5667 | 2563668 | 1149657.3 | 3713325.3 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PIPE TO PIPE JOINT, DN63 | 1 | 1 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 597901.7274 | 82376.8 | 680278.5274 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | REDUCING PIPE TO PIPE JOINT, DN63-DN40 | 1 | 1 | pcs | 684154.799 | 82376.8 | 766531.599 | 684154.799 | 82376.8 | 766531.599 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | TUBE CLIP, DN40 (POLYMER) | 92 | 77 | pcs | 32609.857 | 57608.1 | 90217.957 | 2510958.9859 | 4435823.7 | 6946782.6859 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PIPE TO PIPE JOINT, DN40 | 45 | 45 | pcs | 317946.1054 | 57608.1 | 375554.2054 | 14307574.7412 | 2592364.5 | 16899939.2412 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | QUICK DROP, DN40-25 | 45 | 45 | pcs | 318435.2532 | 57608.1 | 376043.3532 | 14329586.3946 | 2592364.5 | 16921950.8946 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Pressureless decouling | 96 | 96 | pcs | 387040 | 30056.4 | 417096.4 | 37155840 | 2885414.4 | 40041254.4 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | BRASS VALVE, DN63-DN63 | 1 | 1 | pcs | 2445739.272 | 82376.8 | 2528116.072 | 2445739.272 | 82376.8 | 2528116.072 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | BRASS VALVE, DN40-DN40 | 2 | 2 | pcs | 1451138.6347 | 57608.1 | 1508746.7347 | 2902277.2694 | 115216.2 | 3017493.4694 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LOCKABLE BRASS VALVE, DN25-1/2" FEMALE THREAD, WITH FIXING PLATE | 28 | 28 | pcs | 680241.6162 | 53385.955 | 733627.5712 | 19046765.2532 | 1494806.7411 | 20541571.9943 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | LOCKABLE BRASS VALVE, DN25-3/8" FEMALE THREAD, WITH FIXING PLATE | 68 | 68 | pcs | 680241.6162 | 53385.955 | 733627.5712 | 46256429.9006 | 3630244.9427 | 49886674.8433 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | BRASS VALVE, DN25-1/2" FEMALE THREAD, WITH FIXING PLATE | 6 | 6 | pcs | 617304.5923 | 53385.955 | 670690.5473 | 3703827.5535 | 320315.7302 | 4024143.2838 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | T-split 3 way outlet tap | 28 | 28 | pcs | 451350 | 27500 | 478850 | 12637800 | 770000 | 13407800 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | T-BOLT, M8, 6CM | 92 | 92 | pcs | 3260.9857 | 3850 | 7110.9857 | 300010.684 | 354200 | 654210.684 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | THREADED ROD, M8, 3 METER | 50 | 50 | pcs | 48914.7854 | 11000 | 59914.7854 | 2445739.272 | 550000 | 2995739.272 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | WALL MOUNTED BRACKET, 50CM | 92 | 92 | pcs | 92448.9445 | 8250 | 100698.9445 | 8505302.8923 | 759000 | 9264302.8923 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | BEAM CLAMP, 2.5CM | 184 | 184 | pcs | 37990.4834 | 8250 | 46240.4834 | 6990248.9379 | 1518000 | 8508248.9379 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 19260740.9985 | 5778222.2996 | 25038963.2981 | 19260740.9985 | 5778222.2996 | 25038963.2981 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | T&C | 1 | 1 | lot | 0 | 11364728.3288 | 11364728.3288 | 0 | 11364728.3288 | 11364728.3288 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
5. |  | Scooter Garage | [6 empty] | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
6. |  | Canteen | [6 empty] | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
7. |  | Exterior Area | [6 empty] | 28542816 | 17816848.8 | 46359664.8 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
7. 3. |  | Mechanical Engineering | [6 empty] | 28542816 | 17816848.8 | 46359664.8 |  |  | #REF! |  |  | 0% |  |  | 0%
7. 3. 10. |  | Underground Compressed Air Connection | 1 |  | PSCH |  |  |  | 28542816 | 17816848.8 | 46359664.8 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | HDPE Pipe DN100 | 115 | 115 | m | 179254.4 | 96096 | 275350.4 | 20614256 | 11051040 | 31665296 |  |  | #REF! | 20% |  | 20% |  |  | 20%
|  | Fitting for connecting HDPE pipes with aluminum pipes | 1 | 1 | lot | 4757136 | 1427140.8 | 6184276.8 | 4757136 | 1427140.8 | 6184276.8 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger support & accessories | 1 | 1 | lot | 3171424 | 951427.2 | 4122851.2 | 3171424 | 951427.2 | 4122851.2 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | T&C | 1 | 1 | lot | 0 | 4387240.8 | 4387240.8 | 0 | 4387240.8 | 4387240.8 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
8. |  | Adjustments Hall 2 | [6 empty] | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
8. 5. |  | Additional Compressed Air Equipment | [6 empty] | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
8. 5. 10. |  | Additional Compressed Air Equipment | 1 |  | PSCH |  |  |  | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Main equipments | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Rotary screw air compressor | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Air dryer | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ball Valve D63 | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ball Valve D40 | 6 |  | Pcs |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Oil removal filter | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Pressure maintainance system | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Condensate drain pipe D19 | 15 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Condensate drain pipe D15.9 | 25 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 |  | lot |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | T&C | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[8 empty] | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ventilation for Air compressor | [5 empty] | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Tole 0.95mm | 12 |  | m2 |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Motor fire damper 550x500x450 | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Flexiable connection | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cat6A | 66 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | Cable 1 pair 18AWG | 22 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/PVC/PVC 2Cx1.5mm2 | 22 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 39 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | GI flexible conduct D20 | 42 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable tray 50x50x1.0mm | 7 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger support | 1 |  | lot |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 |  | lot |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[8 empty] | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Compressed air pipes and valves | [5 empty] | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Aluminium Air pipe D63 | 11 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Aluminium Air pipe D40 | 8 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Fiiting for Aluminium pipe | 1 |  | lot |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger support + Accessories | 1 |  | lot |  |  | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | IV. 4.VENTILATION | [8 empty] | 3204713406.5221 |  |  | #REF! |  |  | 0% |  |  | 0%
2. |  | Production and Logistic building (Hall 3) | [6 empty] | 876156669.5216 | 245761873.2789 | 1121918542.8005 |  |  | #REF! |  |  | 0 |  |  | 0%
2. 3. |  | Mechanical Engineering | [6 empty] | 876156669.5216 | 245761873.2789 | 1121918542.8005 |  |  | #REF! |  |  | 0 |  |  | 0%
2. 3. 10. |  | Ventilation System Production | 1 | 1 | PSCH |  |  |  | 304034489.6043 | 189644193.2889 | 493678682.8931 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Logistics Area | [6 empty] | 32646354.8705 | 20550720.3964 | 53197075.267 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Overhead Propeller Fans | 2 | 2 | pcs | 0 | 6300000 | 6300000 | 0 | 12600000 | 12600000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Control panel for Overhead Fans | 1 | 1 | pcs | 19550000 | 385000 | 19935000 | 19550000 | 385000 | 19935000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/PVC/PVC 4Cx1.5mm2 | 160 | 163.8 | m | 25928.4 | 7485.665 | 33414.065 | 4247071.92 | 1226151.927 | 5473223.847 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/PVC/PVC 2Cx1.5mm2 | 165 | 163.8 | m | 15443.88 | 5031.18 | 20475.06 | 2529707.544 | 824107.284 | 3353814.828 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 243 | 300 | m | 8773.9726 | 14594.0164 | 23367.989 | 2632191.7808 | 4378204.9235 | 7010396.7044 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 7 | 7.35 | m | 3554.7229 | 5289.7059 | 8844.4288 | 26127.2135 | 38879.3382 | 65006.5517 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 15 |  | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger, support | 1 | 1 | lot | 1220418.8041 | 366125.6412 | 1586544.4453 | 1220418.8041 | 366125.6412 | 1586544.4453 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 2440837.6082 | 732251.2824 | 3173088.8906 | 2440837.6082 | 732251.2824 | 3173088.8906 |  |  | #REF! |  |  | 0% |  |  | 0%
|  |  | 0 | 0 | [9 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Production Hall 1 | 0 | 0 |  |  |  |  | 233479516.9276 | 145274230.7072 | 378753747.6348 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Overhead Propeller Fans | 14 | 14 | pcs | 0 | 6300000 | 6300000 | 0 | 88200000 | 88200000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Control panel for Overhead Fans | 7 | 7 | m | 19550000 | 385000 | 19935000 | 136850000 | 2695000 | 139545000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 4Cx-1.5mm2 Cu/PVC/PVC | 1600 | 1556.5 | m | 25928.4 | 7485.665 | 33414.065 | 40357554.6 | 11651437.5725 | 52008992.1725 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 2Cx-1.5mm2 Cu/PVC/PVC | 1050 | 1156.5 | m | 15443.88 | 5031.18 | 20475.06 | 17860847.22 | 5818559.67 | 23679406.89 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 2125 | 2100 | m | 8773.9726 | 14594.0164 | 23367.989 | 18425342.4658 | 30647434.4647 | 49072776.9305 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 70 | 63 | m | 3554.7229 | 5289.7059 | 8844.4288 | 223947.544 | 333251.4706 | 557199.0145 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 150 |  | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger, support | 1 | 1 | lot | 8982647.7718 | 2694794.3315 | 11677442.1033 | 8982647.7718 | 2694794.3315 | 11677442.1033 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 10779177.3261 | 3233753.1978 | 14012930.524 | 10779177.3261 | 3233753.1978 | 14012930.524 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Production Hall 2 | 0 | 0 |  |  |  |  | 30503490.5753 | 19149107.5868 | 49652598.1621 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Overhead Propeller Fans | 2 | 2 | pcs | 0 | 6300000 | 6300000 | 0 | 12600000 | 12600000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Control panel for Overhead Fans | 1 | 1 | m | 19550000 | 385000 | 19935000 | 19550000 | 385000 | 19935000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 4Cx-1.5mm2 Cu/PVC/PVC | 160 | 108.15 | m | 25928.4 | 7485.665 | 33414.065 | 2804156.46 | 809574.6698 | 3613731.1298 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 2Cx-1.5mm2 Cu/PVC/PVC | 165 | 170 | m | 15443.88 | 5031.18 | 20475.06 | 2625459.6 | 855300.6 | 3480760.2 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 243 | 220 | m | 8773.9726 | 14594.0164 | 23367.989 | 1930273.9726 | 3210683.6106 | 5140957.5832 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 7 | 7.35 | m | 3554.7229 | 5289.7059 | 8844.4288 | 26127.2135 | 38879.3382 | 65006.5517 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 15 | 15 | m | 8773.9726 | 14594.0164 | 23367.989 | 131609.589 | 218910.2462 | 350519.8352 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger, support | 1 | 1 | lot | 1145287.9134 | 343586.374 | 1488874.2874 | 1145287.9134 | 343586.374 | 1488874.2874 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 2290575.8268 | 687172.748 | 2977748.5748 | 2290575.8268 | 687172.748 | 2977748.5748 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Interface between fire alarm and fan system | 0 | 0 |  |  |  |  | 7405127.2308 | 4670134.5985 | 12075261.8293 |  |  | #REF! |  |  | 0% |  |  | 0%
| 8 | Fire signal cable: (2x1.0)mm2 Dây tín hiệu báo cháy: (2x1.0)mm2 | 830 | 830 | M | 7457.49 | 3300 | 10757.49 | 6189716.7 | 2739000 | 8928716.7 |  |  | #REF! |  |  | 0% |  |  | 0%
| 10 | D16 PVC conduit & accessories Ống bảo vệ dây dẫn D16 và phụ kiện | 140 | 140 | M | 6646.8692 | 13183.4282 | 19830.2974 | 930561.6849 | 1845679.9447 | 2776241.6296 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 284848.8459 | 85454.6538 | 370303.4997 | 284848.8459 | 85454.6538 | 370303.4997 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
2. 3. 60. |  | SMOKE EXHAUST SYSTEM | [6 empty] | 572122179.9173 | 56117679.99 | 628239859.9073 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Equipment | [6 empty] | 474178458 | 32835793.1 | 507014251.1 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Roof smoke exhaust FAN - SEAF @26500m3/h, 100Pa, 3.0kW, 300oC in 2hrs | 6 | 6 | pcs | 43434300 | 2241801.1 | 45676101.1 | 260605800 | 13450806.6 | 274056606.6 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Roof smoke exhaust FAN - SEAF @8000m3/h, 100Pa, 0.5kW, 300oC in 2hrs | 4 | 4 | pcs | 17612370 | 923094.7 | 18535464.7 | 70449480 | 3692378.8 | 74141858.8 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Wall mounted smoke exhaust FAN - SEAF @26500m3/h, 100Pa, 3kW, 300oC in 2hrs | 3 | 3 | pcs | 25306446 | 2241801.1 | 27548247.1 | 75919338 | 6725403.3 | 82644741.3 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Wall mounted smoke exhaust FAN - SEAF @16000m3/h, 100Pa, 1.5kW, 300oC in 2hrs | 4 | 4 | pcs | 16800960 | 2241801.1 | 19042761.1 | 67203840 | 8967204.4 | 76171044.4 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable power supply & conduit | [6 empty] | 97943721.9173 | 23281886.89 | 121225608.8073 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/Fr/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 1156 | 1281 | m | 60411.45 | 9350 | 69761.45 | 77387067.45 | 11977350 | 89364417.45 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D25 | 463 | 415 | m | 12762.0356 | 15805 | 28567.0356 | 5296244.7808 | 6559075 | 11855319.7808 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC flexible conduct D25 | 120 | 53.55 | m | 8113.63 | 5559 | 13672.63 | 434484.8865 | 297684.45 | 732169.3365 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 14825924.8 | 4447777.44 | 19273702.24 | 14825924.8 | 4447777.44 | 19273702.24 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. |  | Office, Social and Technical Areas (Hall 3) | [6 empty] | 1272946321.0445 | 134316312.1879 | 1407262633.2324 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 3. |  | Mechanical Engineering | [6 empty] | 1272946321.0445 | 134316312.1879 | 1407262633.2324 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 3. 40. |  | Ventilation System | 1 | 1 | PSCH |  |  |  | 915624507.9952 | 94236583.2039 | 1009861091.1991 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ground floor - west side | [6 empty] | 259524148.7256 | 33244549.9752 | 292768698.7008 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Equipments | [6 empty] | 32262384 | 3815280.7 | 36077664.7 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exhaust air fan in-line centrifugal type (Q = 1240/620 m3/h, 220 Pa) | 1 | 1 | pcs | 7426788 | 923094.7 | 8349882.7 | 7426788 | 923094.7 | 8349882.7 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exhaust air fan in-line centrifugal type (Q = 460/230 m3/h, 200 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exhaust air fan in-line centrifugal type (Q = 680/340 m3/h, 200 Pa) | 1 | 1 | pcs | 4734816 | 495000 | 5229816 | 4734816 | 495000 | 5229816 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exhaust air fan in-line centrifugal type (Q = 550/275 m3/h, 180 Pa) | 2 | 2 | pcs | 4658448 | 495000 | 5153448 | 9316896 | 990000 | 10306896 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exhaust air fan in-line centrifugal type (Q = 120 m3/h, 120 Pa) | 1 | 1 | pcs | 4734816 | 495000 | 5229816 | 4734816 | 495000 | 5229816 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 1390620 | 417186 | 1807806 | 1390620 | 417186 | 1807806 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Air grille, louver | [6 empty] | 167427120 | 9290400 | 176717520 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Poppet Valves D160 | 3 | 3 | pcs | 1079160 | 84000 | 1163160 | 3237480 | 252000 | 3489480 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Poppet Valves D100 | 43 | 43 | pcs | 921840 | 84000 | 1005840 | 39639120 | 3612000 | 43251120 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Fresh air grille 500x200 | 18 | 18 | pcs | 1117800 | 140000 | 1257800 | 20120400 | 2520000 | 22640400 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Exhaust air grille 200x200 | 1 | 1 | pcs | 797640 | 117600 | 915240 | 797640 | 117600 | 915240 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Louver 200x200 + IS | 1 | 1 | pcs | 698280 | 117600 | 815880 | 698280 | 117600 | 815880 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Louver 400x200 + IS | 1 | 1 | pcs | 844560 | 117600 | 962160 | 844560 | 117600 | 962160 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Louver 400x250 + IS | 3 | 3 | pcs | 1073640 | 117600 | 1191240 | 3220920 | 352800 | 3573720 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Louver 700x300 + IS | 1 | 1 | pcs | 2152800 | 140000 | 2292800 | 2152800 | 140000 | 2292800 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Volume control damper VCD D100 | 1 | 1 | pcs | 979800 | 84000 | 1063800 | 979800 | 84000 | 1063800 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Volume control damper VCD D160 | 6 | 6 | pcs | 1208880 | 84000 | 1292880 | 7253280 | 504000 | 7757280 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Volume control damper VCD D200 | 1 | 1 | pcs | 1479360 | 84000 | 1563360 | 1479360 | 84000 | 1563360 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Volume control controller D160 | 1 | 1 | pcs | 2718600 | 84000 | 2802600 | 2718600 | 84000 | 2802600 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Pressure release flap 345x400 | 2 | 2 | pcs | 30674640 | 280000 | 30954640 | 61349280 | 560000 | 61909280 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Silencer D120xL500 | 1 | 1 | pcs | 2368080 | 106400 | 2474480 | 2368080 | 106400 | 2474480 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Silencer D190xL500 | 6 | 6 | pcs | 3427920 | 106400 | 3534320 | 20567520 | 638400 | 21205920 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Ductwork sheet | [6 empty] | 59834644.7256 | 20138869.2752 | 79973514.0008 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Rigid duct Z8, thickness 0.58mm | 52 | 51.7 | m2 | 236291.3455 | 106400 | 342691.3455 | 12216262.56 | 5500880 | 17717142.56 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Insulation 6mmT | 57 | 55 | m2 | 104230.8 | 44800 | 149030.8 | 5732694 | 2464000 | 8196694 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Simili for fan | 12 | 12 | pcs | 90000 | 35000 | 125000 | 1080000 | 420000 | 1500000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 15556006.38 | 4666801.914 | 20222808.294 | 15556006.38 | 4666801.914 | 20222808.294 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable power supply & conduit | [6 empty] | 25249681.7856 | 7087187.3612 | 32336869.1468 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Timer delay | 5 | 5 | pcs | 2875000 | 82500 | 2957500 | 14375000 | 412500 | 14787500 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Switch 1way - 1gang 10A-220V | 1 | 1 | m | 46800 | 54500 | 101300 | 46800 | 54500 | 101300 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 330 | 308 | m | 22980.09 | 5743.9305 | 28724.0205 | 7077867.72 | 1769130.594 | 8846998.314 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 9 | 9.9 | m | 3554.7229 | 5289.7059 | 8844.4288 | 35191.7569 | 52368.0882 | 87559.8451 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 333 | 308 | m | 8773.9726 | 14594.0164 | 23367.989 | 2702383.5616 | 4494957.0548 | 7197340.6165 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 1012438.7471 | 303731.6241 | 1316170.3712 | 1012438.7471 | 303731.6241 | 1316170.3712 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ground floor - east side | [6 empty] | 540527596.8724 | 42856692.0376 | 583384288.91 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Equipments | [6 empty] | 41276280 | 4988745 | 46265025 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exhaust air fan in-line centrifugal type (Q = 800/400 m3/h, 200 Pa) | 1 | 1 | pcs | 4734816 | 495000 | 5229816 | 4734816 | 495000 | 5229816 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exhaust air fan in-line centrifugal type (Q = 600/300 m3/h, 220 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exhaust air fan in-line centrifugal type (Q = 550/275 m3/h, 180 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exhaust air fan in-line centrifugal type (Q = 500 m3/h, 200 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exhaust air fan wall type (Q = 120 m3/h, 50 Pa) | 1 | 1 | pcs | 2324562 | 495000 | 2819562 | 2324562 | 495000 | 2819562 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exhaust air fan wall type (Q = 1210 m3/h, 50 Pa) | 4 | 4 | pcs | 4615602 | 495000 | 5110602 | 18462408 | 1980000 | 20442408 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 1779150 | 533745 | 2312895 | 1779150 | 533745 | 2312895 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Air grille, louver | [6 empty] | 429116520 | 10169600 | 439286120 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Poppet Valves D160 | 1 | 1 | pcs | 1079160 | 84000 | 1163160 | 1079160 | 84000 | 1163160 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Poppet Valves D100 | 23 | 23 | pcs | 921840 | 84000 | 1005840 | 21202320 | 1932000 | 23134320 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Fresh air grille 500x200 | 18 | 18 | pcs | 1117800 | 140000 | 1257800 | 20120400 | 2520000 | 22640400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exhaust air grille 200x200 | 1 | 1 | pcs | 797640 | 117600 | 915240 | 797640 | 117600 | 915240 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Exhaust air grille 500x200 + OBD | 13 | 13 | pcs | 1349640 | 140000 | 1489640 | 17545320 | 1820000 | 19365320 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Louver 200x200 + IS | 1 | 1 | pcs | 698280 | 117600 | 815880 | 698280 | 117600 | 815880 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Louver 400x250 + IS | 3 | 3 | pcs | 1073640 | 117600 | 1191240 | 3220920 | 352800 | 3573720 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Louver 500x500 + IS | 4 | 4 | pcs | 2484000 | 140000 | 2624000 | 9936000 | 560000 | 10496000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Louver 700x250 + IS | 1 | 1 | pcs | 2152800 | 140000 | 2292800 | 2152800 | 140000 | 2292800 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Volume control damper VCD D100 | 1 | 1 | pcs | 979800 | 84000 | 1063800 | 979800 | 84000 | 1063800 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Volume control damper VCD D160 | 3 | 3 | pcs | 1208880 | 84000 | 1292880 | 3626640 | 252000 | 3878640 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Volume control controller D160 | 1 | 1 | pcs | 2718600 | 84000 | 2802600 | 2718600 | 84000 | 2802600 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Pressure release flap 345x400 | 2 | 2 | pcs | 30674640 | 280000 | 30954640 | 61349280 | 560000 | 61909280 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Fire damper D250 | 2 | 2 | pcs | 21834360 | 140000 | 21974360 | 43668720 | 280000 | 43948720 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Overflow air via fire protection flaps 400x250 | 3 | 3 | pcs | 75789600 | 280000 | 76069600 | 227368800 | 840000 | 228208800 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Silencer D120xL500 | 1 | 1 | pcs | 2368080 | 106400 | 2474480 | 2368080 | 106400 | 2474480 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Silencer D190xL500 | 3 | 3 | pcs | 3427920 | 106400 | 3534320 | 10283760 | 319200 | 10602960 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Ductwork sheet | [6 empty] | 42937395.394 | 15270557.0262 | 58207952.4202 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Rigid duct Z8, thickness 0.58mm | 44 | 46.2 | m2 | 236291.3455 | 106400 | 342691.3455 | 10916660.16 | 4915680 | 15832340.16 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Insulation 6mmT | 50 | 50.6 | m2 | 104230.8 | 44800 | 149030.8 | 5274078.48 | 2266880 | 7540958.48 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Simili for fan | 8 | 8 | pcs | 90000 | 35000 | 125000 | 720000 | 280000 | 1000000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 26026656.754 | 7807997.0262 | 33834653.7802 | 26026656.754 | 7807997.0262 | 33834653.7802 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable power supply & conduit | [6 empty] | 27197401.4784 | 12427790.0114 | 39625191.4898 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Timer delay | 2 | 2 | pcs | 2875000 | 82500 | 2957500 | 5750000 | 165000 | 5915000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Switch 1way - 1gang 10A-220V | 1 | 1 | m | 46800 | 54500 | 101300 | 46800 | 54500 | 101300 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Contactor + Box | 3 | 3 | m | 900000 | 163500 | 1063500 | 2700000 | 490500 | 3190500 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 495 | 495 | m | 22980.09 | 5743.9305 | 28724.0205 | 11375144.55 | 2843245.5975 | 14218390.1475 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 2C-1.5mm2 Cu/PVC/PVC | 90 | 90 | m | 15443.88 | 5031.18 | 20475.06 | 1389949.2 | 452806.2 | 1842755.4 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 14 | 14.7 | m | 3554.7229 | 5289.7059 | 8844.4288 | 52254.4269 | 77758.6765 | 130013.1034 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D16 | 495 |  | m | 6646.8692 | 13183.4282 | 19830.2974 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 498 | 550 | m | 8773.9726 | 14594.0164 | 23367.989 | 4825684.9315 | 8026709.0265 | 12852393.958 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 1057568.3699 | 317270.511 | 1374838.8809 | 1057568.3699 | 317270.511 | 1374838.8809 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Fist floor - west side | [6 empty] | 95572762.3972 | 15135341.1911 | 110708103.5883 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Equipments | [6 empty] | 19632768 | 2233872 | 21866640 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exhaust air fan in-line centrifugal type (Q = 830/415 m3/h, 150 Pa) | 2 | 2 | pcs | 4734816 | 495000 | 5229816 | 9469632 | 990000 | 10459632 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exhaust air fan in-line centrifugal type (Q = 480/240 m3/h, 150 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exhaust air fan in-line centrifugal type (Q = 420/210 m3/h, 150 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 846240 | 253872 | 1100112 | 846240 | 253872 | 1100112 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Air grille, louver | [6 empty] | 47615520 | 2996000 | 50611520 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Poppet Valves D100 | 15 | 15 | pcs | 921840 | 84000 | 1005840 | 13827600 | 1260000 | 15087600 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Louver 700x250 + IS | 2 | 2 | pcs | 2152800 | 140000 | 2292800 | 4305600 | 280000 | 4585600 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Louver 400x200 + IS | 2 | 2 | pcs | 844560 | 117600 | 962160 | 1689120 | 235200 | 1924320 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Exhaust air grille EAG-600x600 | 2 | 2 | pcs | 3960600 | 140000 | 4100600 | 7921200 | 280000 | 8201200 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Supply air grille EAG-300x300 | 8 | 8 | pcs | 2484000 | 117600 | 2601600 | 19872000 | 940800 | 20812800 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Ductwork sheet | [6 empty] | 12042039.2045 | 4956818.7105 | 16998857.915 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Rigid duct Z8, thickness 0.58mm | 25 | 25 | m2 | 236291.3455 | 106400 | 342691.3455 | 5907283.6364 | 2660000 | 8567283.6364 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Insulation 6mmT | 29 | 29 | m2 | 104230.8 | 44800 | 149030.8 | 3022693.2 | 1299200 | 4321893.2 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Simili for fan | 8 | 8 | pcs | 90000 | 35000 | 125000 | 720000 | 280000 | 1000000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 2392062.3682 | 717618.7105 | 3109681.0786 | 2392062.3682 | 717618.7105 | 3109681.0786 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable power supply & conduit | [6 empty] | 16282435.1926 | 4948650.4806 | 21231085.6733 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Timer delay | 3 | 3 | pcs | 2875000 | 82500 | 2957500 | 8625000 | 247500 | 8872500 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 220 | 220 | m | 22980.09 | 5743.9305 | 28724.0205 | 5055619.8 | 1263664.71 | 6319284.51 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 220 | 220 | m | 8773.9726 | 14594.0164 | 23367.989 | 1930273.9726 | 3210683.6106 | 5140957.5832 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 6 | 6 | m | 3554.7229 | 5289.7059 | 8844.4288 | 21328.3375 | 31738.2353 | 53066.5728 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 650213.0825 | 195063.9248 | 845277.0073 | 650213.0825 | 195063.9248 | 845277.0073 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Fist floor - esat side | [6 empty] | 20000000 | 3000000 | 23000000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Equipments | [6 empty] | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exhaust air fan in-line centrifugal type (Q = 440/220m3/h, 150 Pa) | 3 |  | pcs | 4658448 | 495000 | 5153448 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Air grille, louver | [6 empty] | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Poppet Valves D220 | 4 |  | pcs | 1484880 | 84000 | 1568880 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Poppet Valves D100 | 19 |  | pcs | 921840 | 84000 | 1005840 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Louver 400x200 + IS | 3 |  | pcs | 844560 | 117600 | 962160 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Volume control damper VCD D100 | 1 |  | pcs | 979800 | 84000 | 1063800 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Volume control damper VCD D160 | 2 |  | pcs | 1208880 | 84000 | 1292880 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Supply air grille EAG-300x300 | 4 |  | pcs | 2484000 | 117600 | 2601600 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Silencer D120xL500 | 1 |  | pcs | 2368080 | 106400 | 2474480 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Silencer D190xL500 | 2 |  | pcs | 3427920 | 106400 | 3534320 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ductwork sheet | [6 empty] | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Rigid duct Z8, thickness 0.58mm | 18 |  | m2 | 236291.3455 | 106400 | 342691.3455 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Insulation 6mmT | 22 |  | m2 | 104230.8 | 44800 | 149030.8 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Simili for fan | 6 |  | pcs | 90000 | 35000 | 125000 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable power supply & conduit | [6 empty] | 20000000 | 3000000 | 23000000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Timer delay | 2 |  | pcs | 2875000 | 82500 | 2957500 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 165 |  | m | 22980.09 | 5743.9305 | 28724.0205 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 165 |  | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 6 |  | m | 3554.7229 | 5289.7059 | 8844.4288 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Fire stop | 3 | 1 | lot | 20000000 | 3000000 | 23000000 | 20000000 | 3000000 | 23000000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 |  | lot | 1000000 | 300000 | 1300000 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 3. 50. |  | Ventilation System 1st Floor Offices Ventilation Units | 1 | 1 | PSCH |  |  |  | 84938287.2586 | 5889562.8377 | 90827850.0963 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | west side | 0 | 0 |  |  |  | 0 | 84938287.2586 | 5889562.8377 | 90827850.0963 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Equipments | [6 empty] | 80634445.35 | 3616553.635 | 84250998.985 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Heat Recovery Ventilation 390 m3/h | 1 | 1 | pcs | 19802999.7 | 1064000 | 20866999.7 | 19802999.7 | 1064000 | 20866999.7 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Heat Recovery Ventilation 2000 m3/h | 1 | 1 | pcs | 54096000.2 | 1400000 | 55496000.2 | 54096000.2 | 1400000 | 55496000.2 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Remote wirring for ERV | 2 | 2 | pcs | 1614800 | 50400 | 1665200 | 3229600 | 100800 | 3330400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger support & Accessories | 1 | 1 | lot | 3505845.45 | 1051753.635 | 4557599.085 | 3505845.45 | 1051753.635 | 4557599.085 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable power supply & conduit | [6 empty] | 4303841.9086 | 2273009.2027 | 6576851.1113 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 3C-2.5mm2 Cu/XLPE/PVC | 100 | 100 | m | 32518.74 | 7485.665 | 40004.405 | 3251874 | 748566.5 | 4000440.5 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 100 | 100 | m | 8773.9726 | 14594.0164 | 23367.989 | 877397.2603 | 1459401.6412 | 2336798.9015 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 3 | 3 | m | 3554.7229 | 5289.7059 | 8844.4288 | 10664.1688 | 15869.1176 | 26533.2864 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 3 |  | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 163906.4796 | 49171.9439 | 213078.4235 | 163906.4796 | 49171.9439 | 213078.4235 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 3. 60. |  | Ventilation System 1st Floor Offices Ducting | 1 | 1 | PSCH |  |  |  | 272383525.7906 | 34190166.1463 | 306573691.937 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | west side | 0 | 0 |  |  |  | 0 | 272383525.7906 | 34190166.1463 | 306573691.937 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Equipments | [6 empty] | 262643773.8955 | 29033956.5687 | 291677730.4642 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exhaust air fan in-line centrifugal type (Q = 2000m3/h, 300 Pa) | 2 | 2 | pcs | 7379058 | 923094.7 | 8302152.7 | 14758116 | 1846189.4 | 16604305.4 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Duct smoke detector | 4 | 4 | pcs | 4140000 | 128800 | 4268800 | 16560000 | 515200 | 17075200 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Rigid duct Z8, thickness 0.58mm | 132 | 132 | m2 | 236291.3455 | 106400 | 342691.3455 | 31190457.6 | 14044800 | 45235257.6 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Insulation 16mmT | 142 | 143 | m2 | 207754.8 | 44800 | 252554.8 | 29708936.4 | 6406400 | 36115336.4 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Supply air grill 300x300 | 6 | 6 | pcs | 2484000 | 117600 | 2601600 | 14904000 | 705600 | 15609600 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Supply air grill 600x600 | 3 | 3 | pcs | 3960600 | 140000 | 4100600 | 11881800 | 420000 | 12301800 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Exhaust air grill 600x600 | 5 | 5 | pcs | 3960600 | 140000 | 4100600 | 19803000 | 700000 | 20503000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Louver 400x200 + IS | 2 | 2 | pcs | 844560 | 117600 | 962160 | 1689120 | 235200 | 1924320 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Louver 900x400 + IS | 2 | 2 | pcs | 3759120 | 140000 | 3899120 | 7518240 | 280000 | 7798240 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Siliencer D240xL1000 | 2 | 2 | pcs | 6668160 | 106400 | 6774560 | 13336320 | 212800 | 13549120 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Siliencer D300xL800 | 6 | 6 | pcs | 7998480 | 106400 | 8104880 | 47990880 | 638400 | 48629280 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Siliencer D420XL1000 | 4 | 4 | pcs | 11155920 | 106400 | 11262320 | 44623680 | 425600 | 45049280 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Hanger support & Accessories | 1 | 1 | lot | 8679223.8955 | 2603767.1687 | 11282991.0642 | 8679223.8955 | 2603767.1687 | 11282991.0642 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable power supply & conduit | [6 empty] | 9739751.8951 | 5156209.5777 | 14895961.4728 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Switch 1way - 2gang 10A-220V | 1 | 1 | m | 46800 | 54500 | 101300 | 46800 | 54500 | 101300 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Contactor + Box | 4 | 4 | m | 900000 | 163500 | 1063500 | 3600000 | 654000 | 4254000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 3C-2.5mm2 Cu/XLPE/PVC | 80 | 79.2 | m | 32518.74 | 7485.665 | 40004.405 | 2575484.208 | 592864.668 | 3168348.876 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 2C-1.5mm2 Cu/PVC/PVC | 80 | 79.2 | m | 15443.88 | 5031.18 | 20475.06 | 1223155.296 | 398469.456 | 1621624.752 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 76 | 160 | m | 8773.9726 | 14594.0164 | 23367.989 | 1403835.6164 | 2335042.6259 | 3738878.2423 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 3 | 3 | m | 3554.7229 | 5289.7059 | 8844.4288 | 10664.1688 | 15869.1176 | 26533.2864 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 3 | 3 | m | 8773.9726 | 14594.0164 | 23367.989 | 26321.9178 | 43782.0492 | 70103.967 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D16 | 72 | 72 | m | 6646.8692 | 13183.4282 | 19830.2974 | 478574.5808 | 949206.8287 | 1427781.4095 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 374916.1073 | 112474.8322 | 487390.9395 | 374916.1073 | 112474.8322 | 487390.9395 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 3. 130. |  | SMOKE EXHAUST SYSTEM | [6 empty] | 143640024.0078 | 24229831.2332 | 167869855.241 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | WEST SIDE | [6 empty] | 32042422.6672 | 2927603.7911 | 34970026.4583 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Equipment | [6 empty] | 26144496 | 990000 | 27134496 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Wall mounted smoke exhaust FAN - SEAF @11550m3/h, 100Pa, 1.5kW, 300oC in 2hrs | 2 | 2 | pcs | 13072248 | 495000 | 13567248 | 26144496 | 990000 | 27134496 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable power supply & conduit | [6 empty] | 5897926.6672 | 1937603.7911 | 7835530.4583 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/Fr/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 70 | 66 | m | 60411.45 | 9350 | 69761.45 | 3987155.7 | 617100 | 4604255.7 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 63 | 60 | m | 8773.9726 | 14594.0164 | 23367.989 | 526438.3562 | 875640.9847 | 1402079.3409 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 7 | 7 | m | 3554.7229 | 5289.7059 | 8844.4288 | 24883.0604 | 37027.9412 | 61911.0016 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 1359449.5506 | 407834.8652 | 1767284.4158 | 1359449.5506 | 407834.8652 | 1767284.4158 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | EAST SIDE | [6 empty] | 111597601.3406 | 21302227.4421 | 132899828.7827 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Equipment | [6 empty] | 23339970 | 2769284.1 | 26109254.1 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | AXIAL Smoke exhaust FAN - SEAF @7320m3/h, 180Pa, 1.25kW, 300oC in 2hrs | 3 | 3 | pcs | 7779990 | 923094.7 | 8703084.7 | 23339970 | 2769284.1 | 26109254.1 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 1051350 | 315405 | 1366755 | 1051350 | 315405 | 1366755 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Air grille, louver | [6 empty] | 23084640 | 840000 | 23924640 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Smoke Exhaust grille 1200x600 + OBD | 3 | 3 | pcs | 3281640 | 140000 | 3421640 | 9844920 | 420000 | 10264920 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Louver 1000x400 + IS | 3 | 3 | pcs | 4413240 | 140000 | 4553240 | 13239720 | 420000 | 13659720 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ductwork sheet | [6 empty] | 48893376.2182 | 12696041.9127 | 61589418.1309 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Rigid duct Z8, thickness 0.58mm | 47 | 42 | m2 | 236291.3455 | 106400 | 342691.3455 | 9924236.5091 | 4468800 | 14393036.5091 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Rockwool 50mmT | 36 | 36 | m2 | 408250 | 61600 | 469850 | 14697000 | 2217600 | 16914600 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Fireproof paint for smoke duct | 33 | 33 | m2 | 432000 | 89600 | 521600 | 14256000 | 2956800 | 17212800 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Simili for fan | 6 | 6 | pcs | 90000 | 35000 | 125000 | 540000 | 210000 | 750000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 9476139.7091 | 2842841.9127 | 12318981.6218 | 9476139.7091 | 2842841.9127 | 12318981.6218 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Cable power supply & conduit | [6 empty] | 15228265.1224 | 4681496.4294 | 19909761.5518 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/Fr/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 195 | 195 | m | 60411.45 | 9350 | 69761.45 | 11780232.75 | 1823250 | 13603482.75 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 176 | 150 | m | 8773.9726 | 14594.0164 | 23367.989 | 1316095.8904 | 2189102.4618 | 3505198.3522 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 7 | 7 | m | 3554.7229 | 5289.7059 | 8844.4288 | 24883.0604 | 37027.9412 | 61911.0016 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 2107053.4216 | 632116.0265 | 2739169.448 | 2107053.4216 | 632116.0265 | 2739169.448 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
4. |  | Machine hook-up (Hall 3) | [6 empty] | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
5. |  | Scooter Garage | [6 empty] | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
6. |  | Canteen | [6 empty] | 435189667.08 | 72472708.1683 | 507662375.2483 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
6. 3. 60. |  | Ventilation System Overhead Fans | 1 | 1 | PSCH |  |  |  | 413174538.3791 | 66328606.8362 | 479503145.2154 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Overhead Propeller Fans, D=3m | 10 | 10 | pcs | 37185000 | 4950000 | 42135000 | 371850000 | 49500000 | 421350000 |  |  | #REF! | 45% |  | 45% |  |  | 45%
|  | 3C-2.5mm2 Cu/XLPE/PVC | 250 | 245 | m | 32518.74 | 7485.665 | 40004.405 | 7967091.3 | 1833987.925 | 9801079.225 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | Control Cable Cu/PVC 2cx1.5mm2 | 450 | 350 | m | 15443.88 | 5031.18 | 20475.06 | 5405358 | 1760913 | 7166271 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | PVC conduit D20 | 515 | 400 | m | 8773.9726 | 14594.0164 | 23367.989 | 3509589.0411 | 5837606.5647 | 9347195.6058 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 20 | 15 | m | 3554.7229 | 5289.7059 | 8844.4288 | 53320.8438 | 79345.5882 | 132666.432 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger, support | 1 | 1 | lot | 10452505.369 | 3135751.6107 | 13588256.9797 | 10452505.369 | 3135751.6107 | 13588256.9797 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 13936673.8253 | 4181002.1476 | 18117675.9729 | 13936673.8253 | 4181002.1476 | 18117675.9729 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
6. 3. 70. |  | Ventilation System | 1 | 1 | PSCH |  |  |  | 22015128.7008 | 6144101.3321 | 28159230.0329 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exhaust air fan Q=100m3/h, 50Pa, type wall | 2 | 2 | pcs | 2324562 | 495000 | 2819562 | 4649124 | 990000 | 5639124 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exhaust air fan Q=140m3/h, 50Pa, type wall | 1 | 1 | pcs | 2324562 | 495000 | 2819562 | 2324562 | 495000 | 2819562 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exhaust air fan Q=180m3/h, 50Pa, type wall | 1 | 1 | pcs | 2324562 | 495000 | 2819562 | 2324562 | 495000 | 2819562 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Exhaust air fan Q=300m3/h, 50Pa, type wall | 1 | 1 | pcs | 2735040 | 495000 | 3230040 | 2735040 | 495000 | 3230040 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Louver 250x250 + IS | 5 | 5 | pcs | 897000 | 117600 | 1014600 | 4485000 | 588000 | 5073000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Switch 1way - 1gang 10A-250V | 5 | 5 | pcs | 46800 | 54500 | 101300 | 234000 | 272500 | 506500 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 111 | 109.25 | m | 22980.09 | 5743.9305 | 28724.0205 | 2510574.8325 | 627524.4071 | 3138099.2396 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 8 | 11.5 | m | 3554.7229 | 5289.7059 | 8844.4288 | 40879.3136 | 60831.6176 | 101710.9312 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 119 | 109.25 | m | 8773.9726 | 14594.0164 | 23367.989 | 958556.5068 | 1594396.293 | 2552952.7998 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger, support, Accessories | 1 | 1 | lot | 1752830.0479 | 525849.0144 | 2278679.0623 | 1752830.0479 | 525849.0144 | 2278679.0623 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | V. AC SYSTEM | [8 empty] | 2228147077.7132 |  |  | #REF! |  |  | 0% |  |  | 0%
3. |  | Office, Social and Technical Areas (Hall 3) | [6 empty] | 1992902350.6879 | 211748078.3635 | 2204650429.0514 |  |  | #REF! |  |  | 0 |  |  | 0%
3. 3. 70. |  | Air Conditioning | 1 | 1 | PSCH |  |  |  | 1992902350.6879 | 211748078.3635 | 2204650429.0514 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | west side | [6 empty] | 1284913905.8615 | 131256535.4444 | 1416170441.3058 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Equipments | [6 empty] | 1094815450 | 55012677.04 | 1149828127.04 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Outdoor unit 56KW | 1 | 1 | pcs | 109143100 | 4434383.52 | 113577483.52 | 109143100 | 4434383.52 | 113577483.52 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Outdoor unit 50.4KW | 1 | 1 | pcs | 102932500 | 4434383.52 | 107366883.52 | 102932500 | 4434383.52 | 107366883.52 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Outdoor unit 40KW | 1 | 1 | pcs | 72590100 | 3920000 | 76510100 | 72590100 | 3920000 | 76510100 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Outdoor unit 33.6KW | 1 | 1 | pcs | 62381000 | 3920000 | 66301000 | 62381000 | 3920000 | 66301000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Outdoor unit 14KW | 1 | 1 | pcs | 30222170 | 840000 | 31062170 | 30222170 | 840000 | 31062170 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Indoor unit cassette type, 9.0kW | 6 | 6 | pcs | 9845660 | 537600 | 10383260 | 59073960 | 3225600 | 62299560 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Indoor unit cassette type, 7.1kW | 11 | 11 | pcs | 9569780 | 537600 | 10107380 | 105267580 | 5913600 | 111181180 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Indoor unit cassette type, 6kW | 7 | 7 | pcs | 8741260 | 504000 | 9245260 | 61188820 | 3528000 | 64716820 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Indoor unit cassette type, 5.6kW | 4 | 4 | pcs | 8464170 | 504000 | 8968170 | 33856680 | 2016000 | 35872680 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Indoor unit cassette type, 3.6kW | 1 | 1 | pcs | 7911200 | 504000 | 8415200 | 7911200 | 504000 | 8415200 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Split Air conditioner, indoor unit wall type, cooling capacity 4.5kW | 4 | 4 | pcs | 12599730 | 621600 | 13221330 | 50398920 | 2486400 | 52885320 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Split Air conditioner, indoor unit wall type, cooling capacity 6.3kW | 2 | 2 | pcs | 16773020 | 733600 | 17506620 | 33546040 | 1467200 | 35013240 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Split Air conditioner, indoor unit wall type, cooling capacity 7.1kW | 1 | 1 | pcs | 31227680 | 733600 | 31961280 | 31227680 | 733600 | 31961280 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Dehumidifiers 1200m3/h | 6 | 6 | pcs | 19690000 | 168000 | 19858000 | 118140000 | 1008000 | 119148000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Controller center for AC | 1 | 1 | pcs | 11532400 | 168000 | 11700400 | 11532400 | 168000 | 11700400 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Remote wirring for AC | 36 | 36 | pcs | 1614800 | 50400 | 1665200 | 58132800 | 1814400 | 59947200 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Controller for AC Split (IT Room, UPS room) | 2 | 2 | pcs | 873400 | 140000 | 1013400 | 1746800 | 280000 | 2026800 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | DB controller | 1 | 1 | pcs | 13200000 | 280000 | 13480000 | 13200000 | 280000 | 13480000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Gas splitter | 16 | 44 | pcs | 1815000 | 0 | 1815000 | 79860000 | 0 | 79860000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Concrete base for outdoor unit | 5 | 5 | pcs | 1300000 | 500000 | 1800000 | 6500000 | 2500000 | 9000000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Extra refrigerant charge R410a or R32 | 1 | 1 | lot | 7500000 | 0 | 7500000 | 7500000 | 0 | 7500000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 38463700 | 11539110 | 50002810 | 38463700 | 11539110 | 50002810 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Copper pipe | [6 empty] | 67284685.7759 | 24357916.6293 | 91642602.4052 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø6.4mm-0.81mmT | 78 | 112.7 | m | 38160 | 22400 | 60560 | 4300632 | 2524480 | 6825112 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø9.5mm-0.81mmT | 249 | 203.55 | m | 60000 | 23520 | 83520 | 12213000 | 4787496 | 17000496 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø12.7mm-0.81mmT | 90 | 119.6 | m | 81840 | 28000 | 109840 | 9788064 | 3348800 | 13136864 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø15.9mm-0.81mmT | 262 | 210.45 | m | 103760 | 38808 | 142568 | 21836292 | 8167143.6 | 30003435.6 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø19.1mm-0.81mmT | 0 | 0 | m | 129600 | 42560 | 172160 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø22.2mm-0.81mmT | 18 | 27.6 | m | 147310.3448 | 49392 | 196702.3448 | 4065765.5172 | 1363219.2 | 5428984.7172 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø28.6mm-1.0mmT | 54 | 52.9 | m | 234206.8966 | 63504 | 297710.8966 | 12389544.8276 | 3359361.6 | 15748906.4276 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger support & Accessories | 1 | 1 | lot | 2691387.431 | 807416.2293 | 3498803.6603 | 2691387.431 | 807416.2293 | 3498803.6603 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Insulation copper pipe | [6 empty] | 14380586.125 | 5959615.4335 | 20340201.5585 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø6.4mm-15mmT | 78 | 112.7 | m | 15358.8 | 5600 | 20958.8 | 1730936.76 | 631120 | 2362056.76 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø9.5mm-15mmT | 249 | 203.55 | m | 16754.4 | 5644.8 | 22399.2 | 3410358.12 | 1148999.04 | 4559357.16 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø12.7mm-15mmT | 90 | 119.6 | m | 17871.6 | 7728 | 25599.6 | 2137443.36 | 924268.8 | 3061712.16 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø15.9mm-15mmT | 262 | 210.45 | m | 20664 | 9172.8 | 29836.8 | 4348738.8 | 1930415.76 | 6279154.56 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø19.1mm-15mmT | 0 | 0 | m | 23176.8 | 101595.2 | 124772 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø22.2mm-15mmT | 18 | 27.6 | m | 24852 | 11995.2 | 36847.2 | 685915.2 | 331067.52 | 1016982.72 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø28.6mm-15mmT | 54 | 52.9 | m | 28203.6 | 15523.2 | 43726.8 | 1491970.44 | 821177.28 | 2313147.72 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 575223.445 | 172567.0335 | 747790.4785 | 575223.445 | 172567.0335 | 747790.4785 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Condensate pipe | [6 empty] | 3756725.28 | 3113650.848 | 6870376.128 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | uPVC-Ø27mm-PN12 | 124 | 127.6 | m | 8236.8 | 11743.2 | 19980 | 1051015.68 | 1498432.32 | 2549448 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | uPVC-Ø34mm-PN12 | 59 | 72.6 | m | 16286.4 | 12639.2 | 28925.6 | 1182392.64 | 917605.92 | 2099998.56 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | uPVC-Ø42mm-PN12 | 33 | 29.7 | m | 21528 | 14560 | 36088 | 639381.6 | 432432 | 1071813.6 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Fitting for UpVC | 1 | 1 | lot | 662951.52 | 198885.456 | 861836.976 | 662951.52 | 198885.456 | 861836.976 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger support & Accessories | 1 | 1 | lot | 220983.84 | 66295.152 | 287278.992 | 220983.84 | 66295.152 | 287278.992 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Insulation condensate pipe | 0 | 0 |  |  |  |  | 3118303.375 | 3148490.6805 | 6266794.0555 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø27mm-10mmT | 124 | 127.6 | m | 11169.6 | 11743.2 | 22912.8 | 1425240.96 | 1498432.32 | 2923673.28 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø34mm-10mmT | 59 | 72.6 | m | 14520 | 15523.2 | 30043.2 | 1054152 | 1126984.32 | 2181136.32 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø42mm-10mmT | 33 | 29.7 | m | 17312.4 | 16352 | 33664.4 | 514178.28 | 485654.4 | 999832.68 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 124732.135 | 37419.6405 | 162151.7755 | 124732.135 | 37419.6405 | 162151.7755 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable power supply & conduit | [6 empty] | 101558155.3056 | 39664184.8131 | 141222340.1186 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Double socket 1P-16A-250V | 6 | 6 | pcs | 150480 | 54500 | 204980 | 902880 | 327000 | 1229880 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 4x1Cx4mm2+E4mm2 | 200 | 174.9 | m | 72299.4 | 17189.865 | 89489.265 | 12645165.06 | 3006507.3885 | 15651672.4485 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 3Cx-2.5mm2Cu/XLPE/PVC | 260 | 177.1 | m | 32518.74 | 7485.665 | 40004.405 | 5759068.854 | 1325711.2715 | 7084780.1255 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 3Cx-1.5mm2Cu/XLPE/PVC | 450 | 338.8 | m | 22980.09 | 5743.9305 | 28724.0205 | 7785654.492 | 1946043.6534 | 9731698.1454 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 4Cx-1.5mm2Cu/PVC/PVC | 105 | 111.1 | m | 25928.4 | 7485.665 | 33414.065 | 2880645.24 | 831657.3815 | 3712302.6215 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 2Cx-1.5mm2Cu/PVC/PVC | 495 | 332.2 | m | 15443.88 | 5031.18 | 20475.06 | 5130456.936 | 1671357.996 | 6801814.932 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 18 core AWG 1 pair | 540 | 607.2 | m | 21976.8 | 3920 | 25896.8 | 13344312.96 | 2380224 | 15724536.96 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 104 | 660 | m | 8773.9726 | 14594.0164 | 23367.989 | 5790821.9178 | 9632050.8318 | 15422872.7496 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D16 | 378 | 935 | m | 6646.8692 | 13183.4282 | 19830.2974 | 6214822.6815 | 12326505.345 | 18541328.0265 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D16 | 891 | 0 | m | 6646.8692 | 13183.4282 | 19830.2974 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 143 | 0 | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D25 | 140 | 154 | m | 12762.0356 | 15805 | 28567.0356 | 1965353.4849 | 2433970 | 4399323.4849 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC flexible conduit D20 | 39 | 55 | m | 3554.7229 | 5289.7059 | 8844.4288 | 195509.7606 | 290933.8235 | 486443.5841 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC flexible conduit D20 | 22 | 0 | m | 3554.7229 | 5289.7059 | 8844.4288 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable tray 200x100x2.0mm | 42 | 45 | m | 776880 | 51045.8655 | 827925.8655 | 34959600 | 2297063.9462 | 37256663.9462 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 3983863.9187 | 1195159.1756 | 5179023.0944 | 3983863.9187 | 1195159.1756 | 5179023.0944 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | East side | [6 empty] | 707988444.8264 | 80491542.9191 | 788479987.7455 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Equipments | [6 empty] | 606357980 | 35796884 | 642154864 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Outdoor unit 33.6KW | 2 | 2 | pcs | 62381000 | 3920000 | 66301000 | 124762000 | 7840000 | 132602000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Outdoor unit 22.4KW | 1 | 1 | pcs | 48310460 | 3304000 | 51614460 | 48310460 | 3304000 | 51614460 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Outdoor unit 14KW | 1 | 1 | pcs | 30222170 | 840000 | 31062170 | 30222170 | 840000 | 31062170 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Indoor unit cassette type, 9.0kW | 6 | 6 | pcs | 9845660 | 537600 | 10383260 | 59073960 | 3225600 | 62299560 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Indoor unit cassette type, 7.1kW | 7 | 7 | pcs | 9569780 | 537600 | 10107380 | 66988460 | 3763200 | 70751660 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Indoor unit cassette type, 6kW | 1 | 1 | pcs | 8741260 | 504000 | 9245260 | 8741260 | 504000 | 9245260 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Split Air conditioner, indoor unit wall type, cooling capacity 4.5kW | 2 | 2 | pcs | 12599730 | 621600 | 13221330 | 25199460 | 1243200 | 26442660 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Split Air conditioner, indoor unit wall type, cooling capacity 7.1kW | 2 | 2 | pcs | 31227680 | 733600 | 31961280 | 62455360 | 1467200 | 63922560 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Split Air conditioner, indoor unit cassette type, cooling capacity 5.2kW | 1 | 1 | pcs | 21620170 | 733600 | 22353770 | 21620170 | 733600 | 22353770 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Dehumidifiers 1500m3/h | 3 | 3 | pcs | 19690000 | 168000 | 19858000 | 59070000 | 504000 | 59574000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Remote wirring for AC | 19 | 19 | pcs | 1614800 | 168000 | 1782800 | 30681200 | 3192000 | 33873200 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Controller for AC | 2 | 10 | pcs | 873400 | 50400 | 923800 | 8734000 | 504000 | 9238000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | DB controller | 1 | 1 | pcs | 13200000 | 280000 | 13480000 | 13200000 | 280000 | 13480000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Gas splitter | 5 | 8 | pcs | 1659900 | 0 | 1659900 | 13279200 | 0 | 13279200 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Concrete base for outdoor unit | 4 | 4 | pcs | 1300000 | 500000 | 1800000 | 5200000 | 2000000 | 7200000 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Extra refrigerant charge R410a or R32 | 1 | 1 | lot | 7500000 | 0 | 7500000 | 7500000 | 0 | 7500000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 21320280 | 6396084 | 27716364 | 21320280 | 6396084 | 27716364 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Copper pipe | 0 | 0 |  |  |  |  | 28355645.2586 | 9993875.3431 | 38349520.6017 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø6.4mm-0.81mmT | 18 | 19.95 | m | 38160 | 22400 | 60560 | 761292 | 446880 | 1208172 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø9.5mm-0.81mmT | 86 | 94.5 | m | 60000 | 23520 | 83520 | 5670000 | 2222640 | 7892640 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø12.7mm-0.81mmT | 28 | 30.45 | m | 81840 | 28000 | 109840 | 2492028 | 852600 | 3344628 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø15.9mm-0.81mmT | 92 | 101.85 | m | 103760 | 38808 | 142568 | 10567956 | 3952594.8 | 14520550.8 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø19.1mm-0.81mmT | 3 | 3.15 | m | 129600 | 42560 | 172160 | 408240 | 134064 | 542304 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø22.2mm-0.81mmT | 6 | 6.3 | m | 147310.3448 | 49392 | 196702.3448 | 928055.1724 | 311169.6 | 1239224.7724 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø28.6mm-1.0mmT | 25 | 27.3 | m | 234206.8966 | 63504 | 297710.8966 | 6393848.2759 | 1733659.2 | 8127507.4759 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 1134225.8103 | 340267.7431 | 1474493.5534 | 1134225.8103 | 340267.7431 | 1474493.5534 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Insulation copper pipe | 0 | 0 |  |  |  |  | 5768802.375 | 2703324.5085 | 8472126.8835 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø6.4mm-15mmT | 18 | 19.95 | m | 15358.8 | 5600 | 20958.8 | 306408.06 | 111720 | 418128.06 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø9.5mm-15mmT | 86 | 94.5 | m | 16754.4 | 5644.8 | 22399.2 | 1583290.8 | 533433.6 | 2116724.4 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø12.7mm-15mmT | 28 | 30.45 | m | 17871.6 | 7728 | 25599.6 | 544190.22 | 235317.6 | 779507.82 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø15.9mm-15mmT | 92 | 101.85 | m | 20664 | 9172.8 | 29836.8 | 2104628.4 | 934249.68 | 3038878.08 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø19.1mm-15mmT | 3 | 3.15 | m | 23176.8 | 101595.2 | 124772 | 73006.92 | 320024.88 | 393031.8 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø22.2mm-15mmT | 6 | 6.3 | m | 24852 | 11995.2 | 36847.2 | 156567.6 | 75569.76 | 232137.36 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø28.6mm-15mmT | 25 | 27.3 | m | 28203.6 | 15523.2 | 43726.8 | 769958.28 | 423783.36 | 1193741.64 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 230752.095 | 69225.6285 | 299977.7235 | 230752.095 | 69225.6285 | 299977.7235 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Condensate pipe | 0 | 0 |  |  |  |  | 4058656.35 | 2146658.409 | 6205314.759 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | uPVC-Ø27mm-PN12 | 46 | 50.4 | m | 8236.8 | 11743.2 | 19980 | 415134.72 | 591857.28 | 1006992 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | uPVC-Ø34mm-PN12 | 38 | 42 | m | 16286.4 | 12639.2 | 28925.6 | 684028.8 | 530846.4 | 1214875.2 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | uPVC-Ø42mm-PN12 | 15 | 16.8 | m | 21528 | 14560 | 36088 | 361670.4 | 244608 | 606278.4 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Fitting for UpVC | 1 | 1 | lot | 1953259.56 | 585977.868 | 2539237.428 | 1953259.56 | 585977.868 | 2539237.428 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 644562.87 | 193368.861 | 837931.731 | 644562.87 | 193368.861 | 837931.731 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Insulation condensate pipe | 0 | 0 |  |  |  |  | 1524621 | 1536840.732 | 3061461.732 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø27mm-10mmT | 46 | 50.4 | m | 11169.6 | 11743.2 | 22912.8 | 562947.84 | 591857.28 | 1154805.12 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø34mm-10mmT | 38 | 42 | m | 14520 | 15523.2 | 30043.2 | 609840 | 651974.4 | 1261814.4 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø42mm-10mmT | 15 | 16.8 | m | 17312.4 | 16352 | 33664.4 | 290848.32 | 274713.6 | 565561.92 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 60984.84 | 18295.452 | 79280.292 | 60984.84 | 18295.452 | 79280.292 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable power supply & conduit | 0 | 0 |  |  |  |  | 61922739.8428 | 28313959.9265 | 90236699.7693 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Double socket 1P-16A-250V | 3 | 3 | pcs | 150480 | 54500 | 204980 | 451440 | 163500 | 614940 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 4x1Cx4mm2+E4mm2 | 135 | 168 | m | 72299.4 | 17189.865 | 89489.265 | 12146299.2 | 2887897.32 | 15034196.52 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 3Cx-2.5mm2Cu/XLPE/PVC | 155 | 43.05 | m | 32518.74 | 7485.665 | 40004.405 | 1399931.757 | 322257.8783 | 1722189.6353 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 3Cx-1.5mm2Cu/XLPE/PVC | 219 | 260.4 | m | 22980.09 | 5743.9305 | 28724.0205 | 5984015.436 | 1495719.5022 | 7479734.9382 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 4Cx-1.5mm2 Cu/PVC/PVC | 75 | 70.35 | m | 25928.4 | 7485.665 | 33414.065 | 1824062.94 | 526616.5328 | 2350679.4728 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 2Cx-1.5mm2 Cu/PVC/PVC | 546 | 176.4 | m | 15443.88 | 5031.18 | 20475.06 | 2724300.432 | 887500.152 | 3611800.584 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 18 core AWG 1 pair | 253 | 396.9 | m | 21976.8 | 3920 | 25896.8 | 8722591.92 | 1555848 | 10278439.92 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 62 | 336 | m | 8773.9726 | 14594.0164 | 23367.989 | 2948054.7945 | 4903589.5144 | 7851644.3089 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D16 | 327 | 840 | m | 6646.8692 | 13183.4282 | 19830.2974 | 5583370.1096 | 11074079.6682 | 16657449.7778 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D16 | 1023 | 0 | m | 6646.8692 | 13183.4282 | 19830.2974 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 86 | 0 | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D25 | 99 | 160 | m | 12762.0356 | 15805 | 28567.0356 | 2041925.6986 | 2528800 | 4570725.6986 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC flexible conduit D20 | 21 | 31.5 | m | 3554.7229 | 5289.7059 | 8844.4288 | 111973.772 | 166625.7353 | 278599.5073 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC flexible conduit D20 | 11 | 11 | m | 3554.7229 | 5289.7059 | 8844.4288 | 39101.9521 | 58186.7647 | 97288.7168 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable tray 200x100x2.0mm | 19 | 20 | m | 776880 | 51045.8655 | 827925.8655 | 15537600 | 1020917.3094 | 16558517.3094 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 2408071.831 | 722421.5493 | 3130493.3802 | 2408071.831 | 722421.5493 | 3130493.3802 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
4. |  | Machine hook-up (Hall 3) | [8 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
5. |  | Scooter Garage | [8 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
6. |  | Canteen | [6 empty] | 21057187.7199 | 2439460.942 | 23496648.6619 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 3. 50. |  | Air Conditioning | 1 | 1 | PSCH |  |  |  | 21057187.7199 | 2439460.942 | 23496648.6619 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Split Air conditioner, indoor unit wall type, cooling capacity 2.5kW | 1 | 1 | pcs | 15455330 | 621600 | 16076930 | 15455330 | 621600 | 16076930 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Remote wirring for AC | 1 | 1 | pcs | 1614800 | 50400 | 1665200 | 1614800 | 50400 | 1665200 |  |  | #REF! |  | 45% | 45% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 775915 | 232774.5 | 1008689.5 | 775915 | 232774.5 | 1008689.5 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Copper pipe | 0 | 0 |  |  |  |  | 1022500 | 471470 | 1493970 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø6.4mm-0.81mmT | 10 | 10 | m | 38160 | 22400 | 60560 | 381600 | 224000 | 605600 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø9.5mm-0.81mmT | 10 | 10 | m | 60000 | 23520 | 83520 | 600000 | 235200 | 835200 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 40900 | 12270 | 53170 | 40900 | 12270 | 53170 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Insulation copper pipe | 0 | 0 |  |  |  |  | 334512.5 | 116462.15 | 450974.65 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø6.4mm-15mmT | 10 | 10 | m | 15358.8 | 5600 | 20958.8 | 153588 | 56000 | 209588 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø9.5mm-15mmT | 10 | 10 | m | 16754.4 | 5644.8 | 22399.2 | 167544 | 56448 | 223992 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 13380.5 | 4014.15 | 17394.65 | 13380.5 | 4014.15 | 17394.65 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Condensate pipe | 0 | 0 |  |  |  |  | 107712 | 125035.2 | 232747.2 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | uPVC-Ø27mm-PN12 | 10 | 10 | m | 8236.8 | 11743.2 | 19980 | 82368 | 117432 | 199800 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Fitting for UpVC | 1 | 1 | lot | 19008 | 5702.4 | 24710.4 | 19008 | 5702.4 | 24710.4 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 6336 | 1900.8 | 8236.8 | 6336 | 1900.8 | 8236.8 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Insulation condensate pipe | 0 | 0 |  |  |  |  | 116350 | 118828.2 | 235178.2 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Ø27mm-10mmT | 10 | 10 | m | 11169.6 | 11743.2 | 22912.8 | 111696 | 117432 | 229128 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 4654 | 1396.2 | 6050.2 | 4654 | 1396.2 | 6050.2 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable power supply & conduit | 0 | 0 |  |  |  |  | 1630068.2199 | 702890.892 | 2332959.1119 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 3Cx-2.5mm2Cu/XLPE/PVC | 15 | 15 | m | 32518.74 | 7485.665 | 40004.405 | 487781.1 | 112284.975 | 600066.075 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 3Cx-1.5mm2Cu/XLPE/PVC | 15 | 15 | m | 22980.09 | 5743.9305 | 28724.0205 | 344701.35 | 86158.9575 | 430860.3075 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 4Cx-1.5mm2 Cu/PVC/PVC | 10 | 10 | m | 25928.4 | 7485.665 | 33414.065 | 259284 | 74856.65 | 334140.65 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 18 core AWG 1 pair | 10 | 10 | m | 26400 | 3360 | 29760 | 264000 | 33600 | 297600 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 15 | 15 | m | 8773.9726 | 14594.0164 | 23367.989 | 131609.589 | 218910.2462 | 350519.8352 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D16 | 12 | 12 | m | 6646.8692 | 13183.4282 | 19830.2974 | 79762.4301 | 158201.1381 | 237963.5683 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 62929.7507 | 18878.9252 | 81808.6759 | 62929.7507 | 18878.9252 | 81808.6759 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | VI. PLUMBING | [8 empty] | 2878365804.8714 |  |  | #REF! |  |  | 0% |  |  | 0%
3. |  | Office, Social and Technical Areas (Hall 3) | [6 empty] | 2135112119.4552 | 210437879.8945 | 2345549999.3497 |  |  | #REF! |  |  | 0 |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 3. |  | Mechanical Engineering | [6 empty] | 2135112119.4552 | 210437879.8945 | 2345549999.3497 |  |  | #REF! |  |  | 0% |  |  | 0%
3. 3. 10. |  | Waste Water System | 1 | 1 | PSCH |  |  |  | 195924697.8575 | 71484007.4162 | 267408705.2737 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | West side | 0 | 0 | m | 0 | 0 | 0 | 79936135.2 | 44199519.52 | 124135654.72 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | uPVC pipe D200 - PN6 | 35 | 40 | m | 356616 | 71941.408 | 428557.408 | 14264640 | 2877656.32 | 17142296.32 |  |  | #REF! |  | 15% | 15%
|  | uPVC pipe D168 - PN6 | 40 | 65 | m | 179337.6 | 57600.928 | 236938.528 | 11656944 | 3744060.32 | 15401004.32 |  |  | #REF! | 30% | 15% | 45%
|  | uPVC pipe D114 - PN6 | 115 | 156 | m | 93225.6 | 42504 | 135729.6 | 14543193.6 | 6630624 | 21173817.6 |  |  | #REF! | 30% | 15% | 45%
|  | uPVC pipe D90 - PN6 | 185 | 209 | m | 65145.6 | 36064 | 101209.6 | 13615430.4 | 7537376 | 21152806.4 |  |  | #REF! | 30% | 15% | 45%
|  | uPVC pipe D60 - PN6 | 153 | 187 | m | 29858.4 | 24884.16 | 54742.56 | 5583520.8 | 4653337.92 | 10236858.72 |  |  | #REF! | 30% | 15% | 45%
|  | uPVC pipe D42 - PN6 | 65 | 68 | m | 21528 | 17851.68 | 39379.68 | 1463904 | 1213914.24 | 2677818.24 |  |  | #REF! | 30% | 15% | 45%
|  | uPVC Fitting | 1 | 1 | lot | 14106376.8 | 4231913.04 | 18338289.84 | 14106376.8 | 4231913.04 | 18338289.84 |  |  | #REF! | 30% | 15% | 45%
|  | Excavation & backfill | 37 | 37 | m3 | 0 | 200000 | 200000 | 0 | 7400000 | 7400000 |  |  | #REF! | 70% | 10% | 80%
|  | Connect to existing manhole | 1 | 1 | lot | 0 | 3000000 | 3000000 | 0 | 3000000 | 3000000 |  |  | #REF! |  | 10% | 10%
|  | Connect to existing pipe | 1 | 1 | lot | 0 | 1500000 | 1500000 | 0 | 1500000 | 1500000 |  |  | #REF! |  | 10% | 10%
|  | Accessories | 1 | 1 | lot | 4702125.6 | 1410637.68 | 6112763.28 | 4702125.6 | 1410637.68 | 6112763.28 |  |  | #REF! |  | 10% | 10%
|  | East side | 0 |  | m |  |  |  | 115988562.6575 | 27284487.8962 | 143273050.5537 |  |  | #REF! |  |  | 0%
|  | Submersible Pump Q=5M3/H, H=8MH20 | 2 | 2 | pcs | 19613000 | 616000 | 20229000 | 39226000 | 1232000 | 40458000 |  |  | #REF! |  |  | 0%
|  | Auto coupling Rp2' | 2 | 2 | pcs | 4488000 | 0 | 4488000 | 8976000 | 0 | 8976000 |  |  | #REF! |  |  | 0%
|  | Slider + chain | 2 | 2 | pcs | 3850000 | 0 | 3850000 | 7700000 | 0 | 7700000 |  |  | #REF! |  |  | 0%
|  | Float for submersible pump | 2 | 2 | pcs | 3850000 | 168000 | 4018000 | 7700000 | 336000 | 8036000 |  |  | #REF! |  |  | 0%
|  | Electrical control panel for submeriable pump | 1 | 1 | pcs | 13420000 | 840000 | 14260000 | 13420000 | 840000 | 14260000 |  |  | #REF! |  |  | 0%
|  | Check valve DN50 | 1 | 1 | pcs | 174200 | 61600 | 235800 | 174200 | 61600 | 235800 |  |  | #REF! |  |  | 0%
|  | Gate valve DN50 | 1 | 1 | pcs | 128700 | 61600 | 190300 | 128700 | 61600 | 190300 |  |  | #REF! |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 30 | 30 | m | 40467 | 9350 | 49817 | 1214010 | 280500 | 1494510 |  |  | #REF! |  |  | 0%
|  | PVC conduit D20 | 30 | 30 | m | 8773.9726 | 14594.0164 | 23367.989 | 263219.1781 | 437820.4924 | 701039.6704 |  |  | #REF! |  |  | 0%
|  | uPVC pipe D168 - PN6 | 29 | 35 | m | 179337.6 | 57600.928 | 236938.528 | 6276816 | 2016032.48 | 8292848.48 |  |  | #REF! | 30% | 15% | 45%
|  | uPVC pipe D114 - PN6 | 39 | 45 | m | 93225.6 | 42504 | 135729.6 | 4195152 | 1912680 | 6107832 |  |  | #REF! | 30% | 15% | 45%
|  | uPVC pipe D90 - PN6 | 149 | 167 | m | 65145.6 | 36064 | 101209.6 | 10879315.2 | 6022688 | 16902003.2 |  |  | #REF! | 30% | 15% | 45%
|  | uPVC pipe D60 - PN6 | 101 | 124 | m | 29858.4 | 24884.16 | 54742.56 | 3702441.6 | 3085635.84 | 6788077.44 |  |  | #REF! | 30% | 15% | 45%
|  | uPVC pipe D42 - PN6 | 18 | 23 | m | 21528 | 17851.68 | 39379.68 | 495144 | 410588.64 | 905732.64 |  |  | #REF! | 30% | 15% | 45%
|  | Pipe clean out D60 | 1 | 1 | pcs | 106423.2 | 28000 | 134423.2 | 106423.2 | 28000 | 134423.2 |  |  | #REF! | 30% | 10% | 40%
|  | uPVC Fitting | 1 | 1 | lot | 5976856.1096 | 1793056.8329 | 7769912.9425 | 5976856.1096 | 1793056.8329 | 7769912.9425 |  |  | #REF! | 30% | 15% | 45%
|  | Excavation & backfill | 21 | 28 | m3 | 0 | 200000 | 200000 | 0 | 5600000 | 5600000 |  |  | #REF! | 70% | 10% | 80%
|  | Connect to existing manhole | 1 | 1 | lot | 0 | 1500000 | 1500000 | 0 | 1500000 | 1500000 |  |  | #REF! |  |  | 0%
|  | Accessories | 1 | 1 | lot | 5554285.3699 | 1666285.611 | 7220570.9808 | 5554285.3699 | 1666285.611 | 7220570.9808 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 3. 20. |  | Service Water System | 1 | 1 | PSCH |  |  |  | 350026408.4568 | 59395813.3191 | 409422221.7759 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | West side | [6 empty] | 205749865.9577 | 34591531.4404 | 240341397.398 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Pump room | [6 empty] | 149717065.9577 | 8068928.1916 | 157785994.1492 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Booster pump Q=9.3 m3, H=30m | 2 | 2 | set | 30745000 | 728000 | 31473000 | 61490000 | 1456000 | 62946000 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | Electrical control panel for booster pump | 1 | 1 | set | 44440000 | 1400000 | 45840000 | 44440000 | 1400000 | 45840000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Pressure tank 100l | 1 | 1 | pcs | 7915200 | 168000 | 8083200 | 7915200 | 168000 | 8083200 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Storage tank 3m3 | 1 | 1 | pcs | 9970909.0909 | 322000 | 10292909.0909 | 9970909.0909 | 322000 | 10292909.0909 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Filter | 1 | 1 | set | 10800000 | 225400 | 11025400 | 10800000 | 225400 | 11025400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Water metter DN40 | 1 | 1 | pcs | 2154000 | 75152 | 2229152 | 2154000 | 75152 | 2229152 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/PVC/PVC 2Cx1.5mm2 | 20 | 25 | m | 15443.88 | 5031.18 | 20475.06 | 386097 | 125779.5 | 511876.5 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 20 | 25 | m | 40467 | 9350 | 49817 | 1011675 | 233750 | 1245425 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 40 | 50 | m | 8773.9726 | 14594.0164 | 23367.989 | 438698.6301 | 729700.8206 | 1168399.4507 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger + Support | 1 | 1 | lot | 6172492.3537 | 1851747.7061 | 8024240.0598 | 6172492.3537 | 1851747.7061 | 8024240.0598 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 4937993.8829 | 1481398.1649 | 6419392.0478 | 4937993.8829 | 1481398.1649 | 6419392.0478 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Valve | [6 empty] | 31053568.8 | 3110074.6696 | 34163643.4696 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Pressure Gauges | 1 | 1 | pcs | 1008000 | 49588 | 1057588 | 1008000 | 49588 | 1057588 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Flexible DN40 | 4 | 4 | pcs | 825600 | 75152 | 900752 | 3302400 | 300608 | 3603008 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Float level indicator | 1 | 1 | pcs | 4200000 | 168000 | 4368000 | 4200000 | 168000 | 4368000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Float valve DN40 | 1 | 1 | pcs | 2809200 | 75152 | 2884352 | 2809200 | 75152 | 2884352 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Y-Strainer DN40 | 2 | 2 | pcs | 726000 | 75152 | 801152 | 1452000 | 150304 | 1602304 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Safety valve DN40 | 3 | 3 | pcs | 3133200 | 75152 | 3208352 | 9399600 | 225456 | 9625056 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Check valve DN40 | 3 | 3 | pcs | 867600 | 75152 | 942752 | 2602800 | 225456 | 2828256 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Gate valve DN40 | 4 | 4 | pcs | 726000 | 75152 | 801152 | 2904000 | 300608 | 3204608 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Gate valve DN25 | 1 | 1 | pcs | 322800 | 50880.368 | 373680.368 | 322800 | 50880.368 | 373680.368 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Gate valve DN32 PPR | 5 | 7 | pcs | 99122.4 | 58877.3007 | 157999.7007 | 693856.8 | 412141.105 | 1105997.905 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Gate valve DN25 PPR | 3 | 2 | pcs | 85924.8 | 49415.0989 | 135339.8989 | 171849.6 | 98830.1978 | 270679.7978 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Gate valve DN20 PPR | 10 | 15 | pcs | 63367.2 | 45472.3119 | 108839.5119 | 950508 | 682084.6788 | 1632592.6788 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 1236554.4 | 370966.32 | 1607520.72 | 1236554.4 | 370966.32 | 1607520.72 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0%
|  | Cold water pipe | [6 empty] | 21159921.6 | 22158696.668 | 43318618.268 |  |  | #REF! |  |  | 0%
|  | PPR pipe D75 - PN10 | 10 | 11 | m | 99964.8 | 39200 | 139164.8 | 1099612.8 | 431200 | 1530812.8 |  |  | #REF! |  |  | 0%
|  | PPR pipe D63 - PN10 | 23 | 25 | m | 71884.8 | 34720 | 106604.8 | 1797120 | 868000 | 2665120 |  |  | #REF! |  |  | 0%
|  | PPR pipe D50 - PN10 | 21 | 26 | m | 45208.8 | 28000 | 73208.8 | 1175428.8 | 728000 | 1903428.8 |  |  | #REF! |  |  | 0%
|  | PPR pipe D40 - PN10 | 29 | 31 | m | 30841.2 | 25388.1544 | 56229.3544 | 956077.2 | 787032.7864 | 1743109.9864 |  |  | #REF! |  |  | 0%
|  | PPR pipe D32 - PN10 | 47 | 72 | m | 22978.8 | 22306.7432 | 45285.5432 | 1654473.6 | 1606085.5104 | 3260559.1104 |  |  | #REF! |  |  | 0%
|  | PPR pipe D25 - PN10 | 68 | 87 | m | 17737.2 | 18258.8168 | 35996.0168 | 1543136.4 | 1588517.0616 | 3131653.4616 |  |  | #REF! |  |  | 0%
|  | PPR pipe D20 - PN10 | 272 | 297 | m | 9921.6 | 15682.8168 | 25604.4168 | 2946715.2 | 4657796.5896 | 7604511.7896 |  |  | #REF! |  |  | 0%
|  | PPR Fitting | 1 | 1 | lot | 2578284 | 773485.2 | 3351769.2 | 2578284 | 773485.2 | 3351769.2 |  |  | #REF! |  |  | 0%
|  | uPVC pipe D60 - PN10 | 54 | 62 | m | 35287.2 | 24884.16 | 60171.36 | 2187806.4 | 1542817.92 | 3730624.32 |  |  | #REF! |  | 40% | 40%
|  | uPVC pipe D34 - PN10 | 104 | 118 | m | 16286.4 | 13440 | 29726.4 | 1921795.2 | 1585920 | 3507715.2 |  |  | #REF! |  | 40% | 40%
|  | uPVC Fitting | 1 | 1 | lot | 948369.6 | 284510.88 | 1232880.48 | 948369.6 | 284510.88 | 1232880.48 |  |  | #REF! |  | 40% | 40%
|  | Connect to existing pipe | 1 | 1 | lot | 0 | 1000000 | 1000000 | 0 | 1000000 | 1000000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Excavation & backfill | 14 | 28 | m3 | 0 | 200000 | 200000 | 0 | 5600000 | 5600000 |  |  | #REF! |  |  | 0%
[14 empty] | #REF! |  |  | 0%
|  | Accessories + Support | 1 | 1 | lot | 2351102.4 | 705330.72 | 3056433.12 | 2351102.4 | 705330.72 | 3056433.12 |  |  | #REF! |  |  | 0%
|  | Hot water pipe | [6 empty] | 3819309.6 | 1253831.9112 | 5073141.5112 |  |  | #REF! |  |  | 0%
|  | PPR pipe D20 - PN20 | 7 | 9 | m | 12261.6 | 15682.8168 | 27944.4168 | 110354.4 | 141145.3512 | 251499.7512 |  |  | #REF! |  |  | 0%
|  | PPR Fitting | 1 | 1 | lot | 25466.4 | 7639.92 | 33106.32 | 25466.4 | 7639.92 | 33106.32 |  |  | #REF! |  |  | 0%
|  | Fire stop | 1 | 1 | lot | 3500000 | 1050000 | 4550000 | 3500000 | 1050000 | 4550000 |  |  | #REF! |  |  | 0%
[14 empty] | #REF! |  |  | 0%
|  | Accessories + Support | 1 | 1 | lot | 183488.8 | 55046.64 | 238535.44 | 183488.8 | 55046.64 | 238535.44 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | East side | [6 empty] | 144276542.4991 | 24804281.8787 | 169080824.3779 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Pump room | [6 empty] | 121538562.8991 | 7728105.642 | 129266668.5411 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Booster pump Q=9.3 m3, H=30m | 2 | 2 | set | 17380000 | 616000 | 17996000 | 34760000 | 1232000 | 35992000 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | Electrical control panel for booster pump | 1 | 1 | set | 44440000 | 1400000 | 45840000 | 44440000 | 1400000 | 45840000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Pressure tank 100l | 1 | 1 | pcs | 7915200 | 168000 | 8083200 | 7915200 | 168000 | 8083200 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Storage tank 3m3 | 1 | 1 | pcs | 9970909.0909 | 322000 | 10292909.0909 | 9970909.0909 | 322000 | 10292909.0909 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Filter | 1 | 1 | set | 10800000 | 225400 | 11025400 | 10800000 | 225400 | 11025400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Water metter DN25 | 1 | 1 | pcs | 1014000 | 50880.368 | 1064880.368 | 1014000 | 50880.368 | 1064880.368 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/PVC/PVC 2Cx1.5mm2 | 20 | 25 | m | 15443.88 | 5031.18 | 20475.06 | 386097 | 125779.5 | 511876.5 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 20 | 25 | m | 40467 | 9350 | 49817 | 1011675 | 233750 | 1245425 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 40 | 50 | m | 8773.9726 | 14594.0164 | 23367.989 | 438698.6301 | 729700.8206 | 1168399.4507 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger + Support | 1 | 1 | lot | 4909992.3537 | 1472997.7061 | 6382990.0598 | 4909992.3537 | 1472997.7061 | 6382990.0598 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 5891990.8244 | 1767597.2473 | 7659588.0717 | 5891990.8244 | 1767597.2473 | 7659588.0717 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Valve | [6 empty] | 15191076.4 | 2017377.4463 | 17208453.8463 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Pressure Gauges | 1 | 1 | pcs | 1008000 | 49588 | 1057588 | 1008000 | 49588 | 1057588 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Flexible DN25 | 4 | 4 | pcs | 568800 | 50880.368 | 619680.368 | 2275200 | 203521.472 | 2478721.472 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Float level indicator | 1 | 1 | pcs | 4200000 | 168000 | 4368000 | 4200000 | 168000 | 4368000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Float valve DN25 | 1 | 1 | pcs | 770400 | 50880.368 | 821280.368 | 770400 | 50880.368 | 821280.368 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Y-Strainer DN25 | 2 | 2 | pcs | 322800 | 50880.368 | 373680.368 | 645600 | 101760.736 | 747360.736 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Safety valve DN25 | 1 | 1 | pcs | 1376400 | 50880.368 | 1427280.368 | 1376400 | 50880.368 | 1427280.368 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Check valve DN25 | 3 | 3 | pcs | 480000 | 50880.368 | 530880.368 | 1440000 | 152641.104 | 1592641.104 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Gate valve DN25 | 5 | 5 | pcs | 322800 | 50880.368 | 373680.368 | 1614000 | 254401.84 | 1868401.84 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Gate valve DN25 PPR | 8 | 8 | pcs | 85924.8 | 49415.0989 | 135339.8989 | 687398.4 | 395320.791 | 1082719.191 |  |  | #REF! |  |  | 0%
|  | Gate valve DN20 PPR | 9 | 9 | pcs | 63367.2 | 45472.3119 | 108839.5119 | 570304.8 | 409250.8073 | 979555.6073 |  |  | #REF! |  |  | 0%
|  | Accessories | 1 | 1 | lot | 603773.2 | 181131.96 | 784905.16 | 603773.2 | 181131.96 | 784905.16 |  |  | #REF! |  |  | 0%
|  | Cold water pipe | [6 empty] | 7418628 | 14924281.536 | 22342909.536 |  |  | #REF! |  |  | 0%
|  | PPR pipe D63 - PN10 | 10 | 12 | m | 71884.8 | 34720 | 106604.8 | 862617.6 | 416640 | 1279257.6 |  |  | #REF! |  |  | 0%
|  | PPR pipe D40 - PN10 | 5 | 7 | m | 30841.2 | 25388.1544 | 56229.3544 | 215888.4 | 177717.0808 | 393605.4808 |  |  | #REF! |  |  | 0%
|  | PPR pipe D32 - PN10 | 29 | 32 | m | 22978.8 | 22306.7432 | 45285.5432 | 735321.6 | 713815.7824 | 1449137.3824 |  |  | #REF! |  |  | 0%
|  | PPR pipe D25 - PN10 | 21 | 28 | m | 17737.2 | 18258.8168 | 35996.0168 | 496641.6 | 511246.8704 | 1007888.4704 |  |  | #REF! |  |  | 0%
|  | PPR pipe D20 - PN10 | 130 | 143 | m | 9921.6 | 15682.8168 | 25604.4168 | 1418788.8 | 2242642.8024 | 3661431.6024 |  |  | #REF! |  |  | 0%
|  | PPR Fitting | 1 | 1 | lot | 860598 | 258179.4 | 1118777.4 | 860598 | 258179.4 | 1118777.4 |  |  | #REF! |  |  | 0%
|  | uPVC pipe D34 - PN10 | 104 | 100 | m | 16286.4 | 13440 | 29726.4 | 1628640 | 1344000 | 2972640 |  |  | #REF! |  | 40% | 40%
|  | uPVC Fitting | 1 | 1 | lot | 375840 | 112752 | 488592 | 375840 | 112752 | 488592 |  |  | #REF! |  | 40% | 40%
|  | Connect to existing pipe | 1 | 1 | lot | 0 | 1000000 | 1000000 | 0 | 1000000 | 1000000 |  |  | #REF! |  |  | 0%
|  | Excavation & backfill | 10 | 20 | m3 | 0 | 200000 | 200000 | 0 | 4000000 | 4000000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cut wall and backfill | 91 | 130 | m | 0 | 30000 | 30000 | 0 | 3900000 | 3900000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories + Support | 1 | 1 | lot | 824292 | 247287.6 | 1071579.6 | 824292 | 247287.6 | 1071579.6 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hot water pipe | [6 empty] | 128275.2 | 134517.2544 | 262792.4544 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PPR pipe D20 - PN20 | 7 | 8 | m | 12261.6 | 15682.8168 | 27944.4168 | 98092.8 | 125462.5344 | 223555.3344 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PPR Fitting | 1 | 1 | lot | 22636.8 | 6791.04 | 29427.84 | 22636.8 | 6791.04 | 29427.84 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Accessories + Support | 1 | 1 | lot | 7545.6 | 2263.68 | 9809.28 | 7545.6 | 2263.68 | 9809.28 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
3. 3. 30. |  | Sanitary Furnishings | 1 | 1 | PSCH |  |  |  | 1589161013.1409 | 79558059.1592 | 1668719072.3001 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | West side | 0 |  | m |  |  |  |  | 50588775.2524 | 1032592350.3478 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Santinary | [6 empty] | 982003575.0955 | 50588775.2524 | 1032592350.3478 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Water closet one block, included stop valve | 37 | 37 | pcs | 14750000 | 413200.4464 | 15163200.4464 | 545750000 | 15288416.5168 | 561038416.5168 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Water closet spray | 37 | 37 | pcs | 638000 | 50232 | 688232 | 23606000 | 1858584 | 25464584 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Paper holder | 37 | 37 | pcs | 653000 | 50232 | 703232 | 24161000 | 1858584 | 26019584 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Lavatory under-mounted type | 43 | 43 | pcs | 1443000 | 300710.7768 | 1743710.7768 | 62049000 | 12930563.4024 | 74979563.4024 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Water tap for lavatory (cold) | 43 | 43 | pcs | 953000 | 50232 | 1003232 | 40979000 | 2159976 | 43138976 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Mirror (H=1m, L according to the lavabo table) | 33 | 33 | m2 | 768883.5 | 123200 | 892083.5 | 25373155.5 | 4065600 | 29438755.5 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hand Dryer | 8 | 8 | pcs | 5018000 | 61600 | 5079600 | 40144000 | 492800 | 40636800 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Uniral included flush valve | 15 | 15 | pcs | 11003000 | 280000 | 11283000 | 165045000 | 4200000 | 169245000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Floor drain DN80 | 16 | 16 | pcs | 855000 | 88480 | 943480 | 13680000 | 1415680 | 15095680 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Floor drain W100xL5100 | 1 | 1 | pcs | 5417500 | 476000 | 5893500 | 5417500 | 476000 | 5893500 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Floor drain W100xL3800 | 1 | 1 | pcs | 4334000 | 380800 | 4714800 | 4334000 | 380800 | 4714800 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Floor drain W100xL3000 | 1 | 1 | pcs | 3250500 | 285600 | 3536100 | 3250500 | 285600 | 3536100 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Shower | 1 | 1 | pcs | 7305000 | 196000 | 7501000 | 7305000 | 196000 | 7501000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Heat Water 5L for kitchen | 2 | 2 | pcs | 1628727.2727 | 168000 | 1796727.2727 | 3257454.5455 | 336000 | 3593454.5455 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Heat Water 50L for shower | 1 | 1 | pcs | 3104727.2727 | 280000 | 3384727.2727 | 3104727.2727 | 280000 | 3384727.2727 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Waterproof for neck pipe | 114 | 114 | nos | 50000 | 15000 | 65000 | 5700000 | 1710000 | 7410000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 8847237.7773 | 2654171.3332 | 11501409.1105 | 8847237.7773 | 2654171.3332 | 11501409.1105 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | East side | [6 empty] | 607157438.0455 | 28969283.9068 | 636126721.9523 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Santinary | [6 empty] | 607157438.0455 | 28969283.9068 | 636126721.9523 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Water closet one block, included stop valve | 24 | 24 | pcs | 14750000 | 413200.4464 | 15163200.4464 | 354000000 | 9916810.7136 | 363916810.7136 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Water closet spray | 24 | 24 | pcs | 638000 | 50232 | 688232 | 15312000 | 1205568 | 16517568 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Paper holder | 24 | 24 | pcs | 653000 | 50232 | 703232 | 15672000 | 1205568 | 16877568 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Lavatory under-mounted type | 12 | 24 | pcs | 1443000 | 300710.7768 | 1743710.7768 | 34632000 | 7217058.6432 | 41849058.6432 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Water tap for lavatory (cold) | 12 | 12 | pcs | 953000 | 50232 | 1003232 | 11436000 | 602784 | 12038784 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Mirror (H=1m, L according to the lavabo table) | 10 | 10 | m2 | 768883.5 | 123200 | 892083.5 | 7688835 | 1232000 | 8920835 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hand Dryer | 4 | 4 | pcs | 5018000 | 61600 | 5079600 | 20072000 | 246400 | 20318400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Uniral included flush valve | 11 | 11 | pcs | 11003000 | 280000 | 11283000 | 121033000 | 3080000 | 124113000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Floor drain DN80 | 10 | 10 | pcs | 855000 | 88480 | 943480 | 8550000 | 884800 | 9434800 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Floor drain W100xL4400 | 1 | 1 | pcs | 4334000 | 380800 | 4714800 | 4334000 | 380800 | 4714800 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Floor drain W100xL3200 | 1 | 1 | pcs | 3250500 | 285600 | 3536100 | 3250500 | 285600 | 3536100 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Heat Water 5L for kitchen | 2 | 2 | pcs | 1628727.2727 | 168000 | 1796727.2727 | 3257454.5455 | 336000 | 3593454.5455 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Waterproof for neck pipe | 49 | 49 | nos | 50000 | 15000 | 65000 | 2450000 | 735000 | 3185000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 5469648.5 | 1640894.55 | 7110543.05 | 5469648.5 | 1640894.55 | 7110543.05 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
4. |  | Machine hook-up (Hall 3) | [8 empty] | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
5. |  | Scooter Garage | [6 empty] | 36457255.9273 | 16528783.2582 | 52986039.1855 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
5. 3. |  | Mechancial Engineering | [6 empty] | 36457255.9273 | 16528783.2582 | 52986039.1855 |  |  | #REF! |  |  | 0% |  |  | 0%
5. 3. 10. |  | Rainwater System | 1 | 1 | PSCH |  |  |  | 36457255.9273 | 16528783.2582 | 52986039.1855 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | uPVC pipe D220-PN6 | 12 | 15 | m | 356616 | 71941.408 | 428557.408 | 5349240 | 1079121.12 | 6428361.12 |  |  | #REF! |  | 50% | 50%
|  | uPVC pipe D110-PN6 | 92 | 112 | m | 93225.6 | 42504 | 135729.6 | 10441267.2 | 4760448 | 15201715.2 |  |  | #REF! |  | 15% | 15%
|  | uPVC pipe D60-PN6 | 59 | 55 | m | 29858.4 | 24884.16 | 54742.56 | 1642212 | 1368628.8 | 3010840.8 |  |  | #REF! |  | 15% | 15%
|  | uPVC Cleanout DN100 | 8 | 8 | pcs | 106423.2 | 28000 | 134423.2 | 851385.6 | 224000 | 1075385.6 |  |  | #REF! |  | 15% | 15%
|  | Leaf gaurd DN100 | 8 | 8 | pcs | 231000 | 50400 | 281400 | 1848000 | 403200 | 2251200 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Floor Drain DN50 | 8 | 8 | pcs | 855000 | 88480 | 943480 | 6840000 | 707840 | 7547840 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Fitting for uPVC piping | 8 | 1 | lot | 6588863.3455 | 1976659.0036 | 8565522.3491 | 6588863.3455 | 1976659.0036 | 8565522.3491 |  |  | #REF! |  | 15% | 15% |  |  | 0%
|  | Excavation and backfill | 15 | 18 | m3 | 0 | 200000 | 200000 | 0 | 3600000 | 3600000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger/ support and Accessories | 1 | 1 | lot | 2196287.7818 | 658886.3345 | 2855174.1164 | 2196287.7818 | 658886.3345 | 2855174.1164 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Conection existing drain stormwater | 1 | 1 | lot | 700000 | 1750000 | 2450000 | 700000 | 1750000 | 2450000 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
6. |  | Canteen | [6 empty] | 420920023.6422 | 58959472.3741 | 479879496.0162 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
6. 3. |  | Mechancial Engineering | [6 empty] | 420920023.6422 | 58959472.3741 | 479879496.0162 |  |  | #REF! |  |  | 0% |  |  | 0%
6. 3. 10. |  | Rainwater System | 1 | 1 | PSCH |  |  |  | 16378977.6 | 11954799.36 | 28333776.96 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | uPVC pipe D110-PN6 | 93 | 112 | m | 93225.6 | 42504 | 135729.6 | 10441267.2 | 4760448 | 15201715.2 |  |  | #REF! |  | 15% | 15% |  |  | 0%
|  | Leaf gaurd DN100 | 6 | 6 | pcs | 231000 | 50400 | 281400 | 1386000 | 302400 | 1688400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | uPVC Cleanout DN100 | 6 | 6 | pcs | 106423.2 | 28000 | 134423.2 | 638539.2 | 168000 | 806539.2 |  |  | #REF! |  | 15% | 15% |  |  | 0%
|  | Fitting for uPVC piping | 1 | 1 | lot | 2934878.4 | 880463.52 | 3815341.92 | 2934878.4 | 880463.52 | 3815341.92 |  |  | #REF! |  | 15% | 15% |  |  | 0%
|  | Excavation and backfill | 13 | 19 | m3 | 0 | 200000 | 200000 | 0 | 3800000 | 3800000 |  |  | #REF! |  | 15% | 15% |  |  | 0%
|  | Hanger/ support and Accessories | 1 | 1 | lot | 978292.8 | 293487.84 | 1271780.64 | 978292.8 | 293487.84 | 1271780.64 |  |  | #REF! |  | 15% | 15% |  |  | 0%
|  | Conection existing drain stormwater | 1 | 1 | lot | 0 | 1750000 | 1750000 | 0 | 1750000 | 1750000 |  |  | #REF! |  | 15% | 15% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
6. 3. 20. |  | Waste Water System | 1 | 1 | PSCH |  |  |  | 20651731.2 | 14688997.44 | 35340728.64 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Piping for Bain maries | [11 empty] | #REF! |  |  | 0% |  |  | 0%
|  | uPVC pipe DN80 | 43 | 50 | m | 65145.6 | 36064 | 101209.6 | 3257280 | 1803200 | 5060480 |  |  | #REF! |  | 15% | 15% |  |  | 0%
|  | Water pipe heating system | 1 | 1 | lot |  |  |  |  | 0 | 0 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Fitting for uPVC piping | 1 | 1 | lot | 751680 | 225504 | 977184 | 751680 | 225504 | 977184 |  |  | #REF! |  | 15% | 15% |  |  | 0%
|  | Hanger/ support and Accessories | 1 | 1 | lot | 250560 | 75168 | 325728 | 250560 | 75168 | 325728 |  |  | #REF! |  |  | 0%
|  | Piping | [6 empty] | 16392211.2 | 12585125.44 | 28977336.64 |  |  | #REF! |  |  | 0%
|  | uPVC pipe DN100 - PN6 | 7 | 9 | m | 93225.6 | 42504 | 135729.6 | 839030.4 | 382536 | 1221566.4 |  |  | #REF! |  | 15% | 15%
|  | uPVC pipe DN80 - PN6 | 89 | 96 | m | 65145.6 | 36064 | 101209.6 | 6253977.6 | 3462144 | 9716121.6 |  |  | #REF! |  | 15% | 15%
|  | uPVC pipe DN50 - PN6 | 75 | 82 | m | 29858.4 | 24884.16 | 54742.56 | 2448388.8 | 2040501.12 | 4488889.92 |  |  | #REF! |  | 15% | 15%
|  | Clean Out DN50 | 1 | 1 | m | 297000 | 84000 | 381000 | 297000 | 84000 | 381000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Clean Out DN80 | 7 | 7 | m | 319000 | 84000 | 403000 | 2233000 | 588000 | 2821000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Clean Out DN100 | 1 | 1 | m | 341000 | 84000 | 425000 | 341000 | 84000 | 425000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Fitting for uPVC piping | 1 | 1 | lot | 2984860.8 | 895458.24 | 3880319.04 | 2984860.8 | 895458.24 | 3880319.04 |  |  | #REF! |  | 15% | 15% |  |  | 0%
|  | Connect pipes to existing manhole | 1 | 1 | lot | 0 | 1750000 | 1750000 | 0 | 1750000 | 1750000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Excavation and backfill | 8 | 15 | m3 | 0 | 200000 | 200000 | 0 | 3000000 | 3000000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger/ support and Accessories | 1 | 1 | lot | 994953.6 | 298486.08 | 1293439.68 | 994953.6 | 298486.08 | 1293439.68 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
6. 3. 30. |  | Service Water System | 1 | 1 | PSCH |  |  |  | 10371428 | 9116560.5373 | 19487988.5373 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Valve | [6 empty] | 2328612.8 | 1693755.9317 | 4022368.7317 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Gate valve DN25 | 1 | 1 | pcs | 322800 | 50880.368 | 373680.368 | 322800 | 50880.368 | 373680.368 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Gate valve DN25 PPR | 7 | 7 | pcs | 85924.8 | 49415.0989 | 135339.8989 | 601473.6 | 345905.6922 | 947379.2922 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Gate valve DN20 PPR | 6 | 6 | pcs | 63367.2 | 45472.3119 | 108839.5119 | 380203.2 | 272833.8715 | 653037.0715 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 1024136 | 1024136 | 2048272 | 1024136 | 1024136 | 2048272 |  |  | #REF! |  |  | 0%
|  | Cold water pipe | [6 empty] | 4239540 | 3735787.3512 | 7975327.3512 |  |  | #REF! |  |  | 0%
|  | PPR pipe DN40 - PN10 | 12 | 8 | m | 45208.8 | 28000 | 73208.8 | 361670.4 | 224000 | 585670.4 |  |  | #REF! |  |  | 0%
|  | PPR pipe DN32 - PN10 | 5 | 6 | m | 30841.2 | 25388.1544 | 56229.3544 | 185047.2 | 152328.9264 | 337376.1264 |  |  | #REF! |  |  | 0%
|  | PPR pipe DN25 - PN10 | 7 | 10 | m | 22978.8 | 22306.7432 | 45285.5432 | 229788 | 223067.432 | 452855.432 |  |  | #REF! |  |  | 0%
|  | PPR pipe DN20 - PN10 | 61 | 71 | m | 17737.2 | 18258.8168 | 35996.0168 | 1259341.2 | 1296375.9928 | 2555717.1928 |  |  | #REF! |  |  | 0%
|  | PPR Fitting | 1 | 1 | lot | 469810.8 | 140943.24 | 610754.04 | 469810.8 | 140943.24 | 610754.04 |  |  | #REF! |  |  | 0%
|  | uPVC pipe D34 - PN10 | 60 | 63 | m | 16286.4 | 13440 | 29726.4 | 1026043.2 | 846720 | 1872763.2 |  |  | #REF! |  | 15% | 15%
|  | Fitting for uPVC piping | 1 | 1 | lot | 236779.2 | 71033.76 | 307812.96 | 236779.2 | 71033.76 | 307812.96 |  |  | #REF! |  | 15% | 15% |  |  | 0%
|  | Excavation and backfill | 2 | 3.2 | m3 | 0 | 200000 | 200000 | 0 | 640000 | 640000 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Accessories + Support | 1 | 1 | lot | 471060 | 141318 | 612378 | 471060 | 141318 | 612378 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | hot water pipe | [6 empty] | 3803275.2 | 3687017.2544 | 7490292.4544 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PPR pipe DN15 - PN20 | 10 | 8 | m | 12261.6 | 15682.8168 | 27944.4168 | 98092.8 | 125462.5344 | 223555.3344 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PPR Fitting | 1 | 1 | lot | 22636.8 | 6791.04 | 29427.84 | 22636.8 | 6791.04 | 29427.84 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Fire stop | 1 | 1 | lot | 3500000 | 3500000 | 7000000 | 3500000 | 3500000 | 7000000 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | Accessories + Support | 1 | 1 | lot | 182545.6 | 54763.68 | 237309.28 | 182545.6 | 54763.68 | 237309.28 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
6. 3. 40. |  | Sanitary Furnishings | 1 | 1 | PSCH |  |  |  | 240793394.3675 | 15204292.8421 | 255997687.2095 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Lavatory under-mounted type | 2 | 2 | pcs | 1443000 | 300710.7768 | 1743710.7768 | 2886000 | 601421.5536 | 3487421.5536 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Lavatory wall mounted type | 1 | 1 | pcs | 1253000 | 300710.7768 | 1553710.7768 | 1253000 | 300710.7768 | 1553710.7768 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Water tap for lavatory (hot and cold) | 2 | 2 | pcs | 1320000 | 50232 | 1370232 | 2640000 | 100464 | 2740464 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Water tap for lavatory (cold) | 1 | 1 | pcs | 953000 | 50232 | 1003232 | 953000 | 50232 | 1003232 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Mirror 700x500x6mm | 3 | 3 | pcs | 2896300 | 61600 | 2957900 | 8688900 | 184800 | 8873700 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Water closet one block, included stop valve | 2 | 2 | set | 14750000 | 413200.4464 | 15163200.4464 | 29500000 | 826400.8928 | 30326400.8928 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Water closet spray | 2 | 2 | pcs | 638000 | 50232 | 688232 | 1276000 | 100464 | 1376464 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Paper holder | 2 | 2 | pcs | 653000 | 50232 | 703232 | 1306000 | 100464 | 1406464 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hand Dryer | 1 | 1 | pcs | 5018000 | 61600 | 5079600 | 5018000 | 61600 | 5079600 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Floor Drain DN50 | 1 | 1 | m | 855000 | 88480 | 943480 | 855000 | 88480 | 943480 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Floor Drain DN80 | 12 | 12 | m | 855000 | 88480 | 943480 | 10260000 | 1061760 | 11321760 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Stainless steel hand washing channel: L10000xH170xD500 | 1 | 1 | pcs | 44000000 | 2240000 | 46240000 | 44000000 | 2240000 | 46240000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Taps for hand washing (Cold) | 14 | 14 | pcs | 7755000 | 50400 | 7805400 | 108570000 | 705600 | 109275600 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Heat Water 5l | 2 | 2 | pcs | 1628727.2727 | 168000 | 1796727.2727 | 3257454.5455 | 336000 | 3593454.5455 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Double Socket 16A/230V | 3 | 3 | pcs | 150480 | 54500 | 204980 | 451440 | 163500 | 614940 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Single Socket 16A/230V | 14 | 14 | pcs | 124560 | 54500 | 179060 | 1743840 | 763000 | 2506840 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 3C-2.5mm2 Cu/XLPE/PVC | 105 | 112 | m | 32518.74 | 7485.665 | 40004.405 | 3642098.88 | 838394.48 | 4480493.36 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 84 | 95 | m | 22980.09 | 5743.9305 | 28724.0205 | 2183108.55 | 545673.3975 | 2728781.9475 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 105 | 110 | m | 8773.9726 | 14594.0164 | 23367.989 | 965136.9863 | 1605341.8053 | 2570478.7916 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 8 | 10 | m | 8773.9726 | 14594.0164 | 23367.989 | 87739.726 | 145940.1641 | 233679.8901 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D16 | 84 | 90 | m | 6646.8692 | 13183.4282 | 19830.2974 | 598218.226 | 1186508.5359 | 1784726.7619 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Waterproof for neck pipe | 5 | 5 | nos | 50000 | 15000 | 65000 | 250000 | 75000 | 325000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 10408457.4536 | 3122537.2361 | 13530994.6897 | 10408457.4536 | 3122537.2361 | 13530994.6897 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
6. 3. 90. |  | Booster pump assembly | 1 |  | PSCH |  |  |  | 132724492.4747 | 7994822.1947 | 140719314.6694 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PUMP ROOM | [6 empty] | 119059072.0747 | 5427258.3947 | 125718330.4694 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Booster pump Q=11.7 m3, H=30m | 2 | 2 | set | 17380000 | 616000 | 17996000 | 34760000 | 1232000 | 35992000 |  |  | #REF! |  | 50% | 50% |  |  | 0%
|  | Electrical control panel for booster pump | 1 | 1 | set | 44440000 | 1400000 | 45840000 | 44440000 | 1400000 | 45840000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Pressure tank 100l | 1 | 1 | pcs | 7915200 | 168000 | 8083200 | 7915200 | 168000 | 8083200 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Storage tank 3m3 | 1 | 1 | pcs | 9970909.0909 | 322000 | 10292909.0909 | 9970909.0909 | 322000 | 10292909.0909 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Filter | 1 | 1 | set | 10800000 | 225400 | 11025400 | 10800000 | 225400 | 11025400 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Water metter DN25 | 1 | 1 | pcs | 1014000 | 50880.368 | 1064880.368 | 1014000 | 50880.368 | 1064880.368 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/PVC/PVC 2Cx1.5mm2 | 20 | 25 | m | 15443.88 | 5031.18 | 20475.06 | 386097 | 125779.5 | 511876.5 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 20 | 25 | m | 40467 | 9350 | 49817 | 1011675 | 233750 | 1245425 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PVC conduit D20 | 40 | 50 | m | 8773.9726 | 14594.0164 | 23367.989 | 438698.6301 | 729700.8206 | 1168399.4507 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Concrete base for pump | 1 | 1 | lot | 2500000 | 450000 | 2950000 | 2500000 | 450000 | 2950000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cover for pump | 1 | 1 | lot | 750000 | 200000 | 950000 | 750000 | 200000 | 950000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Hanger + Support | 1 | 1 | lot | 3043495.4122 | 913048.6237 | 3956544.0359 | 3043495.4122 | 913048.6237 | 3956544.0359 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 2028996.9415 | 608699.0824 | 2637696.0239 | 2028996.9415 | 608699.0824 | 2637696.0239 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Valve | [6 empty] | 13303750 | 1140438.52 | 14444188.52 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Pressure Gauges | 1 | 1 | pcs | 1008000 | 49588 | 1057588 | 1008000 | 49588 | 1057588 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Flexible DN25 | 4 | 4 | pcs | 568800 | 50880.368 | 619680.368 | 2275200 | 203521.472 | 2478721.472 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Float level indicator | 1 | 1 | pcs | 4200000 | 168000 | 4368000 | 4200000 | 168000 | 4368000 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Float valve DN25 | 1 | 1 | pcs | 770400 | 50880.368 | 821280.368 | 770400 | 50880.368 | 821280.368 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Y-Strainer DN25 | 2 | 2 | pcs | 322800 | 50880.368 | 373680.368 | 645600 | 101760.736 | 747360.736 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Safety valve DN25 | 1 | 1 | pcs | 1376400 | 50880.368 | 1427280.368 | 1376400 | 50880.368 | 1427280.368 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Check valve DN25 | 3 | 3 | pcs | 480000 | 50880.368 | 530880.368 | 1440000 | 152641.104 | 1592641.104 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Gate valve DN25 | 4 | 4 | pcs | 264000 | 50880.368 | 314880.368 | 1056000 | 203521.472 | 1259521.472 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 532150 | 159645 | 691795 | 532150 | 159645 | 691795 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Cold water pipe | [6 empty] | 361670.4 | 195125.28 | 556795.68 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PPR pipe DN50 - PN10 | 5 | 6 | m | 45208.8 | 28000 | 73208.8 | 271252.8 | 168000 | 439252.8 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | PPR Fitting | 1 | 1 | lot | 52164 | 15649.2 | 67813.2 | 52164 | 15649.2 | 67813.2 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | Accessories + Support | 1 | 1 | lot | 38253.6 | 11476.08 | 49729.68 | 38253.6 | 11476.08 | 49729.68 |  |  | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | VII.CIVIL | [8 empty] | 337968025 |  |  | #REF! |  |  | 0% |  |  | 0%
7. |  | Exterior Area | [6 empty] | 187529525 | 150438500 | 337968025 |  |  | #REF! |  |  | 0 |  |  | 0%
[14 empty] | #REF! | [5 empty] | 0%
7. 1. |  | Civil Engineering | [6 empty] | 187529525 | 150438500 | 337968025 |  |  | #REF! | [5 empty] | 0%
7. 1. 50. |  | Excavation | 1 | 1 | PSCH |  |  |  | 86750000 | 108855000 | 195605000 |  |  | #REF! | [5 empty] | 0%
|  | LV | [6 empty] | 58500000 | 54800000 | 115800000 |  |  | #REF! | [5 empty] | 0%
|  | Manhole 1000x1000x1000 | 5 | 5 | m | 4500000 | 2000000 | 6500000 | 22500000 | 10000000 | 32500000 |  |  | #REF! |  | 70% | 70% |  |  | 0%
|  | Excavation and backfilling | 164 | 164 | m3 | 0 | 200000 | 200000 | 0 | 32800000 | 32800000 |  |  | #REF! |  | 70% | 70% |  |  | 0%
|  | Concrete crossroads protection | 190 | 120 | m | 300000 | 100000 | 400000 | 36000000 | 12000000 | 48000000 |  |  | #REF! |  | 70% | 70% |  |  | 0%
|  | Labor (Remove old cable) | 1 | 1 | m | 0 | 2500000 | 2500000 | 0 | 2500000 | 2500000 |  |  | #REF! |  | 70% | 70% |  |  | 0%
|  | AIR COMPRESSOR | [6 empty] | 1250000 | 4515000 | 5765000 |  |  | #REF! |  | 70% |  |  |  | 0%
|  | Excavation and backfill | 31 | 20.7 | m3 | 0 | 200000 | 200000 | 0 | 4140000 | 4140000 |  |  | #REF! |  | 70% | 70% |  |  | 0%
|  | The cost of cutting and refinishing the concrete path for the undergruond pipe | 15 | 10 | m | 125000 | 37500 | 162500 | 1250000 | 375000 | 1625000 |  |  | #REF! |  | 70% | 70% |  |  | 0%
|  | ELV |  | 11 |  |  |  |  | 27000000 | 47040000 | 74040000 |  |  | #REF! |  | 70% |  |  |  | 0%
|  | Khoan đường đi ống | 52 | 52 | m | 0 | 300000 | 300000 | 0 | 15600000 | 15600000 |  |  | #REF! |  | 70% | 70% |  |  | 0%
|  | Manhole 1200x1200x1200 | 4 | 6 | pcs | 4500000 | 2000000 | 6500000 | 27000000 | 12000000 | 39000000 |  |  | #REF! |  | 70% | 70% |  |  | 0%
|  | Spare fee for Move and reinstall lighting pole if can't excavation pavement | 6 | 6 | pcs | 0 | 1200000 | 1200000 | 0 | 7200000 | 7200000 |  |  | #REF! |  | 70% | 70% |  |  | 0%
|  | Excavation and backfill | 100 | 61.2 | m3 | 0 | 200000 | 200000 | 0 | 12240000 | 12240000 |  |  | #REF! |  | 70% | 70% |  |  | 0%
[14 empty] | #REF! |  | 70% | 70% |  |  | 0%
7. 1. 60. |  | Laying conduits, pipes, etc. | 1 |  | PSCH |  |  |  | 100779525 | 41583500 | 142363025 |  |  | #REF! | [5 empty] | 0%
|  | LV | [6 empty] | 41773725 | 16061150 | 57834875 |  |  | #REF! | [5 empty] | 0%
|  | HDPE pipe D160/125 | 340 | 421 | m | 88200 | 38150 | 126350 | 37132200 | 16061150 | 53193350 |  |  | #REF! | 30% | 40% | 70% |  |  | 30%
|  | Accessories | 1 | 1 | lot | 4641525 | 0 | 4641525 | 4641525 | 0 | 4641525 |  |  | #REF! |  |  | 0% |  |  | 0%
|  | ELV | [6 empty] | 59005800 | 25522350 | 84528150 |  |  | #REF! | [5 empty] | 0%
|  | HDPE pipe D160/125 | 848 | 669 | m | 88200 | 38150 | 126350 | 59005800 | 25522350 | 84528150 |  |  | #REF! | 30% | 40% | 70% |  |  | 30%
[14 empty] | #REF! |  |  | 0% |  |  | 0%
|  | VIII.EQUIPMENT KITCHEN | [8 empty] | 229689172.3178 |  |  | #REF! |  |  | 0% |  |  | 0%
3. |  | Office, Social and Technical Areas (Hall 3) | [6 empty] | 225500372.3178 | 4188800 | 229689172.3178 |  |  | #REF! |  |  | 0 |  |  | 0%
[14 empty] | #REF! |  |  | 0 |  |  | 0%
3. 3. |  | Mechanical Engineering | [6 empty] | 225500372.3178 | 4188800 | 229689172.3178 |  |  | #REF! |  |  | 0 |  |  | 0%
3. 3. 30. |  | Sanitary Furnishings | 1 | 1 | PSCH |  |  |  | 225500372.3178 | 4188800 | 229689172.3178 |  |  | #REF! |  |  | 0 |  |  | 0%
|  | West side | 0 | 0 | m |  |  | 0 | 107848004.152 | 2094400 | 109942404.152 |  |  | #REF! |  |  | 0 |  |  | 0%
|  | Equiment kitchen | [6 empty] | 107848004.152 | 2094400 | 109942404.152 |  |  | #REF! |  |  | 0 |  |  | 0%
|  | Hafele refrigerator (1-wing refrigerator) | 2 | 2 | pcs | 20093299.732 | 224000 | 20317299.732 | 40186599.464 | 448000 | 40634599.464 |  |  | #REF! |  |  | 0 |  |  | 0%
|  | Single sink for kitchen included faucet waster pop up, flexiable, stop valve | 2 | 2 | pcs | 3486000.21 | 280000 | 3766000.21 | 6972000.42 | 560000 | 7532000.42 |  |  | #REF! |  |  | 0 |  |  | 0%
|  | Hafele semi-sonic dishwasher | 2 | 2 | pcs | 15336300.067 | 168000 | 15504300.067 | 30672600.134 | 336000 | 31008600.134 |  |  | #REF! |  |  | 0 |  |  | 0%
|  | Hafele standalone microwave oven | 2 | 2 | pcs | 2807300.067 | 95200 | 2902500.067 | 5614600.134 | 190400 | 5805000.134 |  |  | #REF! |  |  | 0 |  |  | 0%
|  | Domino's Induction Cooker | 4 | 4 | pcs | 6100551 | 140000 | 6240551 | 24402204 | 560000 | 24962204 |  |  | #REF! |  |  | 0 |  |  | 0%
|  | Accessories | 1 | 1 | lot | 4902182.0069 | 0 | 4902182.0069 | 4902182.0069 | 0 | 4902182.0069 |  |  | #REF! |  |  | 0 |  |  | 0%
|  | East side | [6 empty] | 112750186.1589 | 2094400 | 114844586.1589 |  |  | #REF! |  |  | 0 |  |  | 0%
|  | Equiment kitchen | [6 empty] | 107848004.152 | 2094400 | 109942404.152 |  |  | #REF! |  |  | 0 |  |  | 0%
|  | Hafele refrigerator (1-wing refrigerator) | 2 | 2 | pcs | 20093299.732 | 224000 | 20317299.732 | 40186599.464 | 448000 | 40634599.464 |  |  | #REF! |  |  | 0 |  |  | 0%
|  | Single sink for kitchen included faucet waster pop up, flexiable, stop valve | 2 | 2 | pcs | 3486000.21 | 280000 | 3766000.21 | 6972000.42 | 560000 | 7532000.42 |  |  | #REF! |  |  | 0 |  |  | 0%
|  | Hafele semi-sonic dishwasher | 2 | 2 | pcs | 15336300.067 | 168000 | 15504300.067 | 30672600.134 | 336000 | 31008600.134 |  |  | #REF! |  |  | 0 |  |  | 0%
|  | Hafele standalone microwave oven | 2 | 2 | pcs | 2807300.067 | 95200 | 2902500.067 | 5614600.134 | 190400 | 5805000.134 |  |  | #REF! |  |  | 0 |  |  | 0%
|  | Domino's Induction Cooker | 4 | 4 | pcs | 6100551 | 140000 | 6240551 | 24402204 | 560000 | 24962204 |  |  | #REF! |  |  | 0 |  |  | 0%
|  | Accessories | 1 | 1 | lot | 4902182.0069 | 0 | 4902182.0069 | 4902182.0069 | 0 | 4902182.0069 |  |  | #REF! |  |  | 0 |  |  | 0%
[14 empty] | #REF! |  |  | 0 |  |  | 0%
[14 empty] | #REF! |  |  | 0 |  |  | 0%
|  | IX.ELEVATOR | [8 empty] | 280000000 |  |  | #REF! |  |  | 0% |  |  | 0%
6. |  | Canteen | [6 empty] | 280000000 | 0 | 280000000 |  |  | #REF! |  |  | 0 |  |  | 0%
6. 1. |  | Civil Engineering | [6 empty] | 280000000 | 0 | 280000000 |  |  | #REF! |  |  | 0 |  |  | 0%
6. 1. 260. |  | Elevator for goods | [6 empty] | 280000000 | 0 | 280000000 |  |  | #REF! |  |  | 0 |  |  | 0%
|  | Food elevator without person, no loading machine room weight 200kg/02stop/30m/min | 1 | 1 | lot | 280000000 | 0 | 280000000 | 280000000 | 0 | 280000000 |  |  | #REF! | 0% |  | 0 |  |  | 0%
IV |  | CHI PHÍ QUẢN LÝ | [7 empty] | 0 | 1090000000 | [5 empty] | 0%
|  | Chi phí thuê xe nâng | 1 | 1 | Lot | [5 empty] | 250000000 |  |  | #REF! | 26% | 22% | 48%
|  | Chi phí kho bãi, văn phòng, điện nước tạm | 1 | 1 | Lot | [5 empty] | 70000000 |  |  | #REF! | 26% | 22% | 48%
|  | Chi phí quản lý | 1 | 1 | Lot | [5 empty] | 600000000 |  |  | #REF! | 26% | 22% | 48%
|  | In ấn,submit bản vẽ thi công,hoàn công,hồ sơ nghiệm thu… | 1 | 1 | Lot | [5 empty] | 50000000 |  |  | #REF! | 15% | 22% | 37%
|  | Kiểm định PCCC van gió | 1 | 1 | lot | [5 empty] | 120000000 |  |  | #REF!
| TOTAL (BEFORE VAT) | [9 empty] | 33142000000
| TAX VAT (10%): | [9 empty] | 2651360000
| GRAND TOTAL (AFTER VAT) | [9 empty] | 35793360000
NHÀ THẦU CHÍNH: CÔNG TY CỔ PHẦN CƠ ĐIỆN DITECHCO | [9 empty] | NHÀ THẦU PHỤ: CÔNG TY CỔ PHẦN HMEP |  |  |  |  | NHÀ THẦU PHỤ: CÔNG TY CỔ PHẦN HMEP
CHỈ HUY TRƯỞNG |  | GIÁM SÁT | GIÁM SÁT |  |  |  | GIÁM SÁT |  |  | GIÁM ĐỐC DỰ ÁN CHỈ HUY TRƯỞNG | GIÁM ĐỐC DỰ ÁN CHỈ HUY TRƯỞNG
CAO XUÂN TRƯỜNG |  | ĐỖ PHẠM THANH HỒNG |  |  |  |  | ĐỖ PHẠM THANH HỒNG LÊ NGỌC HOÀNG SƠN |  |  | VÕ HOÀNG KHẮC PHỤC NGUYỄN MINH HẢI | VÕ HOÀNG KHẮC PHỤC NGUYỄN MINH HẢI
Note on C222: PC: Cho group A
Note on C225: PC: cho group A

## BBNT DOT 2
BIÊN BẢN XÁC NHẬN KHỐI LƯỢNG THỰC HIỆN
CÔNG TRÌNH : VN-RENTAL BUILDING HALL 3 ELECTRIC
HẠNG MỤC: HỆ THỐNG CƠ ĐIỆN
ĐỊA ĐIỂM XD : Lô D1, khu công nghiệp Tam Thăng, xã Tam Thăng, thành phố Tam Kỳ, tỉnh Quảng Nam
1 | Thành phần tham gia nghiệm thu :
● | Nhà thầu chính : CÔNG TY CỔ PHẦN CƠ ĐIỆN DITECHCO
| - Ông (Bà) : Cao Xuân Trường |  | Chức vụ: Chỉ huy phó
| - Ông (Bà) : Trần Ngọc Sơn |  | Chức vụ: Giám sát
| - Ông (Bà) : Đỗ Phạm Thanh Hồng |  | Chức vụ: Giám sát
● | Nhà thầu phụ: CÔNG TY CỔ PHẦN HMEP
| - Ông (Bà) : Nguyễn Hữu Huấn |  | Chức vụ: Giám đốc
- Ông (Bà) : Võ Hoàng Khắc Phục
| - Ông (Bà) : Nguyễn Minh Hải |  | Chức vụ: Chỉ huy trưởng
2 | Thời gian tiến hành nghiệm thu :
● | Bắt đầu : 08h00 ngày ... tháng …... năm 2022
● | Kết thúc : 10h30 ngày ... tháng ……. năm 2022
Tại : Công trình
3 | Nghiệm thu khối lượng Hạng mục công việc
a/. | Căn cứ nghiệm thu
- Hợp đồng số : 0310/2022/HĐKT-DRX2/DITECHCO-HMEP
- Khối lượng lắp đặt thực tế trên công trường
- Căn cứ quy chuẩn,tiêu chuẩn áp dụng khi thi công, kiểm tra và nghiệm thu.
- Chứng chỉ xuất xứ, chất lượng vật liệu, thiết bị
b/. | Khối lượng thực tế thi công
Contractor name: HMEP
Position |  | Headline | Quantity | Quantity By contractor | Unit | Material Unit | Labor Unit | Unit rate | Material Amount | Labor Amount | Amount (VND) | % Công việc hoàn thành |  | % lũy kế công việc hoàn thành đến cuối kỳ này
[12 empty] | Đợt 1 | Đợt 2 |  | Đợt 2 | Đợt 3 | % KL hoàn thành lũy kế
|  | I. ELEC | [8 empty] | 18337127645.6357
1. |  | Construction site facilities | [8 empty] | 0
[12 empty] | 0% | 0% | 0% |  |  | 0%
1. 1. |  | Construction site facilities | 1 |  | psch | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
1. 2. |  | Construction site cameras | 1 |  | psch | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
2. |  | Production and Logistic building (Hall 3) | [6 empty] | 4384819997.1499 | 819871975.3259 | 5204691972.4758 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
2.1. |  | Civil Engineering | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
2. 1. 10. |  | Calculations | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 20. |  | Rainwater and waste water sewer | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 30. |  | Earthworks | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 40. |  | Demolition, removal and dismantling works | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 50. |  | Foundation | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 60. |  | Building structure | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 70. |  | General concrete- / reinforced concrete works | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 80. |  | Fire protection | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 90. |  | Fire rated walls | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 100. |  | Cutting base slabs / ceilings / floors | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 110. |  | Cutting holes into existing facades, walls and roofs | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 120. |  | Exterior walls | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 130. |  | Exterior doors and windows | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 140. |  | Fire protection doors | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 150. |  | Internal doors | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 160. |  | Fire protection roller shutter door | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 170. |  | Fire protection bulkhead | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 180. |  | High speed roller shutter | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 190. |  | Fitting and metal work - general | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 200. |  | Railings and hand rails | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 210. |  | Steel stage for installations | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 220. |  | Collision protection | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 230. |  | canopies of exterior doors | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 240. |  | Concerete steps in front of the hall | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 250. |  | Painting and varnishing works | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 260. |  | Guidance systems | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 270. |  | Locking system | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 280. |  | Internal signage | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 290. |  | Adjustment ridge vent | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 300. |  | Roof reinforcment Option 1 | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 310. |  | Insert new ventilation louvers | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 320. |  | Metal louvers to cover mechanical units | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
2. 2. |  | Electrical Engineering | 1 |  | PSCH |  |  |  | 4384819997.1499 | 819871975.3259 | 5204691972.4758 | 0% | 0% | 0% |  |  | 0%
2. 2. 10. |  | Adjustment of existing facilities, dismantling and disposal works | 1 | 1 | PSCH |  |  |  | 0 | 24400000 | 24400000 | 0% | 0% | 0% |  |  | 0%
|  | The cost of dismantling electrical distribution board, trunking & ladder and lighting system existing system | 1 | 1 | lot | 0 | 14000000 | 14000000 | 0 | 14000000 | 14000000 | 0% | 80% | 80% |  |  | 0%
|  | Opening (inluded supports & waterproof) for wall through ductwork fee | 1 | 1 | lot | 0 | 10400000 | 10400000 | 0 | 10400000 | 10400000 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
2. 2. 20. |  | Rennovation existing grounding system and lightning protection | 1 | 1 | PSCH | 0 | 5000000 | 5000000 | 0 | 5000000 | 5000000 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
2. 2. 30. |  | Rennovation existing grounding and equipotential bonding | 1 | 1 | PSCH | 0 | 2500000 | 2500000 | 0 | 2500000 | 2500000 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
2. 2. 40. |  | Power supply | 1 | 1 | PSCH |  |  |  | 1266144274.1142 | 405876628.1459 | 1672020902.2601 | 0% | 0% | 0% |  |  | 0%
|  | From DB SYN-TR1 Panel to Building 3_BMDP | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 6x(4x1Cx300mm2)+E240mm2 | 67 | 64.9 | m | 2672599.35 | 818400 | 3490999.35 | 173451697.815 | 53114160 | 226565857.815 | 36% | 39% | 75% |  |  | 0%
| Option1 | From DB SYN-TR1 Panel to Building 3_BMDP | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 5x(4x1Cx240mm2)+E240mm2 | 67 | 67 | m | 15029239.743 | 686400 |  |  |  |  | 0% | 0% | 0% |  |  | 0%
|  | From Building 3_BMDP Panel to Building 3_PDP 1.0 | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 4x1Cx300mm2+E150mm2 | 15 | 14 | m | 481493.34 | 158400 | 639893.34 | 6740906.76 | 2217600 | 8958506.76 | 36% | 39% | 75% |  |  | 0%
|  | From Building 3_BMDP Panel to Building 3_PDP 1.1 | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 2x(4x1Cx185mm2)+E185mm2 | 116 | 106 | m | 618512.88 | 176000 | 794512.88 | 65562365.28 | 18656000 | 84218365.28 | 36% | 39% | 75% |  |  | 0%
|  | From Building 3_BMDP Panel to Building 3_PDP 2.0 | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 3x(3x1Cx240mm2)+N1Cx240mm2+E120mm2 | 182 | 203.5 | m | 909229.53 | 304700 | 1213929.53 | 185028209.355 | 62006450 | 247034659.355 | 36% | 39% | 75% |  |  | 0%
|  | From Building 3_BMDP Panel to Building 3_PDP 1.2 | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 3x(3x1Cx240mm2)+N2x1Cx240mm2+E185mm2 | 135 | 143 | m | 1018095.6 | 304700 | 1322795.6 | 145587670.8 | 43572100 | 189159770.8 | 36% | 39% | 75% |  |  | 0%
|  | From Building 3_BMDP Panel to Building 3_PDP 2.1 | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 3x(3x1Cx240mm2)+N2x1Cx240mm2+E185mm2 | 136 | 137 | m | 1018095.6 | 304700 | 1322795.6 | 139479097.2 | 41743900 | 181222997.2 | 36% | 39% | 75% |  |  | 0%
|  | From Building 3_BMDP Panel to Building 3_BDP 1.0 | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 4x1Cx150mm2+E70mm2 | 70 | 16.5 | m | 247104.54 | 116765.3025 | 363869.8425 | 4077224.91 | 1926627.4913 | 6003852.4013 | 36% | 39% | 75% |  |  | 0%
|  | From Building 3_BMDP Panel to Building 3_BDP 1.1 | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 2x(4x1Cx150mm2)+E150mm2 | 15 | 99 | m | 497079.9 | 138600 | 635679.9 | 49210910.1 | 13721400 | 62932310.1 | 36% | 39% | 75% |  |  | 0%
|  | From Building 3_BMDP Panel to Building 3_BDP 2.0 | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 3x(3x1Cx240mm2)+N2x1Cx185mm2+E185mm2 | 116 | 191.1 | m | 1018095.6 | 304700 | 1322795.6 | 194558069.16 | 58228170 | 252786239.16 | 36% | 39% | 75% |  |  | 0%
|  | From Building 3_BMDP Panel to Scooter garage BDP 1.0 | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 4x1Cx35mm2+E16mm2 | 131 | 86 | m | 70862.76 | 46119.15 | 116981.91 | 6094197.36 | 3966246.9 | 10060444.26 | 36% | 0% | 36% |  |  | 0%
|  | From Building 3_BMDP Panel to Canteen BDP 1.0 | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 3x1Cx120mm2+N1Cx25mm2+E16mm2 | 174 | 181 | m | 165603.51 | 101462.13 | 267065.64 | 29974235.31 | 18364645.53 | 48338880.84 | 36% | 0% | 36% |  |  | 0%
|  | From Building 3_BDP 1.1 Panel to Building 3_UPS1-100 kVA | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 4x1Cx70mm2+E35mm2 | 106 | 121 | m | 128659.23 | 83182.176 | 211841.406 | 15567766.83 | 10065043.296 | 25632810.126 | 36% | 0% | 36% |  |  | 0%
|  | From Building 3 UPS1-MDP Panel to Building 3_UPS 1 DP 1.3 35kVA | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 4x1Cx70mm2+E35mm2 | 20 | 18.7 | m | 128659.23 | 83182.176 | 211841.406 | 2405927.601 | 1555506.6912 | 3961434.2922 | 36% | 0% | 36% |  |  | 0%
|  | From Building 3_BDP 2.0 Panel to Building 3_UPS2-100 kVA | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 4x1Cx70mm2+E35mm2 | 18 | 27.5 | m | 128659.23 | 83182.176 | 211841.406 | 3538128.825 | 2287509.84 | 5825638.665 | 36% | 0% | 36% |  |  | 0%
|  | From Building 3 UPS1-MDP Panel to Building 3_UPS 2 DP 1.3 35kVA | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 4x1Cx70mm2+E35mm2 | 25 | 27.5 | m | 128659.23 | 83182.176 | 211841.406 | 3538128.825 | 2287509.84 | 5825638.665 | 36% | 0% | 36% |  |  | 0%
|  | From Building 3 UPS1-MDP Panel to Building 3 UPS 2-DP1.2 | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx10mm2 | 185 | 184.8 | m | 102150.27 | 17818.7625 | 119969.0325 | 18877369.896 | 3292907.31 | 22170277.206 | 36% | 0% | 36% |  |  | 0%
|  | From Building 3 UPS1-MDP Panel to Building 3 UPS 2-DP1.3 | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx6mm2 | 115 | 105 | m | 65470.44 | 17189.865 | 82660.305 | 6874396.2 | 1804935.825 | 8679332.025 | 36% | 0% | 36% |  |  | 0%
|  | From Building 3 UPS1-MDP Panel to Building 3_UPS 1 DP 1.3 35kVA | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 4x1Cx50mm2+E10mm2 | 115 | 90 | m | 166514.94 | 52580 | 219094.94 | 14986344.6 | 4732200 | 19718544.6 | 36% | 0% | 36% |  |  | 0%
|  | From Building 3 UPS1-MDP Panel to PDU | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 590 | 480 | m | 32518.74 | 7485.665 | 40004.405 | 15608995.2 | 3593119.2 | 19202114.4 | 36% | 0% | 36% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | From Building 3_BDP 2.0 Panel to Building 3_UPS2-100 kVA | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 4x1Cx35mm2+E16mm2 | 18 | 27.5 | m | 448964.76 | 46119.15 | 495083.91 | 12346530.9 | 1268276.625 | 13614807.525 | 36% | 0% | 36% |  |  | 0%
|  | From Building 3 UPS2-MDP Panel to Building 3 UPS 2-DP1.2 | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx4mm2 | 25 | 20 | m | 46999.53 | 9969.2395 | 56968.7695 | 939990.6 | 199384.79 | 1139375.39 | 36% | 0% | 36% |  |  | 0%
|  | From Building 3 UPS1-MDP Panel to Building 3 UPS 2-DP1.2 | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx10mm2 | 180 | 193.6 | m | 102150.27 | 17818.7625 | 119969.0325 | 19776292.272 | 3449712.42 | 23226004.692 | 36% | 0% | 36% |  |  | 0%
|  | From Building 3 UPS1-MDP Panel to Building 3 UPS 2-DP1.2 | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx6mm2 | 115 | 187 | m | 65470.44 | 14173.4395 | 79643.8795 | 12242972.28 | 2650433.1865 | 14893405.4665 | 36% | 0% | 36% |  |  | 0%
|  | From Building 3 UPS1-MDP Panel to Building 3_UPS 2 DP 1.3 35kVA | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 4x1Cx50mm2+E10mm2 | 115 | 117.7 | m | 166514.94 | 52580 | 219094.94 | 19598808.438 | 6188666 | 25787474.438 | 36% | 0% | 36% |  |  | 0%
|  | From Building 3 UPS2-MDP Panel to PDU | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 590 | 480 | m | 32518.74 | 7485.665 | 40004.405 | 15608995.2 | 3593119.2 | 19202114.4 | 36% | 0% | 36% |  |  | 0%
|  | From DB PDP 1.2 Panel to Cetral feeding unit 1 | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 4x1Cx150mm2+E70mm2 | 24 | 26.4 | m | 247104.54 | 116765.3025 | 363869.8425 | 6523559.856 | 3082603.986 | 9606163.842 | 36% | 39% | 75% |  |  | 0%
|  | From DB PDP 1.2 Panel to Cetral feeding unit 2 | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 4x1Cx150mm2+E70mm2 | 16 | 17.6 | m | 247104.54 | 116765.3025 | 363869.8425 | 4349039.904 | 2055069.324 | 6404109.228 | 36% | 39% | 75% |  |  | 0%
|  | From DB PDP 1.2 Panel to Cetral feeding unit 3 | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 4x1Cx150mm2+E70mm2 | 57 | 68.2 | m | 247104.54 | 116765.3025 | 363869.8425 | 16852529.628 | 7963393.6305 | 24815923.2585 | 36% | 39% | 75% |  |  | 0%
|  | From DB PDP 2.1 Panel to Cetral feeding unit 1 | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 4x1Cx150mm2+E70mm2 | 24 | 26.4 | m | 247104.54 | 116765.3025 | 363869.8425 | 6523559.856 | 3082603.986 | 9606163.842 | 36% | 39% | 75% |  |  | 0%
|  | From DB PDP 2.1 Panel to Cetral feeding unit 2 | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 4x1Cx150mm2+E70mm2 | 16 | 17.6 | m | 247104.54 | 116765.3025 | 363869.8425 | 4349039.904 | 2055069.324 | 6404109.228 | 36% | 39% | 75% |  |  | 0%
|  | From DB PDP 2.1 Panel to Cetral feeding unit 3 | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable AL/XLPE/PVC 4x1Cx150mm2+E70mm2 | 57 | 68.2 | m | 247104.54 | 116765.3025 | 363869.8425 | 16852529.628 | 7963393.6305 | 24815923.2585 | 36% | 39% | 75% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 49018783.6212 | 15188870.1199 | 64207653.7411 | 49018783.6212 | 15188870.1199 | 64207653.7411 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
2. 2. 50. |  | Energy measurement system | 1 | 1 | PSCH |  |  |  | 315804122.0768 | 12524296.2357 | 328328418.3125 | 0% | 0% | 0% |  |  | 0%
|  | SOFTWARE PRODUCTS | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Pre-parameterization per device | 11 | 11 | pcs | 343200 | 0 | 343200 | 3775200 | 0 | 3775200 | 0% | 0% | 0% |  |  | 0%
|  | visual energy ZP5 | 3 | 3 | pcs | 6063200 | 0 | 6063200 | 18189600 | 0 | 18189600 | 0% | 0% | 0% |  |  | 0%
|  | Hourly rate for remote services, Costs per hour / co-worker | 11 | 11 | pcs | 3832400 | 0 | 3832400 | 42156400 | 0 | 42156400 | 0% | 0% | 0% |  |  | 0%
|  | Freight charges | 1 | 1 | lot | 5291000 | 0 | 5291000 | 5291000 | 0 | 5291000 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 3344406 | 1003321.8 | 4347727.8 | 3344406 | 1003321.8 | 4347727.8 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | MULTI METERS | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Multimess F144 | 11 | 11 | pcs | 21251230 | 275000 | 21526230 | 233763530 | 3025000 | 236788530 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | ELV cable | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable Cat6A | 330 | 330 | m | 21639.3443 | 3360 | 24999.3443 | 7140983.6066 | 1108800 | 8249783.6066 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 150 | 150 | m | 8773.9726 | 14594.0164 | 23367.989 | 1316095.8904 | 2189102.4618 | 3505198.3522 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 826906.5798 | 248071.974 | 1074978.5538 | 826906.5798 | 248071.974 | 1074978.5538 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | ENGINEERING SERVICES | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Labour cost for support DRX test funtion of Access control system | 1 | 1 | lot | 0 | 4950000 | 4950000 | 0 | 4950000 | 4950000 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
2. 2. 60. |  | Electrical installation in the production hall | 1 | 1 | PSCH |  |  |  | 2359220157.2575 | 298880144.662 | 2658100301.9195 | 0% | 0% | 0% |  |  | 0%
|  | Cable trays_Hot dip-Galvanized Steel | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Production hall 01 | [6 empty] | 1059238180 | 131854511.8676 | 1191092691.8676 | 0% | 0% | 0% |  |  | 0%
|  | Cable tray 500x100x2.0mm | 0 | 0 | m | 1443780 | 81001.3848 | 1524781.3848 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable tray 300x100x2.0mm | 0 | 129.8 | m | 1009710 | 61078.452 | 1070788.452 | 131060358 | 7927983.0721 | 138988341.0721 | 30% | 45% | 75% | 25% | 25% | 25%
|  | Cable tray 200x100x2.0mm | 13 | 129.8 | m | 776880 | 51045.8655 | 827925.8655 | 100839024 | 6625753.3383 | 107464777.3383 | 30% | 45% | 75% | 25% | 25% | 25%
|  | Cable tray 500x100 with separating bar, c/w cover | 185 | 215.6 | m | 1525680 | 81001.3848 | 1606681.3848 | 328936608 | 17463898.5532 | 346400506.5532 | 30% | 45% | 75% | 25% | 25% | 25%
|  | Cable tray 400x100 with separating bar, c/w cover | 232 | 269.5 | m | 826020 | 68320 | 894340 | 222612390 | 18412240 | 241024630 | 30% | 45% | 75% | 25% | 25% | 25%
|  | Cable tray 300x100 with separating bar, c/w cover | 112 | 0 | m | 1091610 | 61078.452 | 1152688.452 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable tray 200x100 with separating bar, c/w cover | 112 | 0 | m | 858780 | 51045.8655 | 909825.8655 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable tray 200x50 with separating bar, c/w cover | 187 | 0 | m | 669240 | 51045.8655 | 720285.8655 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable ladder 600x100x2.0mm, c/w cover | 9 | 0 | m | 1199250 | 91952 | 1291202 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable ladder 500x100x2.0mm, c/w cover | 0 | 0 | m | 1067040 | 81001.3848 | 1148041.3848 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable ladder 400x100x2.0mm, c/w cover | 5 | 5 | m | 933660 | 68320 | 1001980 | 4668300 | 341600 | 5009900 | 30% | 45% | 75% | 25% | 25% | 25%
|  | Cable ladder 300x100x1.5mm, c/w cover | 2 | 2 | m | 625950 | 61078.452 | 687028.452 | 1251900 | 122156.904 | 1374056.904 | 30% | 45% | 75% | 25% | 25% | 25%
|  | Fitting and accessories | 1 | 1 | lot | 269869600 | 80960880 | 350830480 | 269869600 | 80960880 | 350830480 | 30% | 45% | 75% | 25% | 25% | 25%
[12 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Production hall 02 | [6 empty] | 205951658 | 26469471.7777 | 232421129.7777 | 0% | 0% | 0% |  |  | 0%
|  | Cable tray 500x100x2.0mm | 0 |  | m | 1443780 | 81001.3848 | 1524781.3848 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable tray 300x100x2.0mm | 0 |  | m | 1009710 | 61078.452 | 1070788.452 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable tray 200x100x2.0mm | 10 |  | m | 776880 | 51045.8655 | 827925.8655 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable tray 500x100 with separating bar, c/w cover | 0 |  | m | 1525680 | 81001.3848 | 1606681.3848 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable tray 400x100 with separating bar, c/w cover | 64 | 73.7 | m | 826020 | 68320 | 894340 | 60877674 | 5035184 | 65912858 | 30% | 45% | 75% | 25% | 25% | 25%
|  | Cable tray 300x100 with separating bar, c/w cover | 0 | 0 | m | 1091610 | 61078.452 | 1152688.452 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable tray 200x100 with separating bar, c/w cover | 82 | 94.6 | m | 858780 | 51045.8655 | 909825.8655 | 81240588 | 4828938.8737 | 86069526.8737 | 30% | 45% | 75% | 25% | 25% | 25%
|  | Cable tray 200x50 with separating bar, c/w cover | 66 | 0 | m | 669240 | 51045.8655 | 720285.8655 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable ladder 600x100x2.0mm, c/w cover | 0 | 0 | m | 1199250 | 91952 | 1291202 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable ladder 500x100x2.0mm, c/w cover | 0 | 0 | m | 1067040 | 81001.3848 | 1148041.3848 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable ladder 400x100x2.0mm, c/w cover | 11 | 11 | m | 933660 | 68320 | 1001980 | 10270260 | 751520 | 11021780 | 30% | 45% | 75% | 25% | 25% | 25%
|  | Cable ladder 300x100x1.5mm, c/w cover | 0 | 0 | m | 625950 | 61078.452 | 687028.452 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable ladder 200x100x1.5mm, c/w cover | 2 | 2.2 | m | 496080 | 51045.8655 | 547125.8655 | 1091376 | 112300.904 | 1203676.904 | 30% | 45% | 75% | 25% | 25% | 25%
|  | Fitting and accessories | 1 | 1 | lot | 52471760 | 15741528 | 68213288 | 52471760 | 15741528 | 68213288 | 30% | 45% | 75% | 25% | 25% | 25%
[12 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Electrical installation | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Production hall 01 | [6 empty] | 4068960 | 2081884 | 6150844 | 0% | 0% | 0% |  |  | 0%
|  | 1-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | 2-Way switch, 1 gang for lighting control panel | 0 | 0 | pcs | 0 | 54500 | 54500 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Single Socket NEMA5 | 10 | 10 | pcs | 124560 | 54500 | 179060 | 1245600 | 545000 | 1790600 | 0% | 0% | 0% |  |  | 0%
|  | Double Socket NEMA5 | 0 | 0 | pcs | 249120 | 54500 | 303620 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Single Socket 16A/230V, Lighting outlet general (wall) + Plug | 18 | 18 | pcs | 124560 | 54500 | 179060 | 2242080 | 981000 | 3223080 | 0% | 0% | 0% |  |  | 0%
|  | Socket combination type 1 | 1 | 1 | pcs | 0 | 381500 | 381500 | 0 | 381500 | 381500 | 0% | 0% | 0% |  |  | 0%
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 581280 | 174384 | 755664 | 581280 | 174384 | 755664 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Production hall 02 | [6 empty] | 1017240 | 425096 | 1442336 | 0% | 0% | 0% |  |  | 0%
|  | 1-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | 2-Way switch, 1 gang for lighting control panel | 0 | 0 | pcs | 0 | 54500 | 54500 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Single Socket NEMA5 | 2 | 2 | pcs | 124560 | 54500 | 179060 | 249120 | 109000 | 358120 | 0% | 0% | 0% |  |  | 0%
|  | Double Socket NEMA5 | 0 | 0 | pcs | 249120 | 54500 | 303620 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Single Socket 16A/230V, Lighting outlet general (wall) + Plug | 5 | 5 | pcs | 124560 | 54500 | 179060 | 622800 | 272500 | 895300 | 0% | 0% | 0% |  |  | 0%
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 145320 | 43596 | 188916 | 145320 | 43596 | 188916 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Lighting | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Production hall 01 | [6 empty] | 891792936.3239 | 117504814.1732 | 1009297750.4972 | 0% | 0% | 0% |  |  | 0%
|  | Led Highbay light 115W, Type CI | 154 | 154 | pcs | 4081000 | 196000 | 4277000 | 628474000 | 30184000 | 658658000 | 0% | 0% | 0% |  |  | 0%
|  | LED Frame Lamp 1x46W, Type BII | 2 | 2 | pcs | 1607100 | 63504 | 1670604 | 3214200 | 127008 | 3341208 | 0% | 0% | 0% |  |  | 0%
|  | Wall mounted Light 1x15W, Type E | 18 | 18 | pcs | 585200 | 63504 | 648704 | 10533600 | 1143072 | 11676672 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 19140000 | 3828000 | 22968000 | 19140000 | 3828000 | 22968000 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable for lighting system (Hall 01) | [6 empty] | 230431136.3239 | 82222734.1732 | 312653870.4972 | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE//PVC 3Cx4.0mm2 | 565 | 800 | m | 46999.53 | 8250 | 55249.53 | 37599624 | 6600000 | 44199624 | 36% | 39% | 75% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 2404 | 2550 | m | 32518.74 | 7485.665 | 40004.405 | 82922787 | 19088445.75 | 102011232.75 | 36% | 39% | 75% |  |  | 0%
|  | Cable Cu/XLPE//PVC 3Cx1.5mm2 | 359 | 889 | m | 22980.09 | 5743.9305 | 28724.0205 | 20429300.01 | 5106354.2145 | 25535654.2245 | 36% | 39% | 75% |  |  | 0%
|  | PVC conduit D20 | 1061 | 1850 | m | 8773.9726 | 14594.0164 | 23367.989 | 16231849.3151 | 26998930.3618 | 43230779.6768 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D32(cho PA đổi cáp 3x6mm group A) |  | 749 | m | 19428.0822 | 20044.0164 | 39472.0986 | 14551633.5616 | 15012968.2924 | 29564601.8541 | 0% | 0% | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 220 | 220 | m | 3554.7229 | 5289.7059 | 8844.4288 | 782039.0424 | 1163735.2941 | 1945774.3365 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 5485667.5348 | 1645700.2604 | 7131367.7953 | 5485667.5348 | 1645700.2604 | 7131367.7953 | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE//PVC 3Cx6.0mm2 |  | 800.8 | m | 65469.825 | 8250 | 73719.825 | 52428235.86 | 6606600 | 59034835.86 | 36% | 39% | 75% |  |  | 0%
|  | Production hall 02 | [6 empty] | 171116000 | 9147520 | 180263520 | 0% | 0% | 0% |  |  | 0%
|  | Led Highbay light 115W, Type CI | 40 | 40 | pcs | 4081000 | 196000 | 4277000 | 163240000 | 7840000 | 171080000 | 0% | 0% | 0% |  |  | 0%
|  | LED Frame Lamp 1x46W, Type BII | 0 | 0 | pcs | 1607100 | 63504 | 1670604 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Wall mounted Light 1x15W, Type E | 5 | 5 | pcs | 585200 | 63504 | 648704 | 2926000 | 317520 | 3243520 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 4950000 | 990000 | 5940000 | 4950000 | 990000 | 5940000 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable for lighting system (Hall 02) | [6 empty] | 26035182.9336 | 11396846.8435 | 37432029.777 | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 536 | 560 | m | 32518.74 | 7485.665 | 40004.405 | 18210494.4 | 4191972.4 | 22402466.8 | 36% | 39% | 75% |  |  | 0%
|  | Cable Cu/XLPE//PVC 3Cx1.5mm2 | 96 | 120 | m | 22980.09 | 5743.9305 | 28724.0205 | 2757610.8 | 689271.66 | 3446882.46 | 36% | 39% | 75% |  |  | 0%
|  | PVC conduit D20 | 277 | 398.2 | m | 8773.9726 | 14594.0164 | 23367.989 | 3493795.8904 | 5811337.3352 | 9305133.2256 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 88 | 0 | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 57 | 55 | m | 3554.7229 | 5289.7059 | 8844.4288 | 195509.7606 | 290933.8235 | 486443.5841 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 1377772.0826 | 413331.6248 | 1791103.7073 | 1377772.0826 | 413331.6248 | 1791103.7073 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
2. 2. 70. |  | Electrical installation in the logistics hall | 1 | 1 | PSCH |  |  |  | 365728225.5911 | 45073708.1139 | 410801933.705 | 0% | 0% | 0% |  |  | 0%
|  | Cable trays_Hot dip-Galvanized Steel | [6 empty] | 184238087 | 23645406.8737 | 207883493.8737 | 0% | 0% | 0% |  |  | 0%
|  | Cable tray 500x100x2.0mm | 0 | 0 | m | 1443780 | 81001.3848 | 1524781.3848 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable tray 300x100x2.0mm | 0 | 0 | m | 1009710 | 61078.452 | 1070788.452 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable tray 200x100x2.0mm | 10 |  | m | 776880 | 51045.8655 | 827925.8655 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable tray 500x100 with separating bar | 9 |  | m | 1525680 | 81001.3848 | 1606681.3848 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable tray 400x100 with separating bar | 56 | 66 | m | 826020 | 68320 | 894340 | 54517320 | 4509120 | 59026440 | 30% | 45% | 75% | 25% | 25% | 25%
|  | Cable tray 300x100 with separating bar | 0 | 0 | m | 1091610 | 61078.452 | 1152688.452 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable tray 200x100 with separating bar | 83 | 94.6 | m | 858780 | 51045.8655 | 909825.8655 | 81240588 | 4828938.8737 | 86069526.8737 | 30% | 45% | 75% | 25% | 25% | 25%
|  | Cable tray 200x50 with separating bar | 66 | 0 | m | 669240 | 51045.8655 | 720285.8655 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable ladder 600x100x2.0mm | 0 | 0 | m | 1199250 | 91952 | 1291202 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable ladder 500x100x2.0mm | 0 | 0 | m | 1067040 | 81001.3848 | 1148041.3848 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable ladder 400x100x2.0mm | 3 | 3.3 | m | 466830 | 68320 | 535150 | 1540539 | 225456 | 1765995 | 30% | 45% | 75% | 25% | 25% | 25%
|  | Cable ladder 300x100x1.5mm | 0 | 0 | m | 625950 | 61078.452 | 687028.452 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable ladder 200x100x1.5mm | 0 | 0 | m | 496080 | 51045.8655 | 547125.8655 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Fitting and accessories | 1 | 1 | lot | 46939640 | 14081892 | 61021532 | 46939640 | 14081892 | 61021532 | 30% | 45% | 75% | 25% | 25% | 25%
[12 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Electrical installation | [6 empty] | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | 1-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | 2-Way switch, 1 gang for lighting control panel | 0 | 0 | pcs | 0 | 54500 | 54500 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Single Socket NEMA5 | 0 | 0 | pcs | 124560 | 54500 | 179060 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Double Socket NEMA5 | 0 | 0 | pcs | 249120 | 54500 | 303620 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Lighting | [6 empty] | 147378000 | 7630000 | 155008000 | 0% | 0% | 0% |  |  | 0%
|  | Led Highbay light 115W, Type CII | 35 | 35 | pcs | 4100800 | 196000 | 4296800 | 143528000 | 6860000 | 150388000 | 0% | 0% | 0% |  |  | 0%
|  | LED Frame Lamp 1x46W, Type BII | 0 | 0 | pcs | 1607100 | 63504 | 1670604 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 63504 | 648704 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 3850000 | 770000 | 4620000 | 3850000 | 770000 | 4620000 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable for lighting system | [6 empty] | 34112138.5911 | 13798301.2403 | 47910439.8314 | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 693 | 805 | m | 32518.74 | 7485.665 | 40004.405 | 26177585.7 | 6025960.325 | 32203546.025 | 36% | 39% | 75% |  |  | 0%
|  | Cable Cu/XLPE//PVC 3Cx1.5mm2 | 96 | 90 | m | 22980.09 | 5743.9305 | 28724.0205 | 2068208.1 | 516953.745 | 2585161.845 | 36% | 39% | 75% |  |  | 0%
|  | PVC conduit D20 | 277 | 440 | m | 8773.9726 | 14594.0164 | 23367.989 | 3860547.9452 | 6421367.2212 | 10281915.1664 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 88 | 0 | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 33 | 55 | m | 3554.7229 | 5289.7059 | 8844.4288 | 195509.7606 | 290933.8235 | 486443.5841 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 1810287.0853 | 543086.1256 | 2353373.2109 | 1810287.0853 | 543086.1256 | 2353373.2109 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
2. 2. 80. |  | Power supply of building utilities | 1 | 1 | PSCH |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
2. 2. 90. |  | Three-arm Turnstile | 1 | 1 | PSCH |  |  |  | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
2. 2. 100. |  | Emergency lighting | 1 | 1 | PSCH |  |  |  | 77923218.1103 | 25617198.1684 | 103540416.2786 | 0% | 0% | 0% |  |  | 0%
|  | Production hall 01 | [6 empty] | 18834457.2 | 3323337.16 | 22157794.36 | 0% | 0% | 0% |  |  | 0%
|  | Emergency light | 13 | 13 | pcs | 516120 | 63504 | 579624 | 6709560 | 825552 | 7535112 | 0% | 0% | 0% |  |  | 0%
|  | Exit light | 13 | 13 | pcs | 566280 | 63504 | 629784 | 7361640 | 825552 | 8187192 | 0% | 0% | 0% |  |  | 0%
|  | Single Socket 16A/230V | 26 | 26 | pcs | 150480 | 54500 | 204980 | 3912480 | 1417000 | 5329480 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | pcs | 850777.2 | 255233.16 | 1106010.36 | 850777.2 | 255233.16 | 1106010.36 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable power supply | [6 empty] | 22294958.4377 | 8918664.6672 | 31213623.1048 | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE//PVC 3Cx2.5mm2 | 619 | 569 | m | 32518.74 | 7485.665 | 40004.405 | 18503163.06 | 4259343.385 | 22762506.445 | 36% | 0% | 36% |  |  | 0%
|  | PVC conduit D20 | 371 | 275 | m | 8773.9726 | 14594.0164 | 23367.989 | 2412842.4658 | 4013354.5132 | 6426196.979 | 0% | 0% | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 74 | 55 | m | 3554.7229 | 5289.7059 | 8844.4288 | 195509.7606 | 290933.8235 | 486443.5841 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 1183443.1513 | 355032.9454 | 1538476.0967 | 1183443.1513 | 355032.9454 | 1538476.0967 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Production hall 02 | [6 empty] | 8540160 | 1464048 | 10004208 | 0% | 0% | 0% |  |  | 0%
|  | Emergency light | 6 | 6 | pcs | 516120 | 63504 | 579624 | 3096720 | 381024 | 3477744 | 0% | 0% | 0% |  |  | 0%
|  | Exit light | 6 | 6 | pcs | 566280 | 63504 | 629784 | 3397680 | 381024 | 3778704 | 0% | 0% | 0% |  |  | 0%
|  | Single Socket 16A/230V | 12 | 12 | pcs | 150480 | 54500 | 204980 | 1805760 | 654000 | 2459760 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | pcs | 240000 | 48000 | 288000 | 240000 | 48000 | 288000 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable power supply | [6 empty] | 10420834.2021 | 4757933.0991 | 15178767.3011 | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE//PVC 3Cx2.5mm2 | 286 | 253 | m | 32518.74 | 7485.665 | 40004.405 | 8227241.22 | 1893873.245 | 10121114.465 | 36% | 0% | 36% |  |  | 0%
|  | PVC conduit D20 | 171 | 165 | m | 8773.9726 | 14594.0164 | 23367.989 | 1447705.4795 | 2408012.7079 | 3855718.1874 | 0% | 0% | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 34 | 55 | m | 3554.7229 | 5289.7059 | 8844.4288 | 195509.7606 | 290933.8235 | 486443.5841 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 550377.742 | 165113.3226 | 715491.0646 | 550377.742 | 165113.3226 | 715491.0646 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Logistics area | [6 empty] | 7116800 | 1220040 | 8336840 | 0% | 0% | 0% |  |  | 0%
|  | Emergency light | 5 | 5 | pcs | 516120 | 63504 | 579624 | 2580600 | 317520 | 2898120 | 0% | 0% | 0% |  |  | 0%
|  | Exit light | 5 | 5 | pcs | 566280 | 63504 | 629784 | 2831400 | 317520 | 3148920 | 0% | 0% | 0% |  |  | 0%
|  | Single Socket 16A/230V | 10 | 10 | pcs | 150480 | 54500 | 204980 | 1504800 | 545000 | 2049800 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | pcs | 200000 | 40000 | 240000 | 200000 | 40000 | 240000 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable power supply | [6 empty] | 10716008.2705 | 5933175.2421 | 16649183.5127 | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE//PVC 3Cx2.5mm2 | 238 | 238 | m | 32518.74 | 7485.665 | 40004.405 | 7739460.12 | 1781588.27 | 9521048.39 | 36% | 0% | 36% |  |  | 0%
|  | PVC conduit D20 | 143 | 253 | m | 8773.9726 | 14594.0164 | 23367.989 | 2219815.0685 | 3692286.1522 | 5912101.2207 | 0% | 0% | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 29 | 55 | m | 3554.7229 | 5289.7059 | 8844.4288 | 195509.7606 | 290933.8235 | 486443.5841 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 561223.3215 | 168366.9964 | 729590.3179 | 561223.3215 | 168366.9964 | 729590.3179 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
2. 2. 110. |  | Fire alarm system | 1 | 1 | PSCH |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
2. 2. 120. |  | Network infrastructure | 1 | 1 | PSCH |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
2. 2. 130. |  | Access control preparation | 1 | 1 | PSCH |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
2. 2. 140. |  | CCTV System | 1 | 1 | PSCH |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. |  | Office, Social and Technical Areas (Hall 3) | [6 empty] | 8556494945.4536 | 444494571.6059 | 9000989517.0595 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. |  | Electrical engineering | 1 | 1 | PSCH |  |  |  | 8556494945.4536 | 444494571.6059 | 9000989517.0595 | 0% | 0% | 0% |  |  | 0%
3. 2. 10. |  | Rennovation existing grounding system and lightning protection | 1 | 1 | psch | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 2. 20. |  | Rennovation existing grounding and equipotential bonding | 1 | 1 | psch | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 2. 30. |  | Main Power supply | 1 | 1 | PSCH |  |  |  | 4272504384.025 | 197907035.9748 | 4470411419.9998 | 0% | 0% | 0% |  |  | 0%
|  | Electrical panel | [6 empty] | 2486429270 | 40937031 | 2527366301 | 0% | 0% | 0% |  |  | 0%
|  | Modify SYN - TR1, Add ACB 4P 2250A, 85ka, fixed type | 1 | 1 | pcs | 243347500 | 1400000 | 244747500 | 243347500 | 1400000 | 244747500 | 0% | 0% | 0% |  |  | 0%
|  | Building3_BMDP min 1500kVA | 1 | 1 | pcs | 581849400 | 3920000 | 585769400 | 581849400 | 3920000 | 585769400 | 0% | 0% | 0% |  |  | 0%
|  | Building 3_PDP 1.0 | 1 | 1 | pcs | 137478000 | 1400000 | 138878000 | 137478000 | 1400000 | 138878000 | 0% | 0% | 0% |  |  | 0%
|  | Building 3_PDP 1.1 | 1 | 1 | pcs | 124835700 | 1400000 | 126235700 | 124835700 | 1400000 | 126235700 | 0% | 0% | 0% |  |  | 0%
|  | Building 3_PDP 2.0 | 1 | 1 | pcs | 137478000 | 1400000 | 138878000 | 137478000 | 1400000 | 138878000 | 0% | 0% | 0% |  |  | 0%
|  | Building 3_PDP 1.2 | 1 | 1 | pcs | 160848600 | 1400000 | 162248600 | 160848600 | 1400000 | 162248600 | 0% | 0% | 0% |  |  | 0%
|  | Building 3_PDP 2.1 | 1 | 1 | pcs | 162050900 | 1400000 | 163450900 | 162050900 | 1400000 | 163450900 | 0% | 0% | 0% |  |  | 0%
|  | Building 3_BDP 1.0 | 1 | 1 | pcs | 113520000 | 1400000 | 114920000 | 113520000 | 1400000 | 114920000 | 0% | 0% | 0% |  |  | 0%
|  | Building 3_BDP 1.1 | 1 | 1 | pcs | 232601600 | 1400000 | 234001600 | 232601600 | 1400000 | 234001600 | 0% | 0% | 0% |  |  | 0%
|  | Building 3_BDP 2.0 | 1 | 1 | pcs | 246041400 | 1400000 | 247441400 | 246041400 | 1400000 | 247441400 | 0% | 0% | 0% |  |  | 0%
|  | Scooter garage__BDP 1.0 | 1 | 1 | pcs | 15643100 | 840000 | 16483100 | 15643100 | 840000 | 16483100 | 0% | 0% | 0% |  |  | 0%
|  | Canteen__BDP 1.0 | 1 | 1 | pcs | 47347300 | 1400000 | 48747300 | 47347300 | 1400000 | 48747300 | 0% | 0% | 0% |  |  | 0%
|  | Building 3_DB SEF 1 | 1 | 1 | pcs | 28968500 | 840000 | 29808500 | 28968500 | 840000 | 29808500 | 0% | 0% | 0% |  |  | 0%
|  | Building 3_DB SEF 2 | 1 | 1 | pcs | 24835800 | 840000 | 25675800 | 24835800 | 840000 | 25675800 | 0% | 0% | 0% |  |  | 0%
|  | Building 3_UPS1-MDP | 1 | 1 | pcs | 91081100 | 1400000 | 92481100 | 91081100 | 1400000 | 92481100 | 0% | 0% | 0% |  |  | 0%
|  | Building UPS1-DP1.2 | 1 | 1 | pcs | 79290200 | 1400000 | 80690200 | 79290200 | 1400000 | 80690200 | 0% | 0% | 0% |  |  | 0%
|  | Building 3_UPS 1-DP 1.2 | 1 | 1 | pcs | 10457700 | 840000 | 11297700 | 10457700 | 840000 | 11297700 | 0% | 0% | 0% |  |  | 0%
|  | Building 3_UPS 1 DP 1.3 | 1 | 1 | pcs | 8309400 | 840000 | 9149400 | 8309400 | 840000 | 9149400 | 0% | 0% | 0% |  |  | 0%
|  | Building 3_UPS 1 DP 1.3 35kVA | 1 | 1 | pcs | 70643100 | 1400000 | 72043100 | 70643100 | 1400000 | 72043100 | 0% | 0% | 0% |  |  | 0%
|  | Building 3 UPS2-MD | 1 | 1 | pcs | 79290200 | 1400000 | 80690200 | 79290200 | 1400000 | 80690200 | 0% | 0% | 0% |  |  | 0%
|  | Building UPS2-DP1.2 | 1 | 1 | pcs | 10457700 | 840000 | 11297700 | 10457700 | 840000 | 11297700 | 0% | 0% | 0% |  |  | 0%
|  | Building 3_UPS 2-DP1.2 | 1 | 1 | pcs | 8309400 | 840000 | 9149400 | 8309400 | 840000 | 9149400 | 0% | 0% | 0% |  |  | 0%
|  | Building 3_UPS 2 DP 1.3 | 1 | 1 | pcs | 8309400 | 840000 | 9149400 | 8309400 | 840000 | 9149400 | 0% | 0% | 0% |  |  | 0%
|  | Building 3_UPS 2 DP 1.3 35kVA | 1 | 1 | pcs | 71126000 | 1400000 | 72526000 | 71126000 | 1400000 | 72526000 | 0% | 0% | 0% |  |  | 0%
|  | Building 3_DP PUMP 1 | 1 |  | pcs | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Building 3_DP PUMP 2 | 1 |  | pcs | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Fitting and accessories | 1 | 1 | lot | 35656770 | 10697031 | 46353801 | 35656770 | 10697031 | 46353801 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable trays_Hot dip-Galvanized Steel | [6 empty] | 982315957 | 122770928.7283 | 1105086885.7283 | 0% | 0% | 0% |  |  | 0%
|  | Cable tray 500x100x2.0mm | 0 | 0 | m | 1443780 | 81001.3848 | 1524781.3848 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable tray 300x100x2.0mm | 0 | 0 | m | 1009710 | 61078.452 | 1070788.452 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable tray 200x100x2.0mm | 0 | 0 | m | 776880 | 51045.8655 | 827925.8655 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable tray 500x100 with separating bar, c/w cover | 0 | 93 | m | 1525680 | 81001.3848 | 1606681.3848 | 141888240 | 7533128.7822 | 149421368.7822 | 25% | 20% | 45% |  |  | 25%
|  | Cable tray 400x100 with separating bar, c/w cover | 0 | 0 | m | 826020 | 68320 | 894340 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable tray 300x100 with separating bar, c/w cover | 0 | 0 | m | 1091610 | 61078.452 | 1152688.452 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable tray 200x100 with separating bar, c/w cover | 0 | 0 | m | 858780 | 51045.8655 | 909825.8655 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable tray 600x50 with separating bar, c/w cover | 26 | 28.6 | m | 1568970 | 87472 | 1656442 | 44872542 | 2501699.2 | 47374241.2 | 25% | 20% | 45% |  |  | 25%
|  | Cable tray 500x50 with separating bar, c/w cover | 6 | 6.6 | m | 1334970 | 81001.3848 | 1415971.3848 | 8810802 | 534609.1394 | 9345411.1394 | 25% | 20% | 45% |  |  | 25%
|  | Cable tray 400x50 with separating bar, c/w cover | 165 | 183.7 | m | 1136070 | 68320 | 1204390 | 208696059 | 12550384 | 221246443 | 25% | 20% | 45% |  |  | 25%
|  | Cable tray 200x50 with separating bar, c/w cover | 303 | 453.2 | m | 669240 | 51045.8655 | 720285.8655 | 303299568 | 23133986.2319 | 326433554.2319 | 25% | 20% | 45% |  |  | 25%
|  | Cable tray 100x50 with separating bar, c/w cover | 14 | 15.4 | m | 469170 | 51045.8655 | 520215.8655 | 7225218 | 786106.3283 | 8011324.3283 | 25% | 20% | 45% |  |  | 25%
|  | Cable ladder 600x100x2.0mm, c/w cover | 0 | 0 | m | 1199250 | 91952 | 1291202 | 0 | 0 | 0 | 25% | 20% | 45% |  |  | 25%
|  | Cable ladder 500x100x2.0mm, c/w cover | 2 | 2.2 | m | 1067040 | 81001.3848 | 1148041.3848 | 2347488 | 178203.0465 | 2525691.0465 | 25% | 20% | 45% |  |  | 25%
|  | Cable ladder 400x100x2.0mm, c/w cover | 0 | 0 | m | 933660 | 68320 | 1001980 | 0 | 0 | 0 | 25% | 20% | 45% |  |  | 25%
|  | Cable ladder 300x100x1.5mm, c/w cover | 0 | 0 | m | 625950 | 61078.452 | 687028.452 | 0 | 0 | 0 | 25% | 20% | 45% |  |  | 25%
|  | Cable ladder 200x100x1.5mm, c/w cover | 0 | 0 | m | 496080 | 51045.8655 | 547125.8655 | 0 | 0 | 0 | 25% | 20% | 45% |  |  | 25%
|  | Fitting and accessories | 1 | 1 | lot | 245176040 | 73552812 | 318728852 | 245176040 | 73552812 | 318728852 | 25% | 20% | 45% |  |  | 25%
|  | Fire stop | 1 | 1 | set | 20000000 | 2000000 | 22000000 | 20000000 | 2000000 | 22000000 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Lighting control panel | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | BDP 1.0 | [6 empty] | 97882510.475 | 7025037.0385 | 104907547.5135 | 0% | 0% | 0% |  |  | 0%
|  | 8P smart key, white plastic surface material | 1 | 1 | pcs | 17060781.92 | 137500 | 17198281.92 | 17060781.92 | 137500 | 17198281.92 | 0% | 0% | 0% |  |  | 0%
|  | 4P smart key, white plastic surface material | 2 | 2 | pcs | 13652800 | 137500 | 13790300 | 27305600 | 275000 | 27580600 | 0% | 0% | 0% |  |  | 0%
|  | Smart light control device for 8 independent load groups - 16A/ K | 1 | 1 | pcs | 19992667.52 | 49500 | 20042167.52 | 19992667.52 | 49500 | 20042167.52 | 0% | 0% | 0% |  |  | 0%
|  | Smart light control device for 4 independent load groups - 16A/ K | 1 | 1 | pcs | 14090720 | 49500 | 14140220 | 14090720 | 49500 | 14140220 | 0% | 0% | 0% |  |  | 0%
|  | Power supply for control signals, 24VDC | 2 | 2 | pcs | 8376816 | 49500 | 8426316 | 16753632 | 99000 | 16852632 | 0% | 0% | 0% |  |  | 0%
|  | Base for smart keys | 3 | 3 | pcs | 41884.08 | 49500 | 91384.08 | 125652.24 | 148500 | 274152.24 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 2553456.795 | 766037.0385 | 3319493.8335 | 2553456.795 | 766037.0385 | 3319493.8335 | 0% | 0% | 0% |  |  | 0%
|  | T&C | 1 | 1 | lot | 0 | 5500000 | 5500000 | 0 | 5500000 | 5500000 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | BDP 1.1 | [6 empty] | 162133437.125 | 10750870.3775 | 172884307.5025 | 0% | 0% | 0% |  |  | 0%
|  | 8P smart key, white plastic surface material | 3 | 3 | pcs | 17060781.92 | 137500 | 17198281.92 | 51182345.76 | 412500 | 51594845.76 | 0% | 0% | 0% |  |  | 0%
|  | 4P smart key, white plastic surface material | 2 | 2 | pcs | 13652800 | 137500 | 13790300 | 27305600 | 275000 | 27580600 | 0% | 0% | 0% |  |  | 0%
|  | Smart light control device for 8 independent load groups - 16A/ K | 2 | 2 | pcs | 19992667.52 | 49500 | 20042167.52 | 39985335.04 | 99000 | 40084335.04 | 0% | 0% | 0% |  |  | 0%
|  | Smart light control device for 4 independent load groups - 16A/ K | 1 | 1 | pcs | 14090720 | 49500 | 14140220 | 14090720 | 49500 | 14140220 | 0% | 0% | 0% |  |  | 0%
|  | Power supply for control signals, 24VDC | 3 | 3 | pcs | 8376816 | 49500 | 8426316 | 25130448 | 148500 | 25278948 | 0% | 0% | 0% |  |  | 0%
|  | Base for smart keys | 5 | 5 | pcs | 41884.08 | 49500 | 91384.08 | 209420.4 | 247500 | 456920.4 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 4229567.925 | 1268870.3775 | 5498438.3025 | 4229567.925 | 1268870.3775 | 5498438.3025 | 0% | 0% | 0% |  |  | 0%
|  | T&C | 1 | 1 | lot | 0 | 8250000 | 8250000 | 0 | 8250000 | 8250000 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | BDP 2.0 | [6 empty] | 290635290.425 | 12702537.0555 | 303337827.4805 | 0% | 0% | 0% |  |  | 0%
|  | 8P smart key, white plastic surface material | 7 | 7 | pcs | 17060781.92 | 137500 | 17198281.92 | 119425473.44 | 962500 | 120387973.44 | 0% | 0% | 0% |  |  | 0%
|  | 4P smart key, white plastic surface material | 2 | 2 | pcs | 13652800 | 137500 | 13790300 | 27305600 | 275000 | 27580600 | 0% | 0% | 0% |  |  | 0%
|  | Smart light control device for 8 independent load groups - 16A/ K | 4 | 4 | pcs | 19992667.52 | 49500 | 20042167.52 | 79970670.08 | 198000 | 80168670.08 | 0% | 0% | 0% |  |  | 0%
|  | Smart light control device for 4 independent load groups - 16A/ K | 1 | 1 | pcs | 14090720 | 49500 | 14140220 | 14090720 | 49500 | 14140220 | 0% | 0% | 0% |  |  | 0%
|  | Power supply for control signals, 24VDC | 5 | 5 | pcs | 8376816 | 49500 | 8426316 | 41884080 | 247500 | 42131580 | 0% | 0% | 0% |  |  | 0%
|  | Base for smart keys | 9 | 9 | pcs | 41884.08 | 49500 | 91384.08 | 376956.72 | 445500 | 822456.72 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 7581790.185 | 2274537.0555 | 9856327.2405 | 7581790.185 | 2274537.0555 | 9856327.2405 | 0% | 0% | 0% |  |  | 0%
|  | T&C | 1 | 1 | lot | 0 | 8250000 | 8250000 | 0 | 8250000 | 8250000 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable power supply | [6 empty] | 9760419 | 2320631.775 | 12081050.775 | 0% | 0% | 0% |  |  | 0%
|  | From Building 3_BDP 1.1 Panel to DB-PUMP1 | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 4x1Cx4mm2+E4mm2 | 71 | 64 | m | 72299.4 | 17189.865 | 89489.265 | 4627161.6 | 1100151.36 | 5727312.96 | 36% | 0% | 36% |  |  | 0%
|  | From Building 3_BDP 2.0 Panel to DB-PUMP2 | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 4x1Cx4mm2+E4mm2 | 71 | 71 | m | 72299.4 | 17189.865 | 89489.265 | 5133257.4 | 1220480.415 | 6353737.815 | 36% | 0% | 36% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. 40. |  | Uninterrupted power supply (UPS) | 1 | 1 | PSCH |  |  |  | 2008718012.8938 | 15050660.8087 | 2023768673.7025 | 0% | 0% | 0% |  |  | 0%
|  | UPS 93PR 60kW*100%load, backup 15 Minutes, frame 125kw | 2 | 2 | set | 967016600 | 3300000 | 970316600 | 1934033200 | 6600000 | 1940633200 | 0% | 0% | 0% |  |  | 0%
|  | 93PR 125kW Frame to contain up to max. 6 Power Modules, Back-Feed, MBS & 1 x internal PDU | 0 | 0 |  | 310491720 | 0 | 310491720 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | 93PR Power Module of 25KW capacity (Rev B) | 0 | 0 |  | 101372040 | 0 | 101372040 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Industrial Gateway Card | 0 | 0 |  | 9882180 | 0 | 9882180 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Eaton battery backup 15 mins @ 75kW | 0 | 0 |  | 6021400 | 0 | 6021400 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Battery cabinet, MCB, cable to connect Battery to UPS and accesoriess. | 0 | 0 |  | 99429000 | 0 | 99429000 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 10000000 | 2000000 | 12000000 | 10000000 | 2000000 | 12000000 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | water leak warning system | 2 | 2 | lot |  |  |  | 64684812.8938 | 6450660.8087 | 71135473.7025 | 0% | 0% | 0% |  |  | 0%
|  | Water leak detector | 4 | 4 | pcs | 1587000 | 49500 | 1636500 | 6348000 | 198000 | 6546000 | 0% | 0% | 0% |  |  | 0%
|  | Cabinet for Water leak detector | 4 | 4 | pcs | 1725000 | 220000 | 1945000 | 6900000 | 880000 | 7780000 | 0% | 0% | 0% |  |  | 0%
|  | Power supply | 4 | 4 | pcs | 862500 | 165000 | 1027500 | 3450000 | 660000 | 4110000 | 0% | 0% | 0% |  |  | 0%
|  | water leak cable | 140 | 120 | m | 317400 | 22000 | 339400 | 38088000 | 2640000 | 40728000 | 0% | 0% | 0% |  |  | 0%
|  | Connection conductor A-LLW58; wire holder permanent | 4 | 4 | pcs | 1269600 | 49500 | 1319100 | 5078400 | 198000 | 5276400 | 0% | 0% | 0% |  |  | 0%
|  | Single Socket 1P-16A-250V | 4 | 4 | pcs | 124560 | 54500 | 179060 | 498240 | 218000 | 716240 | 0% | 0% | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 60 | 51 | m | 22980.09 | 5743.9305 | 28724.0205 | 1171984.59 | 292940.4555 | 1464925.0455 | 36% | 0% | 36% |  |  | 0%
|  | PVC conduit D20 | 58 | 35 | m | 8773.9726 | 14594.0164 | 23367.989 | 307089.0411 | 510790.5744 | 817879.6155 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 2843099.2627 | 852929.7788 | 3696029.0415 | 2843099.2627 | 852929.7788 | 3696029.0415 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. 50. |  | Electrical Capacitor bank | 1 | 1 | PSCH |  |  |  | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Electrical Capacitor bank Building3_BMDP min 1500kVA | 1 |  | pcs | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. 60. |  | Power supply of building utilities | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. 70. |  | Energy measurement system | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. 80. |  | Electrical installation in offices and meeting rooms | 1 | 1 | PSCH |  |  |  | 1229075412.0457 | 66404103.9782 | 1295479516.0239 | 0% | 0% | 0% |  |  | 0%
|  | Switch & Socket | [6 empty] | 221333361.2618 | 14243567.4985 | 235576928.7604 | 0% | 0% | 0% |  |  | 0%
|  | 1-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Push-button - (switch) | 37 | 37 | pcs | 223200 | 54500 | 277700 | 8258400 | 2016500 | 10274900 | 0% | 0% | 0% |  |  | 0%
|  | Single Socket NEMA5 | 15 | 15 | pcs | 124560 | 54500 | 179060 | 1868400 | 817500 | 2685900 | 0% | 0% | 0% |  |  | 0%
|  | Double Socket NEMA5 | 15 | 15 | pcs | 249120 | 54500 | 303620 | 3736800 | 817500 | 4554300 | 0% | 0% | 0% |  |  | 0%
|  | Dimmer Switch | 6 | 6 | pcs | 254400 | 54500 | 308900 | 1526400 | 327000 | 1853400 | 0% | 0% | 0% |  |  | 0%
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cord outlet socket with 2m cable reserve with connection terminals, E1 | 6 | 6 | pcs | 507247.2 | 54500 | 561747.2 | 3043483.2 | 327000 | 3370483.2 | 0% | 0% | 0% |  |  | 0%
|  | Cord outlet socket with 4m cable reserve with connection terminals, E2 | 0 | 0 | pcs | 507247.2 | 54500 | 561747.2 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cord outlet socket with 6m cable reserve with connection terminals, E3 | 33 | 33 | pcs | 507247.2 | 54500 | 561747.2 | 16739157.6 | 1798500 | 18537657.6 | 0% | 0% | 0% |  |  | 0%
|  | Floor box, recessed (3xDouble Socket NEMA5, 2xIT - Double socket) | 3 | 3 | pcs | 8885676 | 272500 | 9158176 | 26657028 | 817500 | 27474528 | 0% | 0% | 0% |  |  | 0%
|  | Floor box, recessed (4xDouble Socket NEMA5, 2xIT - Double socket) | 1 | 1 | pcs | 9467332.8 | 272500 | 9739832.8 | 9467332.8 | 272500 | 9739832.8 | 0% | 0% | 0% |  |  | 0%
|  | Floor box, recessed (1xDouble Socket NEMA5, 1xIT - Double socket,1x HDMI connection to the projector) | 3 | 3 | pcs | 9216914.4 | 272500 | 9489414.4 | 27650743.2 | 817500 | 28468243.2 | 0% | 0% | 0% |  |  | 0%
|  | Floor box, recessed (2xDouble Socket NEMA5, 2xIT - Double socket, 1x HDMI connection to the projector) | 1 | 1 | pcs | 10490947.2 | 272500 | 10763447.2 | 10490947.2 | 272500 | 10763447.2 | 0% | 0% | 0% |  |  | 0%
|  | Floor box, recessed (3xDouble Socket NEMA5, 2xIT - Double socket, 1x HDMI connection to the projector) | 0 | 0 | pcs | 11072604 | 272500 | 11345104 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Floor box, recessed (4xDouble Socket NEMA5, 2xIT - Double socket, 1x HDMI connection to the projector) | 2 | 2 | pcs | 11654260.8 | 272500 | 11926760.8 | 23308521.6 | 545000 | 23853521.6 | 0% | 0% | 0% |  |  | 0%
|  | Projector + Accessories | 3 | 3 | pcs | 18650000 | 381500 | 19031500 | 55950000 | 1144500 | 57094500 | 0% | 0% | 0% |  |  | 0%
|  | Motion sensor | 19 | 19 | pcs | 1150224 | 54500 | 1204724 | 21854256 | 1035500 | 22889756 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 10781891.6618 | 3234567.4985 | 14016459.1604 | 10781891.6618 | 3234567.4985 | 14016459.1604 | 0% | 0% | 0% |  |  | 0%
|  |  | 0 | 0 | [7 empty] | 0% | 0% | 0% |  |  | 0%
|  | Lighting | 0 | 0 |  |  |  |  | 643593600 | 11842000 | 655435600 | 0% | 0% | 0% |  |  | 0%
|  | LED Panel 36W, Type AI | 168 | 168 | pcs | 3339600 | 56000 | 3395600 | 561052800 | 9408000 | 570460800 | 0% | 0% | 0% |  |  | 0%
|  | LED Panel 36W, Type AI - Dali Dim | 23 | 23 | pcs | 3339600 | 56000 | 3395600 | 76810800 | 1288000 | 78098800 | 0% | 0% | 0% |  |  | 0%
|  | LED Frame Lamp 1x46W, Type BII | 0 | 0 | pcs | 1607100 | 56000 | 1663100 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 56000 | 641200 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 5730000 | 1146000 | 6876000 | 5730000 | 1146000 | 6876000 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable power | [6 empty] | 364148450.7839 | 40318536.4797 | 404466987.2635 | 0% | 0% | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 1142 | 1002 | m | 22980.09 | 5743.9305 | 28724.0205 | 23026050.18 | 5755418.361 | 28781468.541 | 36% | 0% | 36% |  |  | 0%
|  | 3C-2.5mm2 Cu/XLPE/PVC | 630 | 570 | m | 32518.74 | 7485.665 | 40004.405 | 18535681.8 | 4266829.05 | 22802510.85 | 36% | 0% | 36% |  |  | 0%
|  | 3C-2.5mm2 Cu/XLPE/PVC for E1, E2, E3 | 303 | 303 | m | 32518.74 | 7485.665 | 40004.405 | 9853178.22 | 2268156.495 | 12121334.715 | 36% | 0% | 36% |  |  | 0%
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 0 | 0 | m | 72299.4 | 17189.865 | 89489.265 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 0 | 0 | m | 102372.9 | 18573.4395 | 120946.3395 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Dado duct 50x130mm | 296 | 296 | m | 985945.6609 | 53025 | 1038970.6609 | 291839915.6313 | 15695400 | 307535315.6313 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 507 | 507 | m | 8773.9726 | 14594.0164 | 23367.989 | 4448404.1096 | 7399166.3208 | 11847570.4304 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 16445220.843 | 4933566.2529 | 21378787.0959 | 16445220.843 | 4933566.2529 | 21378787.0959 | 0% | 0% | 0% |  |  | 0%
|  |  | 0 | 0 | [7 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. 90. |  | Electrical installation in social rooms | 1 | 1 | PSCH |  |  |  | 258752977.5651 | 35385729.898 | 294138707.4631 | 0% | 0% | 0% |  |  | 0%
|  | Switch & Socket | [6 empty] | 10372584.6 | 3183623.38 | 13556207.98 | 0% | 0% | 0% |  |  | 0%
|  | 1-Way switch, 1 gang | 2 | 2 | pcs | 46800 | 54500 | 101300 | 93600 | 109000 | 202600 | 0% | 0% | 0% |  |  | 0%
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Single Socket NEMA5 | 29 | 29 | pcs | 124560 | 54500 | 179060 | 3612240 | 1580500 | 5192740 | 0% | 0% | 0% |  |  | 0%
|  | Double Socket NEMA5 | 25 | 25 | pcs | 249120 | 54500 | 303620 | 6228000 | 1362500 | 7590500 | 0% | 0% | 0% |  |  | 0%
|  | Power outlet general, 3p/4W, grounded | 0 | 0 | pcs | 150480 | 54500 | 204980 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 438744.6 | 131623.38 | 570367.98 | 438744.6 | 131623.38 | 570367.98 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Lighting | [6 empty] | 180626800 | 8680000 | 189306800 | 0% | 0% | 0% |  |  | 0%
|  | LED Panel 36W, Type AI | 0 | 0 | pcs | 3339600 | 56000 | 3395600 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | LED Frame Lamp 1x30W, Type BI | 56 | 56 | pcs | 1346400 | 56000 | 1402400 | 75398400 | 3136000 | 78534400 | 0% | 0% | 0% |  |  | 0%
|  | LED Frame Lamp 1x46W, Type BII | 4 | 4 | pcs | 1607100 | 56000 | 1663100 | 6428400 | 224000 | 6652400 | 0% | 0% | 0% |  |  | 0%
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 56000 | 641200 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | LED Ceiling mounted Light 1x19W, Type D | 80 | 80 | pcs | 1182500 | 56000 | 1238500 | 94600000 | 4480000 | 99080000 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 4200000 | 840000 | 5040000 | 4200000 | 840000 | 5040000 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable power | [6 empty] | 67753592.9651 | 23522106.518 | 91275699.4831 | 0% | 0% | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 1187 | 1492.7 | m | 22980.09 | 5743.9305 | 28724.0205 | 34302380.343 | 8573965.0574 | 42876345.4004 | 36% | 0% | 36% |  |  | 0%
|  | 3C-2.5mm2 Cu/XLPE/PVC | 690 | 792 | m | 32518.74 | 7485.665 | 40004.405 | 25754842.08 | 5928646.68 | 31683488.76 | 36% | 0% | 36% |  |  | 0%
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 0 | 0 | m | 72299.4 | 17189.865 | 89489.265 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 0 | 0 | m | 102372.9 | 18573.4395 | 120946.3395 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Dado duct 50x130mm | 0 | 0 | m | 985945.6609 | 53025 | 1038970.6609 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 703 | 561 | m | 8773.9726 | 14594.0164 | 23367.989 | 4922198.6301 | 8187243.207 | 13109441.8371 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 2774171.912 | 832251.5736 | 3606423.4856 | 2774171.912 | 832251.5736 | 3606423.4856 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. 100. |  | Electrical installation in corridors and stairways | 1 | 1 | PSCH |  |  |  | 74974338.2247 | 17389802.6953 | 92364140.92 | 0% | 0% | 0% |  |  | 0%
|  | Switch & Socket | [6 empty] | 13582018.8 | 4641349.64 | 18223368.44 | 0% | 0% | 0% |  |  | 0%
|  | 1-Way switch, 1 gang | 6 | 6 | pcs | 46800 | 54500 | 101300 | 280800 | 327000 | 607800 | 0% | 0% | 0% |  |  | 0%
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Push-button switch | 32 | 32 | pcs | 223200 | 54500 | 277700 | 7142400 | 1744000 | 8886400 | 0% | 0% | 0% |  |  | 0%
|  | Single Socket NEMA5 | 12 | 12 | pcs | 124560 | 54500 | 179060 | 1494720 | 654000 | 2148720 | 0% | 0% | 0% |  |  | 0%
|  | Double Socket NEMA5 | 0 | 0 | pcs | 249120 | 54500 | 303620 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Power outlet general, 1p/2W, grounded | 4 | 4 | pcs | 150480 | 54500 | 204980 | 601920 | 218000 | 819920 | 0% | 0% | 0% |  |  | 0%
|  | Power outlet general, 3p/4W, grounded | 0 | 0 | pcs | 150480 | 54500 | 204980 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Single Socket 16A/230V, Lighting outlet general (wall) + Plug | 28 | 28 | pcs | 124560 | 54500 | 179060 | 3487680 | 1526000 | 5013680 | 0% | 0% | 0% |  |  | 0%
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 574498.8 | 172349.64 | 746848.44 | 574498.8 | 172349.64 | 746848.44 | 0% | 0% | 0% |  |  | 0%
|  |  | 0 | 0 | [7 empty] | 0% | 0% | 0% |  |  | 0%
|  | Lighting | 0 | 0 |  |  |  |  | 40385700 | 2790000 | 43175700 | 0% | 0% | 0% |  |  | 0%
|  | LED Panel 36W, Type AI | 0 | 0 | pcs | 3339600 | 56000 | 3395600 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | LED Frame Lamp 1x30W, Type BI | 0 | 0 | pcs | 1346400 | 56000 | 1402400 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | LED Frame Lamp 1x46W, Type BII for Canopy | 6 | 6 | pcs | 1607100 | 56000 | 1663100 | 9642600 | 336000 | 9978600 | 0% | 0% | 0% |  |  | 0%
|  | Wall mounted Light 1x15W, Type E | 28 | 28 | pcs | 585200 | 56000 | 641200 | 16385600 | 1568000 | 17953600 | 0% | 0% | 0% |  |  | 0%
|  | LED Ceiling mounted Light 1x19W, Type D | 16 | 11 | pcs | 1182500 | 56000 | 1238500 | 13007500 | 616000 | 13623500 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 0 | 1 | lot | 1350000 | 270000 | 1620000 | 1350000 | 270000 | 1620000 | 0% | 0% | 0% |  |  | 0%
|  |  | 0 | 0 | [7 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable power | 0 | 0 |  |  |  |  | 21006619.4247 | 9958453.0553 | 30965072.48 | 0% | 0% | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 478 | 450 | m | 22980.09 | 5743.9305 | 28724.0205 | 10341040.5 | 2584768.725 | 12925809.225 | 36% | 0% | 36% |  |  | 0%
|  | 3C-2.5mm2 Cu/XLPE/PVC | 217 | 190 | m | 32518.74 | 7485.665 | 40004.405 | 6178560.6 | 1422276.35 | 7600836.95 | 36% | 0% | 36% |  |  | 0%
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 0 | 0 | m | 72299.4 | 17189.865 | 89489.265 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 0 | 0 | m | 102372.9 | 18573.4395 | 120946.3395 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Dado duct 50x130mm | 0 | 0 | m | 985945.6609 | 53025 | 1038970.6609 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 384 | 385 | m | 8773.9726 | 14594.0164 | 23367.989 | 3377979.4521 | 5618696.3185 | 8996675.7706 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 1109038.8726 | 332711.6618 | 1441750.5344 | 1109038.8726 | 332711.6618 | 1441750.5344 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. 110. |  | Electrical installation in technical areas | 1 | 1 | PSCH |  |  |  | 86058509.2699 | 9713896.6252 | 95772405.895 | 0% | 0% | 0% |  |  | 0%
|  | Switch & Socket | [6 empty] | 2553112.8 | 2375897.84 | 4929010.64 | 0% | 0% | 0% |  |  | 0%
|  | 1-Way switch, 1 gang | 7 | 7 | pcs | 46800 | 54500 | 101300 | 327600 | 381500 | 709100 | 0% | 0% | 0% |  |  | 0%
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Single Socket NEMA5 | 13 | 13 | pcs | 124560 | 54500 | 179060 | 1619280 | 708500 | 2327780 | 0% | 0% | 0% |  |  | 0%
|  | Double Socket NEMA5 | 2 | 2 | pcs | 249120 | 54500 | 303620 | 498240 | 109000 | 607240 | 0% | 0% | 0% |  |  | 0%
|  | Power outlet general, 3p/4W, grounded | 0 | 0 | pcs | 150480 | 54500 | 204980 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Single Socket 16A/230V, Lighting outlet general (wall) + Plug | 0 | 0 | pcs | 124560 | 54500 | 179060 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Socket combination type 1 | 3 | 3 | pcs | 0 | 381500 | 381500 | 0 | 1144500 | 1144500 | 0% | 0% | 0% |  |  | 0%
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 107992.8 | 32397.84 | 140390.64 | 107992.8 | 32397.84 | 140390.64 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Lighting | [6 empty] | 68830900 | 2170000 | 71000900 | 0% | 0% | 0% |  |  | 0%
|  | LED Panel 36W, Type AI | 0 | 0 | pcs | 3339600 | 56000 | 3395600 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | LED Frame Lamp 1x30W, Type BI | 0 | 0 | pcs | 1346400 | 56000 | 1402400 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | LED Frame Lamp 1x46W, Type BII | 28 | 28 | pcs | 1607100 | 56000 | 1663100 | 44998800 | 1568000 | 46566800 | 0% | 0% | 0% |  |  | 0%
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 56000 | 641200 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | LED Ceiling mounted Light 1x19W, Type D | 0 | 0 | pcs | 1182500 | 56000 | 1238500 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Battery-operated hand lamp | 7 | 7 | pcs | 3254585.7143 | 56000 | 3310585.7143 | 22782100 | 392000 | 23174100 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 1050000 | 210000 | 1260000 | 1050000 | 210000 | 1260000 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable power | [6 empty] | 14674496.4699 | 5167998.7852 | 19842495.255 | 0% | 0% | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 167 | 150 | m | 22980.09 | 5743.9305 | 28724.0205 | 3447013.5 | 861589.575 | 4308603.075 | 36% | 0% | 36% |  |  | 0%
|  | 3C-2.5mm2 Cu/XLPE/PVC | 100 | 110 | m | 32518.74 | 7485.665 | 40004.405 | 3577061.4 | 823423.15 | 4400484.55 | 36% | 0% | 36% |  |  | 0%
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 0 | 0 | m | 72299.4 | 17189.865 | 89489.265 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 43 | 53.9 | m | 102372.9 | 18573.4395 | 120946.3395 | 5517899.31 | 1001108.3891 | 6519007.6991 | 36% | 0% | 36% |  |  | 0%
|  | Dado duct 50x130mm | 0 | 0 | m | 985945.6609 | 53025 | 1038970.6609 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 150 | 154 | m | 8773.9726 | 14594.0164 | 23367.989 | 1351191.7808 | 2247478.5274 | 3598670.3082 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 781330.479 | 234399.1437 | 1015729.6228 | 781330.479 | 234399.1437 | 1015729.6228 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. 120. |  | Electrical installation in kitchenette areas | 1 | 1 | PSCH |  |  |  | 92827708.5941 | 16840279.0483 | 109667987.6424 | 0% | 0% | 0% |  |  | 0%
|  | Switch & Socket | [6 empty] | 9916993.8 | 3613842.14 | 13530835.94 | 0% | 0% | 0% |  |  | 0%
|  | 1-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Single Socket NEMA5 | 47 | 47 | pcs | 124560 | 54500 | 179060 | 5854320 | 2561500 | 8415820 | 0% | 0% | 0% |  |  | 0%
|  | Double Socket NEMA5 | 11 | 11 | pcs | 249120 | 54500 | 303620 | 2740320 | 599500 | 3339820 | 0% | 0% | 0% |  |  | 0%
|  | Power outlet general, 3p/4W, grounded | 6 | 6 | pcs | 150480 | 54500 | 204980 | 902880 | 327000 | 1229880 | 0% | 0% | 0% |  |  | 0%
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 419473.8 | 125842.14 | 545315.94 | 419473.8 | 125842.14 | 545315.94 | 0% | 0% | 0% |  |  | 0%
|  |  | 0 | 0 | [7 empty] | 0% | 0% | 0% |  |  | 0%
|  | Lighting | 0 | 0 |  |  |  |  | 40075200 | 672000 | 40747200 | 0% | 0% | 0% |  |  | 0%
|  | LED Panel 36W, Type AI | 12 | 12 | pcs | 3339600 | 56000 | 3395600 | 40075200 | 672000 | 40747200 | 0% | 0% | 0% |  |  | 0%
|  | LED Frame Lamp 1x46W, Type BII | 0 | 0 | pcs | 1607100 | 56000 | 1663100 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 56000 | 641200 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 0 | 0 | lot | 240000 | 48000 | 288000 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  |  | 0 | 0 | [7 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable power | 0 | 0 |  |  |  |  | 42835514.7941 | 12554436.9083 | 55389951.7024 | 0% | 0% | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 196 | 210 | m | 22980.09 | 5743.9305 | 28724.0205 | 4825818.9 | 1206225.405 | 6032044.305 | 36% | 0% | 36% |  |  | 0%
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 501 | 480 | m | 72299.4 | 17189.865 | 89489.265 | 34703712 | 8251135.2 | 42954847.2 | 36% | 0% | 36% |  |  | 0%
|  | Dado duct 50x130mm | 0 | 0 | m | 985945.6609 | 53025 | 1038970.6609 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 120 | 176 | m | 8773.9726 | 14594.0164 | 23367.989 | 1544219.1781 | 2568546.8885 | 4112766.0666 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 1761764.716 | 528529.4148 | 2290294.1308 | 1761764.716 | 528529.4148 | 2290294.1308 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. 130. |  | Electrical installation for Workshop/Formbrettbau | 1 | 1 | PSCH |  |  |  | 90067954.1041 | 12614941.0865 | 102682895.1906 | 0% | 0% | 0% |  |  | 0%
|  | Switch & Socket | [6 empty] | 596177.4 | 1315565.22 | 1911742.62 | 0% | 0% | 0% |  |  | 0%
|  | 1-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Push-button switch | 2 | 2 | pcs | 223200 | 54500 | 277700 | 446400 | 109000 | 555400 | 0% | 0% | 0% |  |  | 0%
|  | Single Socket NEMA5 | 1 | 1 | pcs | 124560 | 54500 | 179060 | 124560 | 54500 | 179060 | 0% | 0% | 0% |  |  | 0%
|  | Double Socket NEMA5 | 0 | 0 | pcs | 249120 | 54500 | 303620 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Power outlet general, 3p/4W, grounded | 0 | 0 | pcs | 150480 | 54500 | 204980 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Socket combination type 2 | 3 | 3 | pcs | 0 | 381500 | 381500 | 0 | 1144500 | 1144500 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 25217.4 | 7565.22 | 32782.62 | 25217.4 | 7565.22 | 32782.62 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Lighting | [6 empty] | 52067200 | 1920000 | 53987200 | 0% | 0% | 0% |  |  | 0%
|  | LED Panel 36W, Type AI | 0 | 0 | pcs | 3339600 | 56000 | 3395600 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | LED Frame Lamp 1x46W, Type BII | 32 | 32 | pcs | 1607100 | 56000 | 1663100 | 51427200 | 1792000 | 53219200 | 0% | 0% | 0% |  |  | 0%
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 56000 | 641200 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 640000 | 128000 | 768000 | 640000 | 128000 | 768000 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable power | [6 empty] | 37404576.7041 | 9379375.8665 | 46783952.5706 | 0% | 0% | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 222 | 234 | m | 22980.09 | 5743.9305 | 28724.0205 | 5377341.06 | 1344079.737 | 6721420.797 | 36% | 0% | 36% |  |  | 0%
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 94 | 80 | m | 72299.4 | 17189.865 | 89489.265 | 5783952 | 1375189.2 | 7159141.2 | 36% | 0% | 36% |  |  | 0%
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 248 | 230 | m | 102372.9 | 18573.4395 | 120946.3395 | 23545767 | 4271891.085 | 27817658.085 | 36% | 0% | 36% |  |  | 0%
|  | Dado duct 50x130mm | 0 | 0 | m | 985945.6609 | 53025 | 1038970.6609 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 115 | 132 | m | 8773.9726 | 14594.0164 | 23367.989 | 1158164.3836 | 1926410.1664 | 3084574.5499 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 1539352.2605 | 461805.6782 | 2001157.9387 | 1539352.2605 | 461805.6782 | 2001157.9387 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. 140. |  | Electrical installation at the reception | 1 | 1 | PSCH |  |  |  | 41960735.3385 | 4068070.8188 | 46028806.1573 | 0% | 0% | 0% |  |  | 0%
|  | Switch & Socket | [6 empty] | 1915601.436 | 405808.1108 | 2321409.5468 | 0% | 0% | 0% |  |  | 0%
|  | 1-Way switch, 1 gang | 1 | 1 | pcs | 46800 | 54500 | 101300 | 46800 | 54500 | 101300 | 0% | 0% | 0% |  |  | 0%
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Single Socket NEMA5 | 1 | 1 | pcs | 124560 | 54500 | 179060 | 124560 | 54500 | 179060 | 0% | 0% | 0% |  |  | 0%
|  | Double Socket NEMA5 | 2 | 2 | pcs | 249120 | 54500 | 303620 | 498240 | 109000 | 607240 | 0% | 0% | 0% |  |  | 0%
|  | Power outlet general, 1p/2W, grounded | 1 | 1 | pcs | 150480 | 54500 | 204980 | 150480 | 54500 | 204980 | 0% | 0% | 0% |  |  | 0%
|  | Power outlet general, 3p/4W, grounded | 0 | 0 | pcs | 150480 | 54500 | 204980 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Socket combination type 1 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Socket combination type 2 | 0 | 0 | pcs | 0 | 381500 | 381500 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cord outlet socket with 2m cable reserve with connection terminals, E1 | 2 | 2 | pcs | 507247.2 | 54500 | 561747.2 | 1014494.4 | 109000 | 1123494.4 | 0% | 0% | 0% |  |  | 0%
|  | Cord outlet socket with 4m cable reserve with connection terminals, E2 | 0 | 0 | pcs | 507247.2 | 54500 | 561747.2 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cord outlet socket with 6m cable reserve with connection terminals, E3 | 0 | 0 | pcs | 507247.2 | 54500 | 561747.2 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 81027.036 | 24308.1108 | 105335.1468 | 81027.036 | 24308.1108 | 105335.1468 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Lighting | [6 empty] | 13438400 | 240000 | 13678400 | 0% | 0% | 0% |  |  | 0%
|  | LED Panel 36W, Type AI | 4 | 4 | pcs | 3339600 | 56000 | 3395600 | 13358400 | 224000 | 13582400 | 0% | 0% | 0% |  |  | 0%
|  | LED Frame Lamp 1x46W, Type BII | 0 | 0 | pcs | 1607100 | 56000 | 1663100 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 56000 | 641200 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 80000 | 16000 | 96000 | 80000 | 16000 | 96000 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable power | [6 empty] | 26606733.9025 | 3422262.708 | 30028996.6105 | 0% | 0% | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 60 | 55 | m | 22980.09 | 5743.9305 | 28724.0205 | 1263904.95 | 315916.1775 | 1579821.1275 | 36% | 0% | 36% |  |  | 0%
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 80 | 74.8 | m | 72299.4 | 17189.865 | 89489.265 | 5407995.12 | 1285801.902 | 6693797.022 | 36% | 0% | 36% |  |  | 0%
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 3 | 4.4 | m | 102372.9 | 18573.4395 | 120946.3395 | 450440.76 | 81723.1338 | 532163.8938 | 36% | 0% | 36% |  |  | 0%
|  | Dado duct 50x130mm | 18 | 18 | m | 985945.6609 | 53025 | 1038970.6609 | 17747021.8965 | 954450 | 18701471.8965 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 26 | 22 | m | 8773.9726 | 14594.0164 | 23367.989 | 193027.3973 | 321068.3611 | 514095.7583 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 1544343.7787 | 463303.1336 | 2007646.9124 | 1544343.7787 | 463303.1336 | 2007646.9124 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. 150. |  | Electrical installation in other rooms/secondary rooms | 1 | 1 | PSCH |  |  |  | 275591719.5806 | 31538420.0323 | 307130139.6129 | 0% | 0% | 0% |  |  | 0%
|  | Switch & Socket | [6 empty] | 15705304.986 | 4668293.1758 | 20373598.1618 | 0% | 0% | 0% |  |  | 0%
|  | 1-Way switch, 1 gang | 7 | 7 | pcs | 46800 | 54500 | 101300 | 327600 | 381500 | 709100 | 0% | 0% | 0% |  |  | 0%
|  | 2-Way switch, 1 gang | 0 | 0 | pcs | 46800 | 54500 | 101300 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Push-button switch | 9 | 9 | pcs | 223200 | 54500 | 277700 | 2008800 | 490500 | 2499300 | 0% | 0% | 0% |  |  | 0%
|  | Single Socket NEMA5 | 10 | 10 | pcs | 124560 | 54500 | 179060 | 1245600 | 545000 | 1790600 | 0% | 0% | 0% |  |  | 0%
|  | Double Socket NEMA5 | 9 | 9 | pcs | 249120 | 54500 | 303620 | 2242080 | 490500 | 2732580 | 0% | 0% | 0% |  |  | 0%
|  | Power outlet general, 1p/2W, grounded | 0 | 0 | pcs | 150480 | 54500 | 204980 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Power outlet general, 3p/4W, grounded | 0 | 0 | pcs | 150480 | 54500 | 204980 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Socket combination type 1 | 4 | 4 | pcs | 0 | 381500 | 381500 | 0 | 1526000 | 1526000 | 0% | 0% | 0% |  |  | 0%
|  | Socket combination type 2 | 2 | 2 | pcs | 0 | 381500 | 381500 | 0 | 763000 | 763000 | 0% | 0% | 0% |  |  | 0%
|  | Cord outlet socket with 2m cable reserve with connection terminals, E1 | 0 | 0 | pcs | 507247.2 | 54500 | 561747.2 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cord outlet socket with 4m cable reserve with connection terminals, E2 | 0 | 0 | pcs | 507247.2 | 54500 | 561747.2 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cord outlet socket with 6m cable reserve with connection terminals, E3 | 0 | 0 | pcs | 507247.2 | 54500 | 561747.2 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Floor box, recessed (1xDouble Socket NEMA5, 1xIT - Double socket,1x HDMI connection to the projector) | 1 | 1 | pcs | 9216914.4 | 272500 | 9489414.4 | 9216914.4 | 272500 | 9489414.4 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 664310.586 | 199293.1758 | 863603.7618 | 664310.586 | 199293.1758 | 863603.7618 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Lighting | [6 empty] | 135827400 | 4650000 | 140477400 | 0% | 0% | 0% |  |  | 0%
|  | LED Panel 36W, Type AI | 9 | 9 | pcs | 3339600 | 56000 | 3395600 | 30056400 | 504000 | 30560400 | 0% | 0% | 0% |  |  | 0%
|  | LED Frame Lamp 1x46W, Type BII | 58 | 60 | pcs | 1607100 | 56000 | 1663100 | 96426000 | 3360000 | 99786000 | 0% | 0% | 0% |  |  | 0%
|  | Wall mounted Light 1x15W, Type E | 0 | 0 | pcs | 585200 | 56000 | 641200 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | LED Ceiling mounted Light 1x19W, Type D | 6 | 6 | pcs | 1182500 | 56000 | 1238500 | 7095000 | 336000 | 7431000 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 2250000 | 450000 | 2700000 | 2250000 | 450000 | 2700000 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable power | [6 empty] | 124059014.5946 | 22220126.8565 | 146279141.4511 | 0% | 0% | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 693 | 684.5455 | m | 22980.09 | 5743.9305 | 28724.0205 | 15730916.1545 | 3931981.515 | 19662897.6695 | 36% | 0% | 36% |  |  | 0%
|  | 3C-2.5mm2 Cu/XLPE/PVC | 442 | 464 | m | 32518.74 | 7485.665 | 40004.405 | 15088695.36 | 3473348.56 | 18562043.92 | 36% | 0% | 36% |  |  | 0%
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 0 | 0 | m | 72299.4 | 17189.865 | 89489.265 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 317 | 280 | m | 102372.9 | 18573.4395 | 120946.3395 | 28664412 | 5200563.06 | 33864975.06 | 36% | 0% | 36% |  |  | 0%
|  | Dado duct 50x130mm | 57 | 57 | m | 985945.6609 | 53025 | 1038970.6609 | 56198902.6722 | 3022425 | 59221327.6722 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 278 | 341 | m | 8773.9726 | 14594.0164 | 23367.989 | 2991924.6575 | 4976559.5964 | 7968484.2539 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 5384163.7503 | 1615249.1251 | 6999412.8754 | 5384163.7503 | 1615249.1251 | 6999412.8754 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. 160. |  | Emergency lighting | 1 | 1 | PSCH |  |  |  | 125963193.8122 | 37581630.6399 | 163544824.4521 | 0% | 0% | 0% |  |  | 0%
|  | Switch & Socket | [6 empty] | 73296840 | 12022500 | 85319340 | 0% | 0% | 0% |  |  | 0%
|  | Emergency light | 81 | 81 | pcs | 516120 | 56000 | 572120 | 41805720 | 4536000 | 46341720 | 0% | 0% | 0% |  |  | 0%
|  | Exit light | 24 | 24 | pcs | 566280 | 56000 | 622280 | 13590720 | 1344000 | 14934720 | 0% | 0% | 0% |  |  | 0%
|  | Single Socket 16A/230V | 105 | 105 | pcs | 150480 | 54500 | 204980 | 15800400 | 5722500 | 21522900 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | pcs | 2100000 | 420000 | 2520000 | 2100000 | 420000 | 2520000 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable power supply | [6 empty] | 52666353.8122 | 25559130.6399 | 78225484.4521 | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 1575 | 1265 | m | 32518.74 | 7485.665 | 40004.405 | 41136206.1 | 9469366.225 | 50605572.325 | 36% | 0% | 36% |  |  | 0%
|  | PVC conduit D20 | 882 | 950 | m | 8773.9726 | 14594.0164 | 23367.989 | 8335273.9726 | 13864315.5912 | 22199589.5638 | 0% | 0% | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 315 | 300 | m | 3554.7229 | 5289.7059 | 8844.4288 | 1066416.876 | 1586911.7647 | 2653328.6407 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 2128456.8636 | 638537.0591 | 2766993.9226 | 2128456.8636 | 638537.0591 | 2766993.9226 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
4. |  | Machine hook-up (Hall 3) | [6 empty] | 3164184545.4338 | 446703070.7456 | 3610887616.1794 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
4. 1. |  | Electrical engineering | 1 | 1 | PSCH |  |  |  | 3164184545.4338 | 446703070.7456 | 3610887616.1794 | 0% | 0% | 0% |  |  | 0%
4. 1. 10. |  | Machine hook-up | 1 | 1 | PSCH |  |  |  | 3164184545.4338 | 446703070.7456 | 3610887616.1794 | 0% | 0% | 0% |  |  | 0%
|  | Cable trays_Hot dip-Galvanized Steel | [6 empty] | 538685840 | 65789758.3358 | 604475598.3358 | 0% | 0% | 0% |  |  | 0%
|  | Cable tray 400x100x2.0mm | 122 | 122 | m | 776880 | 68320 | 845200 | 94779360 | 8335040 | 103114400 | 30% | 40% | 70% |  |  | 30%
|  | Cable tray 500x100 with separating bar | 195 | 201 | m | 1525680 | 81001.3848 | 1606681.3848 | 306661680 | 16281278.3358 | 322942958.3358 | 30% | 40% | 70% |  |  | 30%
|  | Fitting and accessories | 1 | 1 | lot | 137244800 | 41173440 | 178418240 | 137244800 | 41173440 | 178418240 | 30% | 40% | 70% |  |  | 30%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Busway Canalis KSA 250A 3L+N+PE 10kA/s, IP54 | [6 empty] | 2002937565.0909 | 225436964.9679 | 2228374530.0588 | 0% | 0% | 0% |  |  | 0%
|  | 250A Feeder,3L+N+PE | 190 | 194 | m | 7268140 | 553706.5149 | 7821846.5149 | 1410019160 | 107419063.8906 | 1517438223.8906 | 0% | 0% | 0% |  |  | 0%
|  | 250A Cable Tap Box - End | 6 | 6 | pcs | 5043610 | 497400.75 | 5541010.75 | 30261660 | 2984404.5 | 33246064.5 | 0% | 0% | 0% |  |  | 0%
|  | 100-250A End Cover | 6 | 6 | pcs | 551650 | 27500 | 579150 | 3309900 | 165000 | 3474900 | 0% | 0% | 0% |  |  | 0%
|  | Joint Cover | 70 | 70 | pcs | 813560 | 27500 | 841060 | 56949200 | 1925000 | 58874200 | 0% | 0% | 0% |  |  | 0%
|  | PIO Cover | 282 | 651 | pcs | 90090 | 27500 | 117590 | 58648590 | 17902500 | 76551090 | 0% | 0% | 0% |  |  | 0%
|  | Fixing Bracket | 70 | 70 | pcs | 109450 | 220200.75 | 329650.75 | 7661500 | 15414052.5 | 23075552.5 | 0% | 0% | 0% |  |  | 0%
|  | Screw-on plate for blanking of unused openings | 138 | 138 | pcs | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Tap-off Unit included: - 1x Busbar tap-off unit with 16A/230V 3pin Industrial Socket CEE - 1x MCB 2P 16A | 82 | 69 | pcs | 2882070 | 497400.75 | 3379470.75 | 198862830 | 34320651.75 | 233183481.75 | 0% | 0% | 0% |  |  | 0%
|  | Tap-off Unit included: - 1x Busbar tap-off unit with 16A/400V 5pin Industrial Socket CEE - 1x MCB 3P 16A | 56 | 56 | pcs | 3041460 | 497400.75 | 3538860.75 | 170321760 | 27854442 | 198176202 | 0% | 0% | 0% |  |  | 0%
|  | Industrial plug 16A-230V for Industrial socket 16A-230V | 82 | 69 | pcs | 226176 | 54500 | 280676 | 15606144 | 3760500 | 19366644 | 0% | 0% | 0% |  |  | 0%
|  | Industrial plug 16A-400V for Industrial socket 16A-400V | 56 | 56 | pcs | 282720 | 54500 | 337220 | 15832320 | 3052000 | 18884320 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 35464501.0909 | 10639350.3273 | 46103851.4182 | 35464501.0909 | 10639350.3273 | 46103851.4182 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Electrical installation Production | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Schuko-socket 16A/230V | 0 | 0 | pcs | 0 | 54500 | 54500 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | 16A/230V 3pin Industrial Socket CEE | 41 | 41 | pcs | 381600 | 54500 | 436100 | 15645600 | 2234500 | 17880100 | 0% | 0% | 0% |  |  | 0%
|  | Socket combination type 1 | 21 | 21 | pcs | 0 | 381500 | 381500 | 0 | 8011500 | 8011500 | 0% | 0% | 0% |  |  | 0%
|  | Socket combination type 2 | 10 | 10 | pcs | 0 | 381500 | 381500 | 0 | 3815000 | 3815000 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 691014 | 207304.2 | 898318.2 | 691014 | 207304.2 | 898318.2 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable power | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | From Building 3_UPS 1 DP 1.3 35kVA Panel to16A/230V Socket (19 set) | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | 3C-2.5mm2 Cu/XLPE/PVC | 892 | 737 | m | 32518.74 | 7485.665 | 40004.405 | 23966311.38 | 5516935.105 | 29483246.485 | 36% | 34% | 70% |  |  | 0%
|  | From Building 3_UPS 2 DP 1.3 35kVA Panel to16A/230V Socket (22 set) | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | 3C-2.5mm2 Cu/XLPE/PVC | 1107 | 1033 | m | 32518.74 | 7485.665 | 40004.405 | 33591858.42 | 7732691.945 | 41324550.365 | 36% | 0% | 36% |  |  | 0%
|  | From PDP 1.0 Panel to Combine socket (9 set) | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 587 | 519 | m | 72299.4 | 17189.865 | 89489.265 | 37523388.6 | 8921539.935 | 46444928.535 | 36% | 0% | 36% |  |  | 0%
|  | From PDP 1.1 Panel to Combine socket (3 set) | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 197 | 110 | m | 72299.4 | 17189.865 | 89489.265 | 7952934 | 1890885.15 | 9843819.15 | 36% | 0% | 36% |  |  | 0%
|  | From PDP 1.2 Panel to Combine socket (4 set) | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 182 | 205 | m | 72299.4 | 17189.865 | 89489.265 | 14821377 | 3523922.325 | 18345299.325 | 36% | 0% | 36% |  |  | 0%
|  | From PDP 2.0 Panel to Combine socket (9 set) | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 830 | 811 | m | 72299.4 | 17189.865 | 89489.265 | 58634813.4 | 13940980.515 | 72575793.915 | 36% | 0% | 36% |  |  | 0%
|  | From PDP 2.1 Panel to Combine socket (6 set) | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 440 | 445 | m | 72299.4 | 17189.865 | 89489.265 | 32173233 | 7649489.925 | 39822722.925 | 36% | 0% | 36% |  |  | 0%
|  | PVC conduit D20 | 246 | 250 | m | 8773.9726 | 14594.0164 | 23367.989 | 2193493.1507 | 3648504.1029 | 5841997.2536 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 9074248.7636 | 2722274.6291 | 11796523.3926 | 9074248.7636 | 2722274.6291 | 11796523.3926 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Tel-Data system | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Double data outlet RJ45 | 179 | 191 | pcs | 480000 | 81750 | 561750 | 91680000 | 15614250 | 107294250 | 0% | 45% | 45% |  |  | 0%
|  | Cable Cat6A | 12618 | 12970 | m | 21639.3443 | 3360 | 24999.3443 | 280662295.082 | 43579200 | 324241495.082 | 0% | 45% | 45% |  |  | 0%
|  | PVC conduit D20 | 160 | 170.7263 | m | 8773.9726 | 14594.0164 | 23367.989 | 1497947.5013 | 2491581.7963 | 3989529.2977 | 0% | 0% | 0% |  |  | 0%
|  | Network cable test cost - FO cable |  |  | nos | 0 | 50600 | 50600 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Network cable test cost - Cat6A cable | 376 | 400 | nos | 0 | 50600 | 50600 | 0 | 20240000 | 20240000 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 12452626.0453 | 3735787.8136 | 16188413.8589 | 12452626.0453 | 3735787.8136 | 16188413.8589 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
5. |  | Scooter Garage | [6 empty] | 108075385.8789 | 16341158.0259 | 124416543.9048 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
5. 2. |  | Electrical Engineering | 1 | 1 | PSCH |  |  |  | 108075385.8789 | 16341158.0259 | 124416543.9048 | 0% | 0% | 0% |  |  | 0%
5. 2. 10. |  | Grounding and Lightining protection | 1 |  | PSCH |  |  |  | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Classic lightning rod Ø16, l = 1,000mm | 9 |  | m | 312500 | 120872.0782 | 433372.0783 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Claded copper - steel grounding rod Ø 16, L = 2.4m | 9 |  | m | 210227.2727 | 120872.0782 | 331099.351 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Exothermic welding connection | 19 |  | m | 119318.1818 | 56925 | 176243.1818 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Grounding Test Link box | 1 |  | m | 562500 | 56925 | 619425 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable Bare Copper wire 50sqmm | 322 |  | m | 135322.14 | 22106.7 | 157428.84 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 54 |  | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | T&C | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
5. 2. 20. |  | Power supply | 1 | 1 | PSCH |  |  |  | 48996560 | 6144115.6772 | 55140675.6772 | 0% | 0% | 0% |  |  | 0%
|  | Cable trays | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable tray 200x100x2.0mm, c/w cover | 47 | 47 | m | 776880 | 51045.8655 | 827925.8655 | 36513360 | 2399155.6772 | 38912515.6772 | 30% | 0% | 30% |  |  | 30%
|  | Fitting and accessories | 1 | 1 | lot | 12483200 | 3744960 | 16228160 | 12483200 | 3744960 | 16228160 | 30% | 0% | 30% |  |  | 30%
[12 empty] | 0% | 0% | 0% |  |  | 0%
5. 2. 30. |  | Power supply of building utilities | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
5. 2. 40. |  | Electrical installations | 1 | 1 | PSCH |  |  |  | 44249283.3619 | 5904426.8866 | 50153710.2486 | 0% | 0% | 0% |  |  | 0%
|  | Switch & Socket | [6 empty] | 11703872.04 | 857016.812 | 12560888.852 | 0% | 0% | 0% |  |  | 0%
|  | 1-Way switch, 1 gang | 2 | 2 | pcs | 46800 | 54500 | 101300 | 93600 | 109000 | 202600 | 0% | 0% | 0% |  |  | 0%
|  | 16A/230V 3pin Industrial Socket CEE | 2 | 2 | pcs | 381600 | 54500 | 436100 | 763200 | 109000 | 872200 | 0% | 0% | 0% |  |  | 0%
|  | Motion sensor | 9 | 9 | pcs | 1150224 | 54500 | 1204724 | 10352016 | 490500 | 10842516 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 495056.04 | 148516.812 | 643572.852 | 495056.04 | 148516.812 | 643572.852 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Lighting | [6 empty] | 25171700 | 992000 | 26163700 | 0% | 0% | 0% |  |  | 0%
|  | LED Frame Lamp 1x46W, Type BII | 15 | 15 | pcs | 1607100 | 56000 | 1663100 | 24106500 | 840000 | 24946500 | 0% | 0% | 0% |  |  | 0%
|  | Wall mounted Light 1x15W, Type E | 1 | 1 | pcs | 585200 | 56000 | 641200 | 585200 | 56000 | 641200 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 480000 | 96000 | 576000 | 480000 | 96000 | 576000 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable power | [6 empty] | 7373711.3219 | 4055410.0746 | 11429121.3966 | 0% | 0% | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 164 | 149 | m | 22980.09 | 5743.9305 | 28724.0205 | 3424033.41 | 855845.6445 | 4279879.0545 | 36% | 0% | 36% |  |  | 0%
|  | 3C-2.5mm2 Cu/XLPE/PVC | 68 | 61 | m | 32518.74 | 7485.665 | 40004.405 | 1983643.14 | 456625.565 | 2440268.705 | 36% | 0% | 36% |  |  | 0%
|  | PVC conduit D20 | 12 | 180 | m | 8773.9726 | 14594.0164 | 23367.989 | 1579315.0685 | 2626922.9541 | 4206238.0226 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 386719.7034 | 116015.911 | 502735.6145 | 386719.7034 | 116015.911 | 502735.6145 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
5. 2. 50. |  | Emergency lighting | 1 | 1 | PSCH |  |  |  | 14829542.5169 | 4292615.4621 | 19122157.979 | 0% | 0% | 0% |  |  | 0%
|  | Emergency light | 6 | 12 | pcs | 516120 | 56000 | 572120 | 6193440 | 672000 | 6865440 | 0% | 0% | 0% |  |  | 0%
|  | Exit light | 1 | 2 | pcs | 566280 | 56000 | 622280 | 1132560 | 112000 | 1244560 | 0% | 0% | 0% |  |  | 0%
|  | Single Socket 16A/230V | 8 | 8 | pcs | 124560 | 54500 | 179060 | 996480 | 436000 | 1432480 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | pcs | 440000 | 88000 | 528000 | 440000 | 88000 | 528000 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable power supply | [6 empty] | 6067062.5169 | 2984615.4621 | 9051677.979 | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx1.5mm2 | 120 | 205 | m | 22980.09 | 5743.9305 | 28724.0205 | 4710918.45 | 1177505.7525 | 5888424.2025 | 36% | 0% | 36% |  |  | 0%
|  | PVC conduit D20 | 68 | 110 | m | 8773.9726 | 14594.0164 | 23367.989 | 965136.9863 | 1605341.8053 | 2570478.7916 | 0% | 0% | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 24 | 20 | m | 3554.7229 | 5289.7059 | 8844.4288 | 71094.4584 | 105794.1176 | 176888.576 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 319912.6222 | 95973.7867 | 415886.4089 | 319912.6222 | 95973.7867 | 415886.4089 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
6. |  | Canteen | [6 empty] | 350267145.0631 | 45874850.9531 | 396141996.0162 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
6. 2. |  | Electrical Engineering | 1 | 1 | PSCH |  |  |  | 350267145.0631 | 45874850.9531 | 396141996.0162 | 0% | 0% | 0% |  |  | 0%
|  | Notes Calculation Basis | [9 empty] | 0% | 0% | 0% |  |  | 0%
6. 2. 10. |  | Grounding and Lightining protection | 1 | 1 | PSCH |  |  |  | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Classic lightning rod Ø16, l = 1,000mm | 6 |  | m | 312500 | 120872.0782 | 433372.0783 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Claded copper - steel grounding rod Ø 16, L = 2.4m | 6 |  | m | 210227.2727 | 120872.0782 | 331099.351 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Exothermic welding connection | 21 |  | m | 119318.1818 | 56925 | 176243.1818 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Grounding Test Link box | 2 |  | m | 562500 | 56925 | 619425 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable Bare Copper wire 50sqmm | 259 |  | m | 135322.14 | 22106.7 | 157428.84 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 36 |  | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | T&C | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
6. 2. 20. |  | Power supply | 1 | 1 | PSCH |  |  |  | 106191661.9795 | 12858262.8895 | 119049924.8689 | 0% | 0% | 0% |  |  | 0%
|  | Cable trays_Hot dip-Galvanized Steel | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable tray 200x50 with separating bar | 149 | 149 | m | 669240 | 56000 | 725240 | 99716760 | 8344000 | 108060760 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 215 | 215 | m | 8773.9726 | 14594.0164 | 23367.989 | 1886404.1096 | 3137713.5285 | 5024117.6381 | 0% | 0% | 0% |  |  | 0%
|  | Fitting and accessories | 1 | 1 | lot | 4588497.8699 | 1376549.361 | 5965047.2308 | 4588497.8699 | 1376549.361 | 5965047.2308 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
6. 2. 30. |  | Power supply of building utilities | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 2. 40. |  | Electrical installations | 1 | 1 | PSCH |  |  |  | 220631937.3221 | 25881817.2569 | 246513754.579 | 0% | 0% | 0% |  |  | 0%
|  | Switch & Socket | [6 empty] | 27779110.24 | 5475504.272 | 33254614.512 | 0% | 0% | 0% |  |  | 0%
|  | 1-Way switch, 1 gang | 5 | 5 | pcs | 46800 | 54500 | 101300 | 234000 | 272500 | 506500 | 0% | 0% | 0% |  |  | 0%
|  | Single Socket NEMA5 | 24 | 24 | pcs | 124560 | 54500 | 179060 | 2989440 | 1308000 | 4297440 | 0% | 0% | 0% |  |  | 0%
|  | 16A/230V 3pin Industrial Socket CEE | 4 | 4 | pcs | 381600 | 54500 | 436100 | 1526400 | 218000 | 1744400 | 0% | 0% | 0% |  |  | 0%
|  | Socket combination type 1 | 6 | 6 | pcs | 0 | 381500 | 381500 | 0 | 2289000 | 2289000 | 0% | 0% | 0% |  |  | 0%
|  | Motion sensor | 19 | 19 | pcs | 1150224 | 54500 | 1204724 | 21854256 | 1035500 | 22889756 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 1175014.24 | 352504.272 | 1527518.512 | 1175014.24 | 352504.272 | 1527518.512 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Lighting | [6 empty] | 141953700 | 6649872 | 148603572 | 0% | 0% | 0% |  |  | 0%
|  | LED Frame Lamp 1x46W, Type BII | 5 | 5 | pcs | 1607100 | 63504 | 1670604 | 8035500 | 317520 | 8353020 | 0% | 0% | 0% |  |  | 0%
|  | LED Frame Lamp 1x46W, Type J | 70 | 70 | pcs | 1607100 | 63504 | 1670604 | 112497000 | 4445280 | 116942280 | 0% | 0% | 0% |  |  | 0%
|  | Wall mounted Light 1x15W, Type E | 6 | 6 | pcs | 585200 | 63504 | 648704 | 3511200 | 381024 | 3892224 | 0% | 0% | 0% |  |  | 0%
|  | LED Ceiling mounted Light 1x19W, Type D | 12 | 12 | pcs | 1182500 | 63504 | 1246004 | 14190000 | 762048 | 14952048 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 3720000 | 744000 | 4464000 | 3720000 | 744000 | 4464000 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable power | [6 empty] | 50899127.0821 | 13756440.9849 | 64655568.067 | 0% | 0% | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 697 | 572 | m | 22980.09 | 5743.9305 | 28724.0205 | 13144611.48 | 3285528.246 | 16430139.726 | 36% | 0% | 36% |  |  | 0%
|  | 3C-2.5mm2 Cu/XLPE/PVC | 496 | 464 | m | 32518.74 | 7485.665 | 40004.405 | 15088695.36 | 3473348.56 | 18562043.92 | 36% | 0% | 36% |  |  | 0%
|  | 4C-4.0mm2 Cu/XLPE/PVC + E4.0mm2 Cu/PVC | 242 | 226 | m | 72299.4 | 17189.865 | 89489.265 | 16339664.4 | 3884909.49 | 20224573.89 | 36% | 0% | 36% |  |  | 0%
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 30 | 30 | m | 102372.9 | 18573.4395 | 120946.3395 | 3071187 | 557203.185 | 3628390.185 | 36% | 0% | 36% |  |  | 0%
|  | PVC conduit D20 | 117 | 132 | m | 8773.9726 | 14594.0164 | 23367.989 | 1158164.3836 | 1926410.1664 | 3084574.5499 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 2096804.4585 | 629041.3376 | 2725845.7961 | 2096804.4585 | 629041.3376 | 2725845.7961 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
6. 2. 50. |  | Emergency lighting | 1 | 1 | PSCH |  |  |  | 23443545.7616 | 7134770.8067 | 30578316.5683 | 0% | 0% | 0% |  |  | 0%
|  | Emergency light | 14 | 15 | pcs | 516120 | 63504 | 579624 | 7741800 | 952560 | 8694360 | 0% | 0% | 0% |  |  | 0%
|  | Exit light | 7 | 7 | pcs | 566280 | 63504 | 629784 | 3963960 | 444528 | 4408488 | 0% | 0% | 0% |  |  | 0%
|  | Single Socket 16A/230V | 9 | 15 | pcs | 124560 | 54500 | 179060 | 1868400 | 817500 | 2685900 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | pcs | 440000 | 88000 | 528000 | 440000 | 88000 | 528000 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable power supply | [6 empty] | 9429385.7616 | 4832182.8067 | 14261568.5683 | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 315 | 221 | m | 32518.74 | 7485.665 | 40004.405 | 7186641.54 | 1654331.965 | 8840973.505 | 36% | 0% | 36% |  |  | 0%
|  | PVC conduit D20 | 177 | 190 | m | 8773.9726 | 14594.0164 | 23367.989 | 1667054.7945 | 2772863.1182 | 4439917.9128 | 0% | 0% | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 63 | 55 | m | 3554.7229 | 5289.7059 | 8844.4288 | 195509.7606 | 290933.8235 | 486443.5841 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 380179.6664 | 114053.8999 | 494233.5664 | 380179.6664 | 114053.8999 | 494233.5664 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | II. ELV | [8 empty] | 3412928080.1667 | 0% | 0% | 0% |  |  | 0%
1. |  | Construction site facilities | [6 empty] | 124241733.1691 | 20176036.5818 | 144417769.7509 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
1. 1. |  | Construction site facilities | 1 | 1 | psch | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
1. 2. |  | Construction site cameras | 1 | 1 | psch |  |  |  | 124241733.1691 | 20176036.5818 | 144417769.7509 | 60% | 0% | 60% | 0.5 | 0.5 | 50%
|  | Rack for NVR+Swtich | 1 | 1 | pcs | 1848000 | 165000 | 2013000 | 1848000 | 165000 | 2013000 | 60% | 0% | 60% | 0.5 | 0.5 | 50%
|  | Camera bullet 360' + base, Resolution: 4K | 3 | 3 | pcs | 9067520 | 198000 | 9265520 | 27202560 | 594000 | 27796560 | 60% | 0% | 60% | 0.5 | 0.5 | 50%
|  | NVR 8 chanel | 1 | 1 | pcs | 9431520 | 165000 | 9596520 | 9431520 | 165000 | 9596520 | 60% | 0% | 60% | 0.5 | 0.5 | 50%
|  | 1KVA UPS | 1 | 1 | pcs | 2529000 | 137500 | 2666500 | 2529000 | 137500 | 2666500 | 60% | 0% | 60% | 0.5 | 0.5 | 50%
|  | Switch PoE 4P | 1 | 1 | pcs | 1155000 | 81750 | 1236750 | 1155000 | 81750 | 1236750 | 60% | 0% | 60% | 0.5 | 0.5 | 50%
|  | LCD 32" | 1 | 1 | pcs | 8360000 | 163500 | 8523500 | 8360000 | 163500 | 8523500 | 60% | 0% | 60% | 0.5 | 0.5 | 50%
|  | Double Socket 16A/230V | 3 | 3 | pcs | 150480 | 54500 | 204980 | 451440 | 163500 | 614940 | 60% | 0% | 60% | 0.5 | 0.5 | 50%
|  | PVC box for socket, conver at camera | 3 | 3 | pcs | 36000 | 16350 | 52350 | 108000 | 49050 | 157050 | 60% | 0% | 60% | 0.5 | 0.5 | 50%
|  | surge protection | 2 | 2 | pcs | 4494000 | 49050 | 4543050 | 8988000 | 98100 | 9086100 | 60% | 0% | 60% | 0.5 | 0.5 | 50%
|  | Cable Cat6 | 10 | 10 | m | 10032.7869 | 3360 | 13392.7869 | 100327.8689 | 33600 | 133927.8689 | 60% | 0% | 60% | 0.5 | 0.5 | 50%
|  | converter quang đồng | 6 | 6 | pcs | 770000 | 49050 | 819050 | 4620000 | 294300 | 4914300 | 60% | 0% | 60% | 0.5 | 0.5 | 50%
|  | Fiber optical 2FO | 373 | 373 | m | 14400 | 3360 | 17760 | 5371200 | 1253280 | 6624480 | 60% | 0% | 60% | 0.5 | 0.5 | 50%
|  | Cable Cu/XLPE/PVC 3Cx1.5mm2 | 397 | 397 | m | 22980.09 | 5743.9305 | 28724.0205 | 9123095.73 | 2280340.4085 | 11403436.1385 | 60% | 0% | 60% | 0.5 | 0.5 | 50%
|  | PVC conduit D20 | 81 | 81 | m | 8773.9726 | 14594.0164 | 23367.989 | 710691.7808 | 1182115.3294 | 1892807.1102 | 60% | 0% | 60% | 0.5 | 0.5 | 50%
|  | HDPE pipe D25/32 | 397 | 397 | m | 10550.2392 | 11445 | 21995.2392 | 4188444.9761 | 4543665 | 8732109.9761 | 60% | 0% | 60% | 0.5 | 0.5 | 50%
|  | Camera Pole 15m | 3 | 3 | pcs | 10000000 | 450000 | 10450000 | 30000000 | 1350000 | 31350000 | 60% | 0% | 60% | 0.5 | 0.5 | 50%
|  | Reforce cable for camera pole | 3 | 3 | lot | 550000 | 250000 | 800000 | 1650000 | 750000 | 2400000 | 60% | 0% | 60% | 0.5 | 0.5 | 50%
|  | Concrete plinth | 3 | 3 | lot | 1000000 | 500000 | 1500000 | 3000000 | 1500000 | 4500000 | 60% | 0% | 60% | 0.5 | 0.5 | 50%
|  | Remove Pole + Camera | 3 | 3 | time | 0 | 1250000 | 1250000 | 0 | 3750000 | 3750000 | 60% | 0% | 60% | 0.5 | 0.5 | 50%
|  | Accessories | 1 | 1 | lot | 5404452.8133 | 1621335.844 | 7025788.6573 | 5404452.8133 | 1621335.844 | 7025788.6573 | 60% | 0% | 60% | 0.5 | 0.5 | 50%
[12 empty] | 0% | 0% | 0% |  |  | 0%
2. |  | Production and Logistic building (Hall 3) | [6 empty] | 803801420.8294 | 119493877.9513 | 923295298.7807 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
2.1. |  | Civil Engineering | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
2. 1. 10. |  | Calculations | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 20. |  | Rainwater and waste water sewer | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 30. |  | Earthworks | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 40. |  | Demolition, removal and dismantling works | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 50. |  | Foundation | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 60. |  | Building structure | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 70. |  | General concrete- / reinforced concrete works | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 80. |  | Fire protection | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 90. |  | Fire rated walls | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 100. |  | Cutting base slabs / ceilings / floors | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 110. |  | Cutting holes into existing facades, walls and roofs | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 120. |  | Exterior walls | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 130. |  | Exterior doors and windows | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 140. |  | Fire protection doors | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 150. |  | Internal doors | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 160. |  | Fire protection roller shutter door | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 170. |  | Fire protection bulkhead | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 180. |  | High speed roller shutter | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 190. |  | Fitting and metal work - general | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 200. |  | Railings and hand rails | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 210. |  | Steel stage for installations | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 220. |  | Collision protection | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 230. |  | canopies of exterior doors | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 240. |  | Concerete steps in front of the hall | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 250. |  | Painting and varnishing works | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 260. |  | Guidance systems | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 270. |  | Locking system | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 280. |  | Internal signage | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 290. |  | Adjustment ridge vent | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 300. |  | Roof reinforcment Option 1 | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 310. |  | Insert new ventilation louvers | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 1. 320. |  | Metal louvers to cover mechanical units | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
2. 2. |  | Electrical Engineering | 1 | 1 | PSCH |  |  |  | 120237495.4217 | 36030743.1568 | 156268238.5785 | 0% | 0% | 0% |  |  | 0%
2. 2. 10. |  | Adjustment of existing facilities, dismantling and disposal works | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
2. 2. 20. |  | Rennovation existing grounding system and lightning protection | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
2. 2. 30. |  | Rennovation existing grounding and equipotential bonding | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
2. 2. 40. |  | Power supply | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
2. 2. 50. |  | Energy measurement system | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
2. 2. 60. |  | Electrical installation in the production hall | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
2. 2. 70. |  | Electrical installation in the logistics hall | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
2. 2. 80. |  | Power supply of building utilities | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
2. 2. 90. |  | Three-arm Turnstile | 1 | 1 | PSCH |  |  |  | 120237495.4217 | 36030743.1568 | 156268238.5785 | 0% | 0% | 0% |  |  | 0%
|  | INTUS ACM40e-NT as access control manager | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | INTUS ACM40e-NT (S3840-380) Intelligent access control manager (Supplier by Client) | 4 | 4 | set | 0 | 616000 | 616000 | 0 | 2464000 | 2464000 | 0% | 0% | 0% |  |  | 0%
|  | INTUS ACM40e 2-4 reader-ext (V3841-202) Firmware extension from 2 to 4 access readers (Supplier by Client) | 4 | 4 | set | 0 | 616000 | 616000 | 0 | 2464000 | 2464000 | 0% | 0% | 0% |  |  | 0%
|  | Network configuration setup fee (3000-243) Set up of one IPv4 terminal basis configuration by PCS. Precondition: Excel- or CSV-file with following details: IPaddress and net mask terminal, IP-address gateway, TCPport. Host name. This information must be submitted with the order. (by Client) | 4 | 4 | set | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | INTUS 6xx/7xx as RFID reader for access control | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | NTUS 615/La ( S3850-670) INTUS 615 Legic advant r/w access reader for flush mounting. Reads/writes Legic prime and Legic advant cards/tags. PCS universal coding: VNA00- 000 (Supplier by Client) | 8 | 8 | set | 0 | 616000 | 616000 | 0 | 4928000 | 4928000 | 0% | 0% | 0% |  |  | 0%
|  | INTUS 600/500/400 reader configuration fee (V3000-231) INTUS reader configuration price for customer specific car coding deviating from PCS standard coding. Also required for standalone parametrization. (by Client) | 8 | 8 | set | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | NTUS 600 spacer frame (S3850-607) INTUS 315ro/615/620 spacer frame, mandatory for mounting on metal wall or for surface mounting cable introduction (Supplier by Client) | 8 | 8 | set | 0 | 616000 | 616000 | 0 | 4928000 | 4928000 | 0% | 0% | 0% |  |  | 0%
|  | NTUS 700-Panel/La (S3853-610) SM4200-M Legic advant r/w access reader for mounting in metal panels. Reads/writes Legic prime and Legic advant cards/tags. PCS universal coding: VNA00-000 (Supplier by Client) | 8 | 8 | set | 0 | 616000 | 616000 | 0 | 4928000 | 4928000 | 0% | 0% | 0% |  |  | 0%
|  | INTUS 700 reader configuration fee (V3000-249) INTUS 700 reader configuration price for card coding, deviating from PCS standard coding. (by Client) | 8 | 8 | set | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | 5A, 12VDC Power supply adapter | 1 | 1 | set | 2220000 | 95200 | 2315200 | 2220000 | 95200 | 2315200 | 0% | 0% | 0% |  |  | 0%
|  | Push button for releasing entrance & exit lock at reception area | 1 | 4 | pcs | 528000 | 61600 | 589600 | 2112000 | 246400 | 2358400 | 0% | 0% | 0% |  |  | 0%
|  | Emergency at the reception area | 1 | 4 | pcs | 528000 | 61600 | 589600 | 2112000 | 246400 | 2358400 | 0% | 0% | 0% |  |  | 0%
|  | Cabinet box for controller located at reception | 1 | 1 | set | 3000000 | 280000 | 3280000 | 3000000 | 280000 | 3280000 | 0% | 0% | 0% |  |  | 0%
|  | Backup battery, 12VDC 7Ah | 4 | 4 | set | 540000 | 72800 | 612800 | 2160000 | 291200 | 2451200 | 0% | 0% | 0% |  |  | 0%
|  | Tripod turnstile | 4 | 4 | set | 21600000 | 369600 | 21969600 | 86400000 | 1478400 | 87878400 | 0% | 0% | 0% |  |  | 0%
|  | Double Socket 16A/230V | 4 | 4 | pcs | 150480 | 54500 | 204980 | 601920 | 218000 | 819920 | 0% | 0% | 0% |  |  | 0%
|  | Signal cable, AWG18 - 1Pair | 153 | 153 | m | 15000 | 3360 | 18360 | 2295000 | 514080 | 2809080 | 0% | 0% | 0% |  |  | 0%
|  | Cable Cat6A | 327 | 301 | m | 21639.3443 | 3360 | 24999.3443 | 6513442.623 | 1011360 | 7524802.623 | 0% | 45% | 45% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 50 | 150 | m | 32518.74 | 7485.665 | 40004.405 | 4877811 | 1122849.75 | 6000660.75 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 369 | 360 | m | 8773.9726 | 14594.0164 | 23367.989 | 3158630.137 | 5253845.9082 | 8412476.0452 | 0% | 0% | 0% |  |  | 0%
|  | Cutting concrete background and backfill | 5 | 5 | m | 0 | 125000 | 125000 | 0 | 625000 | 625000 | 0% | 0% | 0% |  |  | 0%
|  | Labour cost for support DRX test funtion of Turnstile system | 1 | 1 | lot | 0 | 3500000 | 3500000 | 0 | 3500000 | 3500000 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 4786691.6618 | 1436007.4985 | 6222699.1603 | 4786691.6618 | 1436007.4985 | 6222699.1603 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
2. 2. 100. |  | Emergency lighting | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
2. 2. 120. |  | Network infrastructure | 1 | 1 | PSCH |  |  | 0 | 307745509.2338 | 64282788.3235 | 372028297.5573 | 0% | 0% | 0% |  |  | 0%
|  | Single Mode OS2 48 fibers SC- Duplex | 207 | 230 | m | 144000 | 28000 | 172000 | 33120000 | 6440000 | 39560000 | 0% | 45% | 45% |  |  | 0%
|  | 20 x 0,8 pair copper phone wire | 0 | 0 | m | 117360 | 13798.4 | 131158.4 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | IDF7 42U (0.8x1.0x2.0), Included PDU, 10 patch panel, Cable routing channel 1U | 1 | 1 | pcs | 68750000 | 1308000 | 70058000 | 68750000 | 1308000 | 70058000 | 0% | 45% | 45% |  |  | 0%
|  | Patch panel 24 Port CAT6A | 8 |  | pcs | 5060000 | 654000 | 5714000 | 0 | 0 | 0 | 0% | 45% | 45% |  |  | 0%
|  | Patch panel 24 Port cat 5e | 2 | 2 | pcs | 2195600 | 654000 | 2849600 | 4391200 | 1308000 | 5699200 | 0% | 45% | 45% |  |  | 0%
|  | Cat 6A Patch Cord, 3m | 77 | 77 | pcs | 600000 | 13440 | 613440 | 46200000 | 1034880 | 47234880 | 0% | 45% | 45% |  |  | 0%
|  | Cat 6A Patch Cord, 3m | 0 | 0 | pcs | 600000 | 13440 | 613440 | 0 | 0 | 0 | 0% | 45% | 45% |  |  | 0%
|  | ODF F.O Singlemode, 48F | 2 | 2 | pcs | 6490000 | 490500 | 6980500 | 12980000 | 981000 | 13961000 | 0% | 45% | 45% |  |  | 0%
|  | Socket strip (PDU) with 7 sockets | 2 | 2 | pcs | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | 16A Turnlock socket | 2 | 2 | pcs | 150480 | 54500 | 204980 | 300960 | 109000 | 409960 | 0% | 0% | 0% |  |  | 0%
|  | Patch panel 24 Port | 0 | 0 | pcs | 5060000 | 654000 | 5714000 | 0 | 0 | 0 | 0% | 45% | 45% |  |  | 0%
|  | Double data outlet RJ45 | 26 | 26 | pcs | 480000 | 81750 | 561750 | 12480000 | 2125500 | 14605500 | 0% | 45% | 45% |  |  | 0%
|  | Wifi module (Wifi supply by Client) | 25 | 25 | pcs | 0 | 136250 | 136250 | 0 | 3406250 | 3406250 | 0% | 0% | 0% |  |  | 0%
|  | FO Patch Cord, SC-SC Duplex, LSOH, SM,3m | 20 | 20 | pcs | 550000 | 10900 | 560900 | 11000000 | 218000 | 11218000 | 0% | 45% | 45% |  |  | 0%
|  | FO Pigtail LC, SM, 1m for welding to optical fibre | 20 | 96 | pcs | 132000 | 65400 | 197400 | 12672000 | 6278400 | 18950400 | 0% | 0% | 0% |  |  | 0%
|  | Cat 6A Patch Cord, 3m from Data outlet to Wifi | 25 | 25 | pcs | 198000 | 10900 | 208900 | 4950000 | 272500 | 5222500 | 0% | 45% | 45% |  |  | 0%
|  | Cable Cat6A | 3219 | 3245 | m | 21639.3443 | 3360 | 24999.3443 | 70219672.1311 | 10903200 | 81122872.1311 | 0% | 45% | 45% |  |  | 0%
|  | PVC conduit D20 | 1610 | 1510 | m | 8773.9726 | 14594.0164 | 23367.989 | 13248698.6301 | 22036964.7818 | 35285663.4119 | 0% | 0% | 0% |  |  | 0%
|  | Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Network cable test cost - Cat6A cable | 52 | 52 | nos | 0 | 50600 | 50600 | 0 | 2631200 | 2631200 | 0% | 45% | 45% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 17432978.4725 | 5229893.5417 | 22662872.0142 | 17432978.4725 | 5229893.5417 | 22662872.0142 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
2. 2. 130. |  | Access control preparation | 1 | 1 | PSCH |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
2. 2. 140. |  | CCTV System | 1 | 1 | PSCH |  |  | 0 | 375818416.1739 | 19180346.471 | 394998762.6449 | 0% | 0% | 0% |  |  | 0%
|  | Outside Camera CE-1-->12 | 12 | 12 | pcs | 19242720 | 198000 | 19440720 | 230912640 | 2376000 | 233288640 | 0% | 0% | 0% |  |  | 0%
|  | Symphony Standard Edition - VMS Device License | 12 | 12 | pcs | 2704800 | 330000 | 3034800 | 32457600 | 3960000 | 36417600 | 0% | 0% | 0% |  |  | 0%
|  | Telescopic parapet mount (T91D62) | 12 | 12 | pcs | 1803200 | 49500 | 1852700 | 21638400 | 594000 | 22232400 | 0% | 0% | 0% |  |  | 0%
|  | Overvoltage protection | 12 | 12 | pcs | 4494000 | 49050 | 4543050 | 53928000 | 588600 | 54516600 | 0% | 0% | 0% |  |  | 0%
|  | Double data outlet RJ45 | 12 | 12 | pcs | 480000 | 81750 | 561750 | 5760000 | 981000 | 6741000 | 0% | 45% | 45% |  |  | 0%
|  | Cat 6A Patch Cord, 3m | 36 | 24 | pcs | 198000 | 10900 | 208900 | 4752000 | 261600 | 5013600 | 0% | 45% | 45% |  |  | 0%
|  | Cable Cat6A | 686 | 658.24 | m | 21639.3443 | 3360 | 24999.3443 | 14243881.9672 | 2211686.4 | 16455568.3672 | 0% | 45% | 45% |  |  | 0%
|  | PVC conduit D20 | 274 | 280.5 | m | 8773.9726 | 14594.0164 | 23367.989 | 2461099.3151 | 4093621.6035 | 6554720.9186 | 0% | 0% | 0% |  |  | 0%
|  | Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Network cable test cost - Cat6A cable | 12 | 24 | nos | 0 | 50600 | 50600 | 0 | 1214400 | 1214400 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 9664794.8916 | 2899438.4675 | 12564233.3591 | 9664794.8916 | 2899438.4675 | 12564233.3591 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
2. 3. |  | Mechanical Engineering | 1 | 1 | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
2. 3. 10. |  | Ventilation System Production | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
2. 3. 20. |  | Fire Protection Engineering | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
2. 3. 30. |  | Installation of In-Rack Sprinkler at Logistic | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
2. 3. 40. |  | Compressed Air Network Production 1 | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
2. 3. 50. |  | Compressed Air Network Production 2 | 1 | 1 | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. |  | Office, Social and Technical Areas (Hall 3) | [6 empty] | 1095015293.254 | 204033421.602 | 1299048714.856 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 1. |  | Civil Engineering | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 10. |  | Rainwater and waste water sewer | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 20. |  | Foundations | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 30. |  | Steel columns | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 40. |  | Building structure | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 50. |  | Concrete works | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 60. |  | Reinforced concrete slabs 1st floor | 0 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 70. |  | Reinforced concrete stairs | 0 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 80. |  | Screed coat | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 90. |  | Metal works | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 100. |  | Exterior walls | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 110. |  | Masonry works | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 120. |  | plastering works | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 130. |  | Drywall works | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 140. |  | Ceiling for new built-ins | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 150. |  | Fire protection | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 160. |  | Fire rated walls | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 170. |  | Cutting holes into existing facades, walls and roofs | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 180. |  | Cuts in Floor/slab/wall | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 190. |  | Exterior doors and windows | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 200. |  | Canopies for exterior doors | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 210. |  | Covering existing windows with mirroring film | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 220. |  | Internal doors | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 230. |  | Fire protection doors | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 240. |  | Suspended ceiling | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 250. |  | Floor covering works | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 260. |  | Tiles | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 270. |  | Needle Felt | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 280. |  | Raised floor | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 290. |  | Drainage of new wet rooms | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 300. |  | Railing and handrail | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 310. |  | Collision protection | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 320. |  | Vertical blinds | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 330. |  | Kitchenette | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 340. |  | Painting and varnishing works | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 350. |  | internal signage | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 360. |  | Locking system | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 1. 370. |  | Tightness Test Gas Extinguished Rooms | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. |  | Electrical engineering | 1 | 1 | PSCH |  |  |  | 1095015293.254 | 204033421.602 | 1299048714.856 | 0% | 0% | 0% |  |  | 0%
3. 2. 10. |  | Rennovation existing grounding system and lightning protection | 1 | 1 | psch | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 2. 20. |  | Rennovation existing grounding and equipotential bonding | 1 | 1 | psch | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 2. 30. |  | Main Power supply | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. 40. |  | Uninterrupted power supply (UPS) | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. 50. |  | Electrical Capacitor bank | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 2. 60. |  | Power supply of building utilities | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. 70. |  | Energy measurement system | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. 80. |  | Electrical installation in offices and meeting rooms | 1 |  | PSCH |  |  |  | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. 90. |  | Electrical installation in social rooms | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. 100. |  | Electrical installation in corridors and stairways | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. 110. |  | Electrical installation in technical areas | 1 |  | PSCH |  |  |  | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. 120. |  | Electrical installation in kitchenette areas | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. 130. |  | Electrical installation for Workshop/Formbrettbau | 1 |  | PSCH |  |  |  | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. 140. |  | Electrical installation at the reception | 1 |  | PSCH |  |  |  | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. 150. |  | Electrical installation in other rooms/secondary rooms | 1 |  | PSCH |  |  |  | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. 160. |  | Emergency lighting | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. 170. |  | Fire alarm system | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. 180. |  | Network infrastructure | 1 | 1 | PSCH |  |  |  | 947613765.2926 | 174994605.0134 | 1122608370.3061 | 0% | 0% | 0% |  |  | 0%
|  | IDF4 42U (0.8x1.0x2.0), Included PDU, 10 patch panel, Cable routing channel 1U | 1 | 1 | pcs | 68750000 | 1308000 | 70058000 | 68750000 | 1308000 | 70058000 | 0% | 45% | 45% |  |  | 0%
|  | IDF5 42U (0.8x1.0x2.0), Included PDU, 10 patch panel, Cable routing channel 1U | 1 | 1 | pcs | 68750000 | 1308000 | 70058000 | 68750000 | 1308000 | 70058000 | 0% | 45% | 45% |  |  | 0%
|  | IDF6 42U (0.8x1.0x2.0), Included PDU, 10 patch panel, Cable routing channel 1U | 1 | 1 | pcs | 68750000 | 1308000 | 70058000 | 68750000 | 1308000 | 70058000 | 0% | 45% | 45% |  |  | 0%
|  | Patch panel 24 Port CAT6A | 24 |  | pcs | 5060000 | 654000 | 5714000 | 0 | 0 | 0 | 0% | 45% | 45% |  |  | 0%
|  | Patch panel 24 Port cat 5e | 6 | 6 | pcs | 2195600 | 654000 | 2849600 | 13173600 | 3924000 | 17097600 | 0% | 45% | 45% |  |  | 0%
|  | Cat 6A Patch Cord, 3m | 423 | 452 | pcs | 198000 | 10900 | 208900 | 89496000 | 4926800 | 94422800 | 0% | 45% | 45% |  |  | 0%
|  | Cat 6A Patch Cord, 3m | 0 | 0 | pcs | 198000 | 10900 | 208900 | 0 | 0 | 0 | 0% | 45% | 45% |  |  | 0%
|  | ODF F.O Singlemode, 48F | 6 | 6 | pcs | 6490000 | 490500 | 6980500 | 38940000 | 2943000 | 41883000 | 0% | 45% | 45% |  |  | 0%
|  | Socket strip (PDU) with 7 sockets | 6 | 6 | pcs |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | 16A Turnlock socket | 6 | 6 | pcs | 150480 | 54500 | 204980 | 902880 | 327000 | 1229880 | 0% | 0% | 0% |  |  | 0%
|  | Double data outlet RJ45 | 197 | 226 | pcs | 480000 | 81750 | 561750 | 108480000 | 18475500 | 126955500 | 0% | 45% | 45% |  |  | 0%
|  | Wifi module (Wifi supply by Client) | 29 | 29 | pcs | 0 | 136250 | 136250 | 0 | 3951250 | 3951250 | 0% | 0% | 0% |  |  | 0%
|  | FO Patch Cord, SC-SC Duplex, LSOH, SM,3m | 60 | 60 | pcs | 550000 | 10900 | 560900 | 33000000 | 654000 | 33654000 | 0% | 45% | 45% |  |  | 0%
|  | FO Pigtail LC, SM, 1m for welding to optical fibre | 60 | 144 | pcs | 132000 | 65400 | 197400 | 19008000 | 9417600 | 28425600 | 0% | 45% | 45% |  |  | 0%
|  | Cat 6A Patch Cord, 3m from Data outlet to Wifi | 29 | 29 | pcs | 198000 | 10900 | 208900 | 5742000 | 316100 | 6058100 | 0% | 45% | 45% |  |  | 0%
|  | Cable Cat6A | 14691 | 14487.8 | m | 21639.3443 | 3360 | 24999.3443 | 313506491.8033 | 48679008 | 362185499.8033 | 0% | 45% | 45% |  |  | 0%
|  | PVC conduit D20 | 138 | 2800 | m | 8773.9726 | 14594.0164 | 23367.989 | 24567123.2877 | 40863245.9529 | 65430369.2406 | 0% | 0% | 0% |  |  | 0%
|  | Network cable test cost - FO cable | 24 | 96 | nos | 0 | 50600 | 50600 | 0 | 4857600 | 4857600 | 0% | 0% | 0% |  |  | 0%
|  | Network cable test cost - Cat6A cable | 197 | 452 | nos | 0 | 50600 | 50600 | 0 | 22871200 | 22871200 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 29547670.2017 | 8864301.0605 | 38411971.2622 | 29547670.2017 | 8864301.0605 | 38411971.2622 | 0% | 0% | 0% |  |  | 0%
|  | Updated for data socket outlet on Dadoduct | 1 | 1 | lot | 65000000 |  | 65000000 | 65000000 | 0 | 65000000 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. 190. |  | CCTV System for custom fence | 1 | 1 | PSCH |  |  |  | 93265409.772 | 9368475.5017 | 102633885.2737 | 0% | 0% | 0% |  |  | 0%
|  | Camera fence CF-5,6 | 2 | 2 | pcs | 1264480 | 137500 | 1401980 | 2528960 | 275000 | 2803960 | 0% | 0% | 0% |  |  | 0%
|  | Camera Inside CI-1, Dome | 1 | 1 | pcs | 20015520 | 198000 | 20213520 | 20015520 | 198000 | 20213520 | 0% | 0% | 0% |  |  | 0%
|  | Symphony Standard Edition - VMS Device License | 1 | 1 | pcs | 2704800 | 330000 | 3034800 | 2704800 | 330000 | 3034800 | 0% | 0% | 0% |  |  | 0%
|  | LCD 43" for CE, CI | 2 | 2 | pcs | 11990000 | 163500 | 12153500 | 23980000 | 327000 | 24307000 | 0% | 0% | 0% |  |  | 0%
|  | LCD 32" for CF | 2 | 2 | pcs | 11990000 | 163500 | 12153500 | 23980000 | 327000 | 24307000 | 0% | 0% | 0% |  |  | 0%
|  | HDMI cable c/w socket, 15m | 2 | 3 | pcs | 979000 | 59950 | 1038950 | 2937000 | 179850 | 3116850 | 0% | 0% | 0% |  |  | 0%
|  | Single data outlet RJ45 | 3 | 3 | pcs | 276000 | 81750 | 357750 | 828000 | 245250 | 1073250 | 0% | 45% | 45% |  |  | 0%
|  | Double Socket 16A/230V | 2 | 2 | pcs | 150480 | 54500 | 204980 | 300960 | 109000 | 409960 | 0% | 0% | 0% |  |  | 0%
|  | Cat 6A Patch Cord, 3m from Data outlet to camera | 3 | 3 | pcs | 198000 | 10900 | 208900 | 594000 | 32700 | 626700 | 0% | 45% | 45% |  |  | 0%
|  | Cable Cat6 | 400 | 403 | m | 10032.7869 | 3360 | 13392.7869 | 4043213.1148 | 1354080 | 5397293.1148 | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 124 | 124 | m | 32518.74 | 7485.665 | 40004.405 | 4032323.76 | 928222.46 | 4960546.22 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 210 | 210 | m | 8773.9726 | 14594.0164 | 23367.989 | 1842534.2466 | 3064743.4465 | 4907277.693 | 0% | 0% | 0% |  |  | 0%
|  | Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Network cable test cost - Cat6A cable | 3 | 7 | nos | 0 | 50600 | 50600 | 0 | 354200 | 354200 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 5478098.6507 | 1643429.5952 | 7121528.2459 | 5478098.6507 | 1643429.5952 | 7121528.2459 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 2. 200. |  | Access control preparation | 1 | 1 | PSCH |  |  |  | 54136118.1893 | 19670341.0869 | 73806459.2762 | 0% | 0% | 0% |  |  | 0%
|  | Exit Button | 5 | 5 | pcs | 528000 | 61600 | 589600 | 2640000 | 308000 | 2948000 | 0% | 0% | 0% |  |  | 0%
|  | Emergency Button | 5 | 5 | pcs | 528000 | 61600 | 589600 | 2640000 | 308000 | 2948000 | 0% | 0% | 0% |  |  | 0%
|  | Door sensor | 55 | 5 | pcs | 2116800 | 95200 | 2212000 | 10584000 | 476000 | 11060000 | 0% | 0% | 0% |  |  | 0%
|  | Access control card reader | 8 | 5 | set | 0 | 95200 | 95200 | 0 | 476000 | 476000 | 0% | 0% | 0% |  |  | 0%
|  | Single Socket 16A/230V | 5 | 5 | pcs | 150480 | 54500 | 204980 | 752400 | 272500 | 1024900 | 0% | 0% | 0% |  |  | 0%
|  | Data outlet RJ45 | 5 | 5 | pcs | 480000 | 81750 | 561750 | 2400000 | 408750 | 2808750 | 0% | 45% | 45% |  |  | 0%
|  | AC/DC converter | 5 | 5 | pcs | 2220000 | 95200 | 2315200 | 11100000 | 476000 | 11576000 | 0% | 0% | 0% |  |  | 0%
|  | Conection box, SS304 | 5 | 5 | pcs | 180000 | 50400 | 230400 | 900000 | 252000 | 1152000 | 0% | 0% | 0% |  |  | 0%
|  | Cable cat6A | 357 | 225 | m | 21639.3443 | 3360 | 24999.3443 | 4868852.459 | 756000 | 5624852.459 | 0% | 45% | 45% |  |  | 0%
|  | Cable telephone cat5e | 357 | 225 | m | 7475.4098 | 3360 | 10835.4098 | 1681967.2131 | 756000 | 2437967.2131 | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 286 | 286 | m | 32518.74 | 7485.665 | 40004.405 | 9300359.64 | 2140900.19 | 11441259.83 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 643 | 586 | m | 8773.9726 | 14594.0164 | 23367.989 | 5141547.9452 | 8552093.6173 | 13693641.5625 | 0% | 0% | 0% |  |  | 0%
|  | Labour cost for support DRX test funtion of Access control system | 1 | 1 | lot | 0 | 3850000 | 3850000 | 0 | 3850000 | 3850000 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 2126990.932 | 638097.2796 | 2765088.2116 | 2126990.932 | 638097.2796 | 2765088.2116 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 3. |  | Mechanical Engineering | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 3. 10. |  | Waste Water System | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
3. 3. 20. |  | Service Water System | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
3. 3. 40. |  | Ventilation System | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
3. 3. 50. |  | Ventilation System 1st Floor Offices Ventilation Units | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
3. 3. 60. |  | Ventilation System 1st Floor Offices Ducting | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
3. 3. 70. |  | Air Conditioning | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
3. 3. 80. |  | Fire Protection Engineering Sprinkler | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 3. 90. |  | Fire Protection Engineering Temperature Controlled Storage | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 3. 100. |  | Fire Protection Engineering Extinguishing Systems | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 3. 110. |  | Door Fan Test for Gas Extinguishing System | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
3. 3. 120. |  | Compressed Air Connections | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
4. |  | Machine hook-up (Hall 3) | [8 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
4. 1. |  | Electrical engineering | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
4. 1. 10. |  | Power cables and lines | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
4. 2. |  | Mechanical Engineering | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
4. 2. 10. |  | Machine hook-up | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
|  | Supply & Installation pipe & fittings: Drop Piping (D25), Considering all drop piping & fittings | 1 |  | lot | 0 | 0 |  |  |  |  | 0% | 0% | 0% |  |  | 0%
|  | Hanger support & accessories | 1 |  | lot | 0 | 0 |  |  |  |  | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
5. |  | Scooter Garage | [8 empty] | 162238150.0078 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
5. 1. |  | Civil Engineering | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
5. 1. 10. |  | Adjustments on the existing scooter garage | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
5. 1. 20. |  | Expansion of Scooter Garage | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
5. 2. |  | Electrical Engineering | 1 | 1 | PSCH |  |  |  | 144640388.5392 | 17597761.4686 | 162238150.0078 | 0% | 0% | 0% |  |  | 0%
5. 2. 10. |  | Grounding and Lightining protection | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
5. 2. 20. |  | Power supply | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
5. 2. 30. |  | Power supply of building utilities | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
5. 2. 40. |  | Electrical installations | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
5. 2. 50. |  | Emergency lighting | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
5. 2. 60. |  | Fire alarms system | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
5. 2. 70. |  | CCTV System | 1 | 1 | PSCH |  |  |  | 144640388.5392 | 17597761.4686 | 162238150.0078 | 0% | 0% | 0% |  |  | 0%
|  | POWER surveillance cabinet | 2 | 2 | pcs | 1650000 | 136250 | 1786250 | 3300000 | 272500 | 3572500 | 0% | 0% | 0% |  |  | 0%
|  | DATA surveillance cabinet | 2 | 2 | pcs | 1650000 | 136250 | 1786250 | 3300000 | 272500 | 3572500 | 0% | 0% | 0% |  |  | 0%
|  | Terminal 4mm2 | 2 | 2 | pcs | 27500 | 10900 | 38400 | 55000 | 21800 | 76800 | 0% | 0% | 0% |  |  | 0%
|  | MCB 1P-16A-230V | 2 | 2 | pcs | 90000 | 49050 | 139050 | 180000 | 98100 | 278100 | 0% | 0% | 0% |  |  | 0%
|  | Power adapter (Mean Well SDR-240-48) | 2 | 2 | pcs | 2833600 | 114450 | 2948050 | 5667200 | 228900 | 5896100 | 0% | 0% | 0% |  |  | 0%
|  | PoE Switch Planet IGS-10020HPT | 2 | 2 | pcs | 15180000 | 272500 | 15452500 | 30360000 | 545000 | 30905000 | 0% | 0% | 0% |  |  | 0%
|  | Outside Camera CF-7-->14 | 8 | 8 | pcs | 1264480 | 137500 | 1401980 | 10115840 | 1100000 | 11215840 | 0% | 0% | 0% |  |  | 0%
|  | Telescopic parapet mount (T91D62) | 8 | 8 | pcs | 1803200 | 49500 | 1852700 | 14425600 | 396000 | 14821600 | 0% | 0% | 0% |  |  | 0%
|  | Overvoltage protection | 8 | 8 | pcs | 4494000 | 49050 | 4543050 | 35952000 | 392400 | 36344400 | 0% | 0% | 0% |  |  | 0%
|  | Single data outlet RJ45 | 8 | 8 | pcs | 276000 | 81750 | 357750 | 2208000 | 654000 | 2862000 | 0% | 45% | 45% |  |  | 0%
|  | Cat 6A Patch Cord, 3m from Data outlet to camera | 8 | 8 | pcs | 198000 | 10900 | 208900 | 1584000 | 87200 | 1671200 | 0% | 45% | 45% |  |  | 0%
|  | Cable Cat6 | 343 | 264 | m | 10032.7869 | 3360 | 13392.7869 | 2648655.7377 | 887040 | 3535695.7377 | 0% | 0% | 0% |  |  | 0%
|  | Gigabit Ethernet LX Mini-GBIC SFP Transceiver | 2 | 2 | pcs | 4032000 | 272500 | 4304500 | 8064000 | 545000 | 8609000 | 0% | 0% | 0% |  |  | 0%
|  | converter quang đồng (Connect from optic cable to Patch panel) | 2 | 2 | pcs | 935000 | 49050 | 984050 | 1870000 | 98100 | 1968100 | 0% | 45% | 45% |  |  | 0%
|  | Cat 6A Patch Cord, 3m from Converter to patch panel | 4 | 4 | pcs | 198000 | 10900 | 208900 | 792000 | 43600 | 835600 | 0% | 45% | 45% |  |  | 0%
|  | FO Patch Cord, SC-SC Duplex, LSOH, SM,3m | 2 | 2 | pcs | 550000 | 10900 | 560900 | 1100000 | 21800 | 1121800 | 0% | 45% | 45% |  |  | 0%
|  | Fiber optical 8FO (SM-OS2 G9/125) | 190 | 190 | m | 54000 | 3360 | 57360 | 10260000 | 638400 | 10898400 | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2 | 100 | 100 | m | 32518.74 | 7485.665 | 40004.405 | 3251874 | 748566.5 | 4000440.5 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 144 | 200 | m | 8773.9726 | 14594.0164 | 23367.989 | 1754794.5205 | 2918803.2824 | 4673597.8029 | 0% | 0% | 0% |  |  | 0%
|  | HDPE pipe D40/50 | 100 | 100 | m | 17049.1866 | 15805 | 32854.1866 | 1704918.6603 | 1580500 | 3285418.6603 | 0% | 0% | 0% |  |  | 0%
|  | The cost of cutting and refinishing the concrete path for the undergruond pipe | 8 | 8 | m | 0 | 175000 | 175000 | 0 | 1400000 | 1400000 | 0% | 0% | 0% |  |  | 0%
|  | Network cable test cost - FO cable | 2 | 48 | nos | 0 | 50600 | 50600 | 0 | 2428800 | 2428800 | 0% | 0% | 0% |  |  | 0%
|  | Network cable test cost - Cat6A cable | 8 | 8 | nos | 0 | 50600 | 50600 | 0 | 404800 | 404800 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 6046505.6207 | 1813951.6862 | 7860457.3069 | 6046505.6207 | 1813951.6862 | 7860457.3069 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
5. 3. |  | Mechancial Engineering | [8 empty] | 0 | 0% | 0% | 0% |  |  | 0%
5. 3. 10. |  | Rainwater System | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
5. 3. 20. |  | Fire Protection System | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
6. |  | Canteen | [8 empty] | 274132627.4702 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
6. 1. |  | Civil Engineering | [8 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 10. |  | Demolition of existing canteen | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 20. |  | Building Structure | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 30. |  | Earthworks | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 40. |  | Rain water and waste water sewer | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 50. |  | Primary construction of reinforced concrete | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 60. |  | Foundations | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 70. |  | Concrete floor | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 80. |  | Concrete plinth | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 90. |  | Reinforced concrete columns | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 100. |  | Reinforced concrete beams | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 110. |  | Reinforced concrete 1st roof slab or structure | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 120. |  | Reinforced concrete stairs | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 130. |  | Concrete steps | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 140. |  | Screed coat | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 150. |  | Roof structure | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 160. |  | Metal facade | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 170. |  | Masonry works | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 180. |  | Exterior doors | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 190. |  | Fire protection | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 200. |  | Fire protection doors | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 210. |  | Interior doors | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 220. |  | Floor covering works | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 230. |  | Tiles | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 240. |  | Painting and finishing works | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 250. |  | Metal and railing works | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 260. |  | Elevator for goods | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 270. |  | Canpoy for the main entrance | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 280. |  | Exterior steel staircase | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 290. |  | Exterior sinks | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 1. 300. |  | Locking system | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
6. 2. |  | Electrical Engineering | [6 empty] | 246947482.5691 | 27185144.9011 | 274132627.4702 | 0% | 0% | 0% |  |  | 0%
|  | Notes Calculation Basis | [9 empty] | 0% | 0% | 0% |  |  | 0%
6. 2. 10. |  | Grounding and Lightining protection | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 2. 20. |  | Power supply | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
6. 2. 30. |  | Power supply of building utilities | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
6. 2. 40. |  | Electrical installations | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
6. 2. 50. |  | Emergency lighting | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
6. 2. 60. |  | Fire alarms system | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 2. 70. |  | CCTV System For Custom fence | 1 | 1 | PSCH |  |  |  | 117565498.5134 | 6055261.4345 | 123620759.9479 | 0% | 0% | 0% |  |  | 0%
|  | LCD 43" for CE, CI | 8 | 8 | pcs | 11990000 | 163500 | 12153500 | 95920000 | 1308000 | 97228000 | 0% | 0% | 0% |  |  | 0%
|  | HDMI cable c/w socket, 15m | 8 | 8 | pcs | 979000 | 59950 | 1038950 | 7832000 | 479600 | 8311600 | 0% | 0% | 0% |  |  | 0%
|  | Outside Camera CF-16-->18 | 4 | 4 | pcs | 1264480 | 137500 | 1401980 | 5057920 | 550000 | 5607920 | 0% | 0% | 0% |  |  | 0%
|  | Single data outlet RJ45 | 4 | 4 | pcs | 276000 | 81750 | 357750 | 1104000 | 327000 | 1431000 | 0% | 45% | 45% |  |  | 0%
|  | Cat 6A Patch Cord, 3m from Data outlet to camera | 4 | 4 | pcs | 198000 | 10900 | 208900 | 792000 | 43600 | 835600 | 0% | 45% | 45% |  |  | 0%
|  | Cable Cat6 | 229 | 200 | m | 10032.7869 | 3360 | 13392.7869 | 2006557.377 | 672000 | 2678557.377 | 0% | 45% | 45% |  |  | 0%
|  | PVC conduit D20 | 91 | 85 | m | 8773.9726 | 14594.0164 | 23367.989 | 745787.6712 | 1240491.395 | 1986279.0662 | 0% | 0% | 0% |  |  | 0%
|  | Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Network cable test cost - Cat6A cable | 4 | 4 | nos | 0 | 50600 | 50600 | 0 | 202400 | 202400 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 4107233.4651 | 1232170.0395 | 5339403.5046 | 4107233.4651 | 1232170.0395 | 5339403.5046 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
6. 2. 80. |  | Network infrastructure | 1 | 1 | PSCH |  |  |  | 129381984.0557 | 21129883.4666 | 150511867.5223 | 0% | 0% | 0% |  |  | 0%
|  | IDF8 12U (0.8x1.0x2.0), Included PDU, 10 patch panel, Cable routing channel 1U | 1 | 1 | pcs | 68750000 | 1308000 | 70058000 | 68750000 | 1308000 | 70058000 | 0% | 45% | 45% |  |  | 0%
|  | Patch panel 24 Port CAT6A | 2 |  | pcs | 5060000 | 654000 | 5714000 | 0 | 0 | 0 | 0% | 45% | 45% |  |  | 0%
|  | Cat 6A Patch Cord, 3m | 28 | 16 | pcs | 198000 | 10900 | 208900 | 3168000 | 174400 | 3342400 | 0% | 45% | 45% |  |  | 0%
|  | Cat 6A Patch Cord, 3m | 0 | 0 | pcs | 198000 | 10900 | 208900 | 0 | 0 | 0 | 0% | 45% | 45% |  |  | 0%
|  | ODF F.O Singlemode, 48F | 1 | 1 | pcs | 6490000 | 490500 | 6980500 | 6490000 | 490500 | 6980500 | 0% | 45% | 45% |  |  | 0%
|  | Socket strip (PDU) with 7 sockets | 2 | 2 | pcs |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | 16A Turnlock socket | 2 | 2 | pcs | 150480 | 54500 | 204980 | 300960 | 109000 | 409960 | 0% | 0% | 0% |  |  | 0%
|  | Double data outlet RJ45 | 12 | 12 | pcs | 480000 | 81750 | 561750 | 5760000 | 981000 | 6741000 | 0% | 45% | 45% |  |  | 0%
|  | Wifi module (Wifi supply by Client) | 4 | 4 | pcs | 0 | 136250 | 136250 | 0 | 545000 | 545000 | 0% | 0% | 0% |  |  | 0%
|  | FO Patch Cord, SC-SC Duplex, LSOH, SM,3m | 2 | 2 | pcs | 550000 | 10900 | 560900 | 1100000 | 21800 | 1121800 | 0% | 45% | 45% |  |  | 0%
|  | FO Pigtail LC, SM, 1m for welding to optical fibre | 2 | 48 | pcs | 132000 | 65400 | 197400 | 6336000 | 3139200 | 9475200 | 0% | 0% | 0% |  |  | 0%
|  | Cat 6A Patch Cord, 3m from Data outlet to wifi | 4 | 4 | pcs | 198000 | 10900 | 208900 | 792000 | 43600 | 835600 | 0% | 45% | 45% |  |  | 0%
|  | Cable Cat6A | 1257 | 1240 | m | 21639.3443 | 3360 | 24999.3443 | 26832786.8852 | 4166400 | 30999186.8852 | 0% | 45% | 45% |  |  | 0%
|  | PVC conduit D20 | 503 | 500 | m | 8773.9726 | 14594.0164 | 23367.989 | 4386986.3014 | 7297008.2059 | 11683994.5073 | 0% | 0% | 0% |  |  | 0%
|  | Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Network cable test cost - Cat6A cable | 12 | 24 | nos | 0 | 50600 | 50600 | 0 | 1214400 | 1214400 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 5465250.8691 | 1639575.2607 | 7104826.1298 | 5465250.8691 | 1639575.2607 | 7104826.1298 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
6. 3. |  | Mechancial Engineering | [8 empty] | 0 | 0% | 0% | 0% |  |  | 0%
6. 3. 10. |  | Rainwater System | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
6. 3. 20. |  | Waste Water System | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
6. 3. 30. |  | Service Water System | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
6. 3. 40. |  | Sanitary Furnishings | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
6. 3. 50. |  | Air Conditioning | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
6. 3. 60. |  | Ventilation System Overhead Fans | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
6. 3. 70. |  | Ventilation System | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
6. 3. 80. |  | Fire Protection System | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
7. |  | Exterior Area | [6 empty] | 509452988.9423 | 100342530.3589 | 609795519.3012 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
7. 1. |  | Civil Engineering | [8 empty] | 0 | 0% | 0% | 0% |  |  | 0%
7. 1. 10. |  | Flag pole | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
7. 1. 20. |  | Fence | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
7. 1. 30. |  | Bollards and delineator panels | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
7. 1. 40. |  | New Septic Tanks | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
7. 1. 50. |  | Excavation | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
7. 1. 60. |  | Laying conduits, pipes, etc. | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
7. 1. 70. |  | Asphalt areas | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
7. 2. |  | Electrical Engineering | [6 empty] | 509452988.9423 | 100342530.3589 | 609795519.3012 | 0% | 0% | 0% |  |  | 0%
7. 2. 10. |  | Electrical Installations General | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
7. 2. 20. |  | Exterior Lighting | 1 |  | PSCH | [6 empty] | 0% | 0% | 0% |  |  | 0%
7. 2. 30. |  | Emergency Lighting | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
7. 2. 40. |  | Building service connections | 1 | 1 | PSCH |  |  |  | 449449440 | 94825780 | 544275220 | 0% | 0% | 0% |  |  | 0%
|  | Single Mode OS2 48 fibers SC- Duplex | 1325 | 2141.26 | m | 144000 | 28000 | 172000 | 308341440 | 59955280 | 368296720 | 0% | 45% | 45% |  |  | 0%
|  | 20 x 0,8 pair copper phone wire (20P cat3) | 0 |  | m | 117360 | 13798.4 | 131158.4 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | ODF F.O Singlemode, 48F add to MDF at server rooms | 5 | 5 | pcs | 6490000 | 490500 | 6980500 | 32450000 | 2452500 | 34902500 | 0% | 45% | 45% |  |  | 0%
|  | Patch panel 24 Port cat 5e | 5 | 5 | pcs | 2195600 | 654000 | 2849600 | 10978000 | 3270000 | 14248000 | 0% | 45% | 45% |  |  | 0%
|  | Cat 6A Patch Cord, 3m | 120 |  | pcs | 198000 | 10900 | 208900 | 0 | 0 | 0 | 0% | 45% | 45% |  |  | 0%
|  | FO Patch Cord, SC-SC Duplex, LSOH, SM,3m | 120 | 120 | pcs | 550000 | 10900 | 560900 | 66000000 | 1308000 | 67308000 | 0% | 45% | 45% |  |  | 0%
|  | FO Pigtail LC, SM, 1m for welding to optical fibre | 120 | 240 | pcs | 132000 | 65400 | 197400 | 31680000 | 15696000 | 47376000 | 0% | 0% | 0% |  |  | 0%
|  | Network cable test cost - FO cable | 120 | 240 | nos | 0 | 50600 | 50600 | 0 | 12144000 | 12144000 | 0% | 0% | 0% |  |  | 0%
|  | Network cable test cost - Cat6A cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
7. 2. 50. |  | CCTV System | 1 | 1 | PSCH |  |  |  | 60003548.9423 | 5516750.3589 | 65520299.3012 | 0% | 0% | 0% |  |  | 0%
|  | For Custom fence | [6 empty] | 60003548.9423 | 5516750.3589 | 65520299.3012 | 0% | 0% | 0% |  |  | 0%
|  | NVR 32 Chanel | 1 | 1 | pcs | 19810560 | 385000 | 20195560 | 19810560 | 385000 | 20195560 | 0% | 0% | 0% |  |  | 0%
|  | Outside Camera CF-1-->4 | 4 | 4 | pcs | 1264480 | 137500 | 1401980 | 5057920 | 550000 | 5607920 | 0% | 0% | 0% |  |  | 0%
|  | Telescopic parapet mount (T91D62) | 4 | 4 | pcs | 1803200 | 49500 | 1852700 | 7212800 | 198000 | 7410800 | 0% | 0% | 0% |  |  | 0%
|  | Overvoltage protection | 4 | 4 | pcs | 4494000 | 49050 | 4543050 | 17976000 | 196200 | 18172200 | 0% | 0% | 0% |  |  | 0%
|  | Double data outlet RJ45 | 4 | 4 | pcs | 480000 | 81750 | 561750 | 1920000 | 327000 | 2247000 | 0% | 45% | 45% |  |  | 0%
|  | Cat 6A Patch Cord, 3m | 12 | 12 | pcs | 198000 | 10900 | 208900 | 2376000 | 130800 | 2506800 | 0% | 45% | 45% |  |  | 0%
|  | Cable Cat6 | 240 | 227 | m | 10032.7869 | 3360 | 13392.7869 | 2277442.623 | 762720 | 3040162.623 | 0% | 45% | 45% |  |  | 0%
|  | PVC conduit D20 | 96 | 100 | m | 8773.9726 | 14594.0164 | 23367.989 | 877397.2603 | 1459401.6412 | 2336798.9015 | 0% | 0% | 0% |  |  | 0%
|  | Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Network cable test cost - Cat6A cable | 4 | 15 | nos | 0 | 50600 | 50600 | 0 | 759000 | 759000 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 2495429.0591 | 748628.7177 | 3244057.7768 | 2495429.0591 | 748628.7177 | 3244057.7768 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
7. 3. |  | Mechanical Engineering | [8 empty] | 0 | 0% | 0% | 0% |  |  | 0%
7. 3. 10. |  | Underground Compressed Air Connection | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
8. |  | Adjustments Hall 2 | [8 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
8. 1. |  | Roof Renovation | [8 empty] | 0 | 0% | 0% | 0% |  |  | 0%
8. 1. 10. |  | Roof Reinforcement Option 1 | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
8. 2. |  | Adjustment Ridge Vent | [8 empty] | 0 | 0% | 0% | 0% |  |  | 0%
8. 2. 10. |  | Adjustment Ridge Vent | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
8. 3. |  | Adjustment Overhead Fans | [8 empty] | 0 | 0% | 0% | 0% |  |  | 0%
8. 3. 10. |  | Adjustment Overhead Fans | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
8. 4. |  | Additonal In-Rack Sprinkler Logistic | [8 empty] | 0 | 0% | 0% | 0% |  |  | 0%
8. 4. 10. |  | Additonal In-Rack Sprinkler Logistic | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
8. 5. |  | Additional Compressed Air Equipment | [8 empty] | 0 | 0% | 0% | 0% |  |  | 0%
8. 5. 10. |  | Additional Compressed Air Equipment | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
8. 6. |  | Flag pole | [8 empty] | 0 | 0% | 0% | 0% |  |  | 0%
8. 6. 10. |  | Flag pole | 0 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
9. |  | As built documentation | [8 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
9. 1. |  | As built documentation all trades | [8 empty] | 0 | 0% | 0% | 0% |  |  | 0%
9. 1. 10. |  | As built documentation | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
10. |  | Service of Architects and Engineers | [8 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
10. 1. |  | Civil engineering | [8 empty] | 0 | 0% | 0% | 0% |  |  | 0%
10. 1. 10. |  | Design works | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
10. 1. 20. |  | Geotechnical survey | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
10. 1. 30. |  | Topographical survey | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
10. 1. 40. |  | Fire protection report | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
10. 1. 50. |  | Compactation report of earthworks | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
10. 1. 60. |  | Structure and welding quality report | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
10. 1. 70. |  | Adherence and width of paint quality control reports | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
10. 1. 80. |  | Material quality control reports | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
10. 1. 90. |  | Planning service Building construction | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
10. 1. 100. |  | Planning service Structural design | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
10. 1. 110. |  | Planning service Structural revision | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
10. 1. 120. |  | Surveying services Inventory registration | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
10. 1. 130. |  | Quality control laboratory for material testing (laboratory and field testing) | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
10. 1. 140. |  | Revision fire department and civil protection | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
10. 2. |  | Electrical engineering | [8 empty] | 0 | 0% | 0% | 0% |  |  | 0%
10. 2. 10. |  | Design & approval works | 1 |  | psch | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
10. 3. |  | Mechanical engineering | [8 empty] | 0 | 0% | 0% | 0% |  |  | 0%
10. 3. 10. |  | Design & approval works | 1 |  | psch | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | III. AIR COMPRESSOR | [8 empty] | 1143011058.0929 | 0% | 0% | 0% |  |  | 0%
2. |  | Production and Logistic building (Hall 3) | [6 empty] | 585597305.9781 | 205702981.3661 | 791300287.3442 | 0 | 0 | 0 |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
2. 3. |  | Mechanical Engineering | [6 empty] | 585597305.9781 | 205702981.3661 | 791300287.3442 | 0% | 0% | 0% |  |  | 0%
2. 3. 40. |  | Compressed Air Network Production 1 | 1 |  | PSCH |  |  |  | 425312121.5169 | 147070051.5988 | 572382173.1157 | 0% | 0% | 0% |  |  | 0%
|  | BLUE ALUMINIUM PIPE, DN63 | 470 | 485 | m | 362322.6857 | 115320.5625 | 477643.2482 | 175726502.5676 | 55930472.8125 | 231656975.3801 | 0% | 50% | 50% |  |  | 0%
|  | BLUE ALUMINIUM PIPE, DN40 | 0 | 30 | pcs | 190224.1656 | 70966.5 | 261190.6656 | 5706724.968 | 2128995 | 7835719.968 | 0% | 50% | 50% |  |  | 0%
|  | BLUE ALUMINIUM PIPE, DN25 | 180 | 174 | m | 94950.6667 | 42579.9 | 137530.5667 | 16521416 | 7408902.6 | 23930318.6 | 0% | 50% | 50% |  |  | 0%
|  | TUBE CLIP, DN63 (POLYMER) | 162 | 172 | pcs | 54295.4118 | 82376.8 | 136672.2118 | 9338810.8362 | 14168809.6 | 23507620.4362 | 0% | 50% | 50% |  |  | 0%
|  | TUBE CLIP, DN40 (POLYMER) | 76 | 10 | pcs | 32609.857 | 57608.1 | 90217.957 | 326098.5696 | 576081 | 902179.5696 | 0% | 50% | 50% |  |  | 0%
|  | PIPE TO PIPE JOINT, DN63 | 79 | 79 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 47234236.4616 | 6507767.2 | 53742003.6616 | 0% | 50% | 50% |  |  | 0%
|  | PIPE TO PIPE JOINT, DN63 | 50 | 50 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 29895086.3681 | 4118840 | 34013926.3681 | 0% | 50% | 50% |  |  | 0%
|  | 90° ELBOW, DN63 | 6 | 8 | pcs | 326098.5696 | 82376.8 | 408475.3696 | 2608788.5568 | 659014.4 | 3267802.9568 | 0% | 50% | 50% |  |  | 0%
|  | EQUAL TEE, DN63 | 3 | 5 | pcs | 543443.2662 | 82376.8 | 625820.0662 | 2717216.3312 | 411884 | 3129100.3312 | 0% | 50% | 50% |  |  | 0%
|  | END CAP, DN63 | 1 | 1 | pcs | 380393.9814 | 82376.8 | 462770.7814 | 380393.9814 | 82376.8 | 462770.7814 | 0% | 50% | 50% |  |  | 0%
|  | REDUCING TEE, DN63-40 | 12 | 14 | pcs | 861389.3716 | 82376.8 | 943766.1716 | 12059451.2024 | 1153275.2 | 13212726.4024 | 0% | 50% | 50% |  |  | 0%
|  | QUICK DROP, DN63-25 | 32 | 32 | pcs | 372241.5172 | 82376.8 | 454618.3172 | 11911728.5503 | 2636057.6 | 14547786.1503 | 0% | 50% | 50% |  |  | 0%
|  | PIPE TO PIPE JOINT, DN40 | 37 | 37 | pcs | 317946.1054 | 57608.1 | 375554.2054 | 11764005.8983 | 2131499.7 | 13895505.5983 | 0% | 50% | 50% |  |  | 0%
|  | LOCKABLE BRASS VALVE, DN25-1/2" FEMALE THREAD, WITH FIXING PLATE | 32 | 32 | pcs | 680241.6162 | 53385.955 | 733627.5712 | 21767731.7179 | 1708350.5613 | 23476082.2792 | 0% | 50% | 50% |  |  | 0%
|  | TWO-WAYS PNEUMATIC CONNECTOR, FEMALE THREAD G1/2" | 0 |  | pcs | 206583.4438 | 53385.955 | 259969.3989 | 0 | 0 | 0 | 0% | 50% | 50% |  |  | 0%
|  | T-BOLT, M8, 6CM | 228 | 228 | pcs | 3260.9857 | 3850 | 7110.9857 | 743504.7387 | 877800 | 1621304.7387 | 0% | 50% | 50% |  |  | 0%
|  | THREADED ROD, M8, 3 METER | 50 | 50 | pcs | 48914.7854 | 11000 | 59914.7854 | 2445739.272 | 550000 | 2995739.272 | 0% | 50% | 50% |  |  | 0%
|  | WALL MOUNTED BRACKET, 50CM | 228 | 228 | pcs | 92448.9445 | 8250 | 100698.9445 | 21078359.3418 | 1881000 | 22959359.3418 | 0% | 50% | 50% |  |  | 0%
|  | BEAM CLAMP, 2.5CM | 456 | 456 | pcs | 37990.4834 | 8250 | 46240.4834 | 17323660.4114 | 3762000 | 21085660.4114 | 0% | 0% | 0% |  |  | 0%
|  | Fire Stop | 1 | 1 | lot | 2500000 | 1000000 | 3500000 | 2500000 | 1000000 | 3500000 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 33262665.7435 | 9978799.7231 | 43241465.4666 | 33262665.7435 | 9978799.7231 | 43241465.4666 | 0% | 0% | 0% |  |  | 0%
|  | T&C | 1 | 1 | lot | 0 | 29398125.4019 | 29398125.4019 | 0 | 29398125.4019 | 29398125.4019 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
2. 3. 50. |  | Compressed Air Network Production 2 | 1 |  | PSCH |  |  |  | 160285184.4612 | 58632929.7673 | 218918114.2285 | 0% | 0% | 0% |  |  | 0%
|  | PRODUCTION 2 | [6 empty] | 83418012.7013 | 26026366.1504 | 109444378.8517 | 0% | 0% | 0% |  |  | 0%
|  | BLUE ALUMINIUM PIPE, DN40 | 109 | 210 | m | 190224.1656 | 70966.5 | 261190.6656 | 39947074.776 | 14902965 | 54850039.776 | 0% | 50% | 50% |  |  | 0%
|  | BLUE ALUMINIUM PIPE, DN25 | 56 | 59 | m | 94950.6667 | 42579.9 | 137530.5667 | 5602089.3333 | 2512214.1 | 8114303.4333 | 0% | 50% | 50% |  |  | 0%
|  | PIPE TO PIPE JOINT, DN63 | 4 | 4 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 2391606.9094 | 329507.2 | 2721114.1094 | 0% | 50% | 50% |  |  | 0%
|  | PIPE TO PIPE JOINT, DN40 | 19 | 19 | pcs | 317946.1054 | 57608.1 | 375554.2054 | 6040976.0018 | 1094553.9 | 7135529.9018 | 0% | 50% | 50% |  |  | 0%
|  | REDUCING TEE, DN63-40 | 2 | 2 | pcs | 861389.3716 | 82376.8 | 943766.1716 | 1722778.7432 | 164753.6 | 1887532.3432 | 0% | 50% | 50% |  |  | 0%
|  | TUBE CLIP, DN40 (POLYMER) | 40 | 70 | pcs | 32609.857 | 57608.1 | 90217.957 | 2282689.9872 | 4032567 | 6315256.9872 | 0% | 50% | 50% |  |  | 0%
|  | 45° ELBOW, DN40 | 6 | 6 | pcs | 741874.2458 | 57608.1 | 799482.3458 | 4451245.475 | 345648.6 | 4796894.075 | 0% | 50% | 50% |  |  | 0%
|  | QUICK DROP, DN40-25 | 10 | 10 | pcs | 318435.2532 | 57608.1 | 376043.3532 | 3184352.5321 | 576081 | 3760433.5321 | 0% | 50% | 50% |  |  | 0%
|  | BRASS VALVE, DN40-DN40 | 2 | 2 | pcs | 1451138.6347 | 57608.1 | 1508746.7347 | 2902277.2694 | 115216.2 | 3017493.4694 | 0% | 50% | 50% |  |  | 0%
|  | LOCKABLE BRASS VALVE, DN25-1/2" FEMALE THREAD, WITH FIXING PLATE | 10 | 10 | pcs | 680241.6162 | 53385.955 | 733627.5712 | 6802416.1619 | 533859.5504 | 7336275.7123 | 0% | 50% | 50% |  |  | 0%
|  | TWO-WAYS PNEUMATIC CONNECTOR, FEMALE THREAD G1/2" | 0 |  | pcs | 206583.4438 | 53385.955 | 259969.3989 | 0 | 0 | 0 | 0% | 50% | 50% |  |  | 0%
|  | T-BOLT, M8, 6CM | 40 | 40 | pcs | 3260.9857 | 3850 | 7110.9857 | 130439.4278 | 154000 | 284439.4278 | 0% | 50% | 50% |  |  | 0%
|  | THREADED ROD, M8, 3 METER | 25 | 25 | pcs | 48914.7854 | 11000 | 59914.7854 | 1222869.636 | 275000 | 1497869.636 | 0% | 50% | 50% |  |  | 0%
|  | WALL MOUNTED BRACKET, 50CM | 40 | 40 | pcs | 92448.9445 | 8250 | 100698.9445 | 3697957.7793 | 330000 | 4027957.7793 | 0% | 50% | 50% |  |  | 0%
|  | BEAM CLAMP, 2.5CM | 80 | 80 | pcs | 37990.4834 | 8250 | 46240.4834 | 3039238.6687 | 660000 | 3699238.6687 | 0% | 50% | 50% |  |  | 0%
|  | LOGICSTIC | [6 empty] | 76867171.7599 | 32606563.6169 | 109473735.3768 | 0% | 0% | 0% |  |  | 0%
|  | BLUE ALUMINIUM PIPE, DN63 | 0 | 30 | m | 362322.6857 | 115320.5625 | 477643.2482 | 10869680.5712 | 3459616.875 | 14329297.4462 | 0% | 50% | 50% |  |  | 0%
|  | BLUE ALUMINIUM PIPE, DN40 | 69 | 72 | m | 190224.1656 | 70966.5 | 261190.6656 | 13696139.9232 | 5109588 | 18805727.9232 | 0% | 50% | 50% |  |  | 0%
|  | BLUE ALUMINIUM PIPE, DN25 | 17 | 21 | m | 94950.6667 | 42579.9 | 137530.5667 | 1993964 | 894177.9 | 2888141.9 | 0% | 50% | 50% |  |  | 0%
|  | TUBE CLIP, DN63 (POLYMER) | 0 | 6 | pcs | 54295.4118 | 82376.8 | 136672.2118 | 325772.471 | 494260.8 | 820033.271 | 0% | 50% | 50% |  |  | 0%
|  | PIPE TO PIPE JOINT, DN63 | 0 | 8 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 4783213.8189 | 659014.4 | 5442228.2189 | 0% | 50% | 50% |  |  | 0%
|  | PIPE TO PIPE JOINT, DN63 | 0 | 8 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 4783213.8189 | 659014.4 | 5442228.2189 | 0% | 50% | 50% |  |  | 0%
|  | EQUAL TEE, DN63 | 0 | 6 | pcs | 543443.2662 | 82376.8 | 625820.0662 | 3260659.5974 | 494260.8 | 3754920.3974 | 0% | 50% | 50% |  |  | 0%
|  | REDUCING TEE, DN63-40 | 2 | 2 | pcs | 861389.3716 | 82376.8 | 943766.1716 | 1722778.7432 | 164753.6 | 1887532.3432 | 0% | 50% | 50% |  |  | 0%
|  | END CAP, DN63 | 1 | 1 | pcs | 380393.9814 | 82376.8 | 462770.7814 | 380393.9814 | 82376.8 | 462770.7814 | 0% | 50% | 50% |  |  | 0%
|  | TUBE CLIP, DN40 (POLYMER) | 26 | 24 | pcs | 32609.857 | 57608.1 | 90217.957 | 782636.567 | 1382594.4 | 2165230.967 | 0% | 50% | 50% |  |  | 0%
|  | PIPE TO PIPE JOINT, DN40 | 12 | 12 | pcs | 317946.1054 | 57608.1 | 375554.2054 | 3815353.2643 | 691297.2 | 4506650.4643 | 0% | 50% | 50% |  |  | 0%
|  | 90° ELBOW, DN40 | 1 | 1 | pcs | 706492.551 | 57608.1 | 764100.651 | 706492.551 | 57608.1 | 764100.651 | 0% | 50% | 50% |  |  | 0%
|  | EQUAL TEE, DN40 | 1 | 1 | pcs | 1066831.4704 | 57608.1 | 1124439.5704 | 1066831.4704 | 57608.1 | 1124439.5704 | 0% | 50% | 50% |  |  | 0%
|  | QUICK DROP, DN63-25 | 1 | 1 | pcs | 372241.5172 | 82376.8 | 454618.3172 | 372241.5172 | 82376.8 | 454618.3172 | 0% | 50% | 50% |  |  | 0%
|  | QUICK DROP, DN40-25 | 2 | 2 | pcs | 318435.2532 | 57608.1 | 376043.3532 | 636870.5064 | 115216.2 | 752086.7064 | 0% | 50% | 50% |  |  | 0%
|  | END CAP, DN40 | 2 | 2 | pcs | 529910.1756 | 57608.1 | 587518.2756 | 1059820.3512 | 115216.2 | 1175036.5512 | 0% | 50% | 50% |  |  | 0%
|  | BRASS VALVE, DN40-DN40 | 2 | 2 | pcs | 1451138.6347 | 57608.1 | 1508746.7347 | 2902277.2694 | 115216.2 | 3017493.4694 | 0% | 50% | 50% |  |  | 0%
|  | BRASS VALVE, DN25-1/2" FEMALE THREAD, WITH FIXING PLATE | 2 | 2 | pcs | 617304.5923 | 53385.955 | 670690.5473 | 1234609.1845 | 106771.9101 | 1341381.0946 | 0% | 50% | 50% |  |  | 0%
|  | TWO-WAYS PNEUMATIC CONNECTOR, FEMALE THREAD G1/2" | 0 |  | pcs | 206583.4438 | 48702.5 | 255285.9438 | 0 | 0 | 0 | 0% | 50% | 50% |  |  | 0%
|  | T-BOLT, M8, 6CM | 40 | 40 | pcs | 3260.9857 | 3850 | 7110.9857 | 130439.4278 | 154000 | 284439.4278 | 0% | 50% | 50% |  |  | 0%
|  | THREADED ROD, M8, 3 METER | 25 | 25 | pcs | 48914.7854 | 11000 | 59914.7854 | 1222869.636 | 275000 | 1497869.636 | 0% | 50% | 50% |  |  | 0%
|  | WALL MOUNTED BRACKET, 50CM | 36 | 36 | pcs | 92448.9445 | 8250 | 100698.9445 | 3328162.0013 | 297000 | 3625162.0013 | 0% | 50% | 50% |  |  | 0%
|  | BEAM CLAMP, 2.5CM | 72 | 72 | pcs | 37990.4834 | 8250 | 46240.4834 | 2735314.8018 | 594000 | 3329314.8018 | 0% | 50% | 50% |  |  | 0%
|  | Fire Stop | 1 | 1 | lot | 2500000 | 1000000 | 3500000 | 2500000 | 1000000 | 3500000 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 12557436.286 | 3767230.8858 | 16324667.1718 | 12557436.286 | 3767230.8858 | 16324667.1718 | 0% | 0% | 0% |  |  | 0%
|  | T&C | 1 | 1 | lot | 0 | 11778364.046 | 11778364.046 | 0 | 11778364.046 | 11778364.046 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. |  | Office, Social and Technical Areas (Hall 3) | [6 empty] | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 3. |  | Mechanical Engineering | [6 empty] | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
3. 3. 120. |  | Compressed Air Connections | 1 |  | PSCH | [5 empty] | 0 | 0% | 0% | 0% |  |  | 0%
4. |  | Machine hook-up (Hall 3) | [6 empty] | 246537484.7813 | 58813621.1675 | 305351105.9487 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
4. 2. |  | Mechanical Engineering | [6 empty] | 246537484.7813 | 58813621.1675 | 305351105.9487 | 0% | 0% | 0% |  |  | 0%
4. 2. 10. |  | Machine hook-up | 1 | 1 | PSCH |  |  |  | 246537484.7813 | 58813621.1675 | 305351105.9487 | 0% | 0% | 0% |  |  | 0%
|  | BLUE ALUMINIUM PIPE, DN63 | 16 | 18 | m | 362322.6857 | 115320.5625 | 477643.2482 | 6521808.3427 | 2075770.125 | 8597578.4677 | 0% | 0% | 0% |  |  | 0%
|  | BLUE ALUMINIUM PIPE, DN40 | 257 | 228 | m | 190224.1656 | 70966.5 | 261190.6656 | 43371109.7568 | 16180362 | 59551471.7568 | 0% | 0% | 0% |  |  | 0%
|  | BLUE ALUMINIUM PIPE, DN25 | 23 | 27 | m | 94950.6667 | 42579.9 | 137530.5667 | 2563668 | 1149657.3 | 3713325.3 | 0% | 0% | 0% |  |  | 0%
|  | PIPE TO PIPE JOINT, DN63 | 1 | 1 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 597901.7274 | 82376.8 | 680278.5274 | 0% | 0% | 0% |  |  | 0%
|  | REDUCING PIPE TO PIPE JOINT, DN63-DN40 | 1 | 1 | pcs | 684154.799 | 82376.8 | 766531.599 | 684154.799 | 82376.8 | 766531.599 | 0% | 0% | 0% |  |  | 0%
|  | TUBE CLIP, DN40 (POLYMER) | 92 | 77 | pcs | 32609.857 | 57608.1 | 90217.957 | 2510958.9859 | 4435823.7 | 6946782.6859 | 0% | 0% | 0% |  |  | 0%
|  | PIPE TO PIPE JOINT, DN40 | 45 | 45 | pcs | 317946.1054 | 57608.1 | 375554.2054 | 14307574.7412 | 2592364.5 | 16899939.2412 | 0% | 0% | 0% |  |  | 0%
|  | QUICK DROP, DN40-25 | 45 | 45 | pcs | 318435.2532 | 57608.1 | 376043.3532 | 14329586.3946 | 2592364.5 | 16921950.8946 | 0% | 0% | 0% |  |  | 0%
|  | Pressureless decouling | 96 | 96 | pcs | 387040 | 30056.4 | 417096.4 | 37155840 | 2885414.4 | 40041254.4 | 0% | 0% | 0% |  |  | 0%
|  | BRASS VALVE, DN63-DN63 | 1 | 1 | pcs | 2445739.272 | 82376.8 | 2528116.072 | 2445739.272 | 82376.8 | 2528116.072 | 0% | 0% | 0% |  |  | 0%
|  | BRASS VALVE, DN40-DN40 | 2 | 2 | pcs | 1451138.6347 | 57608.1 | 1508746.7347 | 2902277.2694 | 115216.2 | 3017493.4694 | 0% | 0% | 0% |  |  | 0%
|  | LOCKABLE BRASS VALVE, DN25-1/2" FEMALE THREAD, WITH FIXING PLATE | 28 | 28 | pcs | 680241.6162 | 53385.955 | 733627.5712 | 19046765.2532 | 1494806.7411 | 20541571.9943 | 0% | 0% | 0% |  |  | 0%
|  | LOCKABLE BRASS VALVE, DN25-3/8" FEMALE THREAD, WITH FIXING PLATE | 68 | 68 | pcs | 680241.6162 | 53385.955 | 733627.5712 | 46256429.9006 | 3630244.9427 | 49886674.8433 | 0% | 0% | 0% |  |  | 0%
|  | BRASS VALVE, DN25-1/2" FEMALE THREAD, WITH FIXING PLATE | 6 | 6 | pcs | 617304.5923 | 53385.955 | 670690.5473 | 3703827.5535 | 320315.7302 | 4024143.2838 | 0% | 0% | 0% |  |  | 0%
|  | T-split 3 way outlet tap | 28 | 28 | pcs | 451350 | 27500 | 478850 | 12637800 | 770000 | 13407800 | 0% | 0% | 0% |  |  | 0%
|  | T-BOLT, M8, 6CM | 92 | 92 | pcs | 3260.9857 | 3850 | 7110.9857 | 300010.684 | 354200 | 654210.684 | 0% | 0% | 0% |  |  | 0%
|  | THREADED ROD, M8, 3 METER | 50 | 50 | pcs | 48914.7854 | 11000 | 59914.7854 | 2445739.272 | 550000 | 2995739.272 | 0% | 0% | 0% |  |  | 0%
|  | WALL MOUNTED BRACKET, 50CM | 92 | 92 | pcs | 92448.9445 | 8250 | 100698.9445 | 8505302.8923 | 759000 | 9264302.8923 | 0% | 0% | 0% |  |  | 0%
|  | BEAM CLAMP, 2.5CM | 184 | 184 | pcs | 37990.4834 | 8250 | 46240.4834 | 6990248.9379 | 1518000 | 8508248.9379 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 19260740.9985 | 5778222.2996 | 25038963.2981 | 19260740.9985 | 5778222.2996 | 25038963.2981 | 0% | 0% | 0% |  |  | 0%
|  | T&C | 1 | 1 | lot | 0 | 11364728.3288 | 11364728.3288 | 0 | 11364728.3288 | 11364728.3288 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
5. |  | Scooter Garage | [6 empty] | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
6. |  | Canteen | [6 empty] | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
7. |  | Exterior Area | [6 empty] | 28542816 | 17816848.8 | 46359664.8 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
7. 3. |  | Mechanical Engineering | [6 empty] | 28542816 | 17816848.8 | 46359664.8 | 0% | 0% | 0% |  |  | 0%
7. 3. 10. |  | Underground Compressed Air Connection | 1 |  | PSCH |  |  |  | 28542816 | 17816848.8 | 46359664.8 | 0% | 0% | 0% |  |  | 0%
|  | HDPE Pipe DN100 | 115 | 115 | m | 179254.4 | 96096 | 275350.4 | 20614256 | 11051040 | 31665296 | 20% | 0% | 20% |  |  | 20%
|  | Fitting for connecting HDPE pipes with aluminum pipes | 1 | 1 | lot | 4757136 | 1427140.8 | 6184276.8 | 4757136 | 1427140.8 | 6184276.8 | 0% | 0% | 0% |  |  | 0%
|  | Hanger support & accessories | 1 | 1 | lot | 3171424 | 951427.2 | 4122851.2 | 3171424 | 951427.2 | 4122851.2 | 0% | 0% | 0% |  |  | 0%
|  | T&C | 1 | 1 | lot | 0 | 4387240.8 | 4387240.8 | 0 | 4387240.8 | 4387240.8 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
8. |  | Adjustments Hall 2 | [6 empty] | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
8. 5. |  | Additional Compressed Air Equipment | [6 empty] | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
8. 5. 10. |  | Additional Compressed Air Equipment | 1 |  | PSCH |  |  |  | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Main equipments | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | Rotary screw air compressor | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Air dryer | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Ball Valve D63 | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Ball Valve D40 | 6 |  | Pcs |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Oil removal filter | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Pressure maintainance system | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Condensate drain pipe D19 | 15 |  | m |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Condensate drain pipe D15.9 | 25 |  | m |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 |  | lot |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | T&C | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Ventilation for Air compressor | [5 empty] | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Tole 0.95mm | 12 |  | m2 |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Motor fire damper 550x500x450 | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Flexiable connection | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable Cat6A | 66 |  | m |  |  | 0 | 0 | 0 | 0 | 0% | 50% | 50% |  |  | 0%
|  | Cable 1 pair 18AWG | 22 |  | m |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/PVC/PVC 2Cx1.5mm2 | 22 |  | m |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 39 |  | m |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | GI flexible conduct D20 | 42 |  | m |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable tray 50x50x1.0mm | 7 |  | m |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Hanger support | 1 |  | lot |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 |  | lot |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
[8 empty] | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Compressed air pipes and valves | [5 empty] | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Aluminium Air pipe D63 | 11 |  | m |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Aluminium Air pipe D40 | 8 |  | m |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Fiiting for Aluminium pipe | 1 |  | lot |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Hanger support + Accessories | 1 |  | lot |  |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | IV. 4.VENTILATION | [8 empty] | 3204713406.5221 | 0% | 0% | 0% |  |  | 0%
2. |  | Production and Logistic building (Hall 3) | [6 empty] | 876156669.5216 | 245761873.2789 | 1121918542.8005 | 0 | 0 | 0 |  |  | 0%
2. 3. |  | Mechanical Engineering | [6 empty] | 876156669.5216 | 245761873.2789 | 1121918542.8005 | 0 | 0 | 0 |  |  | 0%
2. 3. 10. |  | Ventilation System Production | 1 | 1 | PSCH |  |  |  | 304034489.6043 | 189644193.2889 | 493678682.8931 | 0% | 0% | 0% |  |  | 0%
|  | Logistics Area | [6 empty] | 32646354.8705 | 20550720.3964 | 53197075.267 | 0% | 0% | 0% |  |  | 0%
|  | Overhead Propeller Fans | 2 | 2 | pcs | 0 | 6300000 | 6300000 | 0 | 12600000 | 12600000 | 0% | 0% | 0% |  |  | 0%
|  | Control panel for Overhead Fans | 1 | 1 | pcs | 19550000 | 385000 | 19935000 | 19550000 | 385000 | 19935000 | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/PVC/PVC 4Cx1.5mm2 | 160 | 163.8 | m | 25928.4 | 7485.665 | 33414.065 | 4247071.92 | 1226151.927 | 5473223.847 | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/PVC/PVC 2Cx1.5mm2 | 165 | 163.8 | m | 15443.88 | 5031.18 | 20475.06 | 2529707.544 | 824107.284 | 3353814.828 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 243 | 300 | m | 8773.9726 | 14594.0164 | 23367.989 | 2632191.7808 | 4378204.9235 | 7010396.7044 | 0% | 0% | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 7 | 7.35 | m | 3554.7229 | 5289.7059 | 8844.4288 | 26127.2135 | 38879.3382 | 65006.5517 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 15 |  | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Hanger, support | 1 | 1 | lot | 1220418.8041 | 366125.6412 | 1586544.4453 | 1220418.8041 | 366125.6412 | 1586544.4453 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 2440837.6082 | 732251.2824 | 3173088.8906 | 2440837.6082 | 732251.2824 | 3173088.8906 | 0% | 0% | 0% |  |  | 0%
|  |  | 0 | 0 | [7 empty] | 0% | 0% | 0% |  |  | 0%
|  | Production Hall 1 | 0 | 0 |  |  |  |  | 233479516.9276 | 145274230.7072 | 378753747.6348 | 0% | 0% | 0% |  |  | 0%
|  | Overhead Propeller Fans | 14 | 14 | pcs | 0 | 6300000 | 6300000 | 0 | 88200000 | 88200000 | 0% | 0% | 0% |  |  | 0%
|  | Control panel for Overhead Fans | 7 | 7 | m | 19550000 | 385000 | 19935000 | 136850000 | 2695000 | 139545000 | 0% | 0% | 0% |  |  | 0%
|  | 4Cx-1.5mm2 Cu/PVC/PVC | 1600 | 1556.5 | m | 25928.4 | 7485.665 | 33414.065 | 40357554.6 | 11651437.5725 | 52008992.1725 | 0% | 0% | 0% |  |  | 0%
|  | 2Cx-1.5mm2 Cu/PVC/PVC | 1050 | 1156.5 | m | 15443.88 | 5031.18 | 20475.06 | 17860847.22 | 5818559.67 | 23679406.89 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 2125 | 2100 | m | 8773.9726 | 14594.0164 | 23367.989 | 18425342.4658 | 30647434.4647 | 49072776.9305 | 0% | 0% | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 70 | 63 | m | 3554.7229 | 5289.7059 | 8844.4288 | 223947.544 | 333251.4706 | 557199.0145 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 150 |  | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Hanger, support | 1 | 1 | lot | 8982647.7718 | 2694794.3315 | 11677442.1033 | 8982647.7718 | 2694794.3315 | 11677442.1033 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 10779177.3261 | 3233753.1978 | 14012930.524 | 10779177.3261 | 3233753.1978 | 14012930.524 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Production Hall 2 | 0 | 0 |  |  |  |  | 30503490.5753 | 19149107.5868 | 49652598.1621 | 0% | 0% | 0% |  |  | 0%
|  | Overhead Propeller Fans | 2 | 2 | pcs | 0 | 6300000 | 6300000 | 0 | 12600000 | 12600000 | 0% | 0% | 0% |  |  | 0%
|  | Control panel for Overhead Fans | 1 | 1 | m | 19550000 | 385000 | 19935000 | 19550000 | 385000 | 19935000 | 0% | 0% | 0% |  |  | 0%
|  | 4Cx-1.5mm2 Cu/PVC/PVC | 160 | 108.15 | m | 25928.4 | 7485.665 | 33414.065 | 2804156.46 | 809574.6698 | 3613731.1298 | 0% | 0% | 0% |  |  | 0%
|  | 2Cx-1.5mm2 Cu/PVC/PVC | 165 | 170 | m | 15443.88 | 5031.18 | 20475.06 | 2625459.6 | 855300.6 | 3480760.2 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 243 | 220 | m | 8773.9726 | 14594.0164 | 23367.989 | 1930273.9726 | 3210683.6106 | 5140957.5832 | 0% | 0% | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 7 | 7.35 | m | 3554.7229 | 5289.7059 | 8844.4288 | 26127.2135 | 38879.3382 | 65006.5517 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 15 | 15 | m | 8773.9726 | 14594.0164 | 23367.989 | 131609.589 | 218910.2462 | 350519.8352 | 0% | 0% | 0% |  |  | 0%
|  | Hanger, support | 1 | 1 | lot | 1145287.9134 | 343586.374 | 1488874.2874 | 1145287.9134 | 343586.374 | 1488874.2874 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 2290575.8268 | 687172.748 | 2977748.5748 | 2290575.8268 | 687172.748 | 2977748.5748 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Interface between fire alarm and fan system | 0 | 0 |  |  |  |  | 7405127.2308 | 4670134.5985 | 12075261.8293 | 0% | 0% | 0% |  |  | 0%
| 8 | Fire signal cable: (2x1.0)mm2 Dây tín hiệu báo cháy: (2x1.0)mm2 | 830 | 830 | M | 7457.49 | 3300 | 10757.49 | 6189716.7 | 2739000 | 8928716.7 | 0% | 0% | 0% |  |  | 0%
| 10 | D16 PVC conduit & accessories Ống bảo vệ dây dẫn D16 và phụ kiện | 140 | 140 | M | 6646.8692 | 13183.4282 | 19830.2974 | 930561.6849 | 1845679.9447 | 2776241.6296 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 284848.8459 | 85454.6538 | 370303.4997 | 284848.8459 | 85454.6538 | 370303.4997 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
2. 3. 60. |  | SMOKE EXHAUST SYSTEM | [6 empty] | 572122179.9173 | 56117679.99 | 628239859.9073 | 0% | 0% | 0% |  |  | 0%
|  | Equipment | [6 empty] | 474178458 | 32835793.1 | 507014251.1 | 0% | 0% | 0% |  |  | 0%
|  | Roof smoke exhaust FAN - SEAF @26500m3/h, 100Pa, 3.0kW, 300oC in 2hrs | 6 | 6 | pcs | 43434300 | 2241801.1 | 45676101.1 | 260605800 | 13450806.6 | 274056606.6 | 0% | 0% | 0% |  |  | 0%
|  | Roof smoke exhaust FAN - SEAF @8000m3/h, 100Pa, 0.5kW, 300oC in 2hrs | 4 | 4 | pcs | 17612370 | 923094.7 | 18535464.7 | 70449480 | 3692378.8 | 74141858.8 | 0% | 0% | 0% |  |  | 0%
|  | Wall mounted smoke exhaust FAN - SEAF @26500m3/h, 100Pa, 3kW, 300oC in 2hrs | 3 | 3 | pcs | 25306446 | 2241801.1 | 27548247.1 | 75919338 | 6725403.3 | 82644741.3 | 0% | 0% | 0% |  |  | 0%
|  | Wall mounted smoke exhaust FAN - SEAF @16000m3/h, 100Pa, 1.5kW, 300oC in 2hrs | 4 | 4 | pcs | 16800960 | 2241801.1 | 19042761.1 | 67203840 | 8967204.4 | 76171044.4 | 0% | 0% | 0% |  |  | 0%
|  | Cable power supply & conduit | [6 empty] | 97943721.9173 | 23281886.89 | 121225608.8073 | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/Fr/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 1156 | 1281 | m | 60411.45 | 9350 | 69761.45 | 77387067.45 | 11977350 | 89364417.45 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D25 | 463 | 415 | m | 12762.0356 | 15805 | 28567.0356 | 5296244.7808 | 6559075 | 11855319.7808 | 0% | 0% | 0% |  |  | 0%
|  | PVC flexible conduct D25 | 120 | 53.55 | m | 8113.63 | 5559 | 13672.63 | 434484.8865 | 297684.45 | 732169.3365 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 14825924.8 | 4447777.44 | 19273702.24 | 14825924.8 | 4447777.44 | 19273702.24 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. |  | Office, Social and Technical Areas (Hall 3) | [6 empty] | 1272946321.0445 | 134316312.1879 | 1407262633.2324 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 3. |  | Mechanical Engineering | [6 empty] | 1272946321.0445 | 134316312.1879 | 1407262633.2324 | 0% | 0% | 0% |  |  | 0%
3. 3. 40. |  | Ventilation System | 1 | 1 | PSCH |  |  |  | 915624507.9952 | 94236583.2039 | 1009861091.1991 | 0% | 0% | 0% |  |  | 0%
|  | Ground floor - west side | [6 empty] | 259524148.7256 | 33244549.9752 | 292768698.7008 | 0% | 0% | 0% |  |  | 0%
|  | Equipments | [6 empty] | 32262384 | 3815280.7 | 36077664.7 | 0% | 0% | 0% |  |  | 0%
|  | Exhaust air fan in-line centrifugal type (Q = 1240/620 m3/h, 220 Pa) | 1 | 1 | pcs | 7426788 | 923094.7 | 8349882.7 | 7426788 | 923094.7 | 8349882.7 | 0% | 0% | 0% |  |  | 0%
|  | Exhaust air fan in-line centrifugal type (Q = 460/230 m3/h, 200 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 | 0% | 0% | 0% |  |  | 0%
|  | Exhaust air fan in-line centrifugal type (Q = 680/340 m3/h, 200 Pa) | 1 | 1 | pcs | 4734816 | 495000 | 5229816 | 4734816 | 495000 | 5229816 | 0% | 0% | 0% |  |  | 0%
|  | Exhaust air fan in-line centrifugal type (Q = 550/275 m3/h, 180 Pa) | 2 | 2 | pcs | 4658448 | 495000 | 5153448 | 9316896 | 990000 | 10306896 | 0% | 0% | 0% |  |  | 0%
|  | Exhaust air fan in-line centrifugal type (Q = 120 m3/h, 120 Pa) | 1 | 1 | pcs | 4734816 | 495000 | 5229816 | 4734816 | 495000 | 5229816 | 0% | 0% | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 1390620 | 417186 | 1807806 | 1390620 | 417186 | 1807806 | 0% | 0% | 0% |  |  | 0%
|  | Air grille, louver | [6 empty] | 167427120 | 9290400 | 176717520 | 0% | 0% | 0% |  |  | 0%
|  | Poppet Valves D160 | 3 | 3 | pcs | 1079160 | 84000 | 1163160 | 3237480 | 252000 | 3489480 | 0% | 0% | 0% |  |  | 0%
|  | Poppet Valves D100 | 43 | 43 | pcs | 921840 | 84000 | 1005840 | 39639120 | 3612000 | 43251120 | 0% | 0% | 0% |  |  | 0%
|  | Fresh air grille 500x200 | 18 | 18 | pcs | 1117800 | 140000 | 1257800 | 20120400 | 2520000 | 22640400 | 0% | 45% | 45% |  |  | 0%
|  | Exhaust air grille 200x200 | 1 | 1 | pcs | 797640 | 117600 | 915240 | 797640 | 117600 | 915240 | 0% | 0% | 0% |  |  | 0%
|  | Louver 200x200 + IS | 1 | 1 | pcs | 698280 | 117600 | 815880 | 698280 | 117600 | 815880 | 0% | 45% | 45% |  |  | 0%
|  | Louver 400x200 + IS | 1 | 1 | pcs | 844560 | 117600 | 962160 | 844560 | 117600 | 962160 | 0% | 45% | 45% |  |  | 0%
|  | Louver 400x250 + IS | 3 | 3 | pcs | 1073640 | 117600 | 1191240 | 3220920 | 352800 | 3573720 | 0% | 45% | 45% |  |  | 0%
|  | Louver 700x300 + IS | 1 | 1 | pcs | 2152800 | 140000 | 2292800 | 2152800 | 140000 | 2292800 | 0% | 45% | 45% |  |  | 0%
|  | Volume control damper VCD D100 | 1 | 1 | pcs | 979800 | 84000 | 1063800 | 979800 | 84000 | 1063800 | 0% | 45% | 45% |  |  | 0%
|  | Volume control damper VCD D160 | 6 | 6 | pcs | 1208880 | 84000 | 1292880 | 7253280 | 504000 | 7757280 | 0% | 45% | 45% |  |  | 0%
|  | Volume control damper VCD D200 | 1 | 1 | pcs | 1479360 | 84000 | 1563360 | 1479360 | 84000 | 1563360 | 0% | 45% | 45% |  |  | 0%
|  | Volume control controller D160 | 1 | 1 | pcs | 2718600 | 84000 | 2802600 | 2718600 | 84000 | 2802600 | 0% | 45% | 45% |  |  | 0%
|  | Pressure release flap 345x400 | 2 | 2 | pcs | 30674640 | 280000 | 30954640 | 61349280 | 560000 | 61909280 | 0% | 0% | 0% |  |  | 0%
|  | Silencer D120xL500 | 1 | 1 | pcs | 2368080 | 106400 | 2474480 | 2368080 | 106400 | 2474480 | 0% | 45% | 45% |  |  | 0%
|  | Silencer D190xL500 | 6 | 6 | pcs | 3427920 | 106400 | 3534320 | 20567520 | 638400 | 21205920 | 0% | 45% | 45% |  |  | 0%
|  | Ductwork sheet | [6 empty] | 59834644.7256 | 20138869.2752 | 79973514.0008 | 0% | 0% | 0% |  |  | 0%
|  | Rigid duct Z8, thickness 0.58mm | 52 | 51.7 | m2 | 236291.3455 | 106400 | 342691.3455 | 12216262.56 | 5500880 | 17717142.56 | 0% | 0% | 0% |  |  | 0%
|  | Insulation 6mmT | 57 | 55 | m2 | 104230.8 | 44800 | 149030.8 | 5732694 | 2464000 | 8196694 | 0% | 0% | 0% |  |  | 0%
|  | Simili for fan | 12 | 12 | pcs | 90000 | 35000 | 125000 | 1080000 | 420000 | 1500000 | 0% | 0% | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 15556006.38 | 4666801.914 | 20222808.294 | 15556006.38 | 4666801.914 | 20222808.294 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable power supply & conduit | [6 empty] | 25249681.7856 | 7087187.3612 | 32336869.1468 | 0% | 0% | 0% |  |  | 0%
|  | Timer delay | 5 | 5 | pcs | 2875000 | 82500 | 2957500 | 14375000 | 412500 | 14787500 | 0% | 0% | 0% |  |  | 0%
|  | Switch 1way - 1gang 10A-220V | 1 | 1 | m | 46800 | 54500 | 101300 | 46800 | 54500 | 101300 | 0% | 0% | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 330 | 308 | m | 22980.09 | 5743.9305 | 28724.0205 | 7077867.72 | 1769130.594 | 8846998.314 | 0% | 0% | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 9 | 9.9 | m | 3554.7229 | 5289.7059 | 8844.4288 | 35191.7569 | 52368.0882 | 87559.8451 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 333 | 308 | m | 8773.9726 | 14594.0164 | 23367.989 | 2702383.5616 | 4494957.0548 | 7197340.6165 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 1012438.7471 | 303731.6241 | 1316170.3712 | 1012438.7471 | 303731.6241 | 1316170.3712 | 0% | 0% | 0% |  |  | 0%
|  | Ground floor - east side | [6 empty] | 540527596.8724 | 42856692.0376 | 583384288.91 | 0% | 0% | 0% |  |  | 0%
|  | Equipments | [6 empty] | 41276280 | 4988745 | 46265025 | 0% | 0% | 0% |  |  | 0%
|  | Exhaust air fan in-line centrifugal type (Q = 800/400 m3/h, 200 Pa) | 1 | 1 | pcs | 4734816 | 495000 | 5229816 | 4734816 | 495000 | 5229816 | 0% | 0% | 0% |  |  | 0%
|  | Exhaust air fan in-line centrifugal type (Q = 600/300 m3/h, 220 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 | 0% | 0% | 0% |  |  | 0%
|  | Exhaust air fan in-line centrifugal type (Q = 550/275 m3/h, 180 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 | 0% | 0% | 0% |  |  | 0%
|  | Exhaust air fan in-line centrifugal type (Q = 500 m3/h, 200 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 | 0% | 0% | 0% |  |  | 0%
|  | Exhaust air fan wall type (Q = 120 m3/h, 50 Pa) | 1 | 1 | pcs | 2324562 | 495000 | 2819562 | 2324562 | 495000 | 2819562 | 0% | 0% | 0% |  |  | 0%
|  | Exhaust air fan wall type (Q = 1210 m3/h, 50 Pa) | 4 | 4 | pcs | 4615602 | 495000 | 5110602 | 18462408 | 1980000 | 20442408 | 0% | 0% | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 1779150 | 533745 | 2312895 | 1779150 | 533745 | 2312895 | 0% | 0% | 0% |  |  | 0%
|  | Air grille, louver | [6 empty] | 429116520 | 10169600 | 439286120 | 0% | 0% | 0% |  |  | 0%
|  | Poppet Valves D160 | 1 | 1 | pcs | 1079160 | 84000 | 1163160 | 1079160 | 84000 | 1163160 | 0% | 0% | 0% |  |  | 0%
|  | Poppet Valves D100 | 23 | 23 | pcs | 921840 | 84000 | 1005840 | 21202320 | 1932000 | 23134320 | 0% | 0% | 0% |  |  | 0%
|  | Fresh air grille 500x200 | 18 | 18 | pcs | 1117800 | 140000 | 1257800 | 20120400 | 2520000 | 22640400 | 0% | 0% | 0% |  |  | 0%
|  | Exhaust air grille 200x200 | 1 | 1 | pcs | 797640 | 117600 | 915240 | 797640 | 117600 | 915240 | 0% | 45% | 45% |  |  | 0%
|  | Exhaust air grille 500x200 + OBD | 13 | 13 | pcs | 1349640 | 140000 | 1489640 | 17545320 | 1820000 | 19365320 | 0% | 45% | 45% |  |  | 0%
|  | Louver 200x200 + IS | 1 | 1 | pcs | 698280 | 117600 | 815880 | 698280 | 117600 | 815880 | 0% | 45% | 45% |  |  | 0%
|  | Louver 400x250 + IS | 3 | 3 | pcs | 1073640 | 117600 | 1191240 | 3220920 | 352800 | 3573720 | 0% | 45% | 45% |  |  | 0%
|  | Louver 500x500 + IS | 4 | 4 | pcs | 2484000 | 140000 | 2624000 | 9936000 | 560000 | 10496000 | 0% | 45% | 45% |  |  | 0%
|  | Louver 700x250 + IS | 1 | 1 | pcs | 2152800 | 140000 | 2292800 | 2152800 | 140000 | 2292800 | 0% | 45% | 45% |  |  | 0%
|  | Volume control damper VCD D100 | 1 | 1 | pcs | 979800 | 84000 | 1063800 | 979800 | 84000 | 1063800 | 0% | 45% | 45% |  |  | 0%
|  | Volume control damper VCD D160 | 3 | 3 | pcs | 1208880 | 84000 | 1292880 | 3626640 | 252000 | 3878640 | 0% | 45% | 45% |  |  | 0%
|  | Volume control controller D160 | 1 | 1 | pcs | 2718600 | 84000 | 2802600 | 2718600 | 84000 | 2802600 | 0% | 45% | 45% |  |  | 0%
|  | Pressure release flap 345x400 | 2 | 2 | pcs | 30674640 | 280000 | 30954640 | 61349280 | 560000 | 61909280 | 0% | 0% | 0% |  |  | 0%
|  | Fire damper D250 | 2 | 2 | pcs | 21834360 | 140000 | 21974360 | 43668720 | 280000 | 43948720 | 0% | 0% | 0% |  |  | 0%
|  | Overflow air via fire protection flaps 400x250 | 3 | 3 | pcs | 75789600 | 280000 | 76069600 | 227368800 | 840000 | 228208800 | 0% | 0% | 0% |  |  | 0%
|  | Silencer D120xL500 | 1 | 1 | pcs | 2368080 | 106400 | 2474480 | 2368080 | 106400 | 2474480 | 0% | 45% | 45% |  |  | 0%
|  | Silencer D190xL500 | 3 | 3 | pcs | 3427920 | 106400 | 3534320 | 10283760 | 319200 | 10602960 | 0% | 45% | 45% |  |  | 0%
|  | Ductwork sheet | [6 empty] | 42937395.394 | 15270557.0262 | 58207952.4202 | 0% | 0% | 0% |  |  | 0%
|  | Rigid duct Z8, thickness 0.58mm | 44 | 46.2 | m2 | 236291.3455 | 106400 | 342691.3455 | 10916660.16 | 4915680 | 15832340.16 | 0% | 0% | 0% |  |  | 0%
|  | Insulation 6mmT | 50 | 50.6 | m2 | 104230.8 | 44800 | 149030.8 | 5274078.48 | 2266880 | 7540958.48 | 0% | 0% | 0% |  |  | 0%
|  | Simili for fan | 8 | 8 | pcs | 90000 | 35000 | 125000 | 720000 | 280000 | 1000000 | 0% | 0% | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 26026656.754 | 7807997.0262 | 33834653.7802 | 26026656.754 | 7807997.0262 | 33834653.7802 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable power supply & conduit | [6 empty] | 27197401.4784 | 12427790.0114 | 39625191.4898 | 0% | 0% | 0% |  |  | 0%
|  | Timer delay | 2 | 2 | pcs | 2875000 | 82500 | 2957500 | 5750000 | 165000 | 5915000 | 0% | 0% | 0% |  |  | 0%
|  | Switch 1way - 1gang 10A-220V | 1 | 1 | m | 46800 | 54500 | 101300 | 46800 | 54500 | 101300 | 0% | 0% | 0% |  |  | 0%
|  | Contactor + Box | 3 | 3 | m | 900000 | 163500 | 1063500 | 2700000 | 490500 | 3190500 | 0% | 0% | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 495 | 495 | m | 22980.09 | 5743.9305 | 28724.0205 | 11375144.55 | 2843245.5975 | 14218390.1475 | 0% | 0% | 0% |  |  | 0%
|  | 2C-1.5mm2 Cu/PVC/PVC | 90 | 90 | m | 15443.88 | 5031.18 | 20475.06 | 1389949.2 | 452806.2 | 1842755.4 | 0% | 0% | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 14 | 14.7 | m | 3554.7229 | 5289.7059 | 8844.4288 | 52254.4269 | 77758.6765 | 130013.1034 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D16 | 495 |  | m | 6646.8692 | 13183.4282 | 19830.2974 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 498 | 550 | m | 8773.9726 | 14594.0164 | 23367.989 | 4825684.9315 | 8026709.0265 | 12852393.958 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 1057568.3699 | 317270.511 | 1374838.8809 | 1057568.3699 | 317270.511 | 1374838.8809 | 0% | 0% | 0% |  |  | 0%
|  | Fist floor - west side | [6 empty] | 95572762.3972 | 15135341.1911 | 110708103.5883 | 0% | 0% | 0% |  |  | 0%
|  | Equipments | [6 empty] | 19632768 | 2233872 | 21866640 | 0% | 0% | 0% |  |  | 0%
|  | Exhaust air fan in-line centrifugal type (Q = 830/415 m3/h, 150 Pa) | 2 | 2 | pcs | 4734816 | 495000 | 5229816 | 9469632 | 990000 | 10459632 | 0% | 0% | 0% |  |  | 0%
|  | Exhaust air fan in-line centrifugal type (Q = 480/240 m3/h, 150 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 | 0% | 0% | 0% |  |  | 0%
|  | Exhaust air fan in-line centrifugal type (Q = 420/210 m3/h, 150 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 | 0% | 0% | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 846240 | 253872 | 1100112 | 846240 | 253872 | 1100112 | 0% | 0% | 0% |  |  | 0%
|  | Air grille, louver | [6 empty] | 47615520 | 2996000 | 50611520 | 0% | 0% | 0% |  |  | 0%
|  | Poppet Valves D100 | 15 | 15 | pcs | 921840 | 84000 | 1005840 | 13827600 | 1260000 | 15087600 | 0% | 0% | 0% |  |  | 0%
|  | Louver 700x250 + IS | 2 | 2 | pcs | 2152800 | 140000 | 2292800 | 4305600 | 280000 | 4585600 | 0% | 45% | 45% |  |  | 0%
|  | Louver 400x200 + IS | 2 | 2 | pcs | 844560 | 117600 | 962160 | 1689120 | 235200 | 1924320 | 0% | 45% | 45% |  |  | 0%
|  | Exhaust air grille EAG-600x600 | 2 | 2 | pcs | 3960600 | 140000 | 4100600 | 7921200 | 280000 | 8201200 | 0% | 45% | 45% |  |  | 0%
|  | Supply air grille EAG-300x300 | 8 | 8 | pcs | 2484000 | 117600 | 2601600 | 19872000 | 940800 | 20812800 | 0% | 45% | 45% |  |  | 0%
|  | Ductwork sheet | [6 empty] | 12042039.2045 | 4956818.7105 | 16998857.915 | 0% | 0% | 0% |  |  | 0%
|  | Rigid duct Z8, thickness 0.58mm | 25 | 25 | m2 | 236291.3455 | 106400 | 342691.3455 | 5907283.6364 | 2660000 | 8567283.6364 | 0% | 0% | 0% |  |  | 0%
|  | Insulation 6mmT | 29 | 29 | m2 | 104230.8 | 44800 | 149030.8 | 3022693.2 | 1299200 | 4321893.2 | 0% | 0% | 0% |  |  | 0%
|  | Simili for fan | 8 | 8 | pcs | 90000 | 35000 | 125000 | 720000 | 280000 | 1000000 | 0% | 0% | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 2392062.3682 | 717618.7105 | 3109681.0786 | 2392062.3682 | 717618.7105 | 3109681.0786 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable power supply & conduit | [6 empty] | 16282435.1926 | 4948650.4806 | 21231085.6733 | 0% | 0% | 0% |  |  | 0%
|  | Timer delay | 3 | 3 | pcs | 2875000 | 82500 | 2957500 | 8625000 | 247500 | 8872500 | 0% | 0% | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 220 | 220 | m | 22980.09 | 5743.9305 | 28724.0205 | 5055619.8 | 1263664.71 | 6319284.51 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 220 | 220 | m | 8773.9726 | 14594.0164 | 23367.989 | 1930273.9726 | 3210683.6106 | 5140957.5832 | 0% | 0% | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 6 | 6 | m | 3554.7229 | 5289.7059 | 8844.4288 | 21328.3375 | 31738.2353 | 53066.5728 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 650213.0825 | 195063.9248 | 845277.0073 | 650213.0825 | 195063.9248 | 845277.0073 | 0% | 0% | 0% |  |  | 0%
|  | Fist floor - esat side | [6 empty] | 20000000 | 3000000 | 23000000 | 0% | 0% | 0% |  |  | 0%
|  | Equipments | [6 empty] | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Exhaust air fan in-line centrifugal type (Q = 440/220m3/h, 150 Pa) | 3 |  | pcs | 4658448 | 495000 | 5153448 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Air grille, louver | [6 empty] | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Poppet Valves D220 | 4 |  | pcs | 1484880 | 84000 | 1568880 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Poppet Valves D100 | 19 |  | pcs | 921840 | 84000 | 1005840 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Louver 400x200 + IS | 3 |  | pcs | 844560 | 117600 | 962160 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Volume control damper VCD D100 | 1 |  | pcs | 979800 | 84000 | 1063800 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Volume control damper VCD D160 | 2 |  | pcs | 1208880 | 84000 | 1292880 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Supply air grille EAG-300x300 | 4 |  | pcs | 2484000 | 117600 | 2601600 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Silencer D120xL500 | 1 |  | pcs | 2368080 | 106400 | 2474480 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Silencer D190xL500 | 2 |  | pcs | 3427920 | 106400 | 3534320 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Ductwork sheet | [6 empty] | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Rigid duct Z8, thickness 0.58mm | 18 |  | m2 | 236291.3455 | 106400 | 342691.3455 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Insulation 6mmT | 22 |  | m2 | 104230.8 | 44800 | 149030.8 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Simili for fan | 6 |  | pcs | 90000 | 35000 | 125000 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable power supply & conduit | [6 empty] | 20000000 | 3000000 | 23000000 | 0% | 0% | 0% |  |  | 0%
|  | Timer delay | 2 |  | pcs | 2875000 | 82500 | 2957500 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 165 |  | m | 22980.09 | 5743.9305 | 28724.0205 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 165 |  | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 6 |  | m | 3554.7229 | 5289.7059 | 8844.4288 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Fire stop | 3 | 1 | lot | 20000000 | 3000000 | 23000000 | 20000000 | 3000000 | 23000000 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 |  | lot | 1000000 | 300000 | 1300000 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 3. 50. |  | Ventilation System 1st Floor Offices Ventilation Units | 1 | 1 | PSCH |  |  |  | 84938287.2586 | 5889562.8377 | 90827850.0963 | 0% | 0% | 0% |  |  | 0%
|  | west side | 0 | 0 |  |  |  | 0 | 84938287.2586 | 5889562.8377 | 90827850.0963 | 0% | 0% | 0% |  |  | 0%
|  | Equipments | [6 empty] | 80634445.35 | 3616553.635 | 84250998.985 | 0% | 0% | 0% |  |  | 0%
|  | Heat Recovery Ventilation 390 m3/h | 1 | 1 | pcs | 19802999.7 | 1064000 | 20866999.7 | 19802999.7 | 1064000 | 20866999.7 | 0% | 0% | 0% |  |  | 0%
|  | Heat Recovery Ventilation 2000 m3/h | 1 | 1 | pcs | 54096000.2 | 1400000 | 55496000.2 | 54096000.2 | 1400000 | 55496000.2 | 0% | 0% | 0% |  |  | 0%
|  | Remote wirring for ERV | 2 | 2 | pcs | 1614800 | 50400 | 1665200 | 3229600 | 100800 | 3330400 | 0% | 0% | 0% |  |  | 0%
|  | Hanger support & Accessories | 1 | 1 | lot | 3505845.45 | 1051753.635 | 4557599.085 | 3505845.45 | 1051753.635 | 4557599.085 | 0% | 0% | 0% |  |  | 0%
|  | Cable power supply & conduit | [6 empty] | 4303841.9086 | 2273009.2027 | 6576851.1113 | 0% | 0% | 0% |  |  | 0%
|  | 3C-2.5mm2 Cu/XLPE/PVC | 100 | 100 | m | 32518.74 | 7485.665 | 40004.405 | 3251874 | 748566.5 | 4000440.5 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 100 | 100 | m | 8773.9726 | 14594.0164 | 23367.989 | 877397.2603 | 1459401.6412 | 2336798.9015 | 0% | 0% | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 3 | 3 | m | 3554.7229 | 5289.7059 | 8844.4288 | 10664.1688 | 15869.1176 | 26533.2864 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 3 |  | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 163906.4796 | 49171.9439 | 213078.4235 | 163906.4796 | 49171.9439 | 213078.4235 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 3. 60. |  | Ventilation System 1st Floor Offices Ducting | 1 | 1 | PSCH |  |  |  | 272383525.7906 | 34190166.1463 | 306573691.937 | 0% | 0% | 0% |  |  | 0%
|  | west side | 0 | 0 |  |  |  | 0 | 272383525.7906 | 34190166.1463 | 306573691.937 | 0% | 0% | 0% |  |  | 0%
|  | Equipments | [6 empty] | 262643773.8955 | 29033956.5687 | 291677730.4642 | 0% | 0% | 0% |  |  | 0%
|  | Exhaust air fan in-line centrifugal type (Q = 2000m3/h, 300 Pa) | 2 | 2 | pcs | 7379058 | 923094.7 | 8302152.7 | 14758116 | 1846189.4 | 16604305.4 | 0% | 0% | 0% |  |  | 0%
|  | Duct smoke detector | 4 | 4 | pcs | 4140000 | 128800 | 4268800 | 16560000 | 515200 | 17075200 | 0% | 0% | 0% |  |  | 0%
|  | Rigid duct Z8, thickness 0.58mm | 132 | 132 | m2 | 236291.3455 | 106400 | 342691.3455 | 31190457.6 | 14044800 | 45235257.6 | 0% | 0% | 0% |  |  | 0%
|  | Insulation 16mmT | 142 | 143 | m2 | 207754.8 | 44800 | 252554.8 | 29708936.4 | 6406400 | 36115336.4 | 0% | 0% | 0% |  |  | 0%
|  | Supply air grill 300x300 | 6 | 6 | pcs | 2484000 | 117600 | 2601600 | 14904000 | 705600 | 15609600 | 0% | 45% | 45% |  |  | 0%
|  | Supply air grill 600x600 | 3 | 3 | pcs | 3960600 | 140000 | 4100600 | 11881800 | 420000 | 12301800 | 0% | 45% | 45% |  |  | 0%
|  | Exhaust air grill 600x600 | 5 | 5 | pcs | 3960600 | 140000 | 4100600 | 19803000 | 700000 | 20503000 | 0% | 45% | 45% |  |  | 0%
|  | Louver 400x200 + IS | 2 | 2 | pcs | 844560 | 117600 | 962160 | 1689120 | 235200 | 1924320 | 0% | 45% | 45% |  |  | 0%
|  | Louver 900x400 + IS | 2 | 2 | pcs | 3759120 | 140000 | 3899120 | 7518240 | 280000 | 7798240 | 0% | 45% | 45% |  |  | 0%
|  | Siliencer D240xL1000 | 2 | 2 | pcs | 6668160 | 106400 | 6774560 | 13336320 | 212800 | 13549120 | 0% | 45% | 45% |  |  | 0%
|  | Siliencer D300xL800 | 6 | 6 | pcs | 7998480 | 106400 | 8104880 | 47990880 | 638400 | 48629280 | 0% | 45% | 45% |  |  | 0%
|  | Siliencer D420XL1000 | 4 | 4 | pcs | 11155920 | 106400 | 11262320 | 44623680 | 425600 | 45049280 | 0% | 45% | 45% |  |  | 0%
|  | Hanger support & Accessories | 1 | 1 | lot | 8679223.8955 | 2603767.1687 | 11282991.0642 | 8679223.8955 | 2603767.1687 | 11282991.0642 | 0% | 0% | 0% |  |  | 0%
|  | Cable power supply & conduit | [6 empty] | 9739751.8951 | 5156209.5777 | 14895961.4728 | 0% | 0% | 0% |  |  | 0%
|  | Switch 1way - 2gang 10A-220V | 1 | 1 | m | 46800 | 54500 | 101300 | 46800 | 54500 | 101300 | 0% | 0% | 0% |  |  | 0%
|  | Contactor + Box | 4 | 4 | m | 900000 | 163500 | 1063500 | 3600000 | 654000 | 4254000 | 0% | 0% | 0% |  |  | 0%
|  | 3C-2.5mm2 Cu/XLPE/PVC | 80 | 79.2 | m | 32518.74 | 7485.665 | 40004.405 | 2575484.208 | 592864.668 | 3168348.876 | 0% | 0% | 0% |  |  | 0%
|  | 2C-1.5mm2 Cu/PVC/PVC | 80 | 79.2 | m | 15443.88 | 5031.18 | 20475.06 | 1223155.296 | 398469.456 | 1621624.752 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 76 | 160 | m | 8773.9726 | 14594.0164 | 23367.989 | 1403835.6164 | 2335042.6259 | 3738878.2423 | 0% | 0% | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 3 | 3 | m | 3554.7229 | 5289.7059 | 8844.4288 | 10664.1688 | 15869.1176 | 26533.2864 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 3 | 3 | m | 8773.9726 | 14594.0164 | 23367.989 | 26321.9178 | 43782.0492 | 70103.967 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D16 | 72 | 72 | m | 6646.8692 | 13183.4282 | 19830.2974 | 478574.5808 | 949206.8287 | 1427781.4095 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 374916.1073 | 112474.8322 | 487390.9395 | 374916.1073 | 112474.8322 | 487390.9395 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 3. 130. |  | SMOKE EXHAUST SYSTEM | [6 empty] | 143640024.0078 | 24229831.2332 | 167869855.241 | 0% | 0% | 0% |  |  | 0%
|  | WEST SIDE | [6 empty] | 32042422.6672 | 2927603.7911 | 34970026.4583 | 0% | 0% | 0% |  |  | 0%
|  | Equipment | [6 empty] | 26144496 | 990000 | 27134496 | 0% | 0% | 0% |  |  | 0%
|  | Wall mounted smoke exhaust FAN - SEAF @11550m3/h, 100Pa, 1.5kW, 300oC in 2hrs | 2 | 2 | pcs | 13072248 | 495000 | 13567248 | 26144496 | 990000 | 27134496 | 0% | 0% | 0% |  |  | 0%
|  | Cable power supply & conduit | [6 empty] | 5897926.6672 | 1937603.7911 | 7835530.4583 | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/Fr/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 70 | 66 | m | 60411.45 | 9350 | 69761.45 | 3987155.7 | 617100 | 4604255.7 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 63 | 60 | m | 8773.9726 | 14594.0164 | 23367.989 | 526438.3562 | 875640.9847 | 1402079.3409 | 0% | 0% | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 7 | 7 | m | 3554.7229 | 5289.7059 | 8844.4288 | 24883.0604 | 37027.9412 | 61911.0016 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 1359449.5506 | 407834.8652 | 1767284.4158 | 1359449.5506 | 407834.8652 | 1767284.4158 | 0% | 0% | 0% |  |  | 0%
|  | EAST SIDE | [6 empty] | 111597601.3406 | 21302227.4421 | 132899828.7827 | 0% | 0% | 0% |  |  | 0%
|  | Equipment | [6 empty] | 23339970 | 2769284.1 | 26109254.1 | 0% | 0% | 0% |  |  | 0%
|  | AXIAL Smoke exhaust FAN - SEAF @7320m3/h, 180Pa, 1.25kW, 300oC in 2hrs | 3 | 3 | pcs | 7779990 | 923094.7 | 8703084.7 | 23339970 | 2769284.1 | 26109254.1 | 0% | 0% | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 1051350 | 315405 | 1366755 | 1051350 | 315405 | 1366755 | 0% | 0% | 0% |  |  | 0%
|  | Air grille, louver | [6 empty] | 23084640 | 840000 | 23924640 | 0% | 0% | 0% |  |  | 0%
|  | Smoke Exhaust grille 1200x600 + OBD | 3 | 3 | pcs | 3281640 | 140000 | 3421640 | 9844920 | 420000 | 10264920 | 0% | 0% | 0% |  |  | 0%
|  | Louver 1000x400 + IS | 3 | 3 | pcs | 4413240 | 140000 | 4553240 | 13239720 | 420000 | 13659720 | 0% | 0% | 0% |  |  | 0%
|  | Ductwork sheet | [6 empty] | 48893376.2182 | 12696041.9127 | 61589418.1309 | 0% | 0% | 0% |  |  | 0%
|  | Rigid duct Z8, thickness 0.58mm | 47 | 42 | m2 | 236291.3455 | 106400 | 342691.3455 | 9924236.5091 | 4468800 | 14393036.5091 | 0% | 0% | 0% |  |  | 0%
|  | Rockwool 50mmT | 36 | 36 | m2 | 408250 | 61600 | 469850 | 14697000 | 2217600 | 16914600 | 0% | 0% | 0% |  |  | 0%
|  | Fireproof paint for smoke duct | 33 | 33 | m2 | 432000 | 89600 | 521600 | 14256000 | 2956800 | 17212800 | 0% | 0% | 0% |  |  | 0%
|  | Simili for fan | 6 | 6 | pcs | 90000 | 35000 | 125000 | 540000 | 210000 | 750000 | 0% | 0% | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 9476139.7091 | 2842841.9127 | 12318981.6218 | 9476139.7091 | 2842841.9127 | 12318981.6218 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Cable power supply & conduit | [6 empty] | 15228265.1224 | 4681496.4294 | 19909761.5518 | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/Fr/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 195 | 195 | m | 60411.45 | 9350 | 69761.45 | 11780232.75 | 1823250 | 13603482.75 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 176 | 150 | m | 8773.9726 | 14594.0164 | 23367.989 | 1316095.8904 | 2189102.4618 | 3505198.3522 | 0% | 0% | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 7 | 7 | m | 3554.7229 | 5289.7059 | 8844.4288 | 24883.0604 | 37027.9412 | 61911.0016 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 2107053.4216 | 632116.0265 | 2739169.448 | 2107053.4216 | 632116.0265 | 2739169.448 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
4. |  | Machine hook-up (Hall 3) | [6 empty] | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
5. |  | Scooter Garage | [6 empty] | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
6. |  | Canteen | [6 empty] | 435189667.08 | 72472708.1683 | 507662375.2483 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
6. 3. 60. |  | Ventilation System Overhead Fans | 1 | 1 | PSCH |  |  |  | 413174538.3791 | 66328606.8362 | 479503145.2154 | 0% | 0% | 0% |  |  | 0%
|  | Overhead Propeller Fans, D=3m | 10 | 10 | pcs | 37185000 | 4950000 | 42135000 | 371850000 | 49500000 | 421350000 | 45% | 0% | 45% |  |  | 45%
|  | 3C-2.5mm2 Cu/XLPE/PVC | 250 | 245 | m | 32518.74 | 7485.665 | 40004.405 | 7967091.3 | 1833987.925 | 9801079.225 | 0% | 50% | 50% |  |  | 0%
|  | Control Cable Cu/PVC 2cx1.5mm2 | 450 | 350 | m | 15443.88 | 5031.18 | 20475.06 | 5405358 | 1760913 | 7166271 | 0% | 50% | 50% |  |  | 0%
|  | PVC conduit D20 | 515 | 400 | m | 8773.9726 | 14594.0164 | 23367.989 | 3509589.0411 | 5837606.5647 | 9347195.6058 | 0% | 0% | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 20 | 15 | m | 3554.7229 | 5289.7059 | 8844.4288 | 53320.8438 | 79345.5882 | 132666.432 | 0% | 0% | 0% |  |  | 0%
|  | Hanger, support | 1 | 1 | lot | 10452505.369 | 3135751.6107 | 13588256.9797 | 10452505.369 | 3135751.6107 | 13588256.9797 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 13936673.8253 | 4181002.1476 | 18117675.9729 | 13936673.8253 | 4181002.1476 | 18117675.9729 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
6. 3. 70. |  | Ventilation System | 1 | 1 | PSCH |  |  |  | 22015128.7008 | 6144101.3321 | 28159230.0329 | 0% | 0% | 0% |  |  | 0%
|  | Exhaust air fan Q=100m3/h, 50Pa, type wall | 2 | 2 | pcs | 2324562 | 495000 | 2819562 | 4649124 | 990000 | 5639124 | 0% | 0% | 0% |  |  | 0%
|  | Exhaust air fan Q=140m3/h, 50Pa, type wall | 1 | 1 | pcs | 2324562 | 495000 | 2819562 | 2324562 | 495000 | 2819562 | 0% | 0% | 0% |  |  | 0%
|  | Exhaust air fan Q=180m3/h, 50Pa, type wall | 1 | 1 | pcs | 2324562 | 495000 | 2819562 | 2324562 | 495000 | 2819562 | 0% | 0% | 0% |  |  | 0%
|  | Exhaust air fan Q=300m3/h, 50Pa, type wall | 1 | 1 | pcs | 2735040 | 495000 | 3230040 | 2735040 | 495000 | 3230040 | 0% | 0% | 0% |  |  | 0%
|  | Louver 250x250 + IS | 5 | 5 | pcs | 897000 | 117600 | 1014600 | 4485000 | 588000 | 5073000 | 0% | 45% | 45% |  |  | 0%
|  | Switch 1way - 1gang 10A-250V | 5 | 5 | pcs | 46800 | 54500 | 101300 | 234000 | 272500 | 506500 | 0% | 0% | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 111 | 109.25 | m | 22980.09 | 5743.9305 | 28724.0205 | 2510574.8325 | 627524.4071 | 3138099.2396 | 0% | 0% | 0% |  |  | 0%
|  | PVC flexible conduct D20 | 8 | 11.5 | m | 3554.7229 | 5289.7059 | 8844.4288 | 40879.3136 | 60831.6176 | 101710.9312 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 119 | 109.25 | m | 8773.9726 | 14594.0164 | 23367.989 | 958556.5068 | 1594396.293 | 2552952.7998 | 0% | 0% | 0% |  |  | 0%
|  | Hanger, support, Accessories | 1 | 1 | lot | 1752830.0479 | 525849.0144 | 2278679.0623 | 1752830.0479 | 525849.0144 | 2278679.0623 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | V. AC SYSTEM | [8 empty] | 2228147077.7132 | 0% | 0% | 0% |  |  | 0%
3. |  | Office, Social and Technical Areas (Hall 3) | [6 empty] | 1992902350.6879 | 211748078.3635 | 2204650429.0514 | 0 | 0 | 0 |  |  | 0%
3. 3. 70. |  | Air Conditioning | 1 | 1 | PSCH |  |  |  | 1992902350.6879 | 211748078.3635 | 2204650429.0514 | 0% | 0% | 0% |  |  | 0%
|  | west side | [6 empty] | 1284913905.8615 | 131256535.4444 | 1416170441.3058 | 0% | 0% | 0% |  |  | 0%
|  | Equipments | [6 empty] | 1094815450 | 55012677.04 | 1149828127.04 | 0% | 0% | 0% |  |  | 0%
|  | Outdoor unit 56KW | 1 | 1 | pcs | 109143100 | 4434383.52 | 113577483.52 | 109143100 | 4434383.52 | 113577483.52 | 0% | 45% | 45% |  |  | 0%
|  | Outdoor unit 50.4KW | 1 | 1 | pcs | 102932500 | 4434383.52 | 107366883.52 | 102932500 | 4434383.52 | 107366883.52 | 0% | 45% | 45% |  |  | 0%
|  | Outdoor unit 40KW | 1 | 1 | pcs | 72590100 | 3920000 | 76510100 | 72590100 | 3920000 | 76510100 | 0% | 45% | 45% |  |  | 0%
|  | Outdoor unit 33.6KW | 1 | 1 | pcs | 62381000 | 3920000 | 66301000 | 62381000 | 3920000 | 66301000 | 0% | 45% | 45% |  |  | 0%
|  | Outdoor unit 14KW | 1 | 1 | pcs | 30222170 | 840000 | 31062170 | 30222170 | 840000 | 31062170 | 0% | 45% | 45% |  |  | 0%
|  | Indoor unit cassette type, 9.0kW | 6 | 6 | pcs | 9845660 | 537600 | 10383260 | 59073960 | 3225600 | 62299560 | 0% | 45% | 45% |  |  | 0%
|  | Indoor unit cassette type, 7.1kW | 11 | 11 | pcs | 9569780 | 537600 | 10107380 | 105267580 | 5913600 | 111181180 | 0% | 45% | 45% |  |  | 0%
|  | Indoor unit cassette type, 6kW | 7 | 7 | pcs | 8741260 | 504000 | 9245260 | 61188820 | 3528000 | 64716820 | 0% | 45% | 45% |  |  | 0%
|  | Indoor unit cassette type, 5.6kW | 4 | 4 | pcs | 8464170 | 504000 | 8968170 | 33856680 | 2016000 | 35872680 | 0% | 45% | 45% |  |  | 0%
|  | Indoor unit cassette type, 3.6kW | 1 | 1 | pcs | 7911200 | 504000 | 8415200 | 7911200 | 504000 | 8415200 | 0% | 45% | 45% |  |  | 0%
|  | Split Air conditioner, indoor unit wall type, cooling capacity 4.5kW | 4 | 4 | pcs | 12599730 | 621600 | 13221330 | 50398920 | 2486400 | 52885320 | 0% | 45% | 45% |  |  | 0%
|  | Split Air conditioner, indoor unit wall type, cooling capacity 6.3kW | 2 | 2 | pcs | 16773020 | 733600 | 17506620 | 33546040 | 1467200 | 35013240 | 0% | 45% | 45% |  |  | 0%
|  | Split Air conditioner, indoor unit wall type, cooling capacity 7.1kW | 1 | 1 | pcs | 31227680 | 733600 | 31961280 | 31227680 | 733600 | 31961280 | 0% | 45% | 45% |  |  | 0%
|  | Dehumidifiers 1200m3/h | 6 | 6 | pcs | 19690000 | 168000 | 19858000 | 118140000 | 1008000 | 119148000 | 0% | 45% | 45% |  |  | 0%
|  | Controller center for AC | 1 | 1 | pcs | 11532400 | 168000 | 11700400 | 11532400 | 168000 | 11700400 | 0% | 45% | 45% |  |  | 0%
|  | Remote wirring for AC | 36 | 36 | pcs | 1614800 | 50400 | 1665200 | 58132800 | 1814400 | 59947200 | 0% | 45% | 45% |  |  | 0%
|  | Controller for AC Split (IT Room, UPS room) | 2 | 2 | pcs | 873400 | 140000 | 1013400 | 1746800 | 280000 | 2026800 | 0% | 45% | 45% |  |  | 0%
|  | DB controller | 1 | 1 | pcs | 13200000 | 280000 | 13480000 | 13200000 | 280000 | 13480000 | 0% | 45% | 45% |  |  | 0%
|  | Gas splitter | 16 | 44 | pcs | 1815000 | 0 | 1815000 | 79860000 | 0 | 79860000 | 0% | 45% | 45% |  |  | 0%
|  | Concrete base for outdoor unit | 5 | 5 | pcs | 1300000 | 500000 | 1800000 | 6500000 | 2500000 | 9000000 | 0% | 45% | 45% |  |  | 0%
|  | Extra refrigerant charge R410a or R32 | 1 | 1 | lot | 7500000 | 0 | 7500000 | 7500000 | 0 | 7500000 | 0% | 45% | 45% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 38463700 | 11539110 | 50002810 | 38463700 | 11539110 | 50002810 | 0% | 0% | 0% |  |  | 0%
|  | Copper pipe | [6 empty] | 67284685.7759 | 24357916.6293 | 91642602.4052 | 0% | 0% | 0% |  |  | 0%
|  | Ø6.4mm-0.81mmT | 78 | 112.7 | m | 38160 | 22400 | 60560 | 4300632 | 2524480 | 6825112 | 0% | 0% | 0% |  |  | 0%
|  | Ø9.5mm-0.81mmT | 249 | 203.55 | m | 60000 | 23520 | 83520 | 12213000 | 4787496 | 17000496 | 0% | 0% | 0% |  |  | 0%
|  | Ø12.7mm-0.81mmT | 90 | 119.6 | m | 81840 | 28000 | 109840 | 9788064 | 3348800 | 13136864 | 0% | 0% | 0% |  |  | 0%
|  | Ø15.9mm-0.81mmT | 262 | 210.45 | m | 103760 | 38808 | 142568 | 21836292 | 8167143.6 | 30003435.6 | 0% | 0% | 0% |  |  | 0%
|  | Ø19.1mm-0.81mmT | 0 | 0 | m | 129600 | 42560 | 172160 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Ø22.2mm-0.81mmT | 18 | 27.6 | m | 147310.3448 | 49392 | 196702.3448 | 4065765.5172 | 1363219.2 | 5428984.7172 | 0% | 0% | 0% |  |  | 0%
|  | Ø28.6mm-1.0mmT | 54 | 52.9 | m | 234206.8966 | 63504 | 297710.8966 | 12389544.8276 | 3359361.6 | 15748906.4276 | 0% | 0% | 0% |  |  | 0%
|  | Hanger support & Accessories | 1 | 1 | lot | 2691387.431 | 807416.2293 | 3498803.6603 | 2691387.431 | 807416.2293 | 3498803.6603 | 0% | 0% | 0% |  |  | 0%
|  | Insulation copper pipe | [6 empty] | 14380586.125 | 5959615.4335 | 20340201.5585 | 0% | 0% | 0% |  |  | 0%
|  | Ø6.4mm-15mmT | 78 | 112.7 | m | 15358.8 | 5600 | 20958.8 | 1730936.76 | 631120 | 2362056.76 | 0% | 0% | 0% |  |  | 0%
|  | Ø9.5mm-15mmT | 249 | 203.55 | m | 16754.4 | 5644.8 | 22399.2 | 3410358.12 | 1148999.04 | 4559357.16 | 0% | 0% | 0% |  |  | 0%
|  | Ø12.7mm-15mmT | 90 | 119.6 | m | 17871.6 | 7728 | 25599.6 | 2137443.36 | 924268.8 | 3061712.16 | 0% | 0% | 0% |  |  | 0%
|  | Ø15.9mm-15mmT | 262 | 210.45 | m | 20664 | 9172.8 | 29836.8 | 4348738.8 | 1930415.76 | 6279154.56 | 0% | 0% | 0% |  |  | 0%
|  | Ø19.1mm-15mmT | 0 | 0 | m | 23176.8 | 101595.2 | 124772 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Ø22.2mm-15mmT | 18 | 27.6 | m | 24852 | 11995.2 | 36847.2 | 685915.2 | 331067.52 | 1016982.72 | 0% | 0% | 0% |  |  | 0%
|  | Ø28.6mm-15mmT | 54 | 52.9 | m | 28203.6 | 15523.2 | 43726.8 | 1491970.44 | 821177.28 | 2313147.72 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 575223.445 | 172567.0335 | 747790.4785 | 575223.445 | 172567.0335 | 747790.4785 | 0% | 0% | 0% |  |  | 0%
|  | Condensate pipe | [6 empty] | 3756725.28 | 3113650.848 | 6870376.128 | 0% | 0% | 0% |  |  | 0%
|  | uPVC-Ø27mm-PN12 | 124 | 127.6 | m | 8236.8 | 11743.2 | 19980 | 1051015.68 | 1498432.32 | 2549448 | 0% | 0% | 0% |  |  | 0%
|  | uPVC-Ø34mm-PN12 | 59 | 72.6 | m | 16286.4 | 12639.2 | 28925.6 | 1182392.64 | 917605.92 | 2099998.56 | 0% | 0% | 0% |  |  | 0%
|  | uPVC-Ø42mm-PN12 | 33 | 29.7 | m | 21528 | 14560 | 36088 | 639381.6 | 432432 | 1071813.6 | 0% | 0% | 0% |  |  | 0%
|  | Fitting for UpVC | 1 | 1 | lot | 662951.52 | 198885.456 | 861836.976 | 662951.52 | 198885.456 | 861836.976 | 0% | 0% | 0% |  |  | 0%
|  | Hanger support & Accessories | 1 | 1 | lot | 220983.84 | 66295.152 | 287278.992 | 220983.84 | 66295.152 | 287278.992 | 0% | 0% | 0% |  |  | 0%
|  | Insulation condensate pipe | 0 | 0 |  |  |  |  | 3118303.375 | 3148490.6805 | 6266794.0555 | 0% | 0% | 0% |  |  | 0%
|  | Ø27mm-10mmT | 124 | 127.6 | m | 11169.6 | 11743.2 | 22912.8 | 1425240.96 | 1498432.32 | 2923673.28 | 0% | 0% | 0% |  |  | 0%
|  | Ø34mm-10mmT | 59 | 72.6 | m | 14520 | 15523.2 | 30043.2 | 1054152 | 1126984.32 | 2181136.32 | 0% | 0% | 0% |  |  | 0%
|  | Ø42mm-10mmT | 33 | 29.7 | m | 17312.4 | 16352 | 33664.4 | 514178.28 | 485654.4 | 999832.68 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 124732.135 | 37419.6405 | 162151.7755 | 124732.135 | 37419.6405 | 162151.7755 | 0% | 0% | 0% |  |  | 0%
|  | Cable power supply & conduit | [6 empty] | 101558155.3056 | 39664184.8131 | 141222340.1186 | 0% | 0% | 0% |  |  | 0%
|  | Double socket 1P-16A-250V | 6 | 6 | pcs | 150480 | 54500 | 204980 | 902880 | 327000 | 1229880 | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 4x1Cx4mm2+E4mm2 | 200 | 174.9 | m | 72299.4 | 17189.865 | 89489.265 | 12645165.06 | 3006507.3885 | 15651672.4485 | 0% | 0% | 0% |  |  | 0%
|  | 3Cx-2.5mm2Cu/XLPE/PVC | 260 | 177.1 | m | 32518.74 | 7485.665 | 40004.405 | 5759068.854 | 1325711.2715 | 7084780.1255 | 0% | 0% | 0% |  |  | 0%
|  | 3Cx-1.5mm2Cu/XLPE/PVC | 450 | 338.8 | m | 22980.09 | 5743.9305 | 28724.0205 | 7785654.492 | 1946043.6534 | 9731698.1454 | 0% | 0% | 0% |  |  | 0%
|  | 4Cx-1.5mm2Cu/PVC/PVC | 105 | 111.1 | m | 25928.4 | 7485.665 | 33414.065 | 2880645.24 | 831657.3815 | 3712302.6215 | 0% | 0% | 0% |  |  | 0%
|  | 2Cx-1.5mm2Cu/PVC/PVC | 495 | 332.2 | m | 15443.88 | 5031.18 | 20475.06 | 5130456.936 | 1671357.996 | 6801814.932 | 0% | 0% | 0% |  |  | 0%
|  | 18 core AWG 1 pair | 540 | 607.2 | m | 21976.8 | 3920 | 25896.8 | 13344312.96 | 2380224 | 15724536.96 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 104 | 660 | m | 8773.9726 | 14594.0164 | 23367.989 | 5790821.9178 | 9632050.8318 | 15422872.7496 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D16 | 378 | 935 | m | 6646.8692 | 13183.4282 | 19830.2974 | 6214822.6815 | 12326505.345 | 18541328.0265 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D16 | 891 | 0 | m | 6646.8692 | 13183.4282 | 19830.2974 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 143 | 0 | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D25 | 140 | 154 | m | 12762.0356 | 15805 | 28567.0356 | 1965353.4849 | 2433970 | 4399323.4849 | 0% | 0% | 0% |  |  | 0%
|  | PVC flexible conduit D20 | 39 | 55 | m | 3554.7229 | 5289.7059 | 8844.4288 | 195509.7606 | 290933.8235 | 486443.5841 | 0% | 0% | 0% |  |  | 0%
|  | PVC flexible conduit D20 | 22 | 0 | m | 3554.7229 | 5289.7059 | 8844.4288 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Cable tray 200x100x2.0mm | 42 | 45 | m | 776880 | 51045.8655 | 827925.8655 | 34959600 | 2297063.9462 | 37256663.9462 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 3983863.9187 | 1195159.1756 | 5179023.0944 | 3983863.9187 | 1195159.1756 | 5179023.0944 | 0% | 0% | 0% |  |  | 0%
|  | East side | [6 empty] | 707988444.8264 | 80491542.9191 | 788479987.7455 | 0% | 0% | 0% |  |  | 0%
|  | Equipments | [6 empty] | 606357980 | 35796884 | 642154864 | 0% | 0% | 0% |  |  | 0%
|  | Outdoor unit 33.6KW | 2 | 2 | pcs | 62381000 | 3920000 | 66301000 | 124762000 | 7840000 | 132602000 | 0% | 45% | 45% |  |  | 0%
|  | Outdoor unit 22.4KW | 1 | 1 | pcs | 48310460 | 3304000 | 51614460 | 48310460 | 3304000 | 51614460 | 0% | 45% | 45% |  |  | 0%
|  | Outdoor unit 14KW | 1 | 1 | pcs | 30222170 | 840000 | 31062170 | 30222170 | 840000 | 31062170 | 0% | 45% | 45% |  |  | 0%
|  | Indoor unit cassette type, 9.0kW | 6 | 6 | pcs | 9845660 | 537600 | 10383260 | 59073960 | 3225600 | 62299560 | 0% | 45% | 45% |  |  | 0%
|  | Indoor unit cassette type, 7.1kW | 7 | 7 | pcs | 9569780 | 537600 | 10107380 | 66988460 | 3763200 | 70751660 | 0% | 45% | 45% |  |  | 0%
|  | Indoor unit cassette type, 6kW | 1 | 1 | pcs | 8741260 | 504000 | 9245260 | 8741260 | 504000 | 9245260 | 0% | 45% | 45% |  |  | 0%
|  | Split Air conditioner, indoor unit wall type, cooling capacity 4.5kW | 2 | 2 | pcs | 12599730 | 621600 | 13221330 | 25199460 | 1243200 | 26442660 | 0% | 45% | 45% |  |  | 0%
|  | Split Air conditioner, indoor unit wall type, cooling capacity 7.1kW | 2 | 2 | pcs | 31227680 | 733600 | 31961280 | 62455360 | 1467200 | 63922560 | 0% | 45% | 45% |  |  | 0%
|  | Split Air conditioner, indoor unit cassette type, cooling capacity 5.2kW | 1 | 1 | pcs | 21620170 | 733600 | 22353770 | 21620170 | 733600 | 22353770 | 0% | 45% | 45% |  |  | 0%
|  | Dehumidifiers 1500m3/h | 3 | 3 | pcs | 19690000 | 168000 | 19858000 | 59070000 | 504000 | 59574000 | 0% | 45% | 45% |  |  | 0%
|  | Remote wirring for AC | 19 | 19 | pcs | 1614800 | 168000 | 1782800 | 30681200 | 3192000 | 33873200 | 0% | 45% | 45% |  |  | 0%
|  | Controller for AC | 2 | 10 | pcs | 873400 | 50400 | 923800 | 8734000 | 504000 | 9238000 | 0% | 45% | 45% |  |  | 0%
|  | DB controller | 1 | 1 | pcs | 13200000 | 280000 | 13480000 | 13200000 | 280000 | 13480000 | 0% | 45% | 45% |  |  | 0%
|  | Gas splitter | 5 | 8 | pcs | 1659900 | 0 | 1659900 | 13279200 | 0 | 13279200 | 0% | 45% | 45% |  |  | 0%
|  | Concrete base for outdoor unit | 4 | 4 | pcs | 1300000 | 500000 | 1800000 | 5200000 | 2000000 | 7200000 | 0% | 45% | 45% |  |  | 0%
|  | Extra refrigerant charge R410a or R32 | 1 | 1 | lot | 7500000 | 0 | 7500000 | 7500000 | 0 | 7500000 | 0% | 0% | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 21320280 | 6396084 | 27716364 | 21320280 | 6396084 | 27716364 | 0% | 0% | 0% |  |  | 0%
|  | Copper pipe | 0 | 0 |  |  |  |  | 28355645.2586 | 9993875.3431 | 38349520.6017 | 0% | 0% | 0% |  |  | 0%
|  | Ø6.4mm-0.81mmT | 18 | 19.95 | m | 38160 | 22400 | 60560 | 761292 | 446880 | 1208172 | 0% | 0% | 0% |  |  | 0%
|  | Ø9.5mm-0.81mmT | 86 | 94.5 | m | 60000 | 23520 | 83520 | 5670000 | 2222640 | 7892640 | 0% | 0% | 0% |  |  | 0%
|  | Ø12.7mm-0.81mmT | 28 | 30.45 | m | 81840 | 28000 | 109840 | 2492028 | 852600 | 3344628 | 0% | 0% | 0% |  |  | 0%
|  | Ø15.9mm-0.81mmT | 92 | 101.85 | m | 103760 | 38808 | 142568 | 10567956 | 3952594.8 | 14520550.8 | 0% | 0% | 0% |  |  | 0%
|  | Ø19.1mm-0.81mmT | 3 | 3.15 | m | 129600 | 42560 | 172160 | 408240 | 134064 | 542304 | 0% | 0% | 0% |  |  | 0%
|  | Ø22.2mm-0.81mmT | 6 | 6.3 | m | 147310.3448 | 49392 | 196702.3448 | 928055.1724 | 311169.6 | 1239224.7724 | 0% | 0% | 0% |  |  | 0%
|  | Ø28.6mm-1.0mmT | 25 | 27.3 | m | 234206.8966 | 63504 | 297710.8966 | 6393848.2759 | 1733659.2 | 8127507.4759 | 0% | 0% | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 1134225.8103 | 340267.7431 | 1474493.5534 | 1134225.8103 | 340267.7431 | 1474493.5534 | 0% | 0% | 0% |  |  | 0%
|  | Insulation copper pipe | 0 | 0 |  |  |  |  | 5768802.375 | 2703324.5085 | 8472126.8835 | 0% | 0% | 0% |  |  | 0%
|  | Ø6.4mm-15mmT | 18 | 19.95 | m | 15358.8 | 5600 | 20958.8 | 306408.06 | 111720 | 418128.06 | 0% | 0% | 0% |  |  | 0%
|  | Ø9.5mm-15mmT | 86 | 94.5 | m | 16754.4 | 5644.8 | 22399.2 | 1583290.8 | 533433.6 | 2116724.4 | 0% | 0% | 0% |  |  | 0%
|  | Ø12.7mm-15mmT | 28 | 30.45 | m | 17871.6 | 7728 | 25599.6 | 544190.22 | 235317.6 | 779507.82 | 0% | 0% | 0% |  |  | 0%
|  | Ø15.9mm-15mmT | 92 | 101.85 | m | 20664 | 9172.8 | 29836.8 | 2104628.4 | 934249.68 | 3038878.08 | 0% | 0% | 0% |  |  | 0%
|  | Ø19.1mm-15mmT | 3 | 3.15 | m | 23176.8 | 101595.2 | 124772 | 73006.92 | 320024.88 | 393031.8 | 0% | 0% | 0% |  |  | 0%
|  | Ø22.2mm-15mmT | 6 | 6.3 | m | 24852 | 11995.2 | 36847.2 | 156567.6 | 75569.76 | 232137.36 | 0% | 0% | 0% |  |  | 0%
|  | Ø28.6mm-15mmT | 25 | 27.3 | m | 28203.6 | 15523.2 | 43726.8 | 769958.28 | 423783.36 | 1193741.64 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 230752.095 | 69225.6285 | 299977.7235 | 230752.095 | 69225.6285 | 299977.7235 | 0% | 0% | 0% |  |  | 0%
|  | Condensate pipe | 0 | 0 |  |  |  |  | 4058656.35 | 2146658.409 | 6205314.759 | 0% | 0% | 0% |  |  | 0%
|  | uPVC-Ø27mm-PN12 | 46 | 50.4 | m | 8236.8 | 11743.2 | 19980 | 415134.72 | 591857.28 | 1006992 | 0% | 0% | 0% |  |  | 0%
|  | uPVC-Ø34mm-PN12 | 38 | 42 | m | 16286.4 | 12639.2 | 28925.6 | 684028.8 | 530846.4 | 1214875.2 | 0% | 0% | 0% |  |  | 0%
|  | uPVC-Ø42mm-PN12 | 15 | 16.8 | m | 21528 | 14560 | 36088 | 361670.4 | 244608 | 606278.4 | 0% | 0% | 0% |  |  | 0%
|  | Fitting for UpVC | 1 | 1 | lot | 1953259.56 | 585977.868 | 2539237.428 | 1953259.56 | 585977.868 | 2539237.428 | 0% | 0% | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 644562.87 | 193368.861 | 837931.731 | 644562.87 | 193368.861 | 837931.731 | 0% | 0% | 0% |  |  | 0%
|  | Insulation condensate pipe | 0 | 0 |  |  |  |  | 1524621 | 1536840.732 | 3061461.732 | 0% | 0% | 0% |  |  | 0%
|  | Ø27mm-10mmT | 46 | 50.4 | m | 11169.6 | 11743.2 | 22912.8 | 562947.84 | 591857.28 | 1154805.12 | 0% | 0% | 0% |  |  | 0%
|  | Ø34mm-10mmT | 38 | 42 | m | 14520 | 15523.2 | 30043.2 | 609840 | 651974.4 | 1261814.4 | 0% | 0% | 0% |  |  | 0%
|  | Ø42mm-10mmT | 15 | 16.8 | m | 17312.4 | 16352 | 33664.4 | 290848.32 | 274713.6 | 565561.92 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 60984.84 | 18295.452 | 79280.292 | 60984.84 | 18295.452 | 79280.292 | 0% | 0% | 0% |  |  | 0%
|  | Cable power supply & conduit | 0 | 0 |  |  |  |  | 61922739.8428 | 28313959.9265 | 90236699.7693 | 0% | 0% | 0% |  |  | 0%
|  | Double socket 1P-16A-250V | 3 | 3 | pcs | 150480 | 54500 | 204980 | 451440 | 163500 | 614940 | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 4x1Cx4mm2+E4mm2 | 135 | 168 | m | 72299.4 | 17189.865 | 89489.265 | 12146299.2 | 2887897.32 | 15034196.52 | 0% | 0% | 0% |  |  | 0%
|  | 3Cx-2.5mm2Cu/XLPE/PVC | 155 | 43.05 | m | 32518.74 | 7485.665 | 40004.405 | 1399931.757 | 322257.8783 | 1722189.6353 | 0% | 0% | 0% |  |  | 0%
|  | 3Cx-1.5mm2Cu/XLPE/PVC | 219 | 260.4 | m | 22980.09 | 5743.9305 | 28724.0205 | 5984015.436 | 1495719.5022 | 7479734.9382 | 0% | 0% | 0% |  |  | 0%
|  | 4Cx-1.5mm2 Cu/PVC/PVC | 75 | 70.35 | m | 25928.4 | 7485.665 | 33414.065 | 1824062.94 | 526616.5328 | 2350679.4728 | 0% | 0% | 0% |  |  | 0%
|  | 2Cx-1.5mm2 Cu/PVC/PVC | 546 | 176.4 | m | 15443.88 | 5031.18 | 20475.06 | 2724300.432 | 887500.152 | 3611800.584 | 0% | 0% | 0% |  |  | 0%
|  | 18 core AWG 1 pair | 253 | 396.9 | m | 21976.8 | 3920 | 25896.8 | 8722591.92 | 1555848 | 10278439.92 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 62 | 336 | m | 8773.9726 | 14594.0164 | 23367.989 | 2948054.7945 | 4903589.5144 | 7851644.3089 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D16 | 327 | 840 | m | 6646.8692 | 13183.4282 | 19830.2974 | 5583370.1096 | 11074079.6682 | 16657449.7778 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D16 | 1023 | 0 | m | 6646.8692 | 13183.4282 | 19830.2974 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 86 | 0 | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D25 | 99 | 160 | m | 12762.0356 | 15805 | 28567.0356 | 2041925.6986 | 2528800 | 4570725.6986 | 0% | 0% | 0% |  |  | 0%
|  | PVC flexible conduit D20 | 21 | 31.5 | m | 3554.7229 | 5289.7059 | 8844.4288 | 111973.772 | 166625.7353 | 278599.5073 | 0% | 0% | 0% |  |  | 0%
|  | PVC flexible conduit D20 | 11 | 11 | m | 3554.7229 | 5289.7059 | 8844.4288 | 39101.9521 | 58186.7647 | 97288.7168 | 0% | 0% | 0% |  |  | 0%
|  | Cable tray 200x100x2.0mm | 19 | 20 | m | 776880 | 51045.8655 | 827925.8655 | 15537600 | 1020917.3094 | 16558517.3094 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 2408071.831 | 722421.5493 | 3130493.3802 | 2408071.831 | 722421.5493 | 3130493.3802 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
4. |  | Machine hook-up (Hall 3) | [8 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
5. |  | Scooter Garage | [8 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
6. |  | Canteen | [6 empty] | 21057187.7199 | 2439460.942 | 23496648.6619 | 0% | 0% | 0% |  |  | 0%
6. 3. 50. |  | Air Conditioning | 1 | 1 | PSCH |  |  |  | 21057187.7199 | 2439460.942 | 23496648.6619 | 0% | 0% | 0% |  |  | 0%
|  | Split Air conditioner, indoor unit wall type, cooling capacity 2.5kW | 1 | 1 | pcs | 15455330 | 621600 | 16076930 | 15455330 | 621600 | 16076930 | 0% | 45% | 45% |  |  | 0%
|  | Remote wirring for AC | 1 | 1 | pcs | 1614800 | 50400 | 1665200 | 1614800 | 50400 | 1665200 | 0% | 45% | 45% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 775915 | 232774.5 | 1008689.5 | 775915 | 232774.5 | 1008689.5 | 0% | 0% | 0% |  |  | 0%
|  | Copper pipe | 0 | 0 |  |  |  |  | 1022500 | 471470 | 1493970 | 0% | 0% | 0% |  |  | 0%
|  | Ø6.4mm-0.81mmT | 10 | 10 | m | 38160 | 22400 | 60560 | 381600 | 224000 | 605600 | 0% | 0% | 0% |  |  | 0%
|  | Ø9.5mm-0.81mmT | 10 | 10 | m | 60000 | 23520 | 83520 | 600000 | 235200 | 835200 | 0% | 0% | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 40900 | 12270 | 53170 | 40900 | 12270 | 53170 | 0% | 0% | 0% |  |  | 0%
|  | Insulation copper pipe | 0 | 0 |  |  |  |  | 334512.5 | 116462.15 | 450974.65 | 0% | 0% | 0% |  |  | 0%
|  | Ø6.4mm-15mmT | 10 | 10 | m | 15358.8 | 5600 | 20958.8 | 153588 | 56000 | 209588 | 0% | 0% | 0% |  |  | 0%
|  | Ø9.5mm-15mmT | 10 | 10 | m | 16754.4 | 5644.8 | 22399.2 | 167544 | 56448 | 223992 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 13380.5 | 4014.15 | 17394.65 | 13380.5 | 4014.15 | 17394.65 | 0% | 0% | 0% |  |  | 0%
|  | Condensate pipe | 0 | 0 |  |  |  |  | 107712 | 125035.2 | 232747.2 | 0% | 0% | 0% |  |  | 0%
|  | uPVC-Ø27mm-PN12 | 10 | 10 | m | 8236.8 | 11743.2 | 19980 | 82368 | 117432 | 199800 | 0% | 0% | 0% |  |  | 0%
|  | Fitting for UpVC | 1 | 1 | lot | 19008 | 5702.4 | 24710.4 | 19008 | 5702.4 | 24710.4 | 0% | 0% | 0% |  |  | 0%
|  | Hanger support & Sub materials | 1 | 1 | lot | 6336 | 1900.8 | 8236.8 | 6336 | 1900.8 | 8236.8 | 0% | 0% | 0% |  |  | 0%
|  | Insulation condensate pipe | 0 | 0 |  |  |  |  | 116350 | 118828.2 | 235178.2 | 0% | 0% | 0% |  |  | 0%
|  | Ø27mm-10mmT | 10 | 10 | m | 11169.6 | 11743.2 | 22912.8 | 111696 | 117432 | 229128 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 4654 | 1396.2 | 6050.2 | 4654 | 1396.2 | 6050.2 | 0% | 0% | 0% |  |  | 0%
|  | Cable power supply & conduit | 0 | 0 |  |  |  |  | 1630068.2199 | 702890.892 | 2332959.1119 | 0% | 0% | 0% |  |  | 0%
|  | 3Cx-2.5mm2Cu/XLPE/PVC | 15 | 15 | m | 32518.74 | 7485.665 | 40004.405 | 487781.1 | 112284.975 | 600066.075 | 0% | 0% | 0% |  |  | 0%
|  | 3Cx-1.5mm2Cu/XLPE/PVC | 15 | 15 | m | 22980.09 | 5743.9305 | 28724.0205 | 344701.35 | 86158.9575 | 430860.3075 | 0% | 0% | 0% |  |  | 0%
|  | 4Cx-1.5mm2 Cu/PVC/PVC | 10 | 10 | m | 25928.4 | 7485.665 | 33414.065 | 259284 | 74856.65 | 334140.65 | 0% | 0% | 0% |  |  | 0%
|  | 18 core AWG 1 pair | 10 | 10 | m | 26400 | 3360 | 29760 | 264000 | 33600 | 297600 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 15 | 15 | m | 8773.9726 | 14594.0164 | 23367.989 | 131609.589 | 218910.2462 | 350519.8352 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D16 | 12 | 12 | m | 6646.8692 | 13183.4282 | 19830.2974 | 79762.4301 | 158201.1381 | 237963.5683 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 62929.7507 | 18878.9252 | 81808.6759 | 62929.7507 | 18878.9252 | 81808.6759 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | VI. PLUMBING | [8 empty] | 2878365804.8714 | 0% | 0% | 0% |  |  | 0%
3. |  | Office, Social and Technical Areas (Hall 3) | [6 empty] | 2135112119.4552 | 210437879.8945 | 2345549999.3497 | 0 | 0 | 0 |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 3. |  | Mechanical Engineering | [6 empty] | 2135112119.4552 | 210437879.8945 | 2345549999.3497 | 0% | 0% | 0% |  |  | 0%
3. 3. 10. |  | Waste Water System | 1 | 1 | PSCH |  |  |  | 195924697.8575 | 71484007.4162 | 267408705.2737 | 0% | 0% | 0% |  |  | 0%
|  | West side | 0 | 0 | m | 0 | 0 | 0 | 79936135.2 | 44199519.52 | 124135654.72 | 0% | 0% | 0% |  |  | 0%
|  | uPVC pipe D200 - PN6 | 35 | 40 | m | 356616 | 71941.408 | 428557.408 | 14264640 | 2877656.32 | 17142296.32 | 0% | 15% | 15%
|  | uPVC pipe D168 - PN6 | 40 | 65 | m | 179337.6 | 57600.928 | 236938.528 | 11656944 | 3744060.32 | 15401004.32 | 30% | 15% | 45%
|  | uPVC pipe D114 - PN6 | 115 | 156 | m | 93225.6 | 42504 | 135729.6 | 14543193.6 | 6630624 | 21173817.6 | 30% | 15% | 45%
|  | uPVC pipe D90 - PN6 | 185 | 209 | m | 65145.6 | 36064 | 101209.6 | 13615430.4 | 7537376 | 21152806.4 | 30% | 15% | 45%
|  | uPVC pipe D60 - PN6 | 153 | 187 | m | 29858.4 | 24884.16 | 54742.56 | 5583520.8 | 4653337.92 | 10236858.72 | 30% | 15% | 45%
|  | uPVC pipe D42 - PN6 | 65 | 68 | m | 21528 | 17851.68 | 39379.68 | 1463904 | 1213914.24 | 2677818.24 | 30% | 15% | 45%
|  | uPVC Fitting | 1 | 1 | lot | 14106376.8 | 4231913.04 | 18338289.84 | 14106376.8 | 4231913.04 | 18338289.84 | 30% | 15% | 45%
|  | Excavation & backfill | 37 | 37 | m3 | 0 | 200000 | 200000 | 0 | 7400000 | 7400000 | 70% | 10% | 80%
|  | Connect to existing manhole | 1 | 1 | lot | 0 | 3000000 | 3000000 | 0 | 3000000 | 3000000 | 0% | 10% | 10%
|  | Connect to existing pipe | 1 | 1 | lot | 0 | 1500000 | 1500000 | 0 | 1500000 | 1500000 | 0% | 10% | 10%
|  | Accessories | 1 | 1 | lot | 4702125.6 | 1410637.68 | 6112763.28 | 4702125.6 | 1410637.68 | 6112763.28 | 0% | 10% | 10%
|  | East side | 0 |  | m |  |  |  | 115988562.6575 | 27284487.8962 | 143273050.5537 | 0% | 0% | 0%
|  | Submersible Pump Q=5M3/H, H=8MH20 | 2 | 2 | pcs | 19613000 | 616000 | 20229000 | 39226000 | 1232000 | 40458000 | 0% | 0% | 0%
|  | Auto coupling Rp2' | 2 | 2 | pcs | 4488000 | 0 | 4488000 | 8976000 | 0 | 8976000 | 0% | 0% | 0%
|  | Slider + chain | 2 | 2 | pcs | 3850000 | 0 | 3850000 | 7700000 | 0 | 7700000 | 0% | 0% | 0%
|  | Float for submersible pump | 2 | 2 | pcs | 3850000 | 168000 | 4018000 | 7700000 | 336000 | 8036000 | 0% | 0% | 0%
|  | Electrical control panel for submeriable pump | 1 | 1 | pcs | 13420000 | 840000 | 14260000 | 13420000 | 840000 | 14260000 | 0% | 0% | 0%
|  | Check valve DN50 | 1 | 1 | pcs | 174200 | 61600 | 235800 | 174200 | 61600 | 235800 | 0% | 0% | 0%
|  | Gate valve DN50 | 1 | 1 | pcs | 128700 | 61600 | 190300 | 128700 | 61600 | 190300 | 0% | 0% | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 30 | 30 | m | 40467 | 9350 | 49817 | 1214010 | 280500 | 1494510 | 0% | 0% | 0%
|  | PVC conduit D20 | 30 | 30 | m | 8773.9726 | 14594.0164 | 23367.989 | 263219.1781 | 437820.4924 | 701039.6704 | 0% | 0% | 0%
|  | uPVC pipe D168 - PN6 | 29 | 35 | m | 179337.6 | 57600.928 | 236938.528 | 6276816 | 2016032.48 | 8292848.48 | 30% | 15% | 45%
|  | uPVC pipe D114 - PN6 | 39 | 45 | m | 93225.6 | 42504 | 135729.6 | 4195152 | 1912680 | 6107832 | 30% | 15% | 45%
|  | uPVC pipe D90 - PN6 | 149 | 167 | m | 65145.6 | 36064 | 101209.6 | 10879315.2 | 6022688 | 16902003.2 | 30% | 15% | 45%
|  | uPVC pipe D60 - PN6 | 101 | 124 | m | 29858.4 | 24884.16 | 54742.56 | 3702441.6 | 3085635.84 | 6788077.44 | 30% | 15% | 45%
|  | uPVC pipe D42 - PN6 | 18 | 23 | m | 21528 | 17851.68 | 39379.68 | 495144 | 410588.64 | 905732.64 | 30% | 15% | 45%
|  | Pipe clean out D60 | 1 | 1 | pcs | 106423.2 | 28000 | 134423.2 | 106423.2 | 28000 | 134423.2 | 30% | 10% | 40%
|  | uPVC Fitting | 1 | 1 | lot | 5976856.1096 | 1793056.8329 | 7769912.9425 | 5976856.1096 | 1793056.8329 | 7769912.9425 | 30% | 15% | 45%
|  | Excavation & backfill | 21 | 28 | m3 | 0 | 200000 | 200000 | 0 | 5600000 | 5600000 | 70% | 10% | 80%
|  | Connect to existing manhole | 1 | 1 | lot | 0 | 1500000 | 1500000 | 0 | 1500000 | 1500000 | 0% | 0% | 0%
|  | Accessories | 1 | 1 | lot | 5554285.3699 | 1666285.611 | 7220570.9808 | 5554285.3699 | 1666285.611 | 7220570.9808 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 3. 20. |  | Service Water System | 1 | 1 | PSCH |  |  |  | 350026408.4568 | 59395813.3191 | 409422221.7759 | 0% | 0% | 0% |  |  | 0%
|  | West side | [6 empty] | 205749865.9577 | 34591531.4404 | 240341397.398 | 0% | 0% | 0% |  |  | 0%
|  | Pump room | [6 empty] | 149717065.9577 | 8068928.1916 | 157785994.1492 | 0% | 0% | 0% |  |  | 0%
|  | Booster pump Q=9.3 m3, H=30m | 2 | 2 | set | 30745000 | 728000 | 31473000 | 61490000 | 1456000 | 62946000 | 0% | 50% | 50% |  |  | 0%
|  | Electrical control panel for booster pump | 1 | 1 | set | 44440000 | 1400000 | 45840000 | 44440000 | 1400000 | 45840000 | 0% | 0% | 0% |  |  | 0%
|  | Pressure tank 100l | 1 | 1 | pcs | 7915200 | 168000 | 8083200 | 7915200 | 168000 | 8083200 | 0% | 0% | 0% |  |  | 0%
|  | Storage tank 3m3 | 1 | 1 | pcs | 9970909.0909 | 322000 | 10292909.0909 | 9970909.0909 | 322000 | 10292909.0909 | 0% | 0% | 0% |  |  | 0%
|  | Filter | 1 | 1 | set | 10800000 | 225400 | 11025400 | 10800000 | 225400 | 11025400 | 0% | 0% | 0% |  |  | 0%
|  | Water metter DN40 | 1 | 1 | pcs | 2154000 | 75152 | 2229152 | 2154000 | 75152 | 2229152 | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/PVC/PVC 2Cx1.5mm2 | 20 | 25 | m | 15443.88 | 5031.18 | 20475.06 | 386097 | 125779.5 | 511876.5 | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 20 | 25 | m | 40467 | 9350 | 49817 | 1011675 | 233750 | 1245425 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 40 | 50 | m | 8773.9726 | 14594.0164 | 23367.989 | 438698.6301 | 729700.8206 | 1168399.4507 | 0% | 0% | 0% |  |  | 0%
|  | Hanger + Support | 1 | 1 | lot | 6172492.3537 | 1851747.7061 | 8024240.0598 | 6172492.3537 | 1851747.7061 | 8024240.0598 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 4937993.8829 | 1481398.1649 | 6419392.0478 | 4937993.8829 | 1481398.1649 | 6419392.0478 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Valve | [6 empty] | 31053568.8 | 3110074.6696 | 34163643.4696 | 0% | 0% | 0% |  |  | 0%
|  | Pressure Gauges | 1 | 1 | pcs | 1008000 | 49588 | 1057588 | 1008000 | 49588 | 1057588 | 0% | 0% | 0% |  |  | 0%
|  | Flexible DN40 | 4 | 4 | pcs | 825600 | 75152 | 900752 | 3302400 | 300608 | 3603008 | 0% | 0% | 0% |  |  | 0%
|  | Float level indicator | 1 | 1 | pcs | 4200000 | 168000 | 4368000 | 4200000 | 168000 | 4368000 | 0% | 0% | 0% |  |  | 0%
|  | Float valve DN40 | 1 | 1 | pcs | 2809200 | 75152 | 2884352 | 2809200 | 75152 | 2884352 | 0% | 0% | 0% |  |  | 0%
|  | Y-Strainer DN40 | 2 | 2 | pcs | 726000 | 75152 | 801152 | 1452000 | 150304 | 1602304 | 0% | 0% | 0% |  |  | 0%
|  | Safety valve DN40 | 3 | 3 | pcs | 3133200 | 75152 | 3208352 | 9399600 | 225456 | 9625056 | 0% | 0% | 0% |  |  | 0%
|  | Check valve DN40 | 3 | 3 | pcs | 867600 | 75152 | 942752 | 2602800 | 225456 | 2828256 | 0% | 0% | 0% |  |  | 0%
|  | Gate valve DN40 | 4 | 4 | pcs | 726000 | 75152 | 801152 | 2904000 | 300608 | 3204608 | 0% | 0% | 0% |  |  | 0%
|  | Gate valve DN25 | 1 | 1 | pcs | 322800 | 50880.368 | 373680.368 | 322800 | 50880.368 | 373680.368 | 0% | 0% | 0% |  |  | 0%
|  | Gate valve DN32 PPR | 5 | 7 | pcs | 99122.4 | 58877.3007 | 157999.7007 | 693856.8 | 412141.105 | 1105997.905 | 0% | 0% | 0% |  |  | 0%
|  | Gate valve DN25 PPR | 3 | 2 | pcs | 85924.8 | 49415.0989 | 135339.8989 | 171849.6 | 98830.1978 | 270679.7978 | 0% | 0% | 0% |  |  | 0%
|  | Gate valve DN20 PPR | 10 | 15 | pcs | 63367.2 | 45472.3119 | 108839.5119 | 950508 | 682084.6788 | 1632592.6788 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 1236554.4 | 370966.32 | 1607520.72 | 1236554.4 | 370966.32 | 1607520.72 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0%
|  | Cold water pipe | [6 empty] | 21159921.6 | 22158696.668 | 43318618.268 | 0% | 0% | 0%
|  | PPR pipe D75 - PN10 | 10 | 11 | m | 99964.8 | 39200 | 139164.8 | 1099612.8 | 431200 | 1530812.8 | 0% | 0% | 0%
|  | PPR pipe D63 - PN10 | 23 | 25 | m | 71884.8 | 34720 | 106604.8 | 1797120 | 868000 | 2665120 | 0% | 0% | 0%
|  | PPR pipe D50 - PN10 | 21 | 26 | m | 45208.8 | 28000 | 73208.8 | 1175428.8 | 728000 | 1903428.8 | 0% | 0% | 0%
|  | PPR pipe D40 - PN10 | 29 | 31 | m | 30841.2 | 25388.1544 | 56229.3544 | 956077.2 | 787032.7864 | 1743109.9864 | 0% | 0% | 0%
|  | PPR pipe D32 - PN10 | 47 | 72 | m | 22978.8 | 22306.7432 | 45285.5432 | 1654473.6 | 1606085.5104 | 3260559.1104 | 0% | 0% | 0%
|  | PPR pipe D25 - PN10 | 68 | 87 | m | 17737.2 | 18258.8168 | 35996.0168 | 1543136.4 | 1588517.0616 | 3131653.4616 | 0% | 0% | 0%
|  | PPR pipe D20 - PN10 | 272 | 297 | m | 9921.6 | 15682.8168 | 25604.4168 | 2946715.2 | 4657796.5896 | 7604511.7896 | 0% | 0% | 0%
|  | PPR Fitting | 1 | 1 | lot | 2578284 | 773485.2 | 3351769.2 | 2578284 | 773485.2 | 3351769.2 | 0% | 0% | 0%
|  | uPVC pipe D60 - PN10 | 54 | 62 | m | 35287.2 | 24884.16 | 60171.36 | 2187806.4 | 1542817.92 | 3730624.32 | 0% | 40% | 40%
|  | uPVC pipe D34 - PN10 | 104 | 118 | m | 16286.4 | 13440 | 29726.4 | 1921795.2 | 1585920 | 3507715.2 | 0% | 40% | 40%
|  | uPVC Fitting | 1 | 1 | lot | 948369.6 | 284510.88 | 1232880.48 | 948369.6 | 284510.88 | 1232880.48 | 0% | 40% | 40%
|  | Connect to existing pipe | 1 | 1 | lot | 0 | 1000000 | 1000000 | 0 | 1000000 | 1000000 | 0% | 0% | 0% |  |  | 0%
|  | Excavation & backfill | 14 | 28 | m3 | 0 | 200000 | 200000 | 0 | 5600000 | 5600000 | 0% | 0% | 0%
[12 empty] | 0% | 0% | 0%
|  | Accessories + Support | 1 | 1 | lot | 2351102.4 | 705330.72 | 3056433.12 | 2351102.4 | 705330.72 | 3056433.12 | 0% | 0% | 0%
|  | Hot water pipe | [6 empty] | 3819309.6 | 1253831.9112 | 5073141.5112 | 0% | 0% | 0%
|  | PPR pipe D20 - PN20 | 7 | 9 | m | 12261.6 | 15682.8168 | 27944.4168 | 110354.4 | 141145.3512 | 251499.7512 | 0% | 0% | 0%
|  | PPR Fitting | 1 | 1 | lot | 25466.4 | 7639.92 | 33106.32 | 25466.4 | 7639.92 | 33106.32 | 0% | 0% | 0%
|  | Fire stop | 1 | 1 | lot | 3500000 | 1050000 | 4550000 | 3500000 | 1050000 | 4550000 | 0% | 0% | 0%
[12 empty] | 0% | 0% | 0%
|  | Accessories + Support | 1 | 1 | lot | 183488.8 | 55046.64 | 238535.44 | 183488.8 | 55046.64 | 238535.44 | 0% | 0% | 0% |  |  | 0%
|  | East side | [6 empty] | 144276542.4991 | 24804281.8787 | 169080824.3779 | 0% | 0% | 0% |  |  | 0%
|  | Pump room | [6 empty] | 121538562.8991 | 7728105.642 | 129266668.5411 | 0% | 0% | 0% |  |  | 0%
|  | Booster pump Q=9.3 m3, H=30m | 2 | 2 | set | 17380000 | 616000 | 17996000 | 34760000 | 1232000 | 35992000 | 0% | 50% | 50% |  |  | 0%
|  | Electrical control panel for booster pump | 1 | 1 | set | 44440000 | 1400000 | 45840000 | 44440000 | 1400000 | 45840000 | 0% | 0% | 0% |  |  | 0%
|  | Pressure tank 100l | 1 | 1 | pcs | 7915200 | 168000 | 8083200 | 7915200 | 168000 | 8083200 | 0% | 0% | 0% |  |  | 0%
|  | Storage tank 3m3 | 1 | 1 | pcs | 9970909.0909 | 322000 | 10292909.0909 | 9970909.0909 | 322000 | 10292909.0909 | 0% | 0% | 0% |  |  | 0%
|  | Filter | 1 | 1 | set | 10800000 | 225400 | 11025400 | 10800000 | 225400 | 11025400 | 0% | 0% | 0% |  |  | 0%
|  | Water metter DN25 | 1 | 1 | pcs | 1014000 | 50880.368 | 1064880.368 | 1014000 | 50880.368 | 1064880.368 | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/PVC/PVC 2Cx1.5mm2 | 20 | 25 | m | 15443.88 | 5031.18 | 20475.06 | 386097 | 125779.5 | 511876.5 | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 20 | 25 | m | 40467 | 9350 | 49817 | 1011675 | 233750 | 1245425 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 40 | 50 | m | 8773.9726 | 14594.0164 | 23367.989 | 438698.6301 | 729700.8206 | 1168399.4507 | 0% | 0% | 0% |  |  | 0%
|  | Hanger + Support | 1 | 1 | lot | 4909992.3537 | 1472997.7061 | 6382990.0598 | 4909992.3537 | 1472997.7061 | 6382990.0598 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 5891990.8244 | 1767597.2473 | 7659588.0717 | 5891990.8244 | 1767597.2473 | 7659588.0717 | 0% | 0% | 0% |  |  | 0%
|  | Valve | [6 empty] | 15191076.4 | 2017377.4463 | 17208453.8463 | 0% | 0% | 0% |  |  | 0%
|  | Pressure Gauges | 1 | 1 | pcs | 1008000 | 49588 | 1057588 | 1008000 | 49588 | 1057588 | 0% | 0% | 0% |  |  | 0%
|  | Flexible DN25 | 4 | 4 | pcs | 568800 | 50880.368 | 619680.368 | 2275200 | 203521.472 | 2478721.472 | 0% | 0% | 0% |  |  | 0%
|  | Float level indicator | 1 | 1 | pcs | 4200000 | 168000 | 4368000 | 4200000 | 168000 | 4368000 | 0% | 0% | 0% |  |  | 0%
|  | Float valve DN25 | 1 | 1 | pcs | 770400 | 50880.368 | 821280.368 | 770400 | 50880.368 | 821280.368 | 0% | 0% | 0% |  |  | 0%
|  | Y-Strainer DN25 | 2 | 2 | pcs | 322800 | 50880.368 | 373680.368 | 645600 | 101760.736 | 747360.736 | 0% | 0% | 0% |  |  | 0%
|  | Safety valve DN25 | 1 | 1 | pcs | 1376400 | 50880.368 | 1427280.368 | 1376400 | 50880.368 | 1427280.368 | 0% | 0% | 0% |  |  | 0%
|  | Check valve DN25 | 3 | 3 | pcs | 480000 | 50880.368 | 530880.368 | 1440000 | 152641.104 | 1592641.104 | 0% | 0% | 0% |  |  | 0%
|  | Gate valve DN25 | 5 | 5 | pcs | 322800 | 50880.368 | 373680.368 | 1614000 | 254401.84 | 1868401.84 | 0% | 0% | 0% |  |  | 0%
|  | Gate valve DN25 PPR | 8 | 8 | pcs | 85924.8 | 49415.0989 | 135339.8989 | 687398.4 | 395320.791 | 1082719.191 | 0% | 0% | 0%
|  | Gate valve DN20 PPR | 9 | 9 | pcs | 63367.2 | 45472.3119 | 108839.5119 | 570304.8 | 409250.8073 | 979555.6073 | 0% | 0% | 0%
|  | Accessories | 1 | 1 | lot | 603773.2 | 181131.96 | 784905.16 | 603773.2 | 181131.96 | 784905.16 | 0% | 0% | 0%
|  | Cold water pipe | [6 empty] | 7418628 | 14924281.536 | 22342909.536 | 0% | 0% | 0%
|  | PPR pipe D63 - PN10 | 10 | 12 | m | 71884.8 | 34720 | 106604.8 | 862617.6 | 416640 | 1279257.6 | 0% | 0% | 0%
|  | PPR pipe D40 - PN10 | 5 | 7 | m | 30841.2 | 25388.1544 | 56229.3544 | 215888.4 | 177717.0808 | 393605.4808 | 0% | 0% | 0%
|  | PPR pipe D32 - PN10 | 29 | 32 | m | 22978.8 | 22306.7432 | 45285.5432 | 735321.6 | 713815.7824 | 1449137.3824 | 0% | 0% | 0%
|  | PPR pipe D25 - PN10 | 21 | 28 | m | 17737.2 | 18258.8168 | 35996.0168 | 496641.6 | 511246.8704 | 1007888.4704 | 0% | 0% | 0%
|  | PPR pipe D20 - PN10 | 130 | 143 | m | 9921.6 | 15682.8168 | 25604.4168 | 1418788.8 | 2242642.8024 | 3661431.6024 | 0% | 0% | 0%
|  | PPR Fitting | 1 | 1 | lot | 860598 | 258179.4 | 1118777.4 | 860598 | 258179.4 | 1118777.4 | 0% | 0% | 0%
|  | uPVC pipe D34 - PN10 | 104 | 100 | m | 16286.4 | 13440 | 29726.4 | 1628640 | 1344000 | 2972640 | 0% | 40% | 40%
|  | uPVC Fitting | 1 | 1 | lot | 375840 | 112752 | 488592 | 375840 | 112752 | 488592 | 0% | 40% | 40%
|  | Connect to existing pipe | 1 | 1 | lot | 0 | 1000000 | 1000000 | 0 | 1000000 | 1000000 | 0% | 0% | 0%
|  | Excavation & backfill | 10 | 20 | m3 | 0 | 200000 | 200000 | 0 | 4000000 | 4000000 | 0% | 0% | 0% |  |  | 0%
|  | Cut wall and backfill | 91 | 130 | m | 0 | 30000 | 30000 | 0 | 3900000 | 3900000 | 0% | 0% | 0% |  |  | 0%
|  | Accessories + Support | 1 | 1 | lot | 824292 | 247287.6 | 1071579.6 | 824292 | 247287.6 | 1071579.6 | 0% | 0% | 0% |  |  | 0%
|  | Hot water pipe | [6 empty] | 128275.2 | 134517.2544 | 262792.4544 | 0% | 0% | 0% |  |  | 0%
|  | PPR pipe D20 - PN20 | 7 | 8 | m | 12261.6 | 15682.8168 | 27944.4168 | 98092.8 | 125462.5344 | 223555.3344 | 0% | 0% | 0% |  |  | 0%
|  | PPR Fitting | 1 | 1 | lot | 22636.8 | 6791.04 | 29427.84 | 22636.8 | 6791.04 | 29427.84 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Accessories + Support | 1 | 1 | lot | 7545.6 | 2263.68 | 9809.28 | 7545.6 | 2263.68 | 9809.28 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
3. 3. 30. |  | Sanitary Furnishings | 1 | 1 | PSCH |  |  |  | 1589161013.1409 | 79558059.1592 | 1668719072.3001 | 0% | 0% | 0% |  |  | 0%
|  | West side | 0 |  | m |  |  |  |  | 50588775.2524 | 1032592350.3478 | 0% | 0% | 0% |  |  | 0%
|  | Santinary | [6 empty] | 982003575.0955 | 50588775.2524 | 1032592350.3478 | 0% | 0% | 0% |  |  | 0%
|  | Water closet one block, included stop valve | 37 | 37 | pcs | 14750000 | 413200.4464 | 15163200.4464 | 545750000 | 15288416.5168 | 561038416.5168 | 0% | 0% | 0% |  |  | 0%
|  | Water closet spray | 37 | 37 | pcs | 638000 | 50232 | 688232 | 23606000 | 1858584 | 25464584 | 0% | 0% | 0% |  |  | 0%
|  | Paper holder | 37 | 37 | pcs | 653000 | 50232 | 703232 | 24161000 | 1858584 | 26019584 | 0% | 0% | 0% |  |  | 0%
|  | Lavatory under-mounted type | 43 | 43 | pcs | 1443000 | 300710.7768 | 1743710.7768 | 62049000 | 12930563.4024 | 74979563.4024 | 0% | 0% | 0% |  |  | 0%
|  | Water tap for lavatory (cold) | 43 | 43 | pcs | 953000 | 50232 | 1003232 | 40979000 | 2159976 | 43138976 | 0% | 0% | 0% |  |  | 0%
|  | Mirror (H=1m, L according to the lavabo table) | 33 | 33 | m2 | 768883.5 | 123200 | 892083.5 | 25373155.5 | 4065600 | 29438755.5 | 0% | 0% | 0% |  |  | 0%
|  | Hand Dryer | 8 | 8 | pcs | 5018000 | 61600 | 5079600 | 40144000 | 492800 | 40636800 | 0% | 0% | 0% |  |  | 0%
|  | Uniral included flush valve | 15 | 15 | pcs | 11003000 | 280000 | 11283000 | 165045000 | 4200000 | 169245000 | 0% | 0% | 0% |  |  | 0%
|  | Floor drain DN80 | 16 | 16 | pcs | 855000 | 88480 | 943480 | 13680000 | 1415680 | 15095680 | 0% | 0% | 0% |  |  | 0%
|  | Floor drain W100xL5100 | 1 | 1 | pcs | 5417500 | 476000 | 5893500 | 5417500 | 476000 | 5893500 | 0% | 0% | 0% |  |  | 0%
|  | Floor drain W100xL3800 | 1 | 1 | pcs | 4334000 | 380800 | 4714800 | 4334000 | 380800 | 4714800 | 0% | 0% | 0% |  |  | 0%
|  | Floor drain W100xL3000 | 1 | 1 | pcs | 3250500 | 285600 | 3536100 | 3250500 | 285600 | 3536100 | 0% | 0% | 0% |  |  | 0%
|  | Shower | 1 | 1 | pcs | 7305000 | 196000 | 7501000 | 7305000 | 196000 | 7501000 | 0% | 0% | 0% |  |  | 0%
|  | Heat Water 5L for kitchen | 2 | 2 | pcs | 1628727.2727 | 168000 | 1796727.2727 | 3257454.5455 | 336000 | 3593454.5455 | 0% | 0% | 0% |  |  | 0%
|  | Heat Water 50L for shower | 1 | 1 | pcs | 3104727.2727 | 280000 | 3384727.2727 | 3104727.2727 | 280000 | 3384727.2727 | 0% | 0% | 0% |  |  | 0%
|  | Waterproof for neck pipe | 114 | 114 | nos | 50000 | 15000 | 65000 | 5700000 | 1710000 | 7410000 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 8847237.7773 | 2654171.3332 | 11501409.1105 | 8847237.7773 | 2654171.3332 | 11501409.1105 | 0% | 0% | 0% |  |  | 0%
|  | East side | [6 empty] | 607157438.0455 | 28969283.9068 | 636126721.9523 | 0% | 0% | 0% |  |  | 0%
|  | Santinary | [6 empty] | 607157438.0455 | 28969283.9068 | 636126721.9523 | 0% | 0% | 0% |  |  | 0%
|  | Water closet one block, included stop valve | 24 | 24 | pcs | 14750000 | 413200.4464 | 15163200.4464 | 354000000 | 9916810.7136 | 363916810.7136 | 0% | 0% | 0% |  |  | 0%
|  | Water closet spray | 24 | 24 | pcs | 638000 | 50232 | 688232 | 15312000 | 1205568 | 16517568 | 0% | 0% | 0% |  |  | 0%
|  | Paper holder | 24 | 24 | pcs | 653000 | 50232 | 703232 | 15672000 | 1205568 | 16877568 | 0% | 0% | 0% |  |  | 0%
|  | Lavatory under-mounted type | 12 | 24 | pcs | 1443000 | 300710.7768 | 1743710.7768 | 34632000 | 7217058.6432 | 41849058.6432 | 0% | 0% | 0% |  |  | 0%
|  | Water tap for lavatory (cold) | 12 | 12 | pcs | 953000 | 50232 | 1003232 | 11436000 | 602784 | 12038784 | 0% | 0% | 0% |  |  | 0%
|  | Mirror (H=1m, L according to the lavabo table) | 10 | 10 | m2 | 768883.5 | 123200 | 892083.5 | 7688835 | 1232000 | 8920835 | 0% | 0% | 0% |  |  | 0%
|  | Hand Dryer | 4 | 4 | pcs | 5018000 | 61600 | 5079600 | 20072000 | 246400 | 20318400 | 0% | 0% | 0% |  |  | 0%
|  | Uniral included flush valve | 11 | 11 | pcs | 11003000 | 280000 | 11283000 | 121033000 | 3080000 | 124113000 | 0% | 0% | 0% |  |  | 0%
|  | Floor drain DN80 | 10 | 10 | pcs | 855000 | 88480 | 943480 | 8550000 | 884800 | 9434800 | 0% | 0% | 0% |  |  | 0%
|  | Floor drain W100xL4400 | 1 | 1 | pcs | 4334000 | 380800 | 4714800 | 4334000 | 380800 | 4714800 | 0% | 0% | 0% |  |  | 0%
|  | Floor drain W100xL3200 | 1 | 1 | pcs | 3250500 | 285600 | 3536100 | 3250500 | 285600 | 3536100 | 0% | 0% | 0% |  |  | 0%
|  | Heat Water 5L for kitchen | 2 | 2 | pcs | 1628727.2727 | 168000 | 1796727.2727 | 3257454.5455 | 336000 | 3593454.5455 | 0% | 0% | 0% |  |  | 0%
|  | Waterproof for neck pipe | 49 | 49 | nos | 50000 | 15000 | 65000 | 2450000 | 735000 | 3185000 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 5469648.5 | 1640894.55 | 7110543.05 | 5469648.5 | 1640894.55 | 7110543.05 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
4. |  | Machine hook-up (Hall 3) | [8 empty] | 0 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
5. |  | Scooter Garage | [6 empty] | 36457255.9273 | 16528783.2582 | 52986039.1855 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
5. 3. |  | Mechancial Engineering | [6 empty] | 36457255.9273 | 16528783.2582 | 52986039.1855 | 0% | 0% | 0% |  |  | 0%
5. 3. 10. |  | Rainwater System | 1 | 1 | PSCH |  |  |  | 36457255.9273 | 16528783.2582 | 52986039.1855 | 0% | 0% | 0% |  |  | 0%
|  | uPVC pipe D220-PN6 | 12 | 15 | m | 356616 | 71941.408 | 428557.408 | 5349240 | 1079121.12 | 6428361.12 | 0% | 50% | 50%
|  | uPVC pipe D110-PN6 | 92 | 112 | m | 93225.6 | 42504 | 135729.6 | 10441267.2 | 4760448 | 15201715.2 | 0% | 15% | 15%
|  | uPVC pipe D60-PN6 | 59 | 55 | m | 29858.4 | 24884.16 | 54742.56 | 1642212 | 1368628.8 | 3010840.8 | 0% | 15% | 15%
|  | uPVC Cleanout DN100 | 8 | 8 | pcs | 106423.2 | 28000 | 134423.2 | 851385.6 | 224000 | 1075385.6 | 0% | 15% | 15%
|  | Leaf gaurd DN100 | 8 | 8 | pcs | 231000 | 50400 | 281400 | 1848000 | 403200 | 2251200 | 0% | 0% | 0% |  |  | 0%
|  | Floor Drain DN50 | 8 | 8 | pcs | 855000 | 88480 | 943480 | 6840000 | 707840 | 7547840 | 0% | 0% | 0% |  |  | 0%
|  | Fitting for uPVC piping | 8 | 1 | lot | 6588863.3455 | 1976659.0036 | 8565522.3491 | 6588863.3455 | 1976659.0036 | 8565522.3491 | 0% | 15% | 15% |  |  | 0%
|  | Excavation and backfill | 15 | 18 | m3 | 0 | 200000 | 200000 | 0 | 3600000 | 3600000 | 0% | 0% | 0% |  |  | 0%
|  | Hanger/ support and Accessories | 1 | 1 | lot | 2196287.7818 | 658886.3345 | 2855174.1164 | 2196287.7818 | 658886.3345 | 2855174.1164 | 0% | 0% | 0% |  |  | 0%
|  | Conection existing drain stormwater | 1 | 1 | lot | 700000 | 1750000 | 2450000 | 700000 | 1750000 | 2450000 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
6. |  | Canteen | [6 empty] | 420920023.6422 | 58959472.3741 | 479879496.0162 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
6. 3. |  | Mechancial Engineering | [6 empty] | 420920023.6422 | 58959472.3741 | 479879496.0162 | 0% | 0% | 0% |  |  | 0%
6. 3. 10. |  | Rainwater System | 1 | 1 | PSCH |  |  |  | 16378977.6 | 11954799.36 | 28333776.96 | 0% | 0% | 0% |  |  | 0%
|  | uPVC pipe D110-PN6 | 93 | 112 | m | 93225.6 | 42504 | 135729.6 | 10441267.2 | 4760448 | 15201715.2 | 0% | 15% | 15% |  |  | 0%
|  | Leaf gaurd DN100 | 6 | 6 | pcs | 231000 | 50400 | 281400 | 1386000 | 302400 | 1688400 | 0% | 0% | 0% |  |  | 0%
|  | uPVC Cleanout DN100 | 6 | 6 | pcs | 106423.2 | 28000 | 134423.2 | 638539.2 | 168000 | 806539.2 | 0% | 15% | 15% |  |  | 0%
|  | Fitting for uPVC piping | 1 | 1 | lot | 2934878.4 | 880463.52 | 3815341.92 | 2934878.4 | 880463.52 | 3815341.92 | 0% | 15% | 15% |  |  | 0%
|  | Excavation and backfill | 13 | 19 | m3 | 0 | 200000 | 200000 | 0 | 3800000 | 3800000 | 0% | 15% | 15% |  |  | 0%
|  | Hanger/ support and Accessories | 1 | 1 | lot | 978292.8 | 293487.84 | 1271780.64 | 978292.8 | 293487.84 | 1271780.64 | 0% | 15% | 15% |  |  | 0%
|  | Conection existing drain stormwater | 1 | 1 | lot | 0 | 1750000 | 1750000 | 0 | 1750000 | 1750000 | 0% | 15% | 15% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
6. 3. 20. |  | Waste Water System | 1 | 1 | PSCH |  |  |  | 20651731.2 | 14688997.44 | 35340728.64 | 0% | 0% | 0% |  |  | 0%
|  | Piping for Bain maries | [9 empty] | 0% | 0% | 0% |  |  | 0%
|  | uPVC pipe DN80 | 43 | 50 | m | 65145.6 | 36064 | 101209.6 | 3257280 | 1803200 | 5060480 | 0% | 15% | 15% |  |  | 0%
|  | Water pipe heating system | 1 | 1 | lot |  |  |  |  | 0 | 0 | 0% | 0% | 0% |  |  | 0%
|  | Fitting for uPVC piping | 1 | 1 | lot | 751680 | 225504 | 977184 | 751680 | 225504 | 977184 | 0% | 15% | 15% |  |  | 0%
|  | Hanger/ support and Accessories | 1 | 1 | lot | 250560 | 75168 | 325728 | 250560 | 75168 | 325728 | 0% | 0% | 0%
|  | Piping | [6 empty] | 16392211.2 | 12585125.44 | 28977336.64 | 0% | 0% | 0%
|  | uPVC pipe DN100 - PN6 | 7 | 9 | m | 93225.6 | 42504 | 135729.6 | 839030.4 | 382536 | 1221566.4 | 0% | 15% | 15%
|  | uPVC pipe DN80 - PN6 | 89 | 96 | m | 65145.6 | 36064 | 101209.6 | 6253977.6 | 3462144 | 9716121.6 | 0% | 15% | 15%
|  | uPVC pipe DN50 - PN6 | 75 | 82 | m | 29858.4 | 24884.16 | 54742.56 | 2448388.8 | 2040501.12 | 4488889.92 | 0% | 15% | 15%
|  | Clean Out DN50 | 1 | 1 | m | 297000 | 84000 | 381000 | 297000 | 84000 | 381000 | 0% | 0% | 0% |  |  | 0%
|  | Clean Out DN80 | 7 | 7 | m | 319000 | 84000 | 403000 | 2233000 | 588000 | 2821000 | 0% | 0% | 0% |  |  | 0%
|  | Clean Out DN100 | 1 | 1 | m | 341000 | 84000 | 425000 | 341000 | 84000 | 425000 | 0% | 0% | 0% |  |  | 0%
|  | Fitting for uPVC piping | 1 | 1 | lot | 2984860.8 | 895458.24 | 3880319.04 | 2984860.8 | 895458.24 | 3880319.04 | 0% | 15% | 15% |  |  | 0%
|  | Connect pipes to existing manhole | 1 | 1 | lot | 0 | 1750000 | 1750000 | 0 | 1750000 | 1750000 | 0% | 0% | 0% |  |  | 0%
|  | Excavation and backfill | 8 | 15 | m3 | 0 | 200000 | 200000 | 0 | 3000000 | 3000000 | 0% | 0% | 0% |  |  | 0%
|  | Hanger/ support and Accessories | 1 | 1 | lot | 994953.6 | 298486.08 | 1293439.68 | 994953.6 | 298486.08 | 1293439.68 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
6. 3. 30. |  | Service Water System | 1 | 1 | PSCH |  |  |  | 10371428 | 9116560.5373 | 19487988.5373 | 0% | 0% | 0% |  |  | 0%
|  | Valve | [6 empty] | 2328612.8 | 1693755.9317 | 4022368.7317 | 0% | 0% | 0% |  |  | 0%
|  | Gate valve DN25 | 1 | 1 | pcs | 322800 | 50880.368 | 373680.368 | 322800 | 50880.368 | 373680.368 | 0% | 0% | 0% |  |  | 0%
|  | Gate valve DN25 PPR | 7 | 7 | pcs | 85924.8 | 49415.0989 | 135339.8989 | 601473.6 | 345905.6922 | 947379.2922 | 0% | 0% | 0% |  |  | 0%
|  | Gate valve DN20 PPR | 6 | 6 | pcs | 63367.2 | 45472.3119 | 108839.5119 | 380203.2 | 272833.8715 | 653037.0715 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 1024136 | 1024136 | 2048272 | 1024136 | 1024136 | 2048272 | 0% | 0% | 0%
|  | Cold water pipe | [6 empty] | 4239540 | 3735787.3512 | 7975327.3512 | 0% | 0% | 0%
|  | PPR pipe DN40 - PN10 | 12 | 8 | m | 45208.8 | 28000 | 73208.8 | 361670.4 | 224000 | 585670.4 | 0% | 0% | 0%
|  | PPR pipe DN32 - PN10 | 5 | 6 | m | 30841.2 | 25388.1544 | 56229.3544 | 185047.2 | 152328.9264 | 337376.1264 | 0% | 0% | 0%
|  | PPR pipe DN25 - PN10 | 7 | 10 | m | 22978.8 | 22306.7432 | 45285.5432 | 229788 | 223067.432 | 452855.432 | 0% | 0% | 0%
|  | PPR pipe DN20 - PN10 | 61 | 71 | m | 17737.2 | 18258.8168 | 35996.0168 | 1259341.2 | 1296375.9928 | 2555717.1928 | 0% | 0% | 0%
|  | PPR Fitting | 1 | 1 | lot | 469810.8 | 140943.24 | 610754.04 | 469810.8 | 140943.24 | 610754.04 | 0% | 0% | 0%
|  | uPVC pipe D34 - PN10 | 60 | 63 | m | 16286.4 | 13440 | 29726.4 | 1026043.2 | 846720 | 1872763.2 | 0% | 15% | 15%
|  | Fitting for uPVC piping | 1 | 1 | lot | 236779.2 | 71033.76 | 307812.96 | 236779.2 | 71033.76 | 307812.96 | 0% | 15% | 15% |  |  | 0%
|  | Excavation and backfill | 2 | 3.2 | m3 | 0 | 200000 | 200000 | 0 | 640000 | 640000 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Accessories + Support | 1 | 1 | lot | 471060 | 141318 | 612378 | 471060 | 141318 | 612378 | 0% | 0% | 0% |  |  | 0%
|  | hot water pipe | [6 empty] | 3803275.2 | 3687017.2544 | 7490292.4544 | 0% | 0% | 0% |  |  | 0%
|  | PPR pipe DN15 - PN20 | 10 | 8 | m | 12261.6 | 15682.8168 | 27944.4168 | 98092.8 | 125462.5344 | 223555.3344 | 0% | 0% | 0% |  |  | 0%
|  | PPR Fitting | 1 | 1 | lot | 22636.8 | 6791.04 | 29427.84 | 22636.8 | 6791.04 | 29427.84 | 0% | 0% | 0% |  |  | 0%
|  | Fire stop | 1 | 1 | lot | 3500000 | 3500000 | 7000000 | 3500000 | 3500000 | 7000000 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | Accessories + Support | 1 | 1 | lot | 182545.6 | 54763.68 | 237309.28 | 182545.6 | 54763.68 | 237309.28 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
6. 3. 40. |  | Sanitary Furnishings | 1 | 1 | PSCH |  |  |  | 240793394.3675 | 15204292.8421 | 255997687.2095 | 0% | 0% | 0% |  |  | 0%
|  | Lavatory under-mounted type | 2 | 2 | pcs | 1443000 | 300710.7768 | 1743710.7768 | 2886000 | 601421.5536 | 3487421.5536 | 0% | 0% | 0% |  |  | 0%
|  | Lavatory wall mounted type | 1 | 1 | pcs | 1253000 | 300710.7768 | 1553710.7768 | 1253000 | 300710.7768 | 1553710.7768 | 0% | 0% | 0% |  |  | 0%
|  | Water tap for lavatory (hot and cold) | 2 | 2 | pcs | 1320000 | 50232 | 1370232 | 2640000 | 100464 | 2740464 | 0% | 0% | 0% |  |  | 0%
|  | Water tap for lavatory (cold) | 1 | 1 | pcs | 953000 | 50232 | 1003232 | 953000 | 50232 | 1003232 | 0% | 0% | 0% |  |  | 0%
|  | Mirror 700x500x6mm | 3 | 3 | pcs | 2896300 | 61600 | 2957900 | 8688900 | 184800 | 8873700 | 0% | 0% | 0% |  |  | 0%
|  | Water closet one block, included stop valve | 2 | 2 | set | 14750000 | 413200.4464 | 15163200.4464 | 29500000 | 826400.8928 | 30326400.8928 | 0% | 0% | 0% |  |  | 0%
|  | Water closet spray | 2 | 2 | pcs | 638000 | 50232 | 688232 | 1276000 | 100464 | 1376464 | 0% | 0% | 0% |  |  | 0%
|  | Paper holder | 2 | 2 | pcs | 653000 | 50232 | 703232 | 1306000 | 100464 | 1406464 | 0% | 0% | 0% |  |  | 0%
|  | Hand Dryer | 1 | 1 | pcs | 5018000 | 61600 | 5079600 | 5018000 | 61600 | 5079600 | 0% | 0% | 0% |  |  | 0%
|  | Floor Drain DN50 | 1 | 1 | m | 855000 | 88480 | 943480 | 855000 | 88480 | 943480 | 0% | 0% | 0% |  |  | 0%
|  | Floor Drain DN80 | 12 | 12 | m | 855000 | 88480 | 943480 | 10260000 | 1061760 | 11321760 | 0% | 0% | 0% |  |  | 0%
|  | Stainless steel hand washing channel: L10000xH170xD500 | 1 | 1 | pcs | 44000000 | 2240000 | 46240000 | 44000000 | 2240000 | 46240000 | 0% | 0% | 0% |  |  | 0%
|  | Taps for hand washing (Cold) | 14 | 14 | pcs | 7755000 | 50400 | 7805400 | 108570000 | 705600 | 109275600 | 0% | 0% | 0% |  |  | 0%
|  | Heat Water 5l | 2 | 2 | pcs | 1628727.2727 | 168000 | 1796727.2727 | 3257454.5455 | 336000 | 3593454.5455 | 0% | 0% | 0% |  |  | 0%
|  | Double Socket 16A/230V | 3 | 3 | pcs | 150480 | 54500 | 204980 | 451440 | 163500 | 614940 | 0% | 0% | 0% |  |  | 0%
|  | Single Socket 16A/230V | 14 | 14 | pcs | 124560 | 54500 | 179060 | 1743840 | 763000 | 2506840 | 0% | 0% | 0% |  |  | 0%
|  | 3C-2.5mm2 Cu/XLPE/PVC | 105 | 112 | m | 32518.74 | 7485.665 | 40004.405 | 3642098.88 | 838394.48 | 4480493.36 | 0% | 0% | 0% |  |  | 0%
|  | 3C-1.5mm2 Cu/XLPE/PVC | 84 | 95 | m | 22980.09 | 5743.9305 | 28724.0205 | 2183108.55 | 545673.3975 | 2728781.9475 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 105 | 110 | m | 8773.9726 | 14594.0164 | 23367.989 | 965136.9863 | 1605341.8053 | 2570478.7916 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 8 | 10 | m | 8773.9726 | 14594.0164 | 23367.989 | 87739.726 | 145940.1641 | 233679.8901 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D16 | 84 | 90 | m | 6646.8692 | 13183.4282 | 19830.2974 | 598218.226 | 1186508.5359 | 1784726.7619 | 0% | 0% | 0% |  |  | 0%
|  | Waterproof for neck pipe | 5 | 5 | nos | 50000 | 15000 | 65000 | 250000 | 75000 | 325000 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 10408457.4536 | 3122537.2361 | 13530994.6897 | 10408457.4536 | 3122537.2361 | 13530994.6897 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
6. 3. 90. |  | Booster pump assembly | 1 |  | PSCH |  |  |  | 132724492.4747 | 7994822.1947 | 140719314.6694 | 0% | 0% | 0% |  |  | 0%
|  | PUMP ROOM | [6 empty] | 119059072.0747 | 5427258.3947 | 125718330.4694 | 0% | 0% | 0% |  |  | 0%
|  | Booster pump Q=11.7 m3, H=30m | 2 | 2 | set | 17380000 | 616000 | 17996000 | 34760000 | 1232000 | 35992000 | 0% | 50% | 50% |  |  | 0%
|  | Electrical control panel for booster pump | 1 | 1 | set | 44440000 | 1400000 | 45840000 | 44440000 | 1400000 | 45840000 | 0% | 0% | 0% |  |  | 0%
|  | Pressure tank 100l | 1 | 1 | pcs | 7915200 | 168000 | 8083200 | 7915200 | 168000 | 8083200 | 0% | 0% | 0% |  |  | 0%
|  | Storage tank 3m3 | 1 | 1 | pcs | 9970909.0909 | 322000 | 10292909.0909 | 9970909.0909 | 322000 | 10292909.0909 | 0% | 0% | 0% |  |  | 0%
|  | Filter | 1 | 1 | set | 10800000 | 225400 | 11025400 | 10800000 | 225400 | 11025400 | 0% | 0% | 0% |  |  | 0%
|  | Water metter DN25 | 1 | 1 | pcs | 1014000 | 50880.368 | 1064880.368 | 1014000 | 50880.368 | 1064880.368 | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/PVC/PVC 2Cx1.5mm2 | 20 | 25 | m | 15443.88 | 5031.18 | 20475.06 | 386097 | 125779.5 | 511876.5 | 0% | 0% | 0% |  |  | 0%
|  | Cable Cu/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 20 | 25 | m | 40467 | 9350 | 49817 | 1011675 | 233750 | 1245425 | 0% | 0% | 0% |  |  | 0%
|  | PVC conduit D20 | 40 | 50 | m | 8773.9726 | 14594.0164 | 23367.989 | 438698.6301 | 729700.8206 | 1168399.4507 | 0% | 0% | 0% |  |  | 0%
|  | Concrete base for pump | 1 | 1 | lot | 2500000 | 450000 | 2950000 | 2500000 | 450000 | 2950000 | 0% | 0% | 0% |  |  | 0%
|  | Cover for pump | 1 | 1 | lot | 750000 | 200000 | 950000 | 750000 | 200000 | 950000 | 0% | 0% | 0% |  |  | 0%
|  | Hanger + Support | 1 | 1 | lot | 3043495.4122 | 913048.6237 | 3956544.0359 | 3043495.4122 | 913048.6237 | 3956544.0359 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 2028996.9415 | 608699.0824 | 2637696.0239 | 2028996.9415 | 608699.0824 | 2637696.0239 | 0% | 0% | 0% |  |  | 0%
|  | Valve | [6 empty] | 13303750 | 1140438.52 | 14444188.52 | 0% | 0% | 0% |  |  | 0%
|  | Pressure Gauges | 1 | 1 | pcs | 1008000 | 49588 | 1057588 | 1008000 | 49588 | 1057588 | 0% | 0% | 0% |  |  | 0%
|  | Flexible DN25 | 4 | 4 | pcs | 568800 | 50880.368 | 619680.368 | 2275200 | 203521.472 | 2478721.472 | 0% | 0% | 0% |  |  | 0%
|  | Float level indicator | 1 | 1 | pcs | 4200000 | 168000 | 4368000 | 4200000 | 168000 | 4368000 | 0% | 0% | 0% |  |  | 0%
|  | Float valve DN25 | 1 | 1 | pcs | 770400 | 50880.368 | 821280.368 | 770400 | 50880.368 | 821280.368 | 0% | 0% | 0% |  |  | 0%
|  | Y-Strainer DN25 | 2 | 2 | pcs | 322800 | 50880.368 | 373680.368 | 645600 | 101760.736 | 747360.736 | 0% | 0% | 0% |  |  | 0%
|  | Safety valve DN25 | 1 | 1 | pcs | 1376400 | 50880.368 | 1427280.368 | 1376400 | 50880.368 | 1427280.368 | 0% | 0% | 0% |  |  | 0%
|  | Check valve DN25 | 3 | 3 | pcs | 480000 | 50880.368 | 530880.368 | 1440000 | 152641.104 | 1592641.104 | 0% | 0% | 0% |  |  | 0%
|  | Gate valve DN25 | 4 | 4 | pcs | 264000 | 50880.368 | 314880.368 | 1056000 | 203521.472 | 1259521.472 | 0% | 0% | 0% |  |  | 0%
|  | Accessories | 1 | 1 | lot | 532150 | 159645 | 691795 | 532150 | 159645 | 691795 | 0% | 0% | 0% |  |  | 0%
|  | Cold water pipe | [6 empty] | 361670.4 | 195125.28 | 556795.68 | 0% | 0% | 0% |  |  | 0%
|  | PPR pipe DN50 - PN10 | 5 | 6 | m | 45208.8 | 28000 | 73208.8 | 271252.8 | 168000 | 439252.8 | 0% | 0% | 0% |  |  | 0%
|  | PPR Fitting | 1 | 1 | lot | 52164 | 15649.2 | 67813.2 | 52164 | 15649.2 | 67813.2 | 0% | 0% | 0% |  |  | 0%
|  | Accessories + Support | 1 | 1 | lot | 38253.6 | 11476.08 | 49729.68 | 38253.6 | 11476.08 | 49729.68 | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | VII.CIVIL | [8 empty] | 337968025 | 0% | 0% | 0% |  |  | 0%
7. |  | Exterior Area | [6 empty] | 187529525 | 150438500 | 337968025 | 0 | 0 | 0 |  |  | 0%
[12 empty] | 0% | 0% | 0% |  |  | 0%
7. 1. |  | Civil Engineering | [6 empty] | 187529525 | 150438500 | 337968025 | 0% | 0% | 0% |  |  | 0%
7. 1. 50. |  | Excavation | 1 | 1 | PSCH |  |  |  | 86750000 | 108855000 | 195605000 | 0% | 0% | 0% |  |  | 0%
|  | LV | [6 empty] | 58500000 | 54800000 | 115800000 | 0% | 0% | 0% |  |  | 0%
|  | Manhole 1000x1000x1000 | 5 | 5 | m | 4500000 | 2000000 | 6500000 | 22500000 | 10000000 | 32500000 | 0% | 70% | 70% |  |  | 0%
|  | Excavation and backfilling | 164 | 164 | m3 | 0 | 200000 | 200000 | 0 | 32800000 | 32800000 | 0% | 70% | 70% |  |  | 0%
|  | Concrete crossroads protection | 190 | 120 | m | 300000 | 100000 | 400000 | 36000000 | 12000000 | 48000000 | 0% | 70% | 70% |  |  | 0%
|  | Labor (Remove old cable) | 1 | 1 | m | 0 | 2500000 | 2500000 | 0 | 2500000 | 2500000 | 0% | 70% | 70% |  |  | 0%
|  | AIR COMPRESSOR | [6 empty] | 1250000 | 4515000 | 5765000 | 0% | 70% | 0% |  |  | 0%
|  | Excavation and backfill | 31 | 20.7 | m3 | 0 | 200000 | 200000 | 0 | 4140000 | 4140000 | 0% | 70% | 70% |  |  | 0%
|  | The cost of cutting and refinishing the concrete path for the undergruond pipe | 15 | 10 | m | 125000 | 37500 | 162500 | 1250000 | 375000 | 1625000 | 0% | 70% | 70% |  |  | 0%
|  | ELV |  | 11 |  |  |  |  | 27000000 | 47040000 | 74040000 | 0% | 70% | 0% |  |  | 0%
|  | Khoan đường đi ống | 52 | 52 | m | 0 | 300000 | 300000 | 0 | 15600000 | 15600000 | 0% | 70% | 70% |  |  | 0%
|  | Manhole 1200x1200x1200 | 4 | 6 | pcs | 4500000 | 2000000 | 6500000 | 27000000 | 12000000 | 39000000 | 0% | 70% | 70% |  |  | 0%
|  | Spare fee for Move and reinstall lighting pole if can't excavation pavement | 6 | 6 | pcs | 0 | 1200000 | 1200000 | 0 | 7200000 | 7200000 | 0% | 70% | 70% |  |  | 0%
|  | Excavation and backfill | 100 | 61.2 | m3 | 0 | 200000 | 200000 | 0 | 12240000 | 12240000 | 0% | 70% | 70% |  |  | 0%
[12 empty] | 0% | 70% | 70% |  |  | 0%
7. 1. 60. |  | Laying conduits, pipes, etc. | 1 |  | PSCH |  |  |  | 100779525 | 41583500 | 142363025 | 0% | 0% | 0% |  |  | 0%
|  | LV | [6 empty] | 41773725 | 16061150 | 57834875 | 0% | 0% | 0% |  |  | 0%
|  | HDPE pipe D160/125 | 340 | 421 | m | 88200 | 38150 | 126350 | 37132200 | 16061150 | 53193350 | 30% | 40% | 70% |  |  | 30%
|  | Accessories | 1 | 1 | lot | 4641525 | 0 | 4641525 | 4641525 | 0 | 4641525 | 0% | 0% | 0% |  |  | 0%
|  | ELV | [6 empty] | 59005800 | 25522350 | 84528150 | 0% | 0% | 0% |  |  | 0%
|  | HDPE pipe D160/125 | 848 | 669 | m | 88200 | 38150 | 126350 | 59005800 | 25522350 | 84528150 | 30% | 40% | 70% |  |  | 30%
[12 empty] | 0% | 0% | 0% |  |  | 0%
|  | VIII.EQUIPMENT KITCHEN | [8 empty] | 229689172.3178 | 0% | 0% | 0% |  |  | 0%
3. |  | Office, Social and Technical Areas (Hall 3) | [6 empty] | 225500372.3178 | 4188800 | 229689172.3178 | 0 | 0 | 0 |  |  | 0%
[12 empty] | 0 | 0 | 0 |  |  | 0%
3. 3. |  | Mechanical Engineering | [6 empty] | 225500372.3178 | 4188800 | 229689172.3178 | 0 | 0 | 0 |  |  | 0%
3. 3. 30. |  | Sanitary Furnishings | 1 | 1 | PSCH |  |  |  | 225500372.3178 | 4188800 | 229689172.3178 | 0 | 0 | 0 |  |  | 0%
|  | West side | 0 | 0 | m |  |  | 0 | 107848004.152 | 2094400 | 109942404.152 | 0 | 0 | 0 |  |  | 0%
|  | Equiment kitchen | [6 empty] | 107848004.152 | 2094400 | 109942404.152 | 0 | 0 | 0 |  |  | 0%
|  | Hafele refrigerator (1-wing refrigerator) | 2 | 2 | pcs | 20093299.732 | 224000 | 20317299.732 | 40186599.464 | 448000 | 40634599.464 | 0 | 0 | 0 |  |  | 0%
|  | Single sink for kitchen included faucet waster pop up, flexiable, stop valve | 2 | 2 | pcs | 3486000.21 | 280000 | 3766000.21 | 6972000.42 | 560000 | 7532000.42 | 0 | 0 | 0 |  |  | 0%
|  | Hafele semi-sonic dishwasher | 2 | 2 | pcs | 15336300.067 | 168000 | 15504300.067 | 30672600.134 | 336000 | 31008600.134 | 0 | 0 | 0 |  |  | 0%
|  | Hafele standalone microwave oven | 2 | 2 | pcs | 2807300.067 | 95200 | 2902500.067 | 5614600.134 | 190400 | 5805000.134 | 0 | 0 | 0 |  |  | 0%
|  | Domino's Induction Cooker | 4 | 4 | pcs | 6100551 | 140000 | 6240551 | 24402204 | 560000 | 24962204 | 0 | 0 | 0 |  |  | 0%
|  | Accessories | 1 | 1 | lot | 4902182.0069 | 0 | 4902182.0069 | 4902182.0069 | 0 | 4902182.0069 | 0 | 0 | 0 |  |  | 0%
|  | East side | [6 empty] | 112750186.1589 | 2094400 | 114844586.1589 | 0 | 0 | 0 |  |  | 0%
|  | Equiment kitchen | [6 empty] | 107848004.152 | 2094400 | 109942404.152 | 0 | 0 | 0 |  |  | 0%
|  | Hafele refrigerator (1-wing refrigerator) | 2 | 2 | pcs | 20093299.732 | 224000 | 20317299.732 | 40186599.464 | 448000 | 40634599.464 | 0 | 0 | 0 |  |  | 0%
|  | Single sink for kitchen included faucet waster pop up, flexiable, stop valve | 2 | 2 | pcs | 3486000.21 | 280000 | 3766000.21 | 6972000.42 | 560000 | 7532000.42 | 0 | 0 | 0 |  |  | 0%
|  | Hafele semi-sonic dishwasher | 2 | 2 | pcs | 15336300.067 | 168000 | 15504300.067 | 30672600.134 | 336000 | 31008600.134 | 0 | 0 | 0 |  |  | 0%
|  | Hafele standalone microwave oven | 2 | 2 | pcs | 2807300.067 | 95200 | 2902500.067 | 5614600.134 | 190400 | 5805000.134 | 0 | 0 | 0 |  |  | 0%
|  | Domino's Induction Cooker | 4 | 4 | pcs | 6100551 | 140000 | 6240551 | 24402204 | 560000 | 24962204 | 0 | 0 | 0 |  |  | 0%
|  | Accessories | 1 | 1 | lot | 4902182.0069 | 0 | 4902182.0069 | 4902182.0069 | 0 | 4902182.0069 | 0 | 0 | 0 |  |  | 0%
[12 empty] | 0 | 0 | 0 |  |  | 0%
[12 empty] | 0 | 0 | 0 |  |  | 0%
|  | IX.ELEVATOR | [8 empty] | 280000000 | 0% | 0% | 0% |  |  | 0%
6. |  | Canteen | [6 empty] | 280000000 | 0 | 280000000 | 0 | 0 | 0 |  |  | 0%
6. 1. |  | Civil Engineering | [6 empty] | 280000000 | 0 | 280000000 | 0 | 0 | 0 |  |  | 0%
6. 1. 260. |  | Elevator for goods | [6 empty] | 280000000 | 0 | 280000000 | 0 | 0 | 0 |  |  | 0%
|  | Food elevator without person, no loading machine room weight 200kg/02stop/30m/min | 1 | 1 | lot | 280000000 | 0 | 280000000 | 280000000 | 0 | 280000000 | 0 | 0 | 0 |  |  | 0%
IV |  | CHI PHÍ QUẢN LÝ | [7 empty] | 0 | 1090000000 | 0% | 0% | 0%
|  | Chi phí thuê xe nâng | 1 | 1 | Lot | [5 empty] | 250000000 | 26% | 22% | 48%
|  | Chi phí kho bãi, văn phòng, điện nước tạm | 1 | 1 | Lot | [5 empty] | 70000000 | 26% | 22% | 48%
|  | Chi phí quản lý | 1 | 1 | Lot | [5 empty] | 600000000 | 26% | 22% | 48%
|  | In ấn,submit bản vẽ thi công,hoàn công,hồ sơ nghiệm thu… | 1 | 1 | Lot | [5 empty] | 50000000 | 15% | 22% | 37%
|  | Kiểm định PCCC van gió | 1 | 1 | lot | [5 empty] | 120000000 | 0% | 0% | 0%
[12 empty] | 0 | 0 | 0
| TOTAL (BEFORE VAT) | [9 empty] | 33142000000
| TAX VAT (10%): | [9 empty] | 2651360000
| GRAND TOTAL (AFTER VAT) | [9 empty] | 35793360000
NHÀ THẦU CHÍNH: CÔNG TY CỔ PHẦN CƠ ĐIỆN DITECHCO | [9 empty] | NHÀ THẦU PHỤ: CÔNG TY CỔ PHẦN HMEP | NHÀ THẦU PHỤ: CÔNG TY CỔ PHẦN HMEP
CHỈ HUY TRƯỞNG |  | GIÁM SÁT | GIÁM SÁT |  |  |  | GIÁM SÁT |  |  | GIÁM ĐỐC DỰ ÁN CHỈ HUY TRƯỞNG | GIÁM ĐỐC DỰ ÁN CHỈ HUY TRƯỞNG | [5 empty] | CHỈ HUY TRƯỞNG
CAO XUÂN TRƯỜNG |  | ĐỖ PHẠM THANH HỒNG |  |  |  |  | ĐỖ PHẠM THANH HỒNG LÊ NGỌC HOÀNG SƠN |  |  | VÕ HOÀNG KHẮC PHỤC NGUYỄN MINH HẢI |  | VÕ HOÀNG KHẮC PHỤC NGUYỄN MINH HẢI
Note on C242: PC: Cho group A
Note on C245: PC: cho group A

## 2. ELV (hidden)
Project: VN-RENTAL BUILDING HALL 3 ELECTRIC
Location: Lô D1, Khu công nghiệp Tam Thăng, Huyện Tam Thăng, thành Phố Tam Kỳ, Tỉnh quản Nam, Việt Nam
Client: Draexlmaier Automotive Vietnam Company Limited
Package: Cơ - Điện
Item: ELV System
Date: 27/02/2022
Contractor name: HMEP
Position | Headline | Quantity | Quantity By contractor | Unit | Material Unit | Labor Unit | Unit rate | Material Amount | Labor Amount | Amount (VND) | % Công việc hoàn thành vật tư |  |  | % Công việc hoàn thành nhân công |  |  | Giá trị thanh toán đợt 1 |  |  | Remark
[11 empty] | Đợt 1 | đợt 2 | % KL hoàn thành lũy kế | Đợt 1 | đợt 2 | % KL hoàn thành lũy kế | Vật tư | Nhân công | Tổng
1. | Construction site facilities | [6 empty] | 124241733.1691 | 20176036.5818 | 144417769.7509 | [6 empty] | 111817559.8522 | 18158432.9237 | 129975992.7758
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
1. 1. | Construction site facilities | 1 | 1 | psch | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
1. 2. | Construction site cameras | 1 | 1 | psch |  |  |  | 124241733.1691 | 20176036.5818 | 144417769.7509 | 90% |  | 90% | 90% |  | 0.9 | 111817559.8522 | 18158432.9237 | 129975992.7758
| Rack for NVR+Swtich | 1 | 1 | pcs | 1848000 | 165000 | 2013000 | 1848000 | 165000 | 2013000 | 90% |  | 90% | 90% |  | 0.9 | 1663200 | 148500 | 1811700 | VN
| Camera bullet 360' + base, Resolution: 4K | 3 | 3 | pcs | 9067520 | 198000 | 9265520 | 27202560 | 594000 | 27796560 | 90% |  | 90% | 90% |  | 0.9 | 24482304 | 534600 | 25016904 | DS-2DE5225IW-AE, HIK Vision
| NVR 8 chanel | 1 | 1 | pcs | 9431520 | 165000 | 9596520 | 9431520 | 165000 | 9596520 | 90% |  | 90% | 90% |  | 0.9 | 8488368 | 148500 | 8636868 | HIK Vision
| 1KVA UPS | 1 | 1 | pcs | 2529000 | 137500 | 2666500 | 2529000 | 137500 | 2666500 | 90% |  | 90% | 90% |  | 0.9 | 2276100 | 123750 | 2399850 | Santank
| Switch PoE 4P | 1 | 1 | pcs | 1155000 | 81750 | 1236750 | 1155000 | 81750 | 1236750 | 90% |  | 90% | 90% |  | 0.9 | 1039500 | 73575 | 1113075 | VN
| LCD 32" | 1 | 1 | pcs | 8360000 | 163500 | 8523500 | 8360000 | 163500 | 8523500 | 90% |  | 90% | 90% |  | 0.9 | 7524000 | 147150 | 7671150 | Saumsung or equivlation
| Double Socket 16A/230V | 3 | 3 | pcs | 150480 | 54500 | 204980 | 451440 | 163500 | 614940 | 90% |  | 90% | 90% |  | 0.9 | 406296 | 147150 | 553446 | KB426UES2_WE_G19/ Schneider/ VN, Plastic type
| PVC box for socket, conver at camera | 3 | 3 | pcs | 36000 | 16350 | 52350 | 108000 | 49050 | 157050 | 90% |  | 90% | 90% |  | 0.9 | 97200 | 44145 | 141345 | Vietnam
| surge protection | 2 | 2 | pcs | 4494000 | 49050 | 4543050 | 8988000 | 98100 | 9086100 | 90% |  | 90% | 90% |  | 0.9 | 8089200 | 88290 | 8177490 | Schneider
| Cable Cat6 | 10 | 10 | m | 10032.7869 | 3360 | 13392.7869 | 100327.8689 | 33600 | 133927.8689 | 90% |  | 90% | 90% |  | 0.9 | 90295.082 | 30240 | 120535.082 | Commposcope / China, or Alantek
| converter quang đồng | 6 | 6 | pcs | 770000 | 49050 | 819050 | 4620000 | 294300 | 4914300 | 90% |  | 90% | 90% |  | 0.9 | 4158000 | 264870 | 4422870 | VN
| Fiber optical 2FO | 373 | 373 | m | 14400 | 3360 | 17760 | 5371200 | 1253280 | 6624480 | 90% |  | 90% | 90% |  | 0.9 | 4834080 | 1127952 | 5962032 | Sacom or Alantek
| Cable Cu/XLPE/PVC 3Cx1.5mm2 | 397 | 397 | m | 22980.09 | 5743.9305 | 28724.0205 | 9123095.73 | 2280340.4085 | 11403436.1385 | 90% |  | 90% | 90% |  | 0.9 | 8210786.157 | 2052306.3677 | 10263092.5247 | Cadivi/ Vietnam
| PVC conduit D20 | 81 | 81 | m | 8773.9726 | 14594.0164 | 23367.989 | 710691.7808 | 1182115.3294 | 1892807.1102 | 90% |  | 90% | 90% |  | 0.9 | 639622.6027 | 1063903.7964 | 1703526.3992 | FPC20, Nano/ VN
| HDPE pipe D25/32 | 397 | 397 | m | 10550.2392 | 11445 | 21995.2392 | 4188444.9761 | 4543665 | 8732109.9761 | 90% |  | 90% | 90% |  | 0.9 | 3769600.4785 | 4089298.5 | 7858898.9785 | Cadivi/ Vietnam
| Camera Pole 15m | 3 | 3 | pcs | 10000000 | 450000 | 10450000 | 30000000 | 1350000 | 31350000 | 90% |  | 90% | 90% |  | 0.9 | 27000000 | 1215000 | 28215000 | Vietnam
| Reforce cable for camera pole | 3 | 3 | lot | 550000 | 250000 | 800000 | 1650000 | 750000 | 2400000 | 90% |  | 90% | 90% |  | 0.9 | 1485000 | 675000 | 2160000 | Vietnam
| Concrete plinth | 3 | 3 | lot | 1000000 | 500000 | 1500000 | 3000000 | 1500000 | 4500000 | 90% |  | 90% | 90% |  | 0.9 | 2700000 | 1350000 | 4050000 | Vietnam
| Remove Pole + Camera | 3 | 3 | time | 0 | 1250000 | 1250000 | 0 | 3750000 | 3750000 | 90% |  | 90% | 90% |  | 0.9 | 0 | 3375000 | 3375000 | Vietnam (re-use the pole and concrete plinth)
| Accessories | 1 | 1 | lot | 5404452.8133 | 1621335.844 | 7025788.6573 | 5404452.8133 | 1621335.844 | 7025788.6573 | 90% |  | 90% | 90% |  | 0.9 | 4864007.532 | 1459202.2596 | 6323209.7916
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. | Production and Logistic building (Hall 3) | [6 empty] | 803801420.8294 | 119493877.9513 | 923295298.7807 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
2.1. | Civil Engineering | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 10. | Calculations | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 20. | Rainwater and waste water sewer | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 30. | Earthworks | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 40. | Demolition, removal and dismantling works | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 50. | Foundation | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 60. | Building structure | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 70. | General concrete- / reinforced concrete works | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 80. | Fire protection | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 90. | Fire rated walls | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 100. | Cutting base slabs / ceilings / floors | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 110. | Cutting holes into existing facades, walls and roofs | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 120. | Exterior walls | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 130. | Exterior doors and windows | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 140. | Fire protection doors | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 150. | Internal doors | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 160. | Fire protection roller shutter door | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 170. | Fire protection bulkhead | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 180. | High speed roller shutter | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 190. | Fitting and metal work - general | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 200. | Railings and hand rails | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 210. | Steel stage for installations | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 220. | Collision protection | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 230. | canopies of exterior doors | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 240. | Concerete steps in front of the hall | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 250. | Painting and varnishing works | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 260. | Guidance systems | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 270. | Locking system | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 280. | Internal signage | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 290. | Adjustment ridge vent | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 300. | Roof reinforcment Option 1 | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 310. | Insert new ventilation louvers | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 1. 320. | Metal louvers to cover mechanical units | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 2. | Electrical Engineering | 1 | 1 | PSCH |  |  |  | 120237495.4217 | 36030743.1568 | 156268238.5785 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 2. 10. | Adjustment of existing facilities, dismantling and disposal works | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 2. 20. | Rennovation existing grounding system and lightning protection | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 2. 30. | Rennovation existing grounding and equipotential bonding | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 2. 40. | Power supply | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 2. 50. | Energy measurement system | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 2. 60. | Electrical installation in the production hall | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 2. 70. | Electrical installation in the logistics hall | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 2. 80. | Power supply of building utilities | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 2. 90. | Three-arm Turnstile | 1 | 1 | PSCH |  |  |  | 120237495.4217 | 36030743.1568 | 156268238.5785 |  |  | 0% |  |  | 0 | 0 | 0 | 0
| INTUS ACM40e-NT as access control manager | [11 empty] | 0% |  |  | 0 | 0 | 0 | 0 | Provide PCS, Only Labor Install
| INTUS ACM40e-NT (S3840-380) Intelligent access control manager (Supplier by Client) | 4 | 4 | set | 0 | 616000 | 616000 | 0 | 2464000 | 2464000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Only installation
| INTUS ACM40e 2-4 reader-ext (V3841-202) Firmware extension from 2 to 4 access readers (Supplier by Client) | 4 | 4 | set | 0 | 616000 | 616000 | 0 | 2464000 | 2464000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Only installation
| Network configuration setup fee (3000-243) Set up of one IPv4 terminal basis configuration by PCS. Precondition: Excel- or CSV-file with following details: IPaddress and net mask terminal, IP-address gateway, TCPport. Host name. This information must be submitted with the order. (by Client) | 4 | 4 | set | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | (by Client)
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
| INTUS 6xx/7xx as RFID reader for access control | [11 empty] | 0% |  |  | 0 | 0 | 0 | 0 | Provide PCS, Only Labor Install
| NTUS 615/La ( S3850-670) INTUS 615 Legic advant r/w access reader for flush mounting. Reads/writes Legic prime and Legic advant cards/tags. PCS universal coding: VNA00- 000 (Supplier by Client) | 8 | 8 | set | 0 | 616000 | 616000 | 0 | 4928000 | 4928000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Only installation
| INTUS 600/500/400 reader configuration fee (V3000-231) INTUS reader configuration price for customer specific car coding deviating from PCS standard coding. Also required for standalone parametrization. (by Client) | 8 | 8 | set | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | (by Client)
| NTUS 600 spacer frame (S3850-607) INTUS 315ro/615/620 spacer frame, mandatory for mounting on metal wall or for surface mounting cable introduction (Supplier by Client) | 8 | 8 | set | 0 | 616000 | 616000 | 0 | 4928000 | 4928000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Only installation
| NTUS 700-Panel/La (S3853-610) SM4200-M Legic advant r/w access reader for mounting in metal panels. Reads/writes Legic prime and Legic advant cards/tags. PCS universal coding: VNA00-000 (Supplier by Client) | 8 | 8 | set | 0 | 616000 | 616000 | 0 | 4928000 | 4928000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Only installation
| INTUS 700 reader configuration fee (V3000-249) INTUS 700 reader configuration price for card coding, deviating from PCS standard coding. (by Client) | 8 | 8 | set | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | (by Client)
| 5A, 12VDC Power supply adapter | 1 | 1 | set | 2220000 | 95200 | 2315200 | 2220000 | 95200 | 2315200 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | YLI
| Push button for releasing entrance & exit lock at reception area | 1 | 4 | pcs | 528000 | 61600 | 589600 | 2112000 | 246400 | 2358400 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | EL-EB3/ Elock/ Malaysia
| Emergency at the reception area | 1 | 4 | pcs | 528000 | 61600 | 589600 | 2112000 | 246400 | 2358400 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | EB-PB/ Elock/ Malaysia
| Cabinet box for controller located at reception | 1 | 1 | set | 3000000 | 280000 | 3280000 | 3000000 | 280000 | 3280000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Vietnam
| Backup battery, 12VDC 7Ah | 4 | 4 | set | 540000 | 72800 | 612800 | 2160000 | 291200 | 2451200 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Phoenix
| Tripod turnstile | 4 | 4 | set | 21600000 | 369600 | 21969600 | 86400000 | 1478400 | 87878400 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | TS2000 Pro, ZKTECO
| Double Socket 16A/230V | 4 | 4 | pcs | 150480 | 54500 | 204980 | 601920 | 218000 | 819920 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | KB413S*2 / Schneider/ VN, Plastic type
| Signal cable, AWG18 - 1Pair | 153 | 153 | m | 15000 | 3360 | 18360 | 2295000 | 514080 | 2809080 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 2MKABLO/ Turkey
| Cable Cat6A | 327 | 301 | m | 21639.3443 | 3360 | 24999.3443 | 6513442.623 | 1011360 | 7524802.623 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Commscope
| Cable Cu/XLPE/PVC 3Cx2.5mm2 | 50 | 150 | m | 32518.74 | 7485.665 | 40004.405 | 4877811 | 1122849.75 | 6000660.75 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Cadivi / VN
| PVC conduit D20 | 369 | 360 | m | 8773.9726 | 14594.0164 | 23367.989 | 3158630.137 | 5253845.9082 | 8412476.0452 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
| Cutting concrete background and backfill | 5 | 5 | m | 0 | 125000 | 125000 | 0 | 625000 | 625000 |  |  | 0% |  |  | 0 | 0 | 0 | 0
| Labour cost for support DRX test funtion of Turnstile system | 1 | 1 | lot | 0 | 3500000 | 3500000 | 0 | 3500000 | 3500000 |  |  | 0% |  |  | 0 | 0 | 0 | 0
| Accessories | 1 | 1 | lot | 4786691.6618 | 1436007.4985 | 6222699.1603 | 4786691.6618 | 1436007.4985 | 6222699.1603 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 2. 100. | Emergency lighting | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 2. 120. | Network infrastructure | 1 | 1 | PSCH |  |  | 0 | 307745509.2338 | 64282788.3235 | 372028297.5573 |  |  | 0% |  |  | 0 | 0 | 0 | 0
| Single Mode OS2 48 fibers SC- Duplex | 207 | 230 | m | 144000 | 28000 | 172000 | 33120000 | 6440000 | 39560000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Commscope
| 20 x 0,8 pair copper phone wire | 0 | 0 | m | 117360 | 13798.4 | 131158.4 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 1499418-1, Commscope/ China
| IDF7 42U (0.8x1.0x2.0), Included PDU, 10 patch panel, Cable routing channel 1U | 1 | 1 | pcs | 68750000 | 1308000 | 70058000 | 68750000 | 1308000 | 70058000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Rack: Rittal/ VN Patch panel: 760237046+2153449-2, Commscope/ China
| Patch panel 24 Port CAT6A | 8 |  | pcs | 5060000 | 654000 | 5714000 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760237046+2153449-2, Commscope/ China
| Patch panel 24 Port cat 5e | 2 | 2 | pcs | 2195600 | 654000 | 2849600 | 4391200 | 1308000 | 5699200 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760237040+9-1375191-2, Commscope/ China
| Cat 6A Patch Cord, 3m | 77 | 77 | pcs | 600000 | 13440 | 613440 | 46200000 | 1034880 | 47234880 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
| Cat 6A Patch Cord, 3m | 0 | 0 | pcs | 600000 | 13440 | 613440 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
| ODF F.O Singlemode, 48F | 2 | 2 | pcs | 6490000 | 490500 | 6980500 | 12980000 | 981000 | 13961000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 4-1671002-4+760241378, Commscope/ China
| Socket strip (PDU) with 7 sockets | 2 | 2 | pcs | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Included
| 16A Turnlock socket | 2 | 2 | pcs | 150480 | 54500 | 204980 | 300960 | 109000 | 409960 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
| Patch panel 24 Port | 0 | 0 | pcs | 5060000 | 654000 | 5714000 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760237046+2153449-2+VRMH01-1F, Commscope/ China
| Double data outlet RJ45 | 26 | 26 | pcs | 480000 | 81750 | 561750 | 12480000 | 2125500 | 14605500 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760245679+2153449-1, Commscope/ China
| Wifi module (Wifi supply by Client) | 25 | 25 | pcs | 0 | 136250 | 136250 | 0 | 3406250 | 3406250 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Only labor
| FO Patch Cord, SC-SC Duplex, LSOH, SM,3m | 20 | 20 | pcs | 550000 | 10900 | 560900 | 11000000 | 218000 | 11218000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FFWSCSC42-JXM003,Commscope/ China
| FO Pigtail LC, SM, 1m for welding to optical fibre | 20 | 96 | pcs | 132000 | 65400 | 197400 | 12672000 | 6278400 | 18950400 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | EH0108-001, Commscope/ China
| Cat 6A Patch Cord, 3m from Data outlet to Wifi | 25 | 25 | pcs | 198000 | 10900 | 208900 | 4950000 | 272500 | 5222500 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
| Cable Cat6A | 3219 | 3245 | m | 21639.3443 | 3360 | 24999.3443 | 70219672.1311 | 10903200 | 81122872.1311 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Commscope
| PVC conduit D20 | 1610 | 1510 | m | 8773.9726 | 14594.0164 | 23367.989 | 13248698.6301 | 22036964.7818 | 35285663.4119 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
| Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
| Network cable test cost - Cat6A cable | 52 | 52 | nos | 0 | 50600 | 50600 | 0 | 2631200 | 2631200 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
| Accessories | 1 | 1 | lot | 17432978.4725 | 5229893.5417 | 22662872.0142 | 17432978.4725 | 5229893.5417 | 22662872.0142 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Vietnam
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 2. 130. | Access control preparation | 1 | 1 | PSCH |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | N/A
2. 2. 140. | CCTV System | 1 | 1 | PSCH |  |  | 0 | 375818416.1739 | 19180346.471 | 394998762.6449 |  |  | 0% |  |  | 0 | 0 | 0 | 0
| Outside Camera CE-1-->12 | 12 | 12 | pcs | 19242720 | 198000 | 19440720 | 230912640 | 2376000 | 233288640 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Axis - P1447-LE
| Symphony Standard Edition - VMS Device License | 12 | 12 | pcs | 2704800 | 330000 | 3034800 | 32457600 | 3960000 | 36417600 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Sentar/ Canada
| Telescopic parapet mount (T91D62) | 12 | 12 | pcs | 1803200 | 49500 | 1852700 | 21638400 | 594000 | 22232400 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | T91D62, Axis
| Overvoltage protection | 12 | 12 | pcs | 4494000 | 49050 | 4543050 | 53928000 | 588600 | 54516600 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | PNET1GB, Schneider
| Double data outlet RJ45 | 12 | 12 | pcs | 480000 | 81750 | 561750 | 5760000 | 981000 | 6741000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760245679+2153449-1, Commscope/ China
| Cat 6A Patch Cord, 3m | 36 | 24 | pcs | 198000 | 10900 | 208900 | 4752000 | 261600 | 5013600 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
| Cable Cat6A | 686 | 658.24 | m | 21639.3443 | 3360 | 24999.3443 | 14243881.9672 | 2211686.4 | 16455568.3672 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Commscope
| PVC conduit D20 | 274 | 280.5 | m | 8773.9726 | 14594.0164 | 23367.989 | 2461099.3151 | 4093621.6035 | 6554720.9186 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
| Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
| Network cable test cost - Cat6A cable | 12 | 24 | nos | 0 | 50600 | 50600 | 0 | 1214400 | 1214400 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
| Accessories | 1 | 1 | lot | 9664794.8916 | 2899438.4675 | 12564233.3591 | 9664794.8916 | 2899438.4675 | 12564233.3591 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 3. | Mechanical Engineering | 1 | 1 | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
2. 3. 10. | Ventilation System Production | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 3. 20. | Fire Protection Engineering | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 3. 30. | Installation of In-Rack Sprinkler at Logistic | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 3. 40. | Compressed Air Network Production 1 | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
2. 3. 50. | Compressed Air Network Production 2 | 1 | 1 | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. | Office, Social and Technical Areas (Hall 3) | [6 empty] | 1095015293.254 | 204033421.602 | 1299048714.856 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 1. | Civil Engineering | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 10. | Rainwater and waste water sewer | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 20. | Foundations | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 30. | Steel columns | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 40. | Building structure | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 50. | Concrete works | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 60. | Reinforced concrete slabs 1st floor | 0 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 70. | Reinforced concrete stairs | 0 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 80. | Screed coat | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 90. | Metal works | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 100. | Exterior walls | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 110. | Masonry works | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 120. | plastering works | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 130. | Drywall works | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 140. | Ceiling for new built-ins | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 150. | Fire protection | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 160. | Fire rated walls | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 170. | Cutting holes into existing facades, walls and roofs | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 180. | Cuts in Floor/slab/wall | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 190. | Exterior doors and windows | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 200. | Canopies for exterior doors | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 210. | Covering existing windows with mirroring film | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 220. | Internal doors | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 230. | Fire protection doors | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 240. | Suspended ceiling | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 250. | Floor covering works | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 260. | Tiles | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 270. | Needle Felt | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 280. | Raised floor | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 290. | Drainage of new wet rooms | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 300. | Railing and handrail | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 310. | Collision protection | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 320. | Vertical blinds | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 330. | Kitchenette | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 340. | Painting and varnishing works | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 350. | internal signage | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 360. | Locking system | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 1. 370. | Tightness Test Gas Extinguished Rooms | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. | Electrical engineering | 1 | 1 | PSCH |  |  |  | 1095015293.254 | 204033421.602 | 1299048714.856 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 10. | Rennovation existing grounding system and lightning protection | 1 | 1 | psch | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Included
3. 2. 20. | Rennovation existing grounding and equipotential bonding | 1 | 1 | psch | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Included
3. 2. 30. | Main Power supply | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 40. | Uninterrupted power supply (UPS) | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 50. | Electrical Capacitor bank | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 60. | Power supply of building utilities | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 70. | Energy measurement system | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 80. | Electrical installation in offices and meeting rooms | 1 |  | PSCH |  |  |  | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 90. | Electrical installation in social rooms | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 100. | Electrical installation in corridors and stairways | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 110. | Electrical installation in technical areas | 1 |  | PSCH |  |  |  | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 120. | Electrical installation in kitchenette areas | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 130. | Electrical installation for Workshop/Formbrettbau | 1 |  | PSCH |  |  |  | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 140. | Electrical installation at the reception | 1 |  | PSCH |  |  |  | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 150. | Electrical installation in other rooms/secondary rooms | 1 |  | PSCH |  |  |  | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 160. | Emergency lighting | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 170. | Fire alarm system | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 180. | Network infrastructure | 1 | 1 | PSCH |  |  |  | 947613765.2926 | 174994605.0134 | 1122608370.3061 |  |  | 0% |  |  | 0 | 0 | 0 | 0
| IDF4 42U (0.8x1.0x2.0), Included PDU, 10 patch panel, Cable routing channel 1U | 1 | 1 | pcs | 68750000 | 1308000 | 70058000 | 68750000 | 1308000 | 70058000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Rack: Rittal/ VN Patch panel: 760237046+2153449-2, Commscope/ China
| IDF5 42U (0.8x1.0x2.0), Included PDU, 10 patch panel, Cable routing channel 1U | 1 | 1 | pcs | 68750000 | 1308000 | 70058000 | 68750000 | 1308000 | 70058000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Rack: Rittal/ VN Patch panel: 760237046+2153449-2, Commscope/ China
| IDF6 42U (0.8x1.0x2.0), Included PDU, 10 patch panel, Cable routing channel 1U | 1 | 1 | pcs | 68750000 | 1308000 | 70058000 | 68750000 | 1308000 | 70058000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Rack: Rittal/ VN Patch panel: 760237046+2153449-2, Commscope/ China
| Patch panel 24 Port CAT6A | 24 |  | pcs | 5060000 | 654000 | 5714000 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760237046+2153449-2, Commscope/ China
| Patch panel 24 Port cat 5e | 6 | 6 | pcs | 2195600 | 654000 | 2849600 | 13173600 | 3924000 | 17097600 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760237040+9-1375191-2, Commscope/ China
| Cat 6A Patch Cord, 3m | 423 | 452 | pcs | 198000 | 10900 | 208900 | 89496000 | 4926800 | 94422800 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
| Cat 6A Patch Cord, 3m | 0 | 0 | pcs | 198000 | 10900 | 208900 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
| ODF F.O Singlemode, 48F | 6 | 6 | pcs | 6490000 | 490500 | 6980500 | 38940000 | 2943000 | 41883000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 4-1671002-4+760241378, Commscope/ China
| Socket strip (PDU) with 7 sockets | 6 | 6 | pcs |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Included
| 16A Turnlock socket | 6 | 6 | pcs | 150480 | 54500 | 204980 | 902880 | 327000 | 1229880 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
| Double data outlet RJ45 | 197 | 226 | pcs | 480000 | 81750 | 561750 | 108480000 | 18475500 | 126955500 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760245679+2153449-1, Commscope/ China
| Wifi module (Wifi supply by Client) | 29 | 29 | pcs | 0 | 136250 | 136250 | 0 | 3951250 | 3951250 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Only labor
| FO Patch Cord, SC-SC Duplex, LSOH, SM,3m | 60 | 60 | pcs | 550000 | 10900 | 560900 | 33000000 | 654000 | 33654000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FFWSCSC42-JXM003,Commscope/ China
| FO Pigtail LC, SM, 1m for welding to optical fibre | 60 | 144 | pcs | 132000 | 65400 | 197400 | 19008000 | 9417600 | 28425600 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | EH0108-001, Commscope/ China
| Cat 6A Patch Cord, 3m from Data outlet to Wifi | 29 | 29 | pcs | 198000 | 10900 | 208900 | 5742000 | 316100 | 6058100 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
| Cable Cat6A | 14691 | 14487.8 | m | 21639.3443 | 3360 | 24999.3443 | 313506491.8033 | 48679008 | 362185499.8033 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Commscope
| PVC conduit D20 | 138 | 2800 | m | 8773.9726 | 14594.0164 | 23367.989 | 24567123.2877 | 40863245.9529 | 65430369.2406 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
| Network cable test cost - FO cable | 24 | 96 | nos | 0 | 50600 | 50600 | 0 | 4857600 | 4857600 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
| Network cable test cost - Cat6A cable | 197 | 452 | nos | 0 | 50600 | 50600 | 0 | 22871200 | 22871200 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
| Accessories | 1 | 1 | lot | 29547670.2017 | 8864301.0605 | 38411971.2622 | 29547670.2017 | 8864301.0605 | 38411971.2622 |  |  | 0% |  |  | 0 | 0 | 0 | 0
| Updated for data socket outlet on Dadoduct | 1 | 1 | lot | 65000000 |  | 65000000 | 65000000 | 0 | 65000000 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 190. | CCTV System for custom fence | 1 | 1 | PSCH |  |  |  | 93265409.772 | 9368475.5017 | 102633885.2737 |  |  | 0% |  |  | 0 | 0 | 0 | 0
| Camera fence CF-5,6 | 2 | 2 | pcs | 1264480 | 137500 | 1401980 | 2528960 | 275000 | 2803960 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | DS-2CD2021G1-I, Hikvision/ China
| Camera Inside CI-1, Dome | 1 | 1 | pcs | 20015520 | 198000 | 20213520 | 20015520 | 198000 | 20213520 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Axis - P3247-LV
| Symphony Standard Edition - VMS Device License | 1 | 1 | pcs | 2704800 | 330000 | 3034800 | 2704800 | 330000 | 3034800 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Sentar/ Canada
| LCD 43" for CE, CI | 2 | 2 | pcs | 11990000 | 163500 | 12153500 | 23980000 | 327000 | 24307000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Samsung UA43T6500AK
| LCD 32" for CF | 2 | 2 | pcs | 11990000 | 163500 | 12153500 | 23980000 | 327000 | 24307000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Samsung UA43T6500AK
| HDMI cable c/w socket, 15m | 2 | 3 | pcs | 979000 | 59950 | 1038950 | 2937000 | 179850 | 3116850 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Unitek
| Single data outlet RJ45 | 3 | 3 | pcs | 276000 | 81750 | 357750 | 828000 | 245250 | 1073250 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760245680-1+2153449-1, Commscope/ China
| Double Socket 16A/230V | 2 | 2 | pcs | 150480 | 54500 | 204980 | 300960 | 109000 | 409960 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | KB426UES2_WE_G19/ Schneider/ VN, Plastic type
| Cat 6A Patch Cord, 3m from Data outlet to camera | 3 | 3 | pcs | 198000 | 10900 | 208900 | 594000 | 32700 | 626700 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
| Cable Cat6 | 400 | 403 | m | 10032.7869 | 3360 | 13392.7869 | 4043213.1148 | 1354080 | 5397293.1148 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Commscope
| Cable Cu/XLPE/PVC 3Cx2.5mm2 | 124 | 124 | m | 32518.74 | 7485.665 | 40004.405 | 4032323.76 | 928222.46 | 4960546.22 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
| PVC conduit D20 | 210 | 210 | m | 8773.9726 | 14594.0164 | 23367.989 | 1842534.2466 | 3064743.4465 | 4907277.693 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
| Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
| Network cable test cost - Cat6A cable | 3 | 7 | nos | 0 | 50600 | 50600 | 0 | 354200 | 354200 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
| Accessories | 1 | 1 | lot | 5478098.6507 | 1643429.5952 | 7121528.2459 | 5478098.6507 | 1643429.5952 | 7121528.2459 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 2. 200. | Access control preparation | 1 | 1 | PSCH |  |  |  | 54136118.1893 | 19670341.0869 | 73806459.2762 |  |  | 0% |  |  | 0 | 0 | 0 | 0
| Exit Button | 5 | 5 | pcs | 528000 | 61600 | 589600 | 2640000 | 308000 | 2948000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | EL-EB3/ Elock/ Malaysia
| Emergency Button | 5 | 5 | pcs | 528000 | 61600 | 589600 | 2640000 | 308000 | 2948000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | EB4R/ Elock/ Malaysia
| Door sensor | 55 | 5 | pcs | 2116800 | 95200 | 2212000 | 10584000 | 476000 | 11060000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | EL-810P/ Elock/ Malaysia/ China
| Access control card reader | 8 | 5 | set | 0 | 95200 | 95200 | 0 | 476000 | 476000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | by PCS, only labor install
| Single Socket 16A/230V | 5 | 5 | pcs | 150480 | 54500 | 204980 | 752400 | 272500 | 1024900 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | KB413S / Schneider/ VN, Plastic type
| Data outlet RJ45 | 5 | 5 | pcs | 480000 | 81750 | 561750 | 2400000 | 408750 | 2808750 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760245679+2153449-1, Commscope/ China
| AC/DC converter | 5 | 5 | pcs | 2220000 | 95200 | 2315200 | 11100000 | 476000 | 11576000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Meanwell/ China
| Conection box, SS304 | 5 | 5 | pcs | 180000 | 50400 | 230400 | 900000 | 252000 | 1152000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
| Cable cat6A | 357 | 225 | m | 21639.3443 | 3360 | 24999.3443 | 4868852.459 | 756000 | 5624852.459 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Commscope
| Cable telephone cat5e | 357 | 225 | m | 7475.4098 | 3360 | 10835.4098 | 1681967.2131 | 756000 | 2437967.2131 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 6-219590-2, Commscope/ China
| Cable Cu/XLPE/PVC 3Cx2.5mm2 | 286 | 286 | m | 32518.74 | 7485.665 | 40004.405 | 9300359.64 | 2140900.19 | 11441259.83 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
| PVC conduit D20 | 643 | 586 | m | 8773.9726 | 14594.0164 | 23367.989 | 5141547.9452 | 8552093.6173 | 13693641.5625 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
| Labour cost for support DRX test funtion of Access control system | 1 | 1 | lot | 0 | 3850000 | 3850000 | 0 | 3850000 | 3850000 |  |  | 0% |  |  | 0 | 0 | 0 | 0
| Accessories | 1 | 1 | lot | 2126990.932 | 638097.2796 | 2765088.2116 | 2126990.932 | 638097.2796 | 2765088.2116 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 3. | Mechanical Engineering | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 3. 10. | Waste Water System | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 3. 20. | Service Water System | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 3. 40. | Ventilation System | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 3. 50. | Ventilation System 1st Floor Offices Ventilation Units | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 3. 60. | Ventilation System 1st Floor Offices Ducting | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 3. 70. | Air Conditioning | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
3. 3. 80. | Fire Protection Engineering Sprinkler | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 3. 90. | Fire Protection Engineering Temperature Controlled Storage | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 3. 100. | Fire Protection Engineering Extinguishing Systems | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 3. 110. | Door Fan Test for Gas Extinguishing System | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
3. 3. 120. | Compressed Air Connections | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
4. | Machine hook-up (Hall 3) | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
4. 1. | Electrical engineering | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
4. 1. 10. | Power cables and lines | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
4. 2. | Mechanical Engineering | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
4. 2. 10. | Machine hook-up | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
| Supply & Installation pipe & fittings: Drop Piping (D25), Considering all drop piping & fittings | 1 |  | lot | 0 | 0 | [6 empty] | 0% |  |  | 0 | 0 | 0 | 0
| Hanger support & accessories | 1 |  | lot | 0 | 0 | [6 empty] | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
5. | Scooter Garage | [8 empty] | 162238150.0078 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
5. 1. | Civil Engineering | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
5. 1. 10. | Adjustments on the existing scooter garage | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
5. 1. 20. | Expansion of Scooter Garage | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
5. 2. | Electrical Engineering | 1 | 1 | PSCH |  |  |  | 144640388.5392 | 17597761.4686 | 162238150.0078 |  |  | 0% |  |  | 0 | 0 | 0 | 0
5. 2. 10. | Grounding and Lightining protection | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
5. 2. 20. | Power supply | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
5. 2. 30. | Power supply of building utilities | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
5. 2. 40. | Electrical installations | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
5. 2. 50. | Emergency lighting | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
5. 2. 60. | Fire alarms system | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
5. 2. 70. | CCTV System | 1 | 1 | PSCH |  |  |  | 144640388.5392 | 17597761.4686 | 162238150.0078 |  |  | 0% |  |  | 0 | 0 | 0 | 0
| POWER surveillance cabinet | 2 | 2 | pcs | 1650000 | 136250 | 1786250 | 3300000 | 272500 | 3572500 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Vietnam
| DATA surveillance cabinet | 2 | 2 | pcs | 1650000 | 136250 | 1786250 | 3300000 | 272500 | 3572500 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Vietnam
| Terminal 4mm2 | 2 | 2 | pcs | 27500 | 10900 | 38400 | 55000 | 21800 | 76800 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Vietnam
| MCB 1P-16A-230V | 2 | 2 | pcs | 90000 | 49050 | 139050 | 180000 | 98100 | 278100 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Schneider
| Power adapter (Mean Well SDR-240-48) | 2 | 2 | pcs | 2833600 | 114450 | 2948050 | 5667200 | 228900 | 5896100 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Mean Well SDR-240-48
| PoE Switch Planet IGS-10020HPT | 2 | 2 | pcs | 15180000 | 272500 | 15452500 | 30360000 | 545000 | 30905000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Planet IGS-10020HPT
| Outside Camera CF-7-->14 | 8 | 8 | pcs | 1264480 | 137500 | 1401980 | 10115840 | 1100000 | 11215840 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | DS-2CD2021G1-I/ HIKVISION
| Telescopic parapet mount (T91D62) | 8 | 8 | pcs | 1803200 | 49500 | 1852700 | 14425600 | 396000 | 14821600 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | DS-2CD2021G1-I/ HIKVISION
| Overvoltage protection | 8 | 8 | pcs | 4494000 | 49050 | 4543050 | 35952000 | 392400 | 36344400 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | PNET1GB, Schneider
| Single data outlet RJ45 | 8 | 8 | pcs | 276000 | 81750 | 357750 | 2208000 | 654000 | 2862000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760245680-1+2153449-1, Commscope/ China
| Cat 6A Patch Cord, 3m from Data outlet to camera | 8 | 8 | pcs | 198000 | 10900 | 208900 | 1584000 | 87200 | 1671200 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
| Cable Cat6 | 343 | 264 | m | 10032.7869 | 3360 | 13392.7869 | 2648655.7377 | 887040 | 3535695.7377 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Commposcope / China, or Alantek
| Gigabit Ethernet LX Mini-GBIC SFP Transceiver | 2 | 2 | pcs | 4032000 | 272500 | 4304500 | 8064000 | 545000 | 8609000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | MGBLX1/ Cisco
| converter quang đồng (Connect from optic cable to Patch panel) | 2 | 2 | pcs | 935000 | 49050 | 984050 | 1870000 | 98100 | 1968100 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
| Cat 6A Patch Cord, 3m from Converter to patch panel | 4 | 4 | pcs | 198000 | 10900 | 208900 | 792000 | 43600 | 835600 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
| FO Patch Cord, SC-SC Duplex, LSOH, SM,3m | 2 | 2 | pcs | 550000 | 10900 | 560900 | 1100000 | 21800 | 1121800 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FFWSCSC42-JXM003,Commscope/ China
| Fiber optical 8FO (SM-OS2 G9/125) | 190 | 190 | m | 54000 | 3360 | 57360 | 10260000 | 638400 | 10898400 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | X-1427452-4, Commscope/ China
| Cable Cu/XLPE/PVC 3Cx2.5mm2 | 100 | 100 | m | 32518.74 | 7485.665 | 40004.405 | 3251874 | 748566.5 | 4000440.5 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
| PVC conduit D20 | 144 | 200 | m | 8773.9726 | 14594.0164 | 23367.989 | 1754794.5205 | 2918803.2824 | 4673597.8029 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
| HDPE pipe D40/50 | 100 | 100 | m | 17049.1866 | 15805 | 32854.1866 | 1704918.6603 | 1580500 | 3285418.6603 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
| The cost of cutting and refinishing the concrete path for the undergruond pipe | 8 | 8 | m | 0 | 175000 | 175000 | 0 | 1400000 | 1400000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Run with at Electrical existing Manhole
| Network cable test cost - FO cable | 2 | 48 | nos | 0 | 50600 | 50600 | 0 | 2428800 | 2428800 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
| Network cable test cost - Cat6A cable | 8 | 8 | nos | 0 | 50600 | 50600 | 0 | 404800 | 404800 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
| Accessories | 1 | 1 | lot | 6046505.6207 | 1813951.6862 | 7860457.3069 | 6046505.6207 | 1813951.6862 | 7860457.3069 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
5. 3. | Mechancial Engineering | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
5. 3. 10. | Rainwater System | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
5. 3. 20. | Fire Protection System | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. | Canteen | [8 empty] | 274132627.4702 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 1. | Civil Engineering | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 10. | Demolition of existing canteen | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 20. | Building Structure | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 30. | Earthworks | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 40. | Rain water and waste water sewer | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 50. | Primary construction of reinforced concrete | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 60. | Foundations | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 70. | Concrete floor | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 80. | Concrete plinth | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 90. | Reinforced concrete columns | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 100. | Reinforced concrete beams | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 110. | Reinforced concrete 1st roof slab or structure | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 120. | Reinforced concrete stairs | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 130. | Concrete steps | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 140. | Screed coat | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 150. | Roof structure | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 160. | Metal facade | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 170. | Masonry works | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 180. | Exterior doors | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 190. | Fire protection | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 200. | Fire protection doors | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 210. | Interior doors | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 220. | Floor covering works | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 230. | Tiles | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 240. | Painting and finishing works | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 250. | Metal and railing works | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 260. | Elevator for goods | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 270. | Canpoy for the main entrance | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 280. | Exterior steel staircase | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 290. | Exterior sinks | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 1. 300. | Locking system | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 2. | Electrical Engineering | [6 empty] | 246947482.5691 | 27185144.9011 | 274132627.4702 |  |  | 0% |  |  | 0 | 0 | 0 | 0
| Notes Calculation Basis | [11 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 2. 10. | Grounding and Lightining protection | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 2. 20. | Power supply | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 2. 30. | Power supply of building utilities | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 2. 40. | Electrical installations | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 2. 50. | Emergency lighting | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 2. 60. | Fire alarms system | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 2. 70. | CCTV System For Custom fence | 1 | 1 | PSCH |  |  |  | 117565498.5134 | 6055261.4345 | 123620759.9479 |  |  | 0% |  |  | 0 | 0 | 0 | 0
| LCD 43" for CE, CI | 8 | 8 | pcs | 11990000 | 163500 | 12153500 | 95920000 | 1308000 | 97228000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Samsung UA43T6500AK
| HDMI cable c/w socket, 15m | 8 | 8 | pcs | 979000 | 59950 | 1038950 | 7832000 | 479600 | 8311600 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Unitek
| Outside Camera CF-16-->18 | 4 | 4 | pcs | 1264480 | 137500 | 1401980 | 5057920 | 550000 | 5607920 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | DS-2CD2021G1-I/ HIKVISION
| Single data outlet RJ45 | 4 | 4 | pcs | 276000 | 81750 | 357750 | 1104000 | 327000 | 1431000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760245680-1+2153449-1, Commscope/ China
| Cat 6A Patch Cord, 3m from Data outlet to camera | 4 | 4 | pcs | 198000 | 10900 | 208900 | 792000 | 43600 | 835600 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
| Cable Cat6 | 229 | 200 | m | 10032.7869 | 3360 | 13392.7869 | 2006557.377 | 672000 | 2678557.377 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Commposcope / China, or Alantek
| PVC conduit D20 | 91 | 85 | m | 8773.9726 | 14594.0164 | 23367.989 | 745787.6712 | 1240491.395 | 1986279.0662 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
| Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
| Network cable test cost - Cat6A cable | 4 | 4 | nos | 0 | 50600 | 50600 | 0 | 202400 | 202400 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
| Accessories | 1 | 1 | lot | 4107233.4651 | 1232170.0395 | 5339403.5046 | 4107233.4651 | 1232170.0395 | 5339403.5046 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 2. 80. | Network infrastructure | 1 | 1 | PSCH |  |  |  | 129381984.0557 | 21129883.4666 | 150511867.5223 |  |  | 0% |  |  | 0 | 0 | 0 | 0
| IDF8 12U (0.8x1.0x2.0), Included PDU, 10 patch panel, Cable routing channel 1U | 1 | 1 | pcs | 68750000 | 1308000 | 70058000 | 68750000 | 1308000 | 70058000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Rack: Rittal/ VN Patch panel: 760237046+2153449-2, Commscope/ China
| Patch panel 24 Port CAT6A | 2 |  | pcs | 5060000 | 654000 | 5714000 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760237046+2153449-2, Commscope/ China
| Cat 6A Patch Cord, 3m | 28 | 16 | pcs | 198000 | 10900 | 208900 | 3168000 | 174400 | 3342400 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
| Cat 6A Patch Cord, 3m | 0 | 0 | pcs | 198000 | 10900 | 208900 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
| ODF F.O Singlemode, 48F | 1 | 1 | pcs | 6490000 | 490500 | 6980500 | 6490000 | 490500 | 6980500 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 4-1671002-4+760241378, Commscope/ China
| Socket strip (PDU) with 7 sockets | 2 | 2 | pcs |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Included
| 16A Turnlock socket | 2 | 2 | pcs | 150480 | 54500 | 204980 | 300960 | 109000 | 409960 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
| Double data outlet RJ45 | 12 | 12 | pcs | 480000 | 81750 | 561750 | 5760000 | 981000 | 6741000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760245679+2153449-1, Commscope/ China
| Wifi module (Wifi supply by Client) | 4 | 4 | pcs | 0 | 136250 | 136250 | 0 | 545000 | 545000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Only labor
| FO Patch Cord, SC-SC Duplex, LSOH, SM,3m | 2 | 2 | pcs | 550000 | 10900 | 560900 | 1100000 | 21800 | 1121800 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FFWSCSC42-JXM003,Commscope/ China
| FO Pigtail LC, SM, 1m for welding to optical fibre | 2 | 48 | pcs | 132000 | 65400 | 197400 | 6336000 | 3139200 | 9475200 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | EH0108-001, Commscope/ China
| Cat 6A Patch Cord, 3m from Data outlet to wifi | 4 | 4 | pcs | 198000 | 10900 | 208900 | 792000 | 43600 | 835600 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
| Cable Cat6A | 1257 | 1240 | m | 21639.3443 | 3360 | 24999.3443 | 26832786.8852 | 4166400 | 30999186.8852 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Commscope
| PVC conduit D20 | 503 | 500 | m | 8773.9726 | 14594.0164 | 23367.989 | 4386986.3014 | 7297008.2059 | 11683994.5073 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
| Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
| Network cable test cost - Cat6A cable | 12 | 24 | nos | 0 | 50600 | 50600 | 0 | 1214400 | 1214400 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
| Accessories | 1 | 1 | lot | 5465250.8691 | 1639575.2607 | 7104826.1298 | 5465250.8691 | 1639575.2607 | 7104826.1298 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Vietnam
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 3. | Mechancial Engineering | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
6. 3. 10. | Rainwater System | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 3. 20. | Waste Water System | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 3. 30. | Service Water System | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 3. 40. | Sanitary Furnishings | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 3. 50. | Air Conditioning | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 3. 60. | Ventilation System Overhead Fans | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 3. 70. | Ventilation System | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
6. 3. 80. | Fire Protection System | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
7. | Exterior Area | [6 empty] | 509452988.9423 | 100342530.3589 | 609795519.3012 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
7. 1. | Civil Engineering | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
7. 1. 10. | Flag pole | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
7. 1. 20. | Fence | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
7. 1. 30. | Bollards and delineator panels | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
7. 1. 40. | New Septic Tanks | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
7. 1. 50. | Excavation | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
7. 1. 60. | Laying conduits, pipes, etc. | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
7. 1. 70. | Asphalt areas | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
7. 2. | Electrical Engineering | [6 empty] | 509452988.9423 | 100342530.3589 | 609795519.3012 |  |  | 0% |  |  | 0 | 0 | 0 | 0
7. 2. 10. | Electrical Installations General | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
7. 2. 20. | Exterior Lighting | 1 |  | PSCH | [8 empty] | 0% |  |  | 0 | 0 | 0 | 0
7. 2. 30. | Emergency Lighting | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
7. 2. 40. | Building service connections | 1 | 1 | PSCH |  |  |  | 449449440 | 94825780 | 544275220 |  |  | 0% |  |  | 0 | 0 | 0 | 0
| Single Mode OS2 48 fibers SC- Duplex | 1325 | 2141.26 | m | 144000 | 28000 | 172000 | 308341440 | 59955280 | 368296720 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Commscope
| 20 x 0,8 pair copper phone wire (20P cat3) | 0 |  | m | 117360 | 13798.4 | 131158.4 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 1499418-1, Commscope/ China
| ODF F.O Singlemode, 48F add to MDF at server rooms | 5 | 5 | pcs | 6490000 | 490500 | 6980500 | 32450000 | 2452500 | 34902500 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 4-1671002-4+760241378, Commscope/ China
| Patch panel 24 Port cat 5e | 5 | 5 | pcs | 2195600 | 654000 | 2849600 | 10978000 | 3270000 | 14248000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760237040+9-1375191-2, Commscope/ China
| Cat 6A Patch Cord, 3m | 120 |  | pcs | 198000 | 10900 | 208900 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
| FO Patch Cord, SC-SC Duplex, LSOH, SM,3m | 120 | 120 | pcs | 550000 | 10900 | 560900 | 66000000 | 1308000 | 67308000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FFWSCSC42-JXM003,Commscope/ China
| FO Pigtail LC, SM, 1m for welding to optical fibre | 120 | 240 | pcs | 132000 | 65400 | 197400 | 31680000 | 15696000 | 47376000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | EH0108-001, Commscope/ China
| Network cable test cost - FO cable | 120 | 240 | nos | 0 | 50600 | 50600 | 0 | 12144000 | 12144000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
| Network cable test cost - Cat6A cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
7. 2. 50. | CCTV System | 1 | 1 | PSCH |  |  |  | 60003548.9423 | 5516750.3589 | 65520299.3012 |  |  | 0% |  |  | 0 | 0 | 0 | 0
| For Custom fence | [6 empty] | 60003548.9423 | 5516750.3589 | 65520299.3012 |  |  | 0% |  |  | 0 | 0 | 0 | 0
| NVR 32 Chanel | 1 | 1 | pcs | 19810560 | 385000 | 20195560 | 19810560 | 385000 | 20195560 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | DS-7616NI-K2/ HIKVISION/ China
| Outside Camera CF-1-->4 | 4 | 4 | pcs | 1264480 | 137500 | 1401980 | 5057920 | 550000 | 5607920 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | DS-2CD2021G1-I, Hikvision/ China
| Telescopic parapet mount (T91D62) | 4 | 4 | pcs | 1803200 | 49500 | 1852700 | 7212800 | 198000 | 7410800 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Axis
| Overvoltage protection | 4 | 4 | pcs | 4494000 | 49050 | 4543050 | 17976000 | 196200 | 18172200 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | PNET1GB, Schneider
| Double data outlet RJ45 | 4 | 4 | pcs | 480000 | 81750 | 561750 | 1920000 | 327000 | 2247000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | 760245679+2153449-1, Commscope/ China
| Cat 6A Patch Cord, 3m | 12 | 12 | pcs | 198000 | 10900 | 208900 | 2376000 | 130800 | 2506800 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | NPC6ASZDB-OR003M, Commscope/ China
| Cable Cat6 | 240 | 227 | m | 10032.7869 | 3360 | 13392.7869 | 2277442.623 | 762720 | 3040162.623 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Commposcope / China, or Alantek
| PVC conduit D20 | 96 | 100 | m | 8773.9726 | 14594.0164 | 23367.989 | 877397.2603 | 1459401.6412 | 2336798.9015 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
| Network cable test cost - FO cable | 0 | 0 | nos | 0 | 50600 | 50600 | 0 | 0 | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
| Network cable test cost - Cat6A cable | 4 | 15 | nos | 0 | 50600 | 50600 | 0 | 759000 | 759000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | VN
| Accessories | 1 | 1 | lot | 2495429.0591 | 748628.7177 | 3244057.7768 | 2495429.0591 | 748628.7177 | 3244057.7768 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
7. 3. | Mechanical Engineering | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
7. 3. 10. | Underground Compressed Air Connection | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
8. | Adjustments Hall 2 | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
8. 1. | Roof Renovation | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
8. 1. 10. | Roof Reinforcement Option 1 | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
8. 2. | Adjustment Ridge Vent | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
8. 2. 10. | Adjustment Ridge Vent | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
8. 3. | Adjustment Overhead Fans | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
8. 3. 10. | Adjustment Overhead Fans | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
8. 4. | Additonal In-Rack Sprinkler Logistic | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
8. 4. 10. | Additonal In-Rack Sprinkler Logistic | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
8. 5. | Additional Compressed Air Equipment | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
8. 5. 10. | Additional Compressed Air Equipment | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
8. 6. | Flag pole | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
8. 6. 10. | Flag pole | 0 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
9. | As built documentation | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
9. 1. | As built documentation all trades | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
9. 1. 10. | As built documentation | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
10. | Service of Architects and Engineers | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
10. 1. | Civil engineering | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 1. 10. | Design works | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 1. 20. | Geotechnical survey | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 1. 30. | Topographical survey | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 1. 40. | Fire protection report | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 1. 50. | Compactation report of earthworks | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 1. 60. | Structure and welding quality report | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 1. 70. | Adherence and width of paint quality control reports | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 1. 80. | Material quality control reports | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 1. 90. | Planning service Building construction | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 1. 100. | Planning service Structural design | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 1. 110. | Planning service Structural revision | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 1. 120. | Surveying services Inventory registration | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 1. 130. | Quality control laboratory for material testing (laboratory and field testing) | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 1. 140. | Revision fire department and civil protection | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
10. 2. | Electrical engineering | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 2. 10. | Design & approval works | 1 |  | psch | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0 | 0
10. 3. | Mechanical engineering | [8 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
10. 3. 10. | Design & approval works | 1 |  | psch | [5 empty] | 0 |  |  | 0% |  |  | 0 | 0 | 0 | 0
[13 empty] | 0% |  |  | 0 | 0 | 0
| TOTAL AMOUNT (Not included VAT) | [6 empty] | 2924099307.303 | 488828772.8637 | 3412928080.1667 | [6 empty] | 111817559.8522 | 18158432.9237 | 129975992.7758
0
NHÀ THẦU PHỤ: CÔNG TY CỔ PHẦN HMEP | [11 empty] | NHÀ THẦU CHÍNH: CÔNG TY CỔ PHẦN KỸ THUẬT XÂY DỰNG DINCO | [8 empty] | -9978600
ĐẠI DIỆN NHÀ THẦU HMEP | [20 empty] | -17953600
[14 empty] | GIÁM SÁT THI CÔNG | CHỈ HUY TRƯỞNG | [5 empty] | -13623500
-1620000
0

## 3. AIR COMPRESSOR (hidden)
Project: VN-RENTAL BUILDING HALL 3 ELECTRIC
Location: Lô D1, Khu công nghiệp Tam Thăng, Huyện Tam Thăng, thành Phố Tam Kỳ, Tỉnh quản Nam, Việt Nam
Client: Draexlmaier Automotive Vietnam Company Limited
Package: Cơ - Điện
Item: Compressed Air System
Date: 27/02/2022
Contractor name: HMEP
Position | Headline | Quantity | Quantity By contractor | Unit | Material Unit | Labor Unit | Unit rate | Material Amount | Labor Amount | Amount (VND) | % Công việc hoàn thành vật tư |  |  | % Công việc hoàn thành nhân công |  |  | Giá trị thanh toán đợt 1 |  |  | Remark
[11 empty] | Đợt 1 | đợt 2 | % KL hoàn thành lũy kế | Đợt 1 | đợt 2 | % KL hoàn thành lũy kế | Vật tư | Nhân công | Tổng
2. | Production and Logistic building (Hall 3) | [6 empty] | 585597305.9781 | 205702981.3661 | 791300287.3442 | [6 empty] | 0 | 0 | 0
[13 empty] | 0% |  |  | 0% | 0 | 0 | 0
2. 3. | Mechanical Engineering | [6 empty] | 585597305.9781 | 205702981.3661 | 791300287.3442 |  |  | 0% |  |  | 0% | 0 | 0 | 0
2. 3. 40. | Compressed Air Network Production 1 | 1 |  | PSCH |  |  |  | 425312121.5169 | 147070051.5988 | 572382173.1157 |  |  | 0% |  |  | 0% | 0 | 0 | 0
| BLUE ALUMINIUM PIPE, DN63 | 470 | 485 | m | 362322.6857 | 115320.5625 | 477643.2482 | 175726502.5676 | 55930472.8125 | 231656975.3801 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 301 00 0600 01, Airpipe/ Vietnam
| BLUE ALUMINIUM PIPE, DN40 | 0 | 30 | pcs | 190224.1656 | 70966.5 | 261190.6656 | 5706724.968 | 2128995 | 7835719.968 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 301 00 0400 01, Airpipe/ Vietnam
| BLUE ALUMINIUM PIPE, DN25 | 180 | 174 | m | 94950.6667 | 42579.9 | 137530.5667 | 16521416 | 7408902.6 | 23930318.6 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 301 00 0200 01, Airpipe/ Vietnam
| TUBE CLIP, DN63 (POLYMER) | 162 | 172 | pcs | 54295.4118 | 82376.8 | 136672.2118 | 9338810.8362 | 14168809.6 | 23507620.4362 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| TUBE CLIP, DN40 (POLYMER) | 76 | 10 | pcs | 32609.857 | 57608.1 | 90217.957 | 326098.5696 | 576081 | 902179.5696 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| PIPE TO PIPE JOINT, DN63 | 79 | 79 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 47234236.4616 | 6507767.2 | 53742003.6616 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| PIPE TO PIPE JOINT, DN63 | 50 | 50 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 29895086.3681 | 4118840 | 34013926.3681 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| 90° ELBOW, DN63 | 6 | 8 | pcs | 326098.5696 | 82376.8 | 408475.3696 | 2608788.5568 | 659014.4 | 3267802.9568 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| EQUAL TEE, DN63 | 3 | 5 | pcs | 543443.2662 | 82376.8 | 625820.0662 | 2717216.3312 | 411884 | 3129100.3312 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| END CAP, DN63 | 1 | 1 | pcs | 380393.9814 | 82376.8 | 462770.7814 | 380393.9814 | 82376.8 | 462770.7814 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| REDUCING TEE, DN63-40 | 12 | 14 | pcs | 861389.3716 | 82376.8 | 943766.1716 | 12059451.2024 | 1153275.2 | 13212726.4024 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| QUICK DROP, DN63-25 | 32 | 32 | pcs | 372241.5172 | 82376.8 | 454618.3172 | 11911728.5503 | 2636057.6 | 14547786.1503 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| PIPE TO PIPE JOINT, DN40 | 37 | 37 | pcs | 317946.1054 | 57608.1 | 375554.2054 | 11764005.8983 | 2131499.7 | 13895505.5983 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| LOCKABLE BRASS VALVE, DN25-1/2" FEMALE THREAD, WITH FIXING PLATE | 32 | 32 | pcs | 680241.6162 | 53385.955 | 733627.5712 | 21767731.7179 | 1708350.5613 | 23476082.2792 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| TWO-WAYS PNEUMATIC CONNECTOR, FEMALE THREAD G1/2" | 0 |  | pcs | 206583.4438 | 53385.955 | 259969.3989 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| T-BOLT, M8, 6CM | 228 | 228 | pcs | 3260.9857 | 3850 | 7110.9857 | 743504.7387 | 877800 | 1621304.7387 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
| THREADED ROD, M8, 3 METER | 50 | 50 | pcs | 48914.7854 | 11000 | 59914.7854 | 2445739.272 | 550000 | 2995739.272 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
| WALL MOUNTED BRACKET, 50CM | 228 | 228 | pcs | 92448.9445 | 8250 | 100698.9445 | 21078359.3418 | 1881000 | 22959359.3418 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
| BEAM CLAMP, 2.5CM | 456 | 456 | pcs | 37990.4834 | 8250 | 46240.4834 | 17323660.4114 | 3762000 | 21085660.4114 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
| Fire Stop | 1 | 1 | lot | 2500000 | 1000000 | 3500000 | 2500000 | 1000000 | 3500000 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
| Accessories | 1 | 1 | lot | 33262665.7435 | 9978799.7231 | 43241465.4666 | 33262665.7435 | 9978799.7231 | 43241465.4666 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Included
| T&C | 1 | 1 | lot | 0 | 29398125.4019 | 29398125.4019 | 0 | 29398125.4019 | 29398125.4019 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
[13 empty] | 0% |  |  | 0% | 0 | 0 | 0
2. 3. 50. | Compressed Air Network Production 2 | 1 |  | PSCH |  |  |  | 160285184.4612 | 58632929.7673 | 218918114.2285 |  |  | 0% |  |  | 0% | 0 | 0 | 0
| PRODUCTION 2 | [6 empty] | 83418012.7013 | 26026366.1504 | 109444378.8517 |  |  | 0% |  |  | 0% | 0 | 0 | 0
| BLUE ALUMINIUM PIPE, DN40 | 109 | 210 | m | 190224.1656 | 70966.5 | 261190.6656 | 39947074.776 | 14902965 | 54850039.776 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 301 00 0400 01, Airpipe/ Vietnam
| BLUE ALUMINIUM PIPE, DN25 | 56 | 59 | m | 94950.6667 | 42579.9 | 137530.5667 | 5602089.3333 | 2512214.1 | 8114303.4333 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 301 00 0200 01, Airpipe/ Vietnam
| PIPE TO PIPE JOINT, DN63 | 4 | 4 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 2391606.9094 | 329507.2 | 2721114.1094 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| PIPE TO PIPE JOINT, DN40 | 19 | 19 | pcs | 317946.1054 | 57608.1 | 375554.2054 | 6040976.0018 | 1094553.9 | 7135529.9018 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| REDUCING TEE, DN63-40 | 2 | 2 | pcs | 861389.3716 | 82376.8 | 943766.1716 | 1722778.7432 | 164753.6 | 1887532.3432 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| TUBE CLIP, DN40 (POLYMER) | 40 | 70 | pcs | 32609.857 | 57608.1 | 90217.957 | 2282689.9872 | 4032567 | 6315256.9872 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| 45° ELBOW, DN40 | 6 | 6 | pcs | 741874.2458 | 57608.1 | 799482.3458 | 4451245.475 | 345648.6 | 4796894.075 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| QUICK DROP, DN40-25 | 10 | 10 | pcs | 318435.2532 | 57608.1 | 376043.3532 | 3184352.5321 | 576081 | 3760433.5321 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| BRASS VALVE, DN40-DN40 | 2 | 2 | pcs | 1451138.6347 | 57608.1 | 1508746.7347 | 2902277.2694 | 115216.2 | 3017493.4694 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| LOCKABLE BRASS VALVE, DN25-1/2" FEMALE THREAD, WITH FIXING PLATE | 10 | 10 | pcs | 680241.6162 | 53385.955 | 733627.5712 | 6802416.1619 | 533859.5504 | 7336275.7123 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| TWO-WAYS PNEUMATIC CONNECTOR, FEMALE THREAD G1/2" | 0 |  | pcs | 206583.4438 | 53385.955 | 259969.3989 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| T-BOLT, M8, 6CM | 40 | 40 | pcs | 3260.9857 | 3850 | 7110.9857 | 130439.4278 | 154000 | 284439.4278 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
| THREADED ROD, M8, 3 METER | 25 | 25 | pcs | 48914.7854 | 11000 | 59914.7854 | 1222869.636 | 275000 | 1497869.636 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
| WALL MOUNTED BRACKET, 50CM | 40 | 40 | pcs | 92448.9445 | 8250 | 100698.9445 | 3697957.7793 | 330000 | 4027957.7793 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
| BEAM CLAMP, 2.5CM | 80 | 80 | pcs | 37990.4834 | 8250 | 46240.4834 | 3039238.6687 | 660000 | 3699238.6687 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
| LOGICSTIC | [6 empty] | 76867171.7599 | 32606563.6169 | 109473735.3768 |  |  | 0% |  |  | 0% | 0 | 0 | 0
| BLUE ALUMINIUM PIPE, DN63 | 0 | 30 | m | 362322.6857 | 115320.5625 | 477643.2482 | 10869680.5712 | 3459616.875 | 14329297.4462 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 301 00 0600 01, Airpipe/ Vietnam
| BLUE ALUMINIUM PIPE, DN40 | 69 | 72 | m | 190224.1656 | 70966.5 | 261190.6656 | 13696139.9232 | 5109588 | 18805727.9232 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 301 00 0400 01, Airpipe/ Vietnam
| BLUE ALUMINIUM PIPE, DN25 | 17 | 21 | m | 94950.6667 | 42579.9 | 137530.5667 | 1993964 | 894177.9 | 2888141.9 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 301 00 0200 01, Airpipe/ Vietnam
| TUBE CLIP, DN63 (POLYMER) | 0 | 6 | pcs | 54295.4118 | 82376.8 | 136672.2118 | 325772.471 | 494260.8 | 820033.271 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| PIPE TO PIPE JOINT, DN63 | 0 | 8 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 4783213.8189 | 659014.4 | 5442228.2189 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| PIPE TO PIPE JOINT, DN63 | 0 | 8 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 4783213.8189 | 659014.4 | 5442228.2189 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| EQUAL TEE, DN63 | 0 | 6 | pcs | 543443.2662 | 82376.8 | 625820.0662 | 3260659.5974 | 494260.8 | 3754920.3974 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| REDUCING TEE, DN63-40 | 2 | 2 | pcs | 861389.3716 | 82376.8 | 943766.1716 | 1722778.7432 | 164753.6 | 1887532.3432 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| END CAP, DN63 | 1 | 1 | pcs | 380393.9814 | 82376.8 | 462770.7814 | 380393.9814 | 82376.8 | 462770.7814 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| TUBE CLIP, DN40 (POLYMER) | 26 | 24 | pcs | 32609.857 | 57608.1 | 90217.957 | 782636.567 | 1382594.4 | 2165230.967 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| PIPE TO PIPE JOINT, DN40 | 12 | 12 | pcs | 317946.1054 | 57608.1 | 375554.2054 | 3815353.2643 | 691297.2 | 4506650.4643 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| 90° ELBOW, DN40 | 1 | 1 | pcs | 706492.551 | 57608.1 | 764100.651 | 706492.551 | 57608.1 | 764100.651 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| EQUAL TEE, DN40 | 1 | 1 | pcs | 1066831.4704 | 57608.1 | 1124439.5704 | 1066831.4704 | 57608.1 | 1124439.5704 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| QUICK DROP, DN63-25 | 1 | 1 | pcs | 372241.5172 | 82376.8 | 454618.3172 | 372241.5172 | 82376.8 | 454618.3172 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| QUICK DROP, DN40-25 | 2 | 2 | pcs | 318435.2532 | 57608.1 | 376043.3532 | 636870.5064 | 115216.2 | 752086.7064 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| END CAP, DN40 | 2 | 2 | pcs | 529910.1756 | 57608.1 | 587518.2756 | 1059820.3512 | 115216.2 | 1175036.5512 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| BRASS VALVE, DN40-DN40 | 2 | 2 | pcs | 1451138.6347 | 57608.1 | 1508746.7347 | 2902277.2694 | 115216.2 | 3017493.4694 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| BRASS VALVE, DN25-1/2" FEMALE THREAD, WITH FIXING PLATE | 2 | 2 | pcs | 617304.5923 | 53385.955 | 670690.5473 | 1234609.1845 | 106771.9101 | 1341381.0946 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| TWO-WAYS PNEUMATIC CONNECTOR, FEMALE THREAD G1/2" | 0 |  | pcs | 206583.4438 | 48702.5 | 255285.9438 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| T-BOLT, M8, 6CM | 40 | 40 | pcs | 3260.9857 | 3850 | 7110.9857 | 130439.4278 | 154000 | 284439.4278 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
| THREADED ROD, M8, 3 METER | 25 | 25 | pcs | 48914.7854 | 11000 | 59914.7854 | 1222869.636 | 275000 | 1497869.636 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
| WALL MOUNTED BRACKET, 50CM | 36 | 36 | pcs | 92448.9445 | 8250 | 100698.9445 | 3328162.0013 | 297000 | 3625162.0013 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
| BEAM CLAMP, 2.5CM | 72 | 72 | pcs | 37990.4834 | 8250 | 46240.4834 | 2735314.8018 | 594000 | 3329314.8018 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
| Fire Stop | 1 | 1 | lot | 2500000 | 1000000 | 3500000 | 2500000 | 1000000 | 3500000 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
| Accessories | 1 | 1 | lot | 12557436.286 | 3767230.8858 | 16324667.1718 | 12557436.286 | 3767230.8858 | 16324667.1718 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Included
| T&C | 1 | 1 | lot | 0 | 11778364.046 | 11778364.046 | 0 | 11778364.046 | 11778364.046 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
[13 empty] | 0% |  |  | 0% | 0 | 0 | 0
3. | Office, Social and Technical Areas (Hall 3) | [6 empty] | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[13 empty] | 0% |  |  | 0% | 0 | 0 | 0
3. 3. | Mechanical Engineering | [6 empty] | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
3. 3. 120. | Compressed Air Connections | 1 |  | PSCH | [5 empty] | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Included in machine hook-up
4. | Machine hook-up (Hall 3) | [6 empty] | 246537484.7813 | 58813621.1675 | 305351105.9487 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[13 empty] | 0% |  |  | 0%
4. 2. | Mechanical Engineering | [6 empty] | 246537484.7813 | 58813621.1675 | 305351105.9487 |  |  | 0% |  |  | 0% | 0 | 0 | 0
4. 2. 10. | Machine hook-up | 1 | 1 | PSCH |  |  |  | 246537484.7813 | 58813621.1675 | 305351105.9487 |  |  | 0% |  |  | 0% | 0 | 0 | 0
| BLUE ALUMINIUM PIPE, DN63 | 16 | 18 | m | 362322.6857 | 115320.5625 | 477643.2482 | 6521808.3427 | 2075770.125 | 8597578.4677 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 301 00 0600 01, Airpipe/ Vietnam
| BLUE ALUMINIUM PIPE, DN40 | 257 | 228 | m | 190224.1656 | 70966.5 | 261190.6656 | 43371109.7568 | 16180362 | 59551471.7568 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 301 00 0400 01, Airpipe/ Vietnam
| BLUE ALUMINIUM PIPE, DN25 | 23 | 27 | m | 94950.6667 | 42579.9 | 137530.5667 | 2563668 | 1149657.3 | 3713325.3 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 301 00 0200 01, Airpipe/ Vietnam
| PIPE TO PIPE JOINT, DN63 | 1 | 1 | pcs | 597901.7274 | 82376.8 | 680278.5274 | 597901.7274 | 82376.8 | 680278.5274 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| REDUCING PIPE TO PIPE JOINT, DN63-DN40 | 1 | 1 | pcs | 684154.799 | 82376.8 | 766531.599 | 684154.799 | 82376.8 | 766531.599 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| TUBE CLIP, DN40 (POLYMER) | 92 | 77 | pcs | 32609.857 | 57608.1 | 90217.957 | 2510958.9859 | 4435823.7 | 6946782.6859 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| PIPE TO PIPE JOINT, DN40 | 45 | 45 | pcs | 317946.1054 | 57608.1 | 375554.2054 | 14307574.7412 | 2592364.5 | 16899939.2412 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| QUICK DROP, DN40-25 | 45 | 45 | pcs | 318435.2532 | 57608.1 | 376043.3532 | 14329586.3946 | 2592364.5 | 16921950.8946 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| Pressureless decouling | 96 | 96 | pcs | 387040 | 30056.4 | 417096.4 | 37155840 | 2885414.4 | 40041254.4 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Festo/ Vietnam
| BRASS VALVE, DN63-DN63 | 1 | 1 | pcs | 2445739.272 | 82376.8 | 2528116.072 | 2445739.272 | 82376.8 | 2528116.072 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| BRASS VALVE, DN40-DN40 | 2 | 2 | pcs | 1451138.6347 | 57608.1 | 1508746.7347 | 2902277.2694 | 115216.2 | 3017493.4694 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| LOCKABLE BRASS VALVE, DN25-1/2" FEMALE THREAD, WITH FIXING PLATE | 28 | 28 | pcs | 680241.6162 | 53385.955 | 733627.5712 | 19046765.2532 | 1494806.7411 | 20541571.9943 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| LOCKABLE BRASS VALVE, DN25-3/8" FEMALE THREAD, WITH FIXING PLATE | 68 | 68 | pcs | 680241.6162 | 53385.955 | 733627.5712 | 46256429.9006 | 3630244.9427 | 49886674.8433 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| BRASS VALVE, DN25-1/2" FEMALE THREAD, WITH FIXING PLATE | 6 | 6 | pcs | 617304.5923 | 53385.955 | 670690.5473 | 3703827.5535 | 320315.7302 | 4024143.2838 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| T-split 3 way outlet tap | 28 | 28 | pcs | 451350 | 27500 | 478850 | 12637800 | 770000 | 13407800 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | VN
| T-BOLT, M8, 6CM | 92 | 92 | pcs | 3260.9857 | 3850 | 7110.9857 | 300010.684 | 354200 | 654210.684 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
| THREADED ROD, M8, 3 METER | 50 | 50 | pcs | 48914.7854 | 11000 | 59914.7854 | 2445739.272 | 550000 | 2995739.272 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
| WALL MOUNTED BRACKET, 50CM | 92 | 92 | pcs | 92448.9445 | 8250 | 100698.9445 | 8505302.8923 | 759000 | 9264302.8923 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
| BEAM CLAMP, 2.5CM | 184 | 184 | pcs | 37990.4834 | 8250 | 46240.4834 | 6990248.9379 | 1518000 | 8508248.9379 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
[13 empty] | 0% |  |  | 0% | 0 | 0 | 0
| Accessories | 1 | 1 | lot | 19260740.9985 | 5778222.2996 | 25038963.2981 | 19260740.9985 | 5778222.2996 | 25038963.2981 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Included
| T&C | 1 | 1 | lot | 0 | 11364728.3288 | 11364728.3288 | 0 | 11364728.3288 | 11364728.3288 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
[13 empty] | 0% |  |  | 0% | 0 | 0 | 0
5. | Scooter Garage | [6 empty] | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[13 empty] | 0% |  |  | 0% | 0 | 0 | 0
6. | Canteen | [6 empty] | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[13 empty] | 0% |  |  | 0% | 0 | 0 | 0
7. | Exterior Area | [6 empty] | 28542816 | 17816848.8 | 46359664.8 |  |  | 0% |  |  | 0% | 16491404.8 | 0 | 16491404.8
[13 empty] | 0% |  |  | 0%
7. 3. | Mechanical Engineering | [6 empty] | 28542816 | 17816848.8 | 46359664.8 |  |  | 0% |  |  | 0% | 16491404.8 | 0 | 16491404.8
7. 3. 10. | Underground Compressed Air Connection | 1 |  | PSCH |  |  |  | 28542816 | 17816848.8 | 46359664.8 |  |  | 0% |  |  | 0% | 16491404.8 | 0 | 16491404.8
| HDPE Pipe DN100 | 115 | 115 | m | 179254.4 | 96096 | 275350.4 | 20614256 | 11051040 | 31665296 | 80% |  | 80% |  |  | 0% | 16491404.8 | 0 | 16491404.8 | De Nhat, VN, Ø110, 10.0mm, PN16
| Fitting for connecting HDPE pipes with aluminum pipes | 1 | 1 | lot | 4757136 | 1427140.8 | 6184276.8 | 4757136 | 1427140.8 | 6184276.8 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Viet Nam
| Hanger support & accessories | 1 | 1 | lot | 3171424 | 951427.2 | 4122851.2 | 3171424 | 951427.2 | 4122851.2 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Viet Nam
| T&C | 1 | 1 | lot | 0 | 4387240.8 | 4387240.8 | 0 | 4387240.8 | 4387240.8 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Viet Nam
[13 empty] | 0% |  |  | 0% | 0 | 0 | 0
8. | Adjustments Hall 2 | [6 empty] | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
[13 empty] | 0% |  |  | 0% | 0 | 0 | 0
8. 5. | Additional Compressed Air Equipment | [6 empty] | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | for the future, not included in this period
8. 5. 10. | Additional Compressed Air Equipment | 1 |  | PSCH |  |  |  | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
| Main equipments | [11 empty] | 0% |  |  | 0% | 0 | 0 | 0
| Rotary screw air compressor | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | ASD 35/ KAESER/ Germany
| Air dryer | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TE102/ KAESER/ Germany
| Ball Valve D63 | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| Ball Valve D40 | 6 |  | Pcs |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Airpipe/ Vietnam
| Oil removal filter | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Filter F83KE with ECO Drain 31F/ KAESER/ Germany
| Pressure maintainance system | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | DHS 50 G/ KAESER/ Germany
| Condensate drain pipe D19 | 15 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Hailiang/ China
| Condensate drain pipe D15.9 | 25 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Hailiang/ China
| Accessories | 1 |  | lot |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Viet Nam
| T&C | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Viet Nam
[7 empty] | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
| Ventilation for Air compressor | [5 empty] | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
| Tole 0.95mm | 12 |  | m2 |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Z08- 0.95mmT/ Hoa Sen/ VN
| Motor fire damper 550x500x450 | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Vietnam
| Flexiable connection | 1 |  | Pcs |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
| Cable Cat6A | 66 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 884024508/10, Commscope/ China
| Cable 1 pair 18AWG | 22 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 2MKABLO/ Turkey
| Cable Cu/PVC/PVC 2Cx1.5mm2 | 22 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
| 4C-6.0mm2 Cu/XLPE/PVC + E6.0mm2 Cu/PVC | 39 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Cadivi/ Vietnam
| GI flexible conduct D20 | 42 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | OMI12/ Cat Van Loi/ VN
| Cable tray 50x50x1.0mm | 7 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | TGE/ VN
| Hanger support | 1 |  | lot |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Viet Nam
| Accessories | 1 |  | lot |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Viet Nam
[7 empty] | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
| Compressed air pipes and valves | [5 empty] | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0
| Aluminium Air pipe D63 | 11 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 301 00 0600 01, Airpipe/ Vietnam
| Aluminium Air pipe D40 | 8 |  | m |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | 301 00 0400 01, Airpipe/ Vietnam
| Fiiting for Aluminium pipe | 1 |  | lot |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Viet Nam
| Hanger support + Accessories | 1 |  | lot |  |  | 0 | 0 | 0 | 0 |  |  | 0% |  |  | 0% | 0 | 0 | 0 | Included
[13 empty] | 0% |  |  | 0% | 0 | 0 | 0
| TOTAL AMOUNT (Not included VAT) | [6 empty] | 860677606.7593 | 282333451.3336 | 1143011058.0929 | [6 empty] | 16491404.8 | 0 | 16491404.8
-1374056.904
NHÀ THẦU PHỤ: CÔNG TY CỔ PHẦN HMEP | [11 empty] | NHÀ THẦU CHÍNH: CÔNG TY CỔ PHẦN KỸ THUẬT XÂY DỰNG DINCO | [8 empty] | -350830480
ĐẠI DIỆN NHÀ THẦU HMEP | [20 empty] | 0
[14 empty] | GIÁM SÁT THI CÔNG | CHỈ HUY TRƯỞNG | [5 empty] | 0
-232421129.7777
0

## 4.VENTILATION (hidden)
Project: VN-RENTAL BUILDING HALL 3 ELECTRIC
Location: Lô D1, Khu công nghiệp Tam Thăng, Huyện Tam Thăng, thành Phố Tam Kỳ, Tỉnh quản Nam, Việt Nam
Client: Draexlmaier Automotive Vietnam Company Limited
Package: Cơ - Điện
Item: Ventilation System
Date: 27/02/2022
Contractor name: HMEP
Position |  | Headline | Quantity | Quantity By contractor | Unit | Material Unit | Labor Unit | Unit rate | Material Amount | Labor Amount | Amount (VND) | % Công việc hoàn thành vật tư |  |  | % Công việc hoàn thành nhân công |  |  | Giá trị thanh toán đợt 1 |  |  | Remark
[12 empty] | Đợt 1 | đợt 2 | % KL hoàn thành lũy kế | Đợt 1 | đợt 2 | % KL hoàn thành lũy kế | Vật tư | Nhân công | Tổng
2. |  | Production and Logistic building (Hall 3) | [6 empty] | 876156669.5216 | 245761873.2789 | 1121918542.8005 | [6 empty] | 44143514.5823 | 0 | 44143514.5823
2. 3. |  | Mechanical Engineering | [6 empty] | 876156669.5216 | 245761873.2789 | 1121918542.8005 |  |  | 0 |  |  | 0 | 44143514.5823 | 0 | 44143514.5823
2. 3. 10. |  | Ventilation System Production | 1 | 1 | PSCH |  |  |  | 304034489.6043 | 189644193.2889 | 493678682.8931 |  |  | 0 |  |  | 0 | 32145968.4485 | 0 | 32145968.4485
|  | Logistics Area | [6 empty] | 32646354.8705 | 20550720.3964 | 53197075.267 |  |  | 0 |  |  | 0 | 3957283.4015 | 0 | 3957283.4015
|  | Overhead Propeller Fans | 2 | 2 | pcs | 0 | 6300000 | 6300000 | 0 | 12600000 | 12600000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Equipment provided by Owner, Contractor only labour
|  | Control panel for Overhead Fans | 1 | 1 | pcs | 19550000 | 385000 | 19935000 | 19550000 | 385000 | 19935000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Encloser: Vietnam Equipment: Regin / Sweden
|  | Cable Cu/PVC/PVC 4Cx1.5mm2 | 160 | 163.8 | m | 25928.4 | 7485.665 | 33414.065 | 4247071.92 | 1226151.927 | 5473223.847 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | Cable Cu/PVC/PVC 2Cx1.5mm2 | 165 | 163.8 | m | 15443.88 | 5031.18 | 20475.06 | 2529707.544 | 824107.284 | 3353814.828 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 243 | 300 | m | 8773.9726 | 14594.0164 | 23367.989 | 2632191.7808 | 4378204.9235 | 7010396.7044 | 80% |  | 0.8 |  |  | 0 | 2105753.4247 | 0 | 2105753.4247 | FPC20, Nano/ VN
|  | PVC flexible conduct D20 | 7 | 7.35 | m | 3554.7229 | 5289.7059 | 8844.4288 | 26127.2135 | 38879.3382 | 65006.5517 | 80% |  | 0.8 |  |  | 0 | 20901.7708 | 0 | 20901.7708 | Nano/ VN
|  | PVC conduit D20 | 15 |  | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | Hanger, support | 1 | 1 | lot | 1220418.8041 | 366125.6412 | 1586544.4453 | 1220418.8041 | 366125.6412 | 1586544.4453 | 50% |  | 0.5 |  |  | 0 | 610209.402 | 0 | 610209.402 | Vietnam
|  | Accessories | 1 | 1 | lot | 2440837.6082 | 732251.2824 | 3173088.8906 | 2440837.6082 | 732251.2824 | 3173088.8906 | 50% |  | 0.5 |  |  | 0 | 1220418.8041 | 0 | 1220418.8041 | included
|  |  | 0 | 0 | [9 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Production Hall 1 | 0 | 0 |  |  |  |  | 233479516.9276 | 145274230.7072 | 378753747.6348 |  |  | 0 |  |  | 0 | 24800344.5567 | 0 | 24800344.5567
|  | Overhead Propeller Fans | 14 | 14 | pcs | 0 | 6300000 | 6300000 | 0 | 88200000 | 88200000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Equipment provided by Owner, Contractor only labour
|  | Control panel for Overhead Fans | 7 | 7 | m | 19550000 | 385000 | 19935000 | 136850000 | 2695000 | 139545000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Encloser: Vietnam Equipment: Regin / Sweden
|  | 4Cx-1.5mm2 Cu/PVC/PVC | 1600 | 1556.5 | m | 25928.4 | 7485.665 | 33414.065 | 40357554.6 | 11651437.5725 | 52008992.1725 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 2Cx-1.5mm2 Cu/PVC/PVC | 1050 | 1156.5 | m | 15443.88 | 5031.18 | 20475.06 | 17860847.22 | 5818559.67 | 23679406.89 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 2125 | 2100 | m | 8773.9726 | 14594.0164 | 23367.989 | 18425342.4658 | 30647434.4647 | 49072776.9305 | 80% |  | 0.8 |  |  | 0 | 14740273.9726 | 0 | 14740273.9726 | FPC20, Nano/ VN
|  | PVC flexible conduct D20 | 70 | 63 | m | 3554.7229 | 5289.7059 | 8844.4288 | 223947.544 | 333251.4706 | 557199.0145 | 80% |  | 0.8 |  |  | 0 | 179158.0352 | 0 | 179158.0352 | Nano/ VN
|  | PVC conduit D20 | 150 |  | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | Hanger, support | 1 | 1 | lot | 8982647.7718 | 2694794.3315 | 11677442.1033 | 8982647.7718 | 2694794.3315 | 11677442.1033 | 50% |  | 0.5 |  |  | 0 | 4491323.8859 | 0 | 4491323.8859 | Vietnam
|  | Accessories | 1 | 1 | lot | 10779177.3261 | 3233753.1978 | 14012930.524 | 10779177.3261 | 3233753.1978 | 14012930.524 | 50% |  | 0.5 |  |  | 0 | 5389588.6631 | 0 | 5389588.6631 | Vietnam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Production Hall 2 | 0 | 0 |  |  |  |  | 30503490.5753 | 19149107.5868 | 49652598.1621 |  |  | 0 |  |  | 0 | 3388340.4902 | 0 | 3388340.4902
|  | Overhead Propeller Fans | 2 | 2 | pcs | 0 | 6300000 | 6300000 | 0 | 12600000 | 12600000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Equipment provided by Owner, Contractor only labour
|  | Control panel for Overhead Fans | 1 | 1 | m | 19550000 | 385000 | 19935000 | 19550000 | 385000 | 19935000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Encloser: Vietnam Equipment: Regin / Sweden
|  | 4Cx-1.5mm2 Cu/PVC/PVC | 160 | 108.15 | m | 25928.4 | 7485.665 | 33414.065 | 2804156.46 | 809574.6698 | 3613731.1298 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 2Cx-1.5mm2 Cu/PVC/PVC | 165 | 170 | m | 15443.88 | 5031.18 | 20475.06 | 2625459.6 | 855300.6 | 3480760.2 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 243 | 220 | m | 8773.9726 | 14594.0164 | 23367.989 | 1930273.9726 | 3210683.6106 | 5140957.5832 | 80% |  | 0.8 |  |  | 0 | 1544219.1781 | 0 | 1544219.1781 | FPC20, Nano/ VN
|  | PVC flexible conduct D20 | 7 | 7.35 | m | 3554.7229 | 5289.7059 | 8844.4288 | 26127.2135 | 38879.3382 | 65006.5517 | 80% |  | 0.8 |  |  | 0 | 20901.7708 | 0 | 20901.7708 | Nano/ VN
|  | PVC conduit D20 | 15 | 15 | m | 8773.9726 | 14594.0164 | 23367.989 | 131609.589 | 218910.2462 | 350519.8352 | 80% |  | 0.8 |  |  | 0 | 105287.6712 | 0 | 105287.6712 | FPC20, Nano/ VN
|  | Hanger, support | 1 | 1 | lot | 1145287.9134 | 343586.374 | 1488874.2874 | 1145287.9134 | 343586.374 | 1488874.2874 | 50% |  | 0.5 |  |  | 0 | 572643.9567 | 0 | 572643.9567 | Vietnam
|  | Accessories | 1 | 1 | lot | 2290575.8268 | 687172.748 | 2977748.5748 | 2290575.8268 | 687172.748 | 2977748.5748 | 50% |  | 0.5 |  |  | 0 | 1145287.9134 | 0 | 1145287.9134 | Vietnam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Interface between fire alarm and fan system | 0 | 0 |  |  |  |  | 7405127.2308 | 4670134.5985 | 12075261.8293 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| 8 | Fire signal cable: (2x1.0)mm2 Dây tín hiệu báo cháy: (2x1.0)mm2 | 830 | 830 | M | 7457.49 | 3300 | 10757.49 | 6189716.7 | 2739000 | 8928716.7 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vcmd/ Cadivi/ Viet Nam
| 10 | D16 PVC conduit & accessories Ống bảo vệ dây dẫn D16 và phụ kiện | 140 | 140 | M | 6646.8692 | 13183.4282 | 19830.2974 | 930561.6849 | 1845679.9447 | 2776241.6296 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC16, Nano/ VN
|  | Accessories | 1 | 1 | lot | 284848.8459 | 85454.6538 | 370303.4997 | 284848.8459 | 85454.6538 | 370303.4997 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
2. 3. 60. |  | SMOKE EXHAUST SYSTEM | [6 empty] | 572122179.9173 | 56117679.99 | 628239859.9073 |  |  | 0 |  |  | 0 | 11997546.1339 | 0 | 11997546.1339
|  | Equipment | [6 empty] | 474178458 | 32835793.1 | 507014251.1 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Roof smoke exhaust FAN - SEAF @26500m3/h, 100Pa, 3.0kW, 300oC in 2hrs | 6 | 6 | pcs | 43434300 | 2241801.1 | 45676101.1 | 260605800 | 13450806.6 | 274056606.6 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | RDA900-14AA-7-7/26, Kruger/ Vietnam
|  | Roof smoke exhaust FAN - SEAF @8000m3/h, 100Pa, 0.5kW, 300oC in 2hrs | 4 | 4 | pcs | 17612370 | 923094.7 | 18535464.7 | 70449480 | 3692378.8 | 74141858.8 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | RDA500-9AA-7-7/36, Kruger/ Vietnam
|  | Wall mounted smoke exhaust FAN - SEAF @26500m3/h, 100Pa, 3kW, 300oC in 2hrs | 3 | 3 | pcs | 25306446 | 2241801.1 | 27548247.1 | 75919338 | 6725403.3 | 82644741.3 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | APN900-14AA-7-7/20, Kruger/ Vietnam
|  | Wall mounted smoke exhaust FAN - SEAF @16000m3/h, 100Pa, 1.5kW, 300oC in 2hrs | 4 | 4 | pcs | 16800960 | 2241801.1 | 19042761.1 | 67203840 | 8967204.4 | 76171044.4 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | APN630-12AA-7-7/32, Kruger/ Vietnam
|  | Cable power supply & conduit | [6 empty] | 97943721.9173 | 23281886.89 | 121225608.8073 |  |  | 0 |  |  | 0 | 11997546.1339 | 0 | 11997546.1339
|  | Cable Cu/Fr/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 1156 | 1281 | m | 60411.45 | 9350 | 69761.45 | 77387067.45 | 11977350 | 89364417.45 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D25 | 463 | 415 | m | 12762.0356 | 15805 | 28567.0356 | 5296244.7808 | 6559075 | 11855319.7808 | 80% |  | 0.8 |  |  | 0 | 4236995.8247 | 0 | 4236995.8247 | FPC25, Nano/ VN
|  | PVC flexible conduct D25 | 120 | 53.55 | m | 8113.63 | 5559 | 13672.63 | 434484.8865 | 297684.45 | 732169.3365 | 80% |  | 0.8 |  |  | 0 | 347587.9092 | 0 | 347587.9092 | Nano/ VN
|  | Accessories | 1 | 1 | lot | 14825924.8 | 4447777.44 | 19273702.24 | 14825924.8 | 4447777.44 | 19273702.24 | 50% |  | 0.5 |  |  | 0 | 7412962.4 | 0 | 7412962.4 | Vietnam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
3. |  | Office, Social and Technical Areas (Hall 3) | [6 empty] | 1272946321.0445 | 134316312.1879 | 1407262633.2324 |  |  | 0 |  |  | 0 | 22047224.0044 | 0 | 22047224.0044
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
3. 3. |  | Mechanical Engineering | [6 empty] | 1272946321.0445 | 134316312.1879 | 1407262633.2324 |  |  | 0 |  |  | 0 | 22047224.0044 | 0 | 22047224.0044
3. 3. 40. |  | Ventilation System | 1 | 1 | PSCH |  |  |  | 915624507.9952 | 94236583.2039 | 1009861091.1991 |  |  | 0 |  |  | 0 | 21336774.8612 | 0 | 21336774.8612
|  | Ground floor - west side | [6 empty] | 259524148.7256 | 33244549.9752 | 292768698.7008 |  |  | 0 |  |  | 0 | 2696279.6284 | 0 | 2696279.6284
|  | Equipments | [6 empty] | 32262384 | 3815280.7 | 36077664.7 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Exhaust air fan in-line centrifugal type (Q = 1240/620 m3/h, 220 Pa) | 1 | 1 | pcs | 7426788 | 923094.7 | 8349882.7 | 7426788 | 923094.7 | 8349882.7 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CCE 9-7T 4P-1 3SY, Kruger/ Vietnam
|  | Exhaust air fan in-line centrifugal type (Q = 460/230 m3/h, 200 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTD Silent 200/1, Kruger/ Vietnam
|  | Exhaust air fan in-line centrifugal type (Q = 680/340 m3/h, 200 Pa) | 1 | 1 | pcs | 4734816 | 495000 | 5229816 | 4734816 | 495000 | 5229816 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTD Silent 200/2, Kruger/ Vietnam
|  | Exhaust air fan in-line centrifugal type (Q = 550/275 m3/h, 180 Pa) | 2 | 2 | pcs | 4658448 | 495000 | 5153448 | 9316896 | 990000 | 10306896 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTD Silent 200/1, Kruger/ Vietnam
|  | Exhaust air fan in-line centrifugal type (Q = 120 m3/h, 120 Pa) | 1 | 1 | pcs | 4734816 | 495000 | 5229816 | 4734816 | 495000 | 5229816 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTD Silent 160, Kruger/ Vietnam
|  | Hanger support & Sub materials | 1 | 1 | lot | 1390620 | 417186 | 1807806 | 1390620 | 417186 | 1807806 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Air grille, louver | [6 empty] | 167427120 | 9290400 | 176717520 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Poppet Valves D160 | 3 | 3 | pcs | 1079160 | 84000 | 1163160 | 3237480 | 252000 | 3489480 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | LVS, Trox/ Germany
|  | Poppet Valves D100 | 43 | 43 | pcs | 921840 | 84000 | 1005840 | 39639120 | 3612000 | 43251120 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | LVS, Trox/ Germany
|  | Fresh air grille 500x200 | 18 | 18 | pcs | 1117800 | 140000 | 1257800 | 20120400 | 2520000 | 22640400 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | VAT-A//R1/S11/0/RAL9010, Trox/ Malaysia
|  | Exhaust air grille 200x200 | 1 | 1 | pcs | 797640 | 117600 | 915240 | 797640 | 117600 | 915240 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | VAT-A//R1/S11/0/RAL9010, Trox/ Malaysia
|  | Louver 200x200 + IS | 1 | 1 | pcs | 698280 | 117600 | 815880 | 698280 | 117600 | 815880 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AWK1//0/0/RAL9010, Trox/ Malaysia
|  | Louver 400x200 + IS | 1 | 1 | pcs | 844560 | 117600 | 962160 | 844560 | 117600 | 962160 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AWK1//0/0/RAL9010, Trox/ Malaysia
|  | Louver 400x250 + IS | 3 | 3 | pcs | 1073640 | 117600 | 1191240 | 3220920 | 352800 | 3573720 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AWK1//0/0/RAL9010, Trox/ Malaysia
|  | Louver 700x300 + IS | 1 | 1 | pcs | 2152800 | 140000 | 2292800 | 2152800 | 140000 | 2292800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AWK1//0/0/RAL9010, Trox/ Malaysia
|  | Volume control damper VCD D100 | 1 | 1 | pcs | 979800 | 84000 | 1063800 | 979800 | 84000 | 1063800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CBD, Trox/ Malaysia
|  | Volume control damper VCD D160 | 6 | 6 | pcs | 1208880 | 84000 | 1292880 | 7253280 | 504000 | 7757280 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CBD, Trox/ Malaysia
|  | Volume control damper VCD D200 | 1 | 1 | pcs | 1479360 | 84000 | 1563360 | 1479360 | 84000 | 1563360 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CBD, Trox/ Malaysia
|  | Volume control controller D160 | 1 | 1 | pcs | 2718600 | 84000 | 2802600 | 2718600 | 84000 | 2802600 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | BDD-A3-R/ Trox/ Malaysia
|  | Pressure release flap 345x400 | 2 | 2 | pcs | 30674640 | 280000 | 30954640 | 61349280 | 560000 | 61909280 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | ARK2-G/0, Trox/ Germany
|  | Silencer D120xL500 | 1 | 1 | pcs | 2368080 | 106400 | 2474480 | 2368080 | 106400 | 2474480 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CA50, Trox/ Malaysia
|  | Silencer D190xL500 | 6 | 6 | pcs | 3427920 | 106400 | 3534320 | 20567520 | 638400 | 21205920 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CA50, Trox/ Malaysia
|  | Ductwork sheet | [6 empty] | 59834644.7256 | 20138869.2752 | 79973514.0008 |  |  | 0 |  |  | 0 | 2696279.6284 | 0 | 2696279.6284
|  | Rigid duct Z8, thickness 0.58mm | 52 | 51.7 | m2 | 236291.3455 | 106400 | 342691.3455 | 12216262.56 | 5500880 | 17717142.56 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Z08- 0.58mmT/ Hoa Sen/ VN
|  | Insulation 6mmT | 57 | 55 | m2 | 104230.8 | 44800 | 149030.8 | 5732694 | 2464000 | 8196694 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Simili for fan | 12 | 12 | pcs | 90000 | 35000 | 125000 | 1080000 | 420000 | 1500000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Hanger support & Sub materials | 1 | 1 | lot | 15556006.38 | 4666801.914 | 20222808.294 | 15556006.38 | 4666801.914 | 20222808.294 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Cable power supply & conduit | [6 empty] | 25249681.7856 | 7087187.3612 | 32336869.1468 |  |  | 0 |  |  | 0 | 2696279.6284 | 0 | 2696279.6284
|  | Timer delay | 5 | 5 | pcs | 2875000 | 82500 | 2957500 | 14375000 | 412500 | 14787500 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Switch 1way - 1gang 10A-220V | 1 | 1 | m | 46800 | 54500 | 101300 | 46800 | 54500 | 101300 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KB31_1_WE_G19/ Schneider/ VN
|  | 3C-1.5mm2 Cu/XLPE/PVC | 330 | 308 | m | 22980.09 | 5743.9305 | 28724.0205 | 7077867.72 | 1769130.594 | 8846998.314 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC flexible conduct D20 | 9 | 9.9 | m | 3554.7229 | 5289.7059 | 8844.4288 | 35191.7569 | 52368.0882 | 87559.8451 | 80% |  | 0.8 |  |  | 0 | 28153.4055 | 0 | 28153.4055 | Vietnam
|  | PVC conduit D20 | 333 | 308 | m | 8773.9726 | 14594.0164 | 23367.989 | 2702383.5616 | 4494957.0548 | 7197340.6165 | 80% |  | 0.8 |  |  | 0 | 2161906.8493 | 0 | 2161906.8493 | FPC20, Nano/ VN
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 1012438.7471 | 303731.6241 | 1316170.3712 | 1012438.7471 | 303731.6241 | 1316170.3712 | 50% |  | 0.5 |  |  | 0 | 506219.3735 | 0 | 506219.3735 | Vietnam
|  | Ground floor - east side | [6 empty] | 540527596.8724 | 42856692.0376 | 583384288.91 |  |  | 0 |  |  | 0 | 17444464.0487 | 0 | 17444464.0487
|  | Equipments | [6 empty] | 41276280 | 4988745 | 46265025 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Exhaust air fan in-line centrifugal type (Q = 800/400 m3/h, 200 Pa) | 1 | 1 | pcs | 4734816 | 495000 | 5229816 | 4734816 | 495000 | 5229816 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTD Silent 200/2, Kruger/ Vietnam
|  | Exhaust air fan in-line centrifugal type (Q = 600/300 m3/h, 220 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTD Silent 200/2, Kruger/ Vietnam
|  | Exhaust air fan in-line centrifugal type (Q = 550/275 m3/h, 180 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTD Silent 200/1, Kruger/ Vietnam
|  | Exhaust air fan in-line centrifugal type (Q = 500 m3/h, 200 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTD Silent 200/1, Kruger/ Vietnam
|  | Exhaust air fan wall type (Q = 120 m3/h, 50 Pa) | 1 | 1 | pcs | 2324562 | 495000 | 2819562 | 2324562 | 495000 | 2819562 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | APM 200, Kruger/ Vietnam
|  | Exhaust air fan wall type (Q = 1210 m3/h, 50 Pa) | 4 | 4 | pcs | 4615602 | 495000 | 5110602 | 18462408 | 1980000 | 20442408 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | APL 315 4P-1 1S, Kruger/ Vietnam
|  | Hanger support & Sub materials | 1 | 1 | lot | 1779150 | 533745 | 2312895 | 1779150 | 533745 | 2312895 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Air grille, louver | [6 empty] | 429116520 | 10169600 | 439286120 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Poppet Valves D160 | 1 | 1 | pcs | 1079160 | 84000 | 1163160 | 1079160 | 84000 | 1163160 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | LVS, Trox/ Germany
|  | Poppet Valves D100 | 23 | 23 | pcs | 921840 | 84000 | 1005840 | 21202320 | 1932000 | 23134320 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | LVS, Trox/ Germany
|  | Fresh air grille 500x200 | 18 | 18 | pcs | 1117800 | 140000 | 1257800 | 20120400 | 2520000 | 22640400 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | VAT-A//R1/S11/0/RAL9010, Trox/ Malaysia
|  | Exhaust air grille 200x200 | 1 | 1 | pcs | 797640 | 117600 | 915240 | 797640 | 117600 | 915240 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | VAT-A//R1/S11/0/RAL9010, Trox/ Malaysia
|  | Exhaust air grille 500x200 + OBD | 13 | 13 | pcs | 1349640 | 140000 | 1489640 | 17545320 | 1820000 | 19365320 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | VAT-A//R1/S11/0/RAL9010, Trox/ Malaysia
|  | Louver 200x200 + IS | 1 | 1 | pcs | 698280 | 117600 | 815880 | 698280 | 117600 | 815880 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AWK1//0/0/RAL9010, Trox/ Malaysia
|  | Louver 400x250 + IS | 3 | 3 | pcs | 1073640 | 117600 | 1191240 | 3220920 | 352800 | 3573720 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AWK1//0/0/RAL9010, Trox/ Malaysia
|  | Louver 500x500 + IS | 4 | 4 | pcs | 2484000 | 140000 | 2624000 | 9936000 | 560000 | 10496000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AWK1//0/0/RAL9010, Trox/ Malaysia
|  | Louver 700x250 + IS | 1 | 1 | pcs | 2152800 | 140000 | 2292800 | 2152800 | 140000 | 2292800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AWK1//0/0/RAL9010, Trox/ Malaysia
|  | Volume control damper VCD D100 | 1 | 1 | pcs | 979800 | 84000 | 1063800 | 979800 | 84000 | 1063800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CBD, Trox/ Malaysia
|  | Volume control damper VCD D160 | 3 | 3 | pcs | 1208880 | 84000 | 1292880 | 3626640 | 252000 | 3878640 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CBD, Trox/ Malaysia
|  | Volume control controller D160 | 1 | 1 | pcs | 2718600 | 84000 | 2802600 | 2718600 | 84000 | 2802600 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | BDD-A3-R/ Trox/ Malaysia
|  | Pressure release flap 345x400 | 2 | 2 | pcs | 30674640 | 280000 | 30954640 | 61349280 | 560000 | 61909280 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | ARK2-G/0, Trox/ Germany
|  | Fire damper D250 | 2 | 2 | pcs | 21834360 | 140000 | 21974360 | 43668720 | 280000 | 43948720 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FKRS-EU-1/EN//Z43, Trox/ Germany
|  | Overflow air via fire protection flaps 400x250 | 3 | 3 | pcs | 75789600 | 280000 | 76069600 | 227368800 | 840000 | 228208800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FK2-EU/EN/AA/Z43RM, Trox/ Germany
|  | Silencer D120xL500 | 1 | 1 | pcs | 2368080 | 106400 | 2474480 | 2368080 | 106400 | 2474480 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CA50, Trox/ Malaysia
|  | Silencer D190xL500 | 3 | 3 | pcs | 3427920 | 106400 | 3534320 | 10283760 | 319200 | 10602960 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CA50, Trox/ Malaysia
|  | Ductwork sheet | [6 empty] | 42937395.394 | 15270557.0262 | 58207952.4202 |  |  | 0 |  |  | 0 | 13013328.377 | 0 | 13013328.377
|  | Rigid duct Z8, thickness 0.58mm | 44 | 46.2 | m2 | 236291.3455 | 106400 | 342691.3455 | 10916660.16 | 4915680 | 15832340.16 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Z08- 0.58mmT/ Hoa Sen/ VN
|  | Insulation 6mmT | 50 | 50.6 | m2 | 104230.8 | 44800 | 149030.8 | 5274078.48 | 2266880 | 7540958.48 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Simili for fan | 8 | 8 | pcs | 90000 | 35000 | 125000 | 720000 | 280000 | 1000000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Hanger support & Sub materials | 1 | 1 | lot | 26026656.754 | 7807997.0262 | 33834653.7802 | 26026656.754 | 7807997.0262 | 33834653.7802 | 50% |  | 0.5 |  |  | 0 | 13013328.377 | 0 | 13013328.377
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Cable power supply & conduit | [6 empty] | 27197401.4784 | 12427790.0114 | 39625191.4898 |  |  | 0 |  |  | 0 | 4431135.6717 | 0 | 4431135.6717
|  | Timer delay | 2 | 2 | pcs | 2875000 | 82500 | 2957500 | 5750000 | 165000 | 5915000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Switch 1way - 1gang 10A-220V | 1 | 1 | m | 46800 | 54500 | 101300 | 46800 | 54500 | 101300 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KB31_1_WE_G19/ Schneider/ VN
|  | Contactor + Box | 3 | 3 | m | 900000 | 163500 | 1063500 | 2700000 | 490500 | 3190500 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | A9C20731,Schneider/ VN
|  | 3C-1.5mm2 Cu/XLPE/PVC | 495 | 495 | m | 22980.09 | 5743.9305 | 28724.0205 | 11375144.55 | 2843245.5975 | 14218390.1475 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 2C-1.5mm2 Cu/PVC/PVC | 90 | 90 | m | 15443.88 | 5031.18 | 20475.06 | 1389949.2 | 452806.2 | 1842755.4 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC flexible conduct D20 | 14 | 14.7 | m | 3554.7229 | 5289.7059 | 8844.4288 | 52254.4269 | 77758.6765 | 130013.1034 | 80% |  | 0.8 |  |  | 0 | 41803.5415 | 0 | 41803.5415 | Vietnam
|  | PVC conduit D16 | 495 |  | m | 6646.8692 | 13183.4282 | 19830.2974 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC16, Nano/ VN
|  | PVC conduit D20 | 498 | 550 | m | 8773.9726 | 14594.0164 | 23367.989 | 4825684.9315 | 8026709.0265 | 12852393.958 | 80% |  | 0.8 |  |  | 0 | 3860547.9452 | 0 | 3860547.9452 | FPC20, Nano/ VN
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 1057568.3699 | 317270.511 | 1374838.8809 | 1057568.3699 | 317270.511 | 1374838.8809 | 50% |  | 0.5 |  |  | 0 | 528784.185 | 0 | 528784.185
|  | Fist floor - west side | [6 empty] | 95572762.3972 | 15135341.1911 | 110708103.5883 |  |  | 0 |  |  | 0 | 1196031.1841 | 0 | 1196031.1841
|  | Equipments | [6 empty] | 19632768 | 2233872 | 21866640 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Exhaust air fan in-line centrifugal type (Q = 830/415 m3/h, 150 Pa) | 2 | 2 | pcs | 4734816 | 495000 | 5229816 | 9469632 | 990000 | 10459632 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTD Silent 200/2, Kruger/ Vietnam
|  | Exhaust air fan in-line centrifugal type (Q = 480/240 m3/h, 150 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTD Silent 200/1, Kruger/ Vietnam
|  | Exhaust air fan in-line centrifugal type (Q = 420/210 m3/h, 150 Pa) | 1 | 1 | pcs | 4658448 | 495000 | 5153448 | 4658448 | 495000 | 5153448 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTD Silent 200/1, Kruger/ Vietnam
|  | Hanger support & Sub materials | 1 | 1 | lot | 846240 | 253872 | 1100112 | 846240 | 253872 | 1100112 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Air grille, louver | [6 empty] | 47615520 | 2996000 | 50611520 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Poppet Valves D100 | 15 | 15 | pcs | 921840 | 84000 | 1005840 | 13827600 | 1260000 | 15087600 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | LVS, Trox/ Germany
|  | Louver 700x250 + IS | 2 | 2 | pcs | 2152800 | 140000 | 2292800 | 4305600 | 280000 | 4585600 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AWK1//0/0/RAL9010, Trox/ Malaysia
|  | Louver 400x200 + IS | 2 | 2 | pcs | 844560 | 117600 | 962160 | 1689120 | 235200 | 1924320 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AWK1//0/0/RAL9010, Trox/ Malaysia
|  | Exhaust air grille EAG-600x600 | 2 | 2 | pcs | 3960600 | 140000 | 4100600 | 7921200 | 280000 | 8201200 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | VAT-A//R1/S11/0/RAL9010, Trox/ Malaysia
|  | Supply air grille EAG-300x300 | 8 | 8 | pcs | 2484000 | 117600 | 2601600 | 19872000 | 940800 | 20812800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | DLQ-A, Trox/ Malaysia
|  | Ductwork sheet | [6 empty] | 12042039.2045 | 4956818.7105 | 16998857.915 |  |  | 0 |  |  | 0 | 1196031.1841 | 0 | 1196031.1841
|  | Rigid duct Z8, thickness 0.58mm | 25 | 25 | m2 | 236291.3455 | 106400 | 342691.3455 | 5907283.6364 | 2660000 | 8567283.6364 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Z08- 0.58mmT/ Hoa Sen/ VN
|  | Insulation 6mmT | 29 | 29 | m2 | 104230.8 | 44800 | 149030.8 | 3022693.2 | 1299200 | 4321893.2 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Simili for fan | 8 | 8 | pcs | 90000 | 35000 | 125000 | 720000 | 280000 | 1000000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Hanger support & Sub materials | 1 | 1 | lot | 2392062.3682 | 717618.7105 | 3109681.0786 | 2392062.3682 | 717618.7105 | 3109681.0786 | 50% |  | 0.5 |  |  | 0 | 1196031.1841 | 0 | 1196031.1841
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Cable power supply & conduit | [6 empty] | 16282435.1926 | 4948650.4806 | 21231085.6733 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Timer delay | 3 | 3 | pcs | 2875000 | 82500 | 2957500 | 8625000 | 247500 | 8872500 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | 3C-1.5mm2 Cu/XLPE/PVC | 220 | 220 | m | 22980.09 | 5743.9305 | 28724.0205 | 5055619.8 | 1263664.71 | 6319284.51 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 220 | 220 | m | 8773.9726 | 14594.0164 | 23367.989 | 1930273.9726 | 3210683.6106 | 5140957.5832 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | PVC flexible conduct D20 | 6 | 6 | m | 3554.7229 | 5289.7059 | 8844.4288 | 21328.3375 | 31738.2353 | 53066.5728 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Nano/ VN
|  | Accessories | 1 | 1 | lot | 650213.0825 | 195063.9248 | 845277.0073 | 650213.0825 | 195063.9248 | 845277.0073 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Fist floor - esat side | [6 empty] | 20000000 | 3000000 | 23000000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Equipments | [6 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Exhaust air fan in-line centrifugal type (Q = 440/220m3/h, 150 Pa) | 3 |  | pcs | 4658448 | 495000 | 5153448 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTD Silent 200/1, Kruger/ Vietnam
|  | Hanger support & Sub materials | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Air grille, louver | [6 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Poppet Valves D220 | 4 |  | pcs | 1484880 | 84000 | 1568880 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | LVS, Trox/ Germany
|  | Poppet Valves D100 | 19 |  | pcs | 921840 | 84000 | 1005840 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | LVS, Trox/ Germany
|  | Louver 400x200 + IS | 3 |  | pcs | 844560 | 117600 | 962160 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AWK1//0/0/RAL9010, Trox/ Malaysia
|  | Volume control damper VCD D100 | 1 |  | pcs | 979800 | 84000 | 1063800 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CBD, Trox/ Malaysia
|  | Volume control damper VCD D160 | 2 |  | pcs | 1208880 | 84000 | 1292880 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CBD, Trox/ Malaysia
|  | Supply air grille EAG-300x300 | 4 |  | pcs | 2484000 | 117600 | 2601600 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | DLQ-A, Trox/ Malaysia
|  | Silencer D120xL500 | 1 |  | pcs | 2368080 | 106400 | 2474480 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CA50, Trox/ Malaysia
|  | Silencer D190xL500 | 2 |  | pcs | 3427920 | 106400 | 3534320 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CA50, Trox/ Malaysia
|  | Ductwork sheet | [6 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Rigid duct Z8, thickness 0.58mm | 18 |  | m2 | 236291.3455 | 106400 | 342691.3455 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Z08- 0.58mmT/ Hoa Sen/ VN
|  | Insulation 6mmT | 22 |  | m2 | 104230.8 | 44800 | 149030.8 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Simili for fan | 6 |  | pcs | 90000 | 35000 | 125000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Hanger support & Sub materials | 1 |  | lot | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Cable power supply & conduit | [6 empty] | 20000000 | 3000000 | 23000000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Timer delay | 2 |  | pcs | 2875000 | 82500 | 2957500 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | 3C-1.5mm2 Cu/XLPE/PVC | 165 |  | m | 22980.09 | 5743.9305 | 28724.0205 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 165 |  | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | PVC flexible conduct D20 | 6 |  | m | 3554.7229 | 5289.7059 | 8844.4288 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Nano/ VN
|  | Fire stop | 3 | 1 | lot | 20000000 | 3000000 | 23000000 | 20000000 | 3000000 | 23000000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam(Tính chung cho toàn hệ thống)
|  | Accessories | 1 |  | lot | 1000000 | 300000 | 1300000 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
3. 3. 50. |  | Ventilation System 1st Floor Offices Ventilation Units | 1 | 1 | PSCH |  |  |  | 84938287.2586 | 5889562.8377 | 90827850.0963 |  |  | 0 |  |  | 0 | 710449.1432 | 0 | 710449.1432
|  | west side | 0 | 0 |  |  |  | 0 | 84938287.2586 | 5889562.8377 | 90827850.0963 |  |  | 0 |  |  | 0 | 710449.1432 | 0 | 710449.1432
|  | Equipments | [6 empty] | 80634445.35 | 3616553.635 | 84250998.985 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Heat Recovery Ventilation 390 m3/h | 1 | 1 | pcs | 19802999.7 | 1064000 | 20866999.7 | 19802999.7 | 1064000 | 20866999.7 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | LZ-H050GBA4, LG/ Korea
|  | Heat Recovery Ventilation 2000 m3/h | 1 | 1 | pcs | 54096000.2 | 1400000 | 55496000.2 | 54096000.2 | 1400000 | 55496000.2 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | LZ-H200GBA4, LG/ Korea
|  | Remote wirring for ERV | 2 | 2 | pcs | 1614800 | 50400 | 1665200 | 3229600 | 100800 | 3330400 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | PREMTB001 / LG/Korea
|  | Hanger support & Accessories | 1 | 1 | lot | 3505845.45 | 1051753.635 | 4557599.085 | 3505845.45 | 1051753.635 | 4557599.085 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Cable power supply & conduit | [6 empty] | 4303841.9086 | 2273009.2027 | 6576851.1113 |  |  | 0 |  |  | 0 | 710449.1432 | 0 | 710449.1432
|  | 3C-2.5mm2 Cu/XLPE/PVC | 100 | 100 | m | 32518.74 | 7485.665 | 40004.405 | 3251874 | 748566.5 | 4000440.5 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 100 | 100 | m | 8773.9726 | 14594.0164 | 23367.989 | 877397.2603 | 1459401.6412 | 2336798.9015 | 80% |  | 0.8 |  |  | 0 | 701917.8082 | 0 | 701917.8082 | FPC20, Nano/ VN
|  | PVC flexible conduct D20 | 3 | 3 | m | 3554.7229 | 5289.7059 | 8844.4288 | 10664.1688 | 15869.1176 | 26533.2864 | 80% |  | 0.8 |  |  | 0 | 8531.335 | 0 | 8531.335 | Nano/ VN
|  | PVC conduit D20 | 3 |  | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 | 80% |  | 0.8 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 163906.4796 | 49171.9439 | 213078.4235 | 163906.4796 | 49171.9439 | 213078.4235 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
3. 3. 60. |  | Ventilation System 1st Floor Offices Ducting | 1 | 1 | PSCH |  |  |  | 272383525.7906 | 34190166.1463 | 306573691.937 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | west side | 0 | 0 |  |  |  | 0 | 272383525.7906 | 34190166.1463 | 306573691.937 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Equipments | [6 empty] | 262643773.8955 | 29033956.5687 | 291677730.4642 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Exhaust air fan in-line centrifugal type (Q = 2000m3/h, 300 Pa) | 2 | 2 | pcs | 7379058 | 923094.7 | 8302152.7 | 14758116 | 1846189.4 | 16604305.4 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CCE 9-9 4P-1 3SY, Kruger/ Vietnam
|  | Duct smoke detector | 4 | 4 | pcs | 4140000 | 128800 | 4268800 | 16560000 | 515200 | 17075200 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | SL-2000-P, Apollo/ USA
|  | Rigid duct Z8, thickness 0.58mm | 132 | 132 | m2 | 236291.3455 | 106400 | 342691.3455 | 31190457.6 | 14044800 | 45235257.6 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Z08- 0.58mmT/ Hoa Sen/ VN
|  | Insulation 16mmT | 142 | 143 | m2 | 207754.8 | 44800 | 252554.8 | 29708936.4 | 6406400 | 36115336.4 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
|  | Supply air grill 300x300 | 6 | 6 | pcs | 2484000 | 117600 | 2601600 | 14904000 | 705600 | 15609600 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | DLQ-A, Trox/ Malaysia
|  | Supply air grill 600x600 | 3 | 3 | pcs | 3960600 | 140000 | 4100600 | 11881800 | 420000 | 12301800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | DLQ-A, Trox/ Malaysia
|  | Exhaust air grill 600x600 | 5 | 5 | pcs | 3960600 | 140000 | 4100600 | 19803000 | 700000 | 20503000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | VAT-A//R1/S11/0/RAL9010, Trox/ Malaysia
|  | Louver 400x200 + IS | 2 | 2 | pcs | 844560 | 117600 | 962160 | 1689120 | 235200 | 1924320 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AWK1//0/0/RAL9010, Trox/ Malaysia
|  | Louver 900x400 + IS | 2 | 2 | pcs | 3759120 | 140000 | 3899120 | 7518240 | 280000 | 7798240 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AWK1//0/0/RAL9010, Trox/ Malaysia
|  | Siliencer D240xL1000 | 2 | 2 | pcs | 6668160 | 106400 | 6774560 | 13336320 | 212800 | 13549120 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CA50, Trox/ Malaysia
|  | Siliencer D300xL800 | 6 | 6 | pcs | 7998480 | 106400 | 8104880 | 47990880 | 638400 | 48629280 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CA50, Trox/ Malaysia
|  | Siliencer D420XL1000 | 4 | 4 | pcs | 11155920 | 106400 | 11262320 | 44623680 | 425600 | 45049280 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CA50, Trox/ Malaysia
|  | Hanger support & Accessories | 1 | 1 | lot | 8679223.8955 | 2603767.1687 | 11282991.0642 | 8679223.8955 | 2603767.1687 | 11282991.0642 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Cable power supply & conduit | [6 empty] | 9739751.8951 | 5156209.5777 | 14895961.4728 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Switch 1way - 2gang 10A-220V | 1 | 1 | m | 46800 | 54500 | 101300 | 46800 | 54500 | 101300 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KB31_WE/ Schneider/ VN
|  | Contactor + Box | 4 | 4 | m | 900000 | 163500 | 1063500 | 3600000 | 654000 | 4254000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | A9C20731,Schneider/ VN
|  | 3C-2.5mm2 Cu/XLPE/PVC | 80 | 79.2 | m | 32518.74 | 7485.665 | 40004.405 | 2575484.208 | 592864.668 | 3168348.876 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | 2C-1.5mm2 Cu/PVC/PVC | 80 | 79.2 | m | 15443.88 | 5031.18 | 20475.06 | 1223155.296 | 398469.456 | 1621624.752 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | PVC conduit D20 | 76 | 160 | m | 8773.9726 | 14594.0164 | 23367.989 | 1403835.6164 | 2335042.6259 | 3738878.2423 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | PVC flexible conduct D20 | 3 | 3 | m | 3554.7229 | 5289.7059 | 8844.4288 | 10664.1688 | 15869.1176 | 26533.2864 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Nano/ VN
|  | PVC conduit D20 | 3 | 3 | m | 8773.9726 | 14594.0164 | 23367.989 | 26321.9178 | 43782.0492 | 70103.967 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | PVC conduit D16 | 72 | 72 | m | 6646.8692 | 13183.4282 | 19830.2974 | 478574.5808 | 949206.8287 | 1427781.4095 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC16, Nano/ VN
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Accessories | 1 | 1 | lot | 374916.1073 | 112474.8322 | 487390.9395 | 374916.1073 | 112474.8322 | 487390.9395 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
3. 3. 130. |  | SMOKE EXHAUST SYSTEM | [6 empty] | 143640024.0078 | 24229831.2332 | 167869855.241 |  |  | 0 |  |  | 0 | 6864379.726 | 0 | 6864379.726
|  | WEST SIDE | [6 empty] | 32042422.6672 | 2927603.7911 | 34970026.4583 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Equipment | [6 empty] | 26144496 | 990000 | 27134496 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Wall mounted smoke exhaust FAN - SEAF @11550m3/h, 100Pa, 1.5kW, 300oC in 2hrs | 2 | 2 | pcs | 13072248 | 495000 | 13567248 | 26144496 | 990000 | 27134496 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | APN560-9AA-5-5/22, Kruger/ Vietnam
|  | Cable power supply & conduit | [6 empty] | 5897926.6672 | 1937603.7911 | 7835530.4583 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Cable Cu/Fr/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 70 | 66 | m | 60411.45 | 9350 | 69761.45 | 3987155.7 | 617100 | 4604255.7 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 63 | 60 | m | 8773.9726 | 14594.0164 | 23367.989 | 526438.3562 | 875640.9847 | 1402079.3409 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | PVC flexible conduct D20 | 7 | 7 | m | 3554.7229 | 5289.7059 | 8844.4288 | 24883.0604 | 37027.9412 | 61911.0016 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Nano/ VN
|  | Accessories | 1 | 1 | lot | 1359449.5506 | 407834.8652 | 1767284.4158 | 1359449.5506 | 407834.8652 | 1767284.4158 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | EAST SIDE | [6 empty] | 111597601.3406 | 21302227.4421 | 132899828.7827 |  |  | 0 |  |  | 0 | 6864379.726 | 0 | 6864379.726
|  | Equipment | [6 empty] | 23339970 | 2769284.1 | 26109254.1 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | AXIAL Smoke exhaust FAN - SEAF @7320m3/h, 180Pa, 1.25kW, 300oC in 2hrs | 3 | 3 | pcs | 7779990 | 923094.7 | 8703084.7 | 23339970 | 2769284.1 | 26109254.1 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TDA400-9AA-5-5/28, Kruger/ Vietnam
|  | Hanger support & Sub materials | 1 | 1 | lot | 1051350 | 315405 | 1366755 | 1051350 | 315405 | 1366755 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Air grille, louver | [6 empty] | 23084640 | 840000 | 23924640 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Smoke Exhaust grille 1200x600 + OBD | 3 | 3 | pcs | 3281640 | 140000 | 3421640 | 9844920 | 420000 | 10264920 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AT-AG/R1/S11/0/RAL9010, Trox/ Malaysia
|  | Louver 1000x400 + IS | 3 | 3 | pcs | 4413240 | 140000 | 4553240 | 13239720 | 420000 | 13659720 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | WGK-AL-1/ ER/P1/RAL9010, Trox/ Malaysia
|  | Ductwork sheet | [6 empty] | 48893376.2182 | 12696041.9127 | 61589418.1309 |  |  | 0 |  |  | 0 | 4738069.8545 | 0 | 4738069.8545
|  | Rigid duct Z8, thickness 0.58mm | 47 | 42 | m2 | 236291.3455 | 106400 | 342691.3455 | 9924236.5091 | 4468800 | 14393036.5091 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Z08- 0.58mmT/ Hoa Sen/ VN
|  | Rockwool 50mmT | 36 | 36 | m2 | 408250 | 61600 | 469850 | 14697000 | 2217600 | 16914600 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Dragon rock wool/ Vietnam
|  | Fireproof paint for smoke duct | 33 | 33 | m2 | 432000 | 89600 | 521600 | 14256000 | 2956800 | 17212800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FLAMEBAR BW11, UK or MALAYSIA
|  | Simili for fan | 6 | 6 | pcs | 90000 | 35000 | 125000 | 540000 | 210000 | 750000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Hanger support & Sub materials | 1 | 1 | lot | 9476139.7091 | 2842841.9127 | 12318981.6218 | 9476139.7091 | 2842841.9127 | 12318981.6218 | 50% |  | 0.5 |  |  | 0 | 4738069.8545 | 0 | 4738069.8545 | Vietnam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | Cable power supply & conduit | [6 empty] | 15228265.1224 | 4681496.4294 | 19909761.5518 |  |  | 0 |  |  | 0 | 2126309.8715 | 0 | 2126309.8715
|  | Cable Cu/Fr/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 195 | 195 | m | 60411.45 | 9350 | 69761.45 | 11780232.75 | 1823250 | 13603482.75 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 176 | 150 | m | 8773.9726 | 14594.0164 | 23367.989 | 1316095.8904 | 2189102.4618 | 3505198.3522 | 80% |  | 0.8 |  |  | 0 | 1052876.7123 | 0 | 1052876.7123 | FPC20, Nano/ VN
|  | PVC flexible conduct D20 | 7 | 7 | m | 3554.7229 | 5289.7059 | 8844.4288 | 24883.0604 | 37027.9412 | 61911.0016 | 80% |  | 0.8 |  |  | 0 | 19906.4484 | 0 | 19906.4484 | Nano/ VN
|  | Accessories | 1 | 1 | lot | 2107053.4216 | 632116.0265 | 2739169.448 | 2107053.4216 | 632116.0265 | 2739169.448 | 50% |  | 0.5 |  |  | 0 | 1053526.7108 | 0 | 1053526.7108 | Vietnam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
4. |  | Machine hook-up (Hall 3) | [6 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
5. |  | Scooter Garage | [6 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
6. |  | Canteen | [6 empty] | 435189667.08 | 72472708.1683 | 507662375.2483 |  |  | 0 |  |  | 0 | 334665000 | 0 | 334665000
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
6. 3. 60. |  | Ventilation System Overhead Fans | 1 | 1 | PSCH |  |  |  | 413174538.3791 | 66328606.8362 | 479503145.2154 |  |  | 0 |  |  | 0 | 334665000 | 0 | 334665000
|  | Overhead Propeller Fans, D=3m | 10 | 10 | pcs | 37185000 | 4950000 | 42135000 | 371850000 | 49500000 | 421350000 | 90% |  | 0.9 |  |  | 0 | 334665000 | 0 | 334665000 | HVLS-3DC, HVLS/ China
|  | 3C-2.5mm2 Cu/XLPE/PVC | 250 | 245 | m | 32518.74 | 7485.665 | 40004.405 | 7967091.3 | 1833987.925 | 9801079.225 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | Control Cable Cu/PVC 2cx1.5mm2 | 450 | 350 | m | 15443.88 | 5031.18 | 20475.06 | 5405358 | 1760913 | 7166271 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC conduit D20 | 515 | 400 | m | 8773.9726 | 14594.0164 | 23367.989 | 3509589.0411 | 5837606.5647 | 9347195.6058 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | PVC flexible conduct D20 | 20 | 15 | m | 3554.7229 | 5289.7059 | 8844.4288 | 53320.8438 | 79345.5882 | 132666.432 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Hanger, support | 1 | 1 | lot | 10452505.369 | 3135751.6107 | 13588256.9797 | 10452505.369 | 3135751.6107 | 13588256.9797 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | Accessories | 1 | 1 | lot | 13936673.8253 | 4181002.1476 | 18117675.9729 | 13936673.8253 | 4181002.1476 | 18117675.9729 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
6. 3. 70. |  | Ventilation System | 1 | 1 | PSCH |  |  |  | 22015128.7008 | 6144101.3321 | 28159230.0329 |  |  | 0 |  |  | 0 | 0 | 0 | 0
|  | Exhaust air fan Q=100m3/h, 50Pa, type wall | 2 | 2 | pcs | 2324562 | 495000 | 2819562 | 4649124 | 990000 | 5639124 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | APM 200, Kruger/ Vietnam
|  | Exhaust air fan Q=140m3/h, 50Pa, type wall | 1 | 1 | pcs | 2324562 | 495000 | 2819562 | 2324562 | 495000 | 2819562 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | APM 200, Kruger/ Vietnam
|  | Exhaust air fan Q=180m3/h, 50Pa, type wall | 1 | 1 | pcs | 2324562 | 495000 | 2819562 | 2324562 | 495000 | 2819562 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | APM 200, Kruger/ Vietnam
|  | Exhaust air fan Q=300m3/h, 50Pa, type wall | 1 | 1 | pcs | 2735040 | 495000 | 3230040 | 2735040 | 495000 | 3230040 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | APM 250, Kruger/ Vietnam
|  | Louver 250x250 + IS | 5 | 5 | pcs | 897000 | 117600 | 1014600 | 4485000 | 588000 | 5073000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AWK1//0/0/RAL9010, Trox/ Malaysia
|  | Switch 1way - 1gang 10A-250V | 5 | 5 | pcs | 46800 | 54500 | 101300 | 234000 | 272500 | 506500 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KB31_1_WE_G19/ Schneider/ VN
|  | 3C-1.5mm2 Cu/XLPE/PVC | 111 | 109.25 | m | 22980.09 | 5743.9305 | 28724.0205 | 2510574.8325 | 627524.4071 | 3138099.2396 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
|  | PVC flexible conduct D20 | 8 | 11.5 | m | 3554.7229 | 5289.7059 | 8844.4288 | 40879.3136 | 60831.6176 | 101710.9312 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
|  | PVC conduit D20 | 119 | 109.25 | m | 8773.9726 | 14594.0164 | 23367.989 | 958556.5068 | 1594396.293 | 2552952.7998 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
|  | Hanger, support, Accessories | 1 | 1 | lot | 1752830.0479 | 525849.0144 | 2278679.0623 | 1752830.0479 | 525849.0144 | 2278679.0623 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
[14 empty] | 0 |  |  | 0 | 0 | 0 | 0
|  | TOTAL AMOUNT (Not included VAT) | [6 empty] | 2727932681.6538 | 476780724.8683 | 3204713406.5221 | [6 empty] | 407720118.3127 | 0 | 407720118.3127
-2898120
NHÀ THẦU PHỤ: CÔNG TY CỔ PHẦN HMEP | [12 empty] | NHÀ THẦU CHÍNH: CÔNG TY CỔ PHẦN KỸ THUẬT XÂY DỰNG DINCO | [8 empty] | -3148920
ĐẠI DIỆN NHÀ THẦU HMEP | [21 empty] | -2049800
[15 empty] | GIÁM SÁT THI CÔNG | CHỈ HUY TRƯỞNG | [5 empty] | -240000
0
-16649183.5127

## 5. AC SYSTEM (hidden)
Project: VN-RENTAL BUILDING HALL 3 ELECTRIC
Location: Lô D1, Khu công nghiệp Tam Thăng, Huyện Tam Thăng, thành Phố Tam Kỳ, Tỉnh quản Nam, Việt Nam
Client: Draexlmaier Automotive Vietnam Company Limited
Package: Cơ - Điện
Item: AC System
Date: 27/02/2022
Contractor name: HMEP
Position | Headline | Quantity | Quantity By contractor | Unit | Material Unit | Labor Unit | Unit rate | Material Amount | Labor Amount | Amount (VND) | % Công việc hoàn thành vật tư |  |  | % Công việc hoàn thành nhân công |  |  | Giá trị thanh toán đợt 1 |  |  | Remark
[11 empty] | Đợt 1 | đợt 2 | % KL hoàn thành lũy kế | Đợt 1 | đợt 2 | % KL hoàn thành lũy kế | Vật tư | Nhân công | Tổng
3. | Office, Social and Technical Areas (Hall 3) | [6 empty] | 1992902350.6879 | 211748078.3635 | 2204650429.0514 | [6 empty] | 20593863.5681 | 0 | 20593863.5681
3. 3. 70. | Air Conditioning | 1 | 1 | PSCH |  |  |  | 1992902350.6879 | 211748078.3635 | 2204650429.0514 |  |  | 0 |  |  | 0 | 20593863.5681 | 0 | 20593863.5681
| west side | [6 empty] | 1284913905.8615 | 131256535.4444 | 1416170441.3058 |  |  | 0 |  |  | 0 | 13168730.4268 | 0 | 13168730.4268
| Equipments | [6 empty] | 1094815450 | 55012677.04 | 1149828127.04 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Outdoor unit 56KW | 1 | 1 | pcs | 109143100 | 4434383.52 | 113577483.52 | 109143100 | 4434383.52 | 113577483.52 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM200MXVAGC/TS, SamSung/ China
| Outdoor unit 50.4KW | 1 | 1 | pcs | 102932500 | 4434383.52 | 107366883.52 | 102932500 | 4434383.52 | 107366883.52 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM180MXVAGC/TS, SamSung/ China
| Outdoor unit 40KW | 1 | 1 | pcs | 72590100 | 3920000 | 76510100 | 72590100 | 3920000 | 76510100 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM140TXMDNC/EA, SamSung/ China
| Outdoor unit 33.6KW | 1 | 1 | pcs | 62381000 | 3920000 | 66301000 | 62381000 | 3920000 | 66301000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM120TXMDNC/EA, SamSung/ China
| Outdoor unit 14KW | 1 | 1 | pcs | 30222170 | 840000 | 31062170 | 30222170 | 840000 | 31062170 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM050TXMDNC/EA, SamSung/ China
| Indoor unit cassette type, 9.0kW | 6 | 6 | pcs | 9845660 | 537600 | 10383260 | 59073960 | 3225600 | 62299560 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM090NN4DEH/EU+PC4NUFMAN, SamSung/ Korea
| Indoor unit cassette type, 7.1kW | 11 | 11 | pcs | 9569780 | 537600 | 10107380 | 105267580 | 5913600 | 111181180 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM071NN4DEH/EU+PC4NUFMAN, SamSung/ Korea
| Indoor unit cassette type, 6kW | 7 | 7 | pcs | 8741260 | 504000 | 9245260 | 61188820 | 3528000 | 64716820 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM060NNNDEH/EU+PC4SUFMAN, SamSung/ Korea
| Indoor unit cassette type, 5.6kW | 4 | 4 | pcs | 8464170 | 504000 | 8968170 | 33856680 | 2016000 | 35872680 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM056NNNDEH/EU+PC4SUFMAN, SamSung/ Korea
| Indoor unit cassette type, 3.6kW | 1 | 1 | pcs | 7911200 | 504000 | 8415200 | 7911200 | 504000 | 8415200 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM036NNNDEH/EU+PC4SUFMAN, SamSung/ Korea
| Split Air conditioner, indoor unit wall type, cooling capacity 4.5kW | 4 | 4 | pcs | 12599730 | 621600 | 13221330 | 50398920 | 2486400 | 52885320 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AR18TYAACWKNSV +AR18TYAACWKXSV, SamSung/ Thailand
| Split Air conditioner, indoor unit wall type, cooling capacity 6.3kW | 2 | 2 | pcs | 16773020 | 733600 | 17506620 | 33546040 | 1467200 | 35013240 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AR24TYHYCWKNSV +AR24TYHYCWKXSV, SamSung/ Thailand
| Split Air conditioner, indoor unit wall type, cooling capacity 7.1kW | 1 | 1 | pcs | 31227680 | 733600 | 31961280 | 31227680 | 733600 | 31961280 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AR28TYHYCWKNSV +AR28TYHYCWKXSV, SamSung/ Thailand
| Dehumidifiers 1200m3/h | 6 | 6 | pcs | 19690000 | 168000 | 19858000 | 118140000 | 1008000 | 119148000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | DID-150/ Decker/Vietnam
| Controller center for AC | 1 | 1 | pcs | 11532400 | 168000 | 11700400 | 11532400 | 168000 | 11700400 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MCM-A300N, SamSung/ Korea
| Remote wirring for AC | 36 | 36 | pcs | 1614800 | 50400 | 1665200 | 58132800 | 1814400 | 59947200 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MWR-WG00JN / SamSung/ Korea
| Controller for AC Split (IT Room, UPS room) | 2 | 2 | pcs | 873400 | 140000 | 1013400 | 1746800 | 280000 | 2026800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MIM-A00N+DB93-17178A , SamSung/ Korea
| DB controller | 1 | 1 | pcs | 13200000 | 280000 | 13480000 | 13200000 | 280000 | 13480000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | VN
| Gas splitter | 16 | 44 | pcs | 1815000 | 0 | 1815000 | 79860000 | 0 | 79860000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | SamSung/ Korea
| Concrete base for outdoor unit | 5 | 5 | pcs | 1300000 | 500000 | 1800000 | 6500000 | 2500000 | 9000000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| Extra refrigerant charge R410a or R32 | 1 | 1 | lot | 7500000 | 0 | 7500000 | 7500000 | 0 | 7500000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| Hanger support & Sub materials | 1 | 1 | lot | 38463700 | 11539110 | 50002810 | 38463700 | 11539110 | 50002810 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| Copper pipe | [6 empty] | 67284685.7759 | 24357916.6293 | 91642602.4052 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Ø6.4mm-0.81mmT | 78 | 112.7 | m | 38160 | 22400 | 60560 | 4300632 | 2524480 | 6825112 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
| Ø9.5mm-0.81mmT | 249 | 203.55 | m | 60000 | 23520 | 83520 | 12213000 | 4787496 | 17000496 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
| Ø12.7mm-0.81mmT | 90 | 119.6 | m | 81840 | 28000 | 109840 | 9788064 | 3348800 | 13136864 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
| Ø15.9mm-0.81mmT | 262 | 210.45 | m | 103760 | 38808 | 142568 | 21836292 | 8167143.6 | 30003435.6 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
| Ø19.1mm-0.81mmT | 0 | 0 | m | 129600 | 42560 | 172160 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
| Ø22.2mm-0.81mmT | 18 | 27.6 | m | 147310.3448 | 49392 | 196702.3448 | 4065765.5172 | 1363219.2 | 5428984.7172 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
| Ø28.6mm-1.0mmT | 54 | 52.9 | m | 234206.8966 | 63504 | 297710.8966 | 12389544.8276 | 3359361.6 | 15748906.4276 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
| Hanger support & Accessories | 1 | 1 | lot | 2691387.431 | 807416.2293 | 3498803.6603 | 2691387.431 | 807416.2293 | 3498803.6603 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| Insulation copper pipe | [6 empty] | 14380586.125 | 5959615.4335 | 20340201.5585 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Ø6.4mm-15mmT | 78 | 112.7 | m | 15358.8 | 5600 | 20958.8 | 1730936.76 | 631120 | 2362056.76 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
| Ø9.5mm-15mmT | 249 | 203.55 | m | 16754.4 | 5644.8 | 22399.2 | 3410358.12 | 1148999.04 | 4559357.16 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
| Ø12.7mm-15mmT | 90 | 119.6 | m | 17871.6 | 7728 | 25599.6 | 2137443.36 | 924268.8 | 3061712.16 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
| Ø15.9mm-15mmT | 262 | 210.45 | m | 20664 | 9172.8 | 29836.8 | 4348738.8 | 1930415.76 | 6279154.56 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
| Ø19.1mm-15mmT | 0 | 0 | m | 23176.8 | 101595.2 | 124772 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
| Ø22.2mm-15mmT | 18 | 27.6 | m | 24852 | 11995.2 | 36847.2 | 685915.2 | 331067.52 | 1016982.72 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
| Ø28.6mm-15mmT | 54 | 52.9 | m | 28203.6 | 15523.2 | 43726.8 | 1491970.44 | 821177.28 | 2313147.72 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
| Accessories | 1 | 1 | lot | 575223.445 | 172567.0335 | 747790.4785 | 575223.445 | 172567.0335 | 747790.4785 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| Condensate pipe | [6 empty] | 3756725.28 | 3113650.848 | 6870376.128 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| uPVC-Ø27mm-PN12 | 124 | 127.6 | m | 8236.8 | 11743.2 | 19980 | 1051015.68 | 1498432.32 | 2549448 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN, Ø34 2.1mm, PN12.5
| uPVC-Ø34mm-PN12 | 59 | 72.6 | m | 16286.4 | 12639.2 | 28925.6 | 1182392.64 | 917605.92 | 2099998.56 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN, Ø34 2.1mm, PN12.5
| uPVC-Ø42mm-PN12 | 33 | 29.7 | m | 21528 | 14560 | 36088 | 639381.6 | 432432 | 1071813.6 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN, Ø42 2.1mm, PN12
| Fitting for UpVC | 1 | 1 | lot | 662951.52 | 198885.456 | 861836.976 | 662951.52 | 198885.456 | 861836.976 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| Hanger support & Accessories | 1 | 1 | lot | 220983.84 | 66295.152 | 287278.992 | 220983.84 | 66295.152 | 287278.992 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| Insulation condensate pipe | 0 | 0 |  |  |  |  | 3118303.375 | 3148490.6805 | 6266794.0555 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Ø27mm-10mmT | 124 | 127.6 | m | 11169.6 | 11743.2 | 22912.8 | 1425240.96 | 1498432.32 | 2923673.28 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
| Ø34mm-10mmT | 59 | 72.6 | m | 14520 | 15523.2 | 30043.2 | 1054152 | 1126984.32 | 2181136.32 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
| Ø42mm-10mmT | 33 | 29.7 | m | 17312.4 | 16352 | 33664.4 | 514178.28 | 485654.4 | 999832.68 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
| Accessories | 1 | 1 | lot | 124732.135 | 37419.6405 | 162151.7755 | 124732.135 | 37419.6405 | 162151.7755 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| Cable power supply & conduit | [6 empty] | 101558155.3056 | 39664184.8131 | 141222340.1186 |  |  | 0 |  |  | 0 | 13168730.4268 | 0 | 13168730.4268
| Double socket 1P-16A-250V | 6 | 6 | pcs | 150480 | 54500 | 204980 | 902880 | 327000 | 1229880 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KB426UES2_WE_G19 / Schneider/ VN, Plastic type
| Cable Cu/XLPE/PVC 4x1Cx4mm2+E4mm2 | 200 | 174.9 | m | 72299.4 | 17189.865 | 89489.265 | 12645165.06 | 3006507.3885 | 15651672.4485 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
| 3Cx-2.5mm2Cu/XLPE/PVC | 260 | 177.1 | m | 32518.74 | 7485.665 | 40004.405 | 5759068.854 | 1325711.2715 | 7084780.1255 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
| 3Cx-1.5mm2Cu/XLPE/PVC | 450 | 338.8 | m | 22980.09 | 5743.9305 | 28724.0205 | 7785654.492 | 1946043.6534 | 9731698.1454 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
| 4Cx-1.5mm2Cu/PVC/PVC | 105 | 111.1 | m | 25928.4 | 7485.665 | 33414.065 | 2880645.24 | 831657.3815 | 3712302.6215 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
| 2Cx-1.5mm2Cu/PVC/PVC | 495 | 332.2 | m | 15443.88 | 5031.18 | 20475.06 | 5130456.936 | 1671357.996 | 6801814.932 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
| 18 core AWG 1 pair | 540 | 607.2 | m | 21976.8 | 3920 | 25896.8 | 13344312.96 | 2380224 | 15724536.96 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 2MKABLO/ Turkey
| PVC conduit D20 | 104 | 660 | m | 8773.9726 | 14594.0164 | 23367.989 | 5790821.9178 | 9632050.8318 | 15422872.7496 | 80% |  | 0.8 |  |  | 0 | 4632657.5342 | 0 | 4632657.5342 | FPC20, Nano/ VN
| PVC conduit D16 | 378 | 935 | m | 6646.8692 | 13183.4282 | 19830.2974 | 6214822.6815 | 12326505.345 | 18541328.0265 | 80% |  | 0.8 |  |  | 0 | 4971858.1452 | 0 | 4971858.1452 | FPC16, Nano/ VN
| PVC conduit D16 | 891 | 0 | m | 6646.8692 | 13183.4282 | 19830.2974 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC16, Nano/ VN
| PVC conduit D20 | 143 | 0 | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
| PVC conduit D25 | 140 | 154 | m | 12762.0356 | 15805 | 28567.0356 | 1965353.4849 | 2433970 | 4399323.4849 | 80% |  | 0.8 |  |  | 0 | 1572282.7879 | 0 | 1572282.7879 | FPC25, Nano/ VN
| PVC flexible conduit D20 | 39 | 55 | m | 3554.7229 | 5289.7059 | 8844.4288 | 195509.7606 | 290933.8235 | 486443.5841 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Nano/ VN
| PVC flexible conduit D20 | 22 | 0 | m | 3554.7229 | 5289.7059 | 8844.4288 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| Cable tray 200x100x2.0mm | 42 | 45 | m | 776880 | 51045.8655 | 827925.8655 | 34959600 | 2297063.9462 | 37256663.9462 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TGE/ VN
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
| Accessories | 1 | 1 | lot | 3983863.9187 | 1195159.1756 | 5179023.0944 | 3983863.9187 | 1195159.1756 | 5179023.0944 | 50% |  | 0.5 |  |  | 0 | 1991931.9594 | 0 | 1991931.9594 | Vietnam
| East side | [6 empty] | 707988444.8264 | 80491542.9191 | 788479987.7455 |  |  | 0 |  |  | 0 | 7425133.1413 | 0 | 7425133.1413
| Equipments | [6 empty] | 606357980 | 35796884 | 642154864 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Outdoor unit 33.6KW | 2 | 2 | pcs | 62381000 | 3920000 | 66301000 | 124762000 | 7840000 | 132602000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM120TXMDNC/EA, SamSung/ China
| Outdoor unit 22.4KW | 1 | 1 | pcs | 48310460 | 3304000 | 51614460 | 48310460 | 3304000 | 51614460 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM080TXMDNC/EA, SamSung/ China
| Outdoor unit 14KW | 1 | 1 | pcs | 30222170 | 840000 | 31062170 | 30222170 | 840000 | 31062170 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM050TXMDNC/EA, SamSung/ China
| Indoor unit cassette type, 9.0kW | 6 | 6 | pcs | 9845660 | 537600 | 10383260 | 59073960 | 3225600 | 62299560 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM090NN4DEH/EU+PC4NUFMAN, SamSung/ Korea
| Indoor unit cassette type, 7.1kW | 7 | 7 | pcs | 9569780 | 537600 | 10107380 | 66988460 | 3763200 | 70751660 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM071NN4DEH/EU+PC4NUFMAN, SamSung/ Korea
| Indoor unit cassette type, 6kW | 1 | 1 | pcs | 8741260 | 504000 | 9245260 | 8741260 | 504000 | 9245260 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AM060NNNDEH/EU+PC4SUFMAN, SamSung/ Korea
| Split Air conditioner, indoor unit wall type, cooling capacity 4.5kW | 2 | 2 | pcs | 12599730 | 621600 | 13221330 | 25199460 | 1243200 | 26442660 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AR18TYAACWKNSV +AR18TYAACWKXSV, SamSung/ Thailand
| Split Air conditioner, indoor unit wall type, cooling capacity 7.1kW | 2 | 2 | pcs | 31227680 | 733600 | 31961280 | 62455360 | 1467200 | 63922560 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AR28TYHYCWKNSV +AR28TYHYCWKXSV, SamSung/ Thailand
| Split Air conditioner, indoor unit cassette type, cooling capacity 5.2kW | 1 | 1 | pcs | 21620170 | 733600 | 22353770 | 21620170 | 733600 | 22353770 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AC052TN4DKC/EA + AC052TXADKC/EA + PC4NUFMAN, SamSung/ Korea
| Dehumidifiers 1500m3/h | 3 | 3 | pcs | 19690000 | 168000 | 19858000 | 59070000 | 504000 | 59574000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | DID-150/ Decker/Vietnam
| Remote wirring for AC | 19 | 19 | pcs | 1614800 | 168000 | 1782800 | 30681200 | 3192000 | 33873200 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MWR-WG00JN / SamSung/ Korea
| Controller for AC | 2 | 10 | pcs | 873400 | 50400 | 923800 | 8734000 | 504000 | 9238000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MIM-A00N+DB93-17178A , SamSung/ Korea
| DB controller | 1 | 1 | pcs | 13200000 | 280000 | 13480000 | 13200000 | 280000 | 13480000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | VN
| Gas splitter | 5 | 8 | pcs | 1659900 | 0 | 1659900 | 13279200 | 0 | 13279200 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | SamSung/ Korea
| Concrete base for outdoor unit | 4 | 4 | pcs | 1300000 | 500000 | 1800000 | 5200000 | 2000000 | 7200000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| Extra refrigerant charge R410a or R32 | 1 | 1 | lot | 7500000 | 0 | 7500000 | 7500000 | 0 | 7500000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| Hanger support & Sub materials | 1 | 1 | lot | 21320280 | 6396084 | 27716364 | 21320280 | 6396084 | 27716364 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| Copper pipe | 0 | 0 |  |  |  |  | 28355645.2586 | 9993875.3431 | 38349520.6017 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Ø6.4mm-0.81mmT | 18 | 19.95 | m | 38160 | 22400 | 60560 | 761292 | 446880 | 1208172 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
| Ø9.5mm-0.81mmT | 86 | 94.5 | m | 60000 | 23520 | 83520 | 5670000 | 2222640 | 7892640 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
| Ø12.7mm-0.81mmT | 28 | 30.45 | m | 81840 | 28000 | 109840 | 2492028 | 852600 | 3344628 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
| Ø15.9mm-0.81mmT | 92 | 101.85 | m | 103760 | 38808 | 142568 | 10567956 | 3952594.8 | 14520550.8 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
| Ø19.1mm-0.81mmT | 3 | 3.15 | m | 129600 | 42560 | 172160 | 408240 | 134064 | 542304 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
| Ø22.2mm-0.81mmT | 6 | 6.3 | m | 147310.3448 | 49392 | 196702.3448 | 928055.1724 | 311169.6 | 1239224.7724 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
| Ø28.6mm-1.0mmT | 25 | 27.3 | m | 234206.8966 | 63504 | 297710.8966 | 6393848.2759 | 1733659.2 | 8127507.4759 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
| Hanger support & Sub materials | 1 | 1 | lot | 1134225.8103 | 340267.7431 | 1474493.5534 | 1134225.8103 | 340267.7431 | 1474493.5534 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| Insulation copper pipe | 0 | 0 |  |  |  |  | 5768802.375 | 2703324.5085 | 8472126.8835 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Ø6.4mm-15mmT | 18 | 19.95 | m | 15358.8 | 5600 | 20958.8 | 306408.06 | 111720 | 418128.06 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
| Ø9.5mm-15mmT | 86 | 94.5 | m | 16754.4 | 5644.8 | 22399.2 | 1583290.8 | 533433.6 | 2116724.4 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
| Ø12.7mm-15mmT | 28 | 30.45 | m | 17871.6 | 7728 | 25599.6 | 544190.22 | 235317.6 | 779507.82 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
| Ø15.9mm-15mmT | 92 | 101.85 | m | 20664 | 9172.8 | 29836.8 | 2104628.4 | 934249.68 | 3038878.08 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
| Ø19.1mm-15mmT | 3 | 3.15 | m | 23176.8 | 101595.2 | 124772 | 73006.92 | 320024.88 | 393031.8 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
| Ø22.2mm-15mmT | 6 | 6.3 | m | 24852 | 11995.2 | 36847.2 | 156567.6 | 75569.76 | 232137.36 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
| Ø28.6mm-15mmT | 25 | 27.3 | m | 28203.6 | 15523.2 | 43726.8 | 769958.28 | 423783.36 | 1193741.64 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
| Accessories | 1 | 1 | lot | 230752.095 | 69225.6285 | 299977.7235 | 230752.095 | 69225.6285 | 299977.7235 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| Condensate pipe | 0 | 0 |  |  |  |  | 4058656.35 | 2146658.409 | 6205314.759 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| uPVC-Ø27mm-PN12 | 46 | 50.4 | m | 8236.8 | 11743.2 | 19980 | 415134.72 | 591857.28 | 1006992 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN, Ø34 2.1mm, PN12.5
| uPVC-Ø34mm-PN12 | 38 | 42 | m | 16286.4 | 12639.2 | 28925.6 | 684028.8 | 530846.4 | 1214875.2 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN, Ø34 2.1mm, PN12.5
| uPVC-Ø42mm-PN12 | 15 | 16.8 | m | 21528 | 14560 | 36088 | 361670.4 | 244608 | 606278.4 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN, Ø42 2.1mm, PN12
| Fitting for UpVC | 1 | 1 | lot | 1953259.56 | 585977.868 | 2539237.428 | 1953259.56 | 585977.868 | 2539237.428 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| Hanger support & Sub materials | 1 | 1 | lot | 644562.87 | 193368.861 | 837931.731 | 644562.87 | 193368.861 | 837931.731 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| Insulation condensate pipe | 0 | 0 |  |  |  |  | 1524621 | 1536840.732 | 3061461.732 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Ø27mm-10mmT | 46 | 50.4 | m | 11169.6 | 11743.2 | 22912.8 | 562947.84 | 591857.28 | 1154805.12 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
| Ø34mm-10mmT | 38 | 42 | m | 14520 | 15523.2 | 30043.2 | 609840 | 651974.4 | 1261814.4 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
| Ø42mm-10mmT | 15 | 16.8 | m | 17312.4 | 16352 | 33664.4 | 290848.32 | 274713.6 | 565561.92 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
| Accessories | 1 | 1 | lot | 60984.84 | 18295.452 | 79280.292 | 60984.84 | 18295.452 | 79280.292 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| Cable power supply & conduit | 0 | 0 |  |  |  |  | 61922739.8428 | 28313959.9265 | 90236699.7693 |  |  | 0 |  |  | 0 | 7425133.1413 | 0 | 7425133.1413
| Double socket 1P-16A-250V | 3 | 3 | pcs | 150480 | 54500 | 204980 | 451440 | 163500 | 614940 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KB426UES2_WE_G19 / Schneider/ VN, Plastic type
| Cable Cu/XLPE/PVC 4x1Cx4mm2+E4mm2 | 135 | 168 | m | 72299.4 | 17189.865 | 89489.265 | 12146299.2 | 2887897.32 | 15034196.52 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
| 3Cx-2.5mm2Cu/XLPE/PVC | 155 | 43.05 | m | 32518.74 | 7485.665 | 40004.405 | 1399931.757 | 322257.8783 | 1722189.6353 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
| 3Cx-1.5mm2Cu/XLPE/PVC | 219 | 260.4 | m | 22980.09 | 5743.9305 | 28724.0205 | 5984015.436 | 1495719.5022 | 7479734.9382 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
| 4Cx-1.5mm2 Cu/PVC/PVC | 75 | 70.35 | m | 25928.4 | 7485.665 | 33414.065 | 1824062.94 | 526616.5328 | 2350679.4728 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
| 2Cx-1.5mm2 Cu/PVC/PVC | 546 | 176.4 | m | 15443.88 | 5031.18 | 20475.06 | 2724300.432 | 887500.152 | 3611800.584 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
| 18 core AWG 1 pair | 253 | 396.9 | m | 21976.8 | 3920 | 25896.8 | 8722591.92 | 1555848 | 10278439.92 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 2MKABLO/ Turkey
| PVC conduit D20 | 62 | 336 | m | 8773.9726 | 14594.0164 | 23367.989 | 2948054.7945 | 4903589.5144 | 7851644.3089 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
| PVC conduit D16 | 327 | 840 | m | 6646.8692 | 13183.4282 | 19830.2974 | 5583370.1096 | 11074079.6682 | 16657449.7778 | 80% |  | 0.8 |  |  | 0 | 4466696.0877 | 0 | 4466696.0877 | FPC16, Nano/ VN
| PVC conduit D16 | 1023 | 0 | m | 6646.8692 | 13183.4282 | 19830.2974 | 0 | 0 | 0 | 80% |  | 0.8 |  |  | 0 | 0 | 0 | 0 | FPC16, Nano/ VN
| PVC conduit D20 | 86 | 0 | m | 8773.9726 | 14594.0164 | 23367.989 | 0 | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
| PVC conduit D25 | 99 | 160 | m | 12762.0356 | 15805 | 28567.0356 | 2041925.6986 | 2528800 | 4570725.6986 | 80% |  | 0.8 |  |  | 0 | 1633540.5589 | 0 | 1633540.5589 | FPC25, Nano/ VN
| PVC flexible conduit D20 | 21 | 31.5 | m | 3554.7229 | 5289.7059 | 8844.4288 | 111973.772 | 166625.7353 | 278599.5073 | 80% |  | 0.8 |  |  | 0 | 89579.0176 | 0 | 89579.0176 | Nano/ VN
| PVC flexible conduit D20 | 11 | 11 | m | 3554.7229 | 5289.7059 | 8844.4288 | 39101.9521 | 58186.7647 | 97288.7168 | 80% |  | 0.8 |  |  | 0 | 31281.5617 | 0 | 31281.5617 | Vietnam
| Cable tray 200x100x2.0mm | 19 | 20 | m | 776880 | 51045.8655 | 827925.8655 | 15537600 | 1020917.3094 | 16558517.3094 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TGE/ VN
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
| Accessories | 1 | 1 | lot | 2408071.831 | 722421.5493 | 3130493.3802 | 2408071.831 | 722421.5493 | 3130493.3802 | 50% |  | 0.5 |  |  | 0 | 1204035.9155 | 0 | 1204035.9155 | Vietnam
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
4. | Machine hook-up (Hall 3) | [8 empty] | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
5. | Scooter Garage | [8 empty] | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
6. | Canteen | [6 empty] | 21057187.7199 | 2439460.942 | 23496648.6619 |  |  | 0 |  |  | 0 | 0 | 0 | 0
6. 3. 50. | Air Conditioning | 1 | 1 | PSCH |  |  |  | 21057187.7199 | 2439460.942 | 23496648.6619 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Split Air conditioner, indoor unit wall type, cooling capacity 2.5kW | 1 | 1 | pcs | 15455330 | 621600 | 16076930 | 15455330 | 621600 | 16076930 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AR13TYAACWKNSV +AR13TYAACWKXSV, SamSung/ Thailand
| Remote wirring for AC | 1 | 1 | pcs | 1614800 | 50400 | 1665200 | 1614800 | 50400 | 1665200 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MWR-WG00JN / SamSung/ Korea
| Hanger support & Sub materials | 1 | 1 | lot | 775915 | 232774.5 | 1008689.5 | 775915 | 232774.5 | 1008689.5 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| Copper pipe | 0 | 0 |  |  |  |  | 1022500 | 471470 | 1493970 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Ø6.4mm-0.81mmT | 10 | 10 | m | 38160 | 22400 | 60560 | 381600 | 224000 | 605600 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
| Ø9.5mm-0.81mmT | 10 | 10 | m | 60000 | 23520 | 83520 | 600000 | 235200 | 835200 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Hailiang/ China
| Hanger support & Sub materials | 1 | 1 | lot | 40900 | 12270 | 53170 | 40900 | 12270 | 53170 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| Insulation copper pipe | 0 | 0 |  |  |  |  | 334512.5 | 116462.15 | 450974.65 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Ø6.4mm-15mmT | 10 | 10 | m | 15358.8 | 5600 | 20958.8 | 153588 | 56000 | 209588 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
| Ø9.5mm-15mmT | 10 | 10 | m | 16754.4 | 5644.8 | 22399.2 | 167544 | 56448 | 223992 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
| Accessories | 1 | 1 | lot | 13380.5 | 4014.15 | 17394.65 | 13380.5 | 4014.15 | 17394.65 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| Condensate pipe | 0 | 0 |  |  |  |  | 107712 | 125035.2 | 232747.2 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| uPVC-Ø27mm-PN12 | 10 | 10 | m | 8236.8 | 11743.2 | 19980 | 82368 | 117432 | 199800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN, Ø34 2.1mm, PN12.5
| Fitting for UpVC | 1 | 1 | lot | 19008 | 5702.4 | 24710.4 | 19008 | 5702.4 | 24710.4 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| Hanger support & Sub materials | 1 | 1 | lot | 6336 | 1900.8 | 8236.8 | 6336 | 1900.8 | 8236.8 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| Insulation condensate pipe | 0 | 0 |  |  |  |  | 116350 | 118828.2 | 235178.2 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Ø27mm-10mmT | 10 | 10 | m | 11169.6 | 11743.2 | 22912.8 | 111696 | 117432 | 229128 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aerofoam NBR/Dubai
| Accessories | 1 | 1 | lot | 4654 | 1396.2 | 6050.2 | 4654 | 1396.2 | 6050.2 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| Cable power supply & conduit | 0 | 0 |  |  |  |  | 1630068.2199 | 702890.892 | 2332959.1119 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| 3Cx-2.5mm2Cu/XLPE/PVC | 15 | 15 | m | 32518.74 | 7485.665 | 40004.405 | 487781.1 | 112284.975 | 600066.075 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
| 3Cx-1.5mm2Cu/XLPE/PVC | 15 | 15 | m | 22980.09 | 5743.9305 | 28724.0205 | 344701.35 | 86158.9575 | 430860.3075 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
| 4Cx-1.5mm2 Cu/PVC/PVC | 10 | 10 | m | 25928.4 | 7485.665 | 33414.065 | 259284 | 74856.65 | 334140.65 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
| 18 core AWG 1 pair | 10 | 10 | m | 26400 | 3360 | 29760 | 264000 | 33600 | 297600 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 2MKABLO/ Turkey
| PVC conduit D20 | 15 | 15 | m | 8773.9726 | 14594.0164 | 23367.989 | 131609.589 | 218910.2462 | 350519.8352 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
| PVC conduit D16 | 12 | 12 | m | 6646.8692 | 13183.4282 | 19830.2974 | 79762.4301 | 158201.1381 | 237963.5683 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC16, Nano/ VN
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
| Accessories | 1 | 1 | lot | 62929.7507 | 18878.9252 | 81808.6759 | 62929.7507 | 18878.9252 | 81808.6759 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
| TOTAL AMOUNT (Not included VAT) | [6 empty] | 2013959538.4077 | 214187539.3055 | 2228147077.7132 | [6 empty] | 20593863.5681 | 0 | 20593863.5681
-755664
NHÀ THẦU PHỤ: CÔNG TY CỔ PHẦN HMEP | [11 empty] | NHÀ THẦU CHÍNH: CÔNG TY CỔ PHẦN KỸ THUẬT XÂY DỰNG DINCO | [8 empty] | 0
ĐẠI DIỆN NHÀ THẦU HMEP | [20 empty] | -1442336
[14 empty] | GIÁM SÁT THI CÔNG | CHỈ HUY TRƯỞNG | [5 empty] | 0
0

## 6. PLUMBING (hidden)
Project: VN-RENTAL BUILDING HALL 3 ELECTRIC
Location: Lô D1, Khu công nghiệp Tam Thăng, Huyện Tam Thăng, thành Phố Tam Kỳ, Tỉnh quản Nam, Việt Nam
Client: Draexlmaier Automotive Vietnam Company Limited
Package: Cơ - Điện
Item: Plumbing system
Date: 27/02/2022
Contractor name: HMEP
Position | Headline | Quantity | Quantity By contractor | Unit | Material Unit | Labor Unit | Unit rate | Material Amount | Labor Amount | Amount (VND) | % Công việc hoàn thành vật tư |  |  | % Công việc hoàn thành nhân công |  |  | Giá trị thanh toán đợt 1 |  |  | Remark
[11 empty] | Đợt 1 | đợt 2 | % KL hoàn thành lũy kế | Đợt 1 | đợt 2 | % KL hoàn thành lũy kế | Vật tư | Nhân công | Tổng
3. | Office, Social and Technical Areas (Hall 3) | [6 empty] | 2135112119.4552 | 210437879.8945 | 2345549999.3497 | [6 empty] | 92683593.5967 | 0 | 92683593.5967
[13 empty] | 0 |  |  | 0
3. 3. | Mechanical Engineering | [6 empty] | 2135112119.4552 | 210437879.8945 | 2345549999.3497 |  |  | 0 |  |  | 0 | 92683593.5967 | 0 | 92683593.5967
3. 3. 10. | Waste Water System | 1 | 1 | PSCH |  |  |  | 195924697.8575 | 71484007.4162 | 267408705.2737 |  |  | 0 |  |  | 0 | 74806310.3967 | 0 | 74806310.3967
| West side | 0 | 0 | m | 0 | 0 | 0 | 79936135.2 | 44199519.52 | 124135654.72 |  |  | 0 |  |  | 0 | 52663806.72 | 0 | 52663806.72
| uPVC pipe D200 - PN6 | 35 | 40 | m | 356616 | 71941.408 | 428557.408 | 14264640 | 2877656.32 | 17142296.32 | 70% |  | 70% |  |  | 0 | 9985248 | 0 | 9985248 | De Nhat, VN, Ø220 5.9mm, PN6
| uPVC pipe D168 - PN6 | 40 | 65 | m | 179337.6 | 57600.928 | 236938.528 | 11656944 | 3744060.32 | 15401004.32 | 70% |  | 70% |  |  | 0 | 8159860.8 | 0 | 8159860.8 | De Nhat, VN, Ø168 4.7mm, PN6
| uPVC pipe D114 - PN6 | 115 | 156 | m | 93225.6 | 42504 | 135729.6 | 14543193.6 | 6630624 | 21173817.6 | 70% |  | 70% |  |  | 0 | 10180235.52 | 0 | 10180235.52 | De Nhat, VN, Ø114 3.2mm, PN6
| uPVC pipe D90 - PN6 | 185 | 209 | m | 65145.6 | 36064 | 101209.6 | 13615430.4 | 7537376 | 21152806.4 | 70% |  | 70% |  |  | 0 | 9530801.28 | 0 | 9530801.28 | De Nhat, VN, Ø90 2.7mm, PN6
| uPVC pipe D60 - PN6 | 153 | 187 | m | 29858.4 | 24884.16 | 54742.56 | 5583520.8 | 4653337.92 | 10236858.72 | 70% |  | 70% |  |  | 0 | 3908464.56 | 0 | 3908464.56 | De Nhat, VN, Ø60 2.0mm, PN6
| uPVC pipe D42 - PN6 | 65 | 68 | m | 21528 | 17851.68 | 39379.68 | 1463904 | 1213914.24 | 2677818.24 | 70% |  | 70% |  |  | 0 | 1024732.8 | 0 | 1024732.8 | De Nhat, VN, Ø42 2.1mm, PN12
| uPVC Fitting | 1 | 1 | lot | 14106376.8 | 4231913.04 | 18338289.84 | 14106376.8 | 4231913.04 | 18338289.84 | 70% |  | 70% |  |  | 0 | 9874463.76 | 0 | 9874463.76 | Viet Nam
| Excavation & backfill | 37 | 37 | m3 | 0 | 200000 | 200000 | 0 | 7400000 | 7400000 | 70% |  | 70% |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Connect to existing manhole | 1 | 1 | lot | 0 | 3000000 | 3000000 | 0 | 3000000 | 3000000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Connect to existing pipe | 1 | 1 | lot | 0 | 1500000 | 1500000 | 0 | 1500000 | 1500000 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Accessories | 1 | 1 | lot | 4702125.6 | 1410637.68 | 6112763.28 | 4702125.6 | 1410637.68 | 6112763.28 |  |  | 0% |  |  | 0 | 0 | 0 | 0 | Viet Nam
| East side | 0 |  | m |  |  |  | 115988562.6575 | 27284487.8962 | 143273050.5537 |  |  | 0 |  |  | 0 | 22142503.6767 | 0 | 22142503.6767
| Submersible Pump Q=5M3/H, H=8MH20 | 2 | 2 | pcs | 19613000 | 616000 | 20229000 | 39226000 | 1232000 | 40458000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | AP50B.50.11.3.V./ Grundfos/ Hungary
| Auto coupling Rp2' | 2 | 2 | pcs | 4488000 | 0 | 4488000 | 8976000 | 0 | 8976000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Grundfos
| Slider + chain | 2 | 2 | pcs | 3850000 | 0 | 3850000 | 7700000 | 0 | 7700000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Float for submersible pump | 2 | 2 | pcs | 3850000 | 168000 | 4018000 | 7700000 | 336000 | 8036000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Electrical control panel for submeriable pump | 1 | 1 | pcs | 13420000 | 840000 | 14260000 | 13420000 | 840000 | 14260000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Check valve DN50 | 1 | 1 | pcs | 174200 | 61600 | 235800 | 174200 | 61600 | 235800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN
| Gate valve DN50 | 1 | 1 | pcs | 128700 | 61600 | 190300 | 128700 | 61600 | 190300 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN
| Cable Cu/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 30 | 30 | m | 40467 | 9350 | 49817 | 1214010 | 280500 | 1494510 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
| PVC conduit D20 | 30 | 30 | m | 8773.9726 | 14594.0164 | 23367.989 | 263219.1781 | 437820.4924 | 701039.6704 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
| uPVC pipe D168 - PN6 | 29 | 35 | m | 179337.6 | 57600.928 | 236938.528 | 6276816 | 2016032.48 | 8292848.48 | 70% |  | 0.7 |  |  | 0 | 4393771.2 | 0 | 4393771.2 | De Nhat, VN, Ø168 4.7mm, PN6
| uPVC pipe D114 - PN6 | 39 | 45 | m | 93225.6 | 42504 | 135729.6 | 4195152 | 1912680 | 6107832 | 70% |  | 0.7 |  |  | 0 | 2936606.4 | 0 | 2936606.4 | De Nhat, VN, Ø114 3.2mm, PN6
| uPVC pipe D90 - PN6 | 149 | 167 | m | 65145.6 | 36064 | 101209.6 | 10879315.2 | 6022688 | 16902003.2 | 70% |  | 0.7 |  |  | 0 | 7615520.64 | 0 | 7615520.64 | De Nhat, VN, Ø90 2.7mm, PN6
| uPVC pipe D60 - PN6 | 101 | 124 | m | 29858.4 | 24884.16 | 54742.56 | 3702441.6 | 3085635.84 | 6788077.44 | 70% |  | 0.7 |  |  | 0 | 2591709.12 | 0 | 2591709.12 | De Nhat, VN, Ø60 2.0mm, PN6
| uPVC pipe D42 - PN6 | 18 | 23 | m | 21528 | 17851.68 | 39379.68 | 495144 | 410588.64 | 905732.64 | 70% |  | 0.7 |  |  | 0 | 346600.8 | 0 | 346600.8 | De Nhat, VN, Ø42 2.1mm, PN12
| Pipe clean out D60 | 1 | 1 | pcs | 106423.2 | 28000 | 134423.2 | 106423.2 | 28000 | 134423.2 | 70% |  | 0.7 |  |  | 0 | 74496.24 | 0 | 74496.24 | Viet Nam
| uPVC Fitting | 1 | 1 | lot | 5976856.1096 | 1793056.8329 | 7769912.9425 | 5976856.1096 | 1793056.8329 | 7769912.9425 | 70% |  | 0.7 |  |  | 0 | 4183799.2767 | 0 | 4183799.2767 | Viet Nam
| Excavation & backfill | 21 | 28 | m3 | 0 | 200000 | 200000 | 0 | 5600000 | 5600000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Connect to existing manhole | 1 | 1 | lot | 0 | 1500000 | 1500000 | 0 | 1500000 | 1500000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Accessories | 1 | 1 | lot | 5554285.3699 | 1666285.611 | 7220570.9808 | 5554285.3699 | 1666285.611 | 7220570.9808 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
3. 3. 20. | Service Water System | 1 | 1 | PSCH |  |  |  | 350026408.4568 | 59395813.3191 | 409422221.7759 |  |  | 0 |  |  | 0 | 17877283.2 | 0 | 17877283.2
| West side | [6 empty] | 205749865.9577 | 34591531.4404 | 240341397.398 |  |  | 0 |  |  | 0 | 13261248 | 0 | 13261248
| Pump room | [6 empty] | 149717065.9577 | 8068928.1916 | 157785994.1492 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Booster pump Q=9.3 m3, H=30m | 2 | 2 | set | 30745000 | 728000 | 31473000 | 61490000 | 1456000 | 62946000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CM 25-2, Grundfos/ Taiwan
| Electrical control panel for booster pump | 1 | 1 | set | 44440000 | 1400000 | 45840000 | 44440000 | 1400000 | 45840000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Encloser: VN Circuit breaker: LS/ Korea
| Pressure tank 100l | 1 | 1 | pcs | 7915200 | 168000 | 8083200 | 7915200 | 168000 | 8083200 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Varem/ Italia
| Storage tank 3m3 | 1 | 1 | pcs | 9970909.0909 | 322000 | 10292909.0909 | 9970909.0909 | 322000 | 10292909.0909 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | SHN3000 (Φ1380)/ Son Ha/ VN
| Filter | 1 | 1 | set | 10800000 | 225400 | 11025400 | 10800000 | 225400 | 11025400 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | VN
| Water metter DN40 | 1 | 1 | pcs | 2154000 | 75152 | 2229152 | 2154000 | 75152 | 2229152 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTM-55, KVS / Turkey
| Cable Cu/PVC/PVC 2Cx1.5mm2 | 20 | 25 | m | 15443.88 | 5031.18 | 20475.06 | 386097 | 125779.5 | 511876.5 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
| Cable Cu/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 20 | 25 | m | 40467 | 9350 | 49817 | 1011675 | 233750 | 1245425 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| PVC conduit D20 | 40 | 50 | m | 8773.9726 | 14594.0164 | 23367.989 | 438698.6301 | 729700.8206 | 1168399.4507 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
| Hanger + Support | 1 | 1 | lot | 6172492.3537 | 1851747.7061 | 8024240.0598 | 6172492.3537 | 1851747.7061 | 8024240.0598 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Accessories | 1 | 1 | lot | 4937993.8829 | 1481398.1649 | 6419392.0478 | 4937993.8829 | 1481398.1649 | 6419392.0478 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
| Valve | [6 empty] | 31053568.8 | 3110074.6696 | 34163643.4696 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Pressure Gauges | 1 | 1 | pcs | 1008000 | 49588 | 1057588 | 1008000 | 49588 | 1057588 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | P - 260, KVS/ Turkey
| Flexible DN40 | 4 | 4 | pcs | 825600 | 75152 | 900752 | 3302400 | 300608 | 3603008 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KVS - 501 T/KVS/ Turkey
| Float level indicator | 1 | 1 | pcs | 4200000 | 168000 | 4368000 | 4200000 | 168000 | 4368000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Omron/ Aisa
| Float valve DN40 | 1 | 1 | pcs | 2809200 | 75152 | 2884352 | 2809200 | 75152 | 2884352 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KVS-703T, KVS/ Turkey
| Y-Strainer DN40 | 2 | 2 | pcs | 726000 | 75152 | 801152 | 1452000 | 150304 | 1602304 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KVS 200 - T/ KVS/ Turkey
| Safety valve DN40 | 3 | 3 | pcs | 3133200 | 75152 | 3208352 | 9399600 | 225456 | 9625056 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 3110N, KVS/ Turkey
| Check valve DN40 | 3 | 3 | pcs | 867600 | 75152 | 942752 | 2602800 | 225456 | 2828256 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KVS - 101/ LVS/ Turkey
| Gate valve DN40 | 4 | 4 | pcs | 726000 | 75152 | 801152 | 2904000 | 300608 | 3204608 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 402, KVS/Turkey
| Gate valve DN25 | 1 | 1 | pcs | 322800 | 50880.368 | 373680.368 | 322800 | 50880.368 | 373680.368 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 402, KVS/Turkey
| Gate valve DN32 PPR | 5 | 7 | pcs | 99122.4 | 58877.3007 | 157999.7007 | 693856.8 | 412141.105 | 1105997.905 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN
| Gate valve DN25 PPR | 3 | 2 | pcs | 85924.8 | 49415.0989 | 135339.8989 | 171849.6 | 98830.1978 | 270679.7978 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN
| Gate valve DN20 PPR | 10 | 15 | pcs | 63367.2 | 45472.3119 | 108839.5119 | 950508 | 682084.6788 | 1632592.6788 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN
| Accessories | 1 | 1 | lot | 1236554.4 | 370966.32 | 1607520.72 | 1236554.4 | 370966.32 | 1607520.72 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
| Cold water pipe | [6 empty] | 21159921.6 | 22158696.668 | 43318618.268 |  |  | 0 |  |  | 0 | 13166173.44 | 0 | 13166173.44
| PPR pipe D75 - PN10 | 10 | 11 | m | 99964.8 | 39200 | 139164.8 | 1099612.8 | 431200 | 1530812.8 | 70% |  | 70% |  |  | 0 | 769728.96 | 0 | 769728.96 | De Nhat, VN, Ø75, 6.8mm, PN10
| PPR pipe D63 - PN10 | 23 | 25 | m | 71884.8 | 34720 | 106604.8 | 1797120 | 868000 | 2665120 | 70% |  | 70% |  |  | 0 | 1257984 | 0 | 1257984 | De Nhat, VN, Ø63, 5.8mm, PN10
| PPR pipe D50 - PN10 | 21 | 26 | m | 45208.8 | 28000 | 73208.8 | 1175428.8 | 728000 | 1903428.8 | 70% |  | 70% |  |  | 0 | 822800.16 | 0 | 822800.16 | De Nhat, VN, Ø50, 4.6mm, PN10
| PPR pipe D40 - PN10 | 29 | 31 | m | 30841.2 | 25388.1544 | 56229.3544 | 956077.2 | 787032.7864 | 1743109.9864 | 70% |  | 70% |  |  | 0 | 669254.04 | 0 | 669254.04 | De Nhat, VN, Ø40, 3.7mm, PN10
| PPR pipe D32 - PN10 | 47 | 72 | m | 22978.8 | 22306.7432 | 45285.5432 | 1654473.6 | 1606085.5104 | 3260559.1104 | 70% |  | 70% |  |  | 0 | 1158131.52 | 0 | 1158131.52 | De Nhat, VN, Ø32, 2.9mm, PN10
| PPR pipe D25 - PN10 | 68 | 87 | m | 17737.2 | 18258.8168 | 35996.0168 | 1543136.4 | 1588517.0616 | 3131653.4616 | 70% |  | 70% |  |  | 0 | 1080195.48 | 0 | 1080195.48 | De Nhat, VN, Ø25, 2.8mm, PN10
| PPR pipe D20 - PN10 | 272 | 297 | m | 9921.6 | 15682.8168 | 25604.4168 | 2946715.2 | 4657796.5896 | 7604511.7896 | 70% |  | 70% |  |  | 0 | 2062700.64 | 0 | 2062700.64 | De Nhat, VN, Ø20, 2.3mm, PN10
| PPR Fitting | 1 | 1 | lot | 2578284 | 773485.2 | 3351769.2 | 2578284 | 773485.2 | 3351769.2 | 70% |  | 70% |  |  | 0 | 1804798.8 | 0 | 1804798.8 | Viet Nam
| uPVC pipe D60 - PN10 | 54 | 62 | m | 35287.2 | 24884.16 | 60171.36 | 2187806.4 | 1542817.92 | 3730624.32 | 70% |  | 70% |  |  | 0 | 1531464.48 | 0 | 1531464.48 | De Nhat, VN, Ø60 2.5mm, PN10
| uPVC pipe D34 - PN10 | 104 | 118 | m | 16286.4 | 13440 | 29726.4 | 1921795.2 | 1585920 | 3507715.2 | 70% |  | 70% |  |  | 0 | 1345256.64 | 0 | 1345256.64 | De Nhat, VN, Ø34 2.1mm, PN12.5
| uPVC Fitting | 1 | 1 | lot | 948369.6 | 284510.88 | 1232880.48 | 948369.6 | 284510.88 | 1232880.48 | 70% |  | 70% |  |  | 0 | 663858.72 | 0 | 663858.72 | Viet Nam
| Connect to existing pipe | 1 | 1 | lot | 0 | 1000000 | 1000000 | 0 | 1000000 | 1000000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Excavation & backfill | 14 | 28 | m3 | 0 | 200000 | 200000 | 0 | 5600000 | 5600000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
| Accessories + Support | 1 | 1 | lot | 2351102.4 | 705330.72 | 3056433.12 | 2351102.4 | 705330.72 | 3056433.12 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Hot water pipe | [6 empty] | 3819309.6 | 1253831.9112 | 5073141.5112 |  |  | 0 |  |  | 0 | 95074.56 | 0 | 95074.56
| PPR pipe D20 - PN20 | 7 | 9 | m | 12261.6 | 15682.8168 | 27944.4168 | 110354.4 | 141145.3512 | 251499.7512 | 70% |  | 0.7 |  |  | 0 | 77248.08 | 0 | 77248.08 | De Nhat, VN, Ø20, 3.4mm, PN20
| PPR Fitting | 1 | 1 | lot | 25466.4 | 7639.92 | 33106.32 | 25466.4 | 7639.92 | 33106.32 | 70% |  | 0.7 |  |  | 0 | 17826.48 | 0 | 17826.48 | Viet Nam
| Fire stop | 1 | 1 | lot | 3500000 | 1050000 | 4550000 | 3500000 | 1050000 | 4550000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
| Accessories + Support | 1 | 1 | lot | 183488.8 | 55046.64 | 238535.44 | 183488.8 | 55046.64 | 238535.44 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| East side | [6 empty] | 144276542.4991 | 24804281.8787 | 169080824.3779 |  |  | 0 |  |  | 0 | 4616035.2 | 0 | 4616035.2
| Pump room | [6 empty] | 121538562.8991 | 7728105.642 | 129266668.5411 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Booster pump Q=9.3 m3, H=30m | 2 | 2 | set | 17380000 | 616000 | 17996000 | 34760000 | 1232000 | 35992000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CM 10-3, Grundfos/ Taiwan
| Electrical control panel for booster pump | 1 | 1 | set | 44440000 | 1400000 | 45840000 | 44440000 | 1400000 | 45840000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Encloser: VN Circuit breaker: LS/ Korea
| Pressure tank 100l | 1 | 1 | pcs | 7915200 | 168000 | 8083200 | 7915200 | 168000 | 8083200 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Varem/ Italia
| Storage tank 3m3 | 1 | 1 | pcs | 9970909.0909 | 322000 | 10292909.0909 | 9970909.0909 | 322000 | 10292909.0909 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | SHN3000 (Φ1380)/ Son Ha/ VN
| Filter | 1 | 1 | set | 10800000 | 225400 | 11025400 | 10800000 | 225400 | 11025400 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | VN
| Water metter DN25 | 1 | 1 | pcs | 1014000 | 50880.368 | 1064880.368 | 1014000 | 50880.368 | 1064880.368 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTM-55, KVS / Turkey
| Cable Cu/PVC/PVC 2Cx1.5mm2 | 20 | 25 | m | 15443.88 | 5031.18 | 20475.06 | 386097 | 125779.5 | 511876.5 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
| Cable Cu/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 20 | 25 | m | 40467 | 9350 | 49817 | 1011675 | 233750 | 1245425 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
| PVC conduit D20 | 40 | 50 | m | 8773.9726 | 14594.0164 | 23367.989 | 438698.6301 | 729700.8206 | 1168399.4507 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
| Hanger + Support | 1 | 1 | lot | 4909992.3537 | 1472997.7061 | 6382990.0598 | 4909992.3537 | 1472997.7061 | 6382990.0598 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Accessories | 1 | 1 | lot | 5891990.8244 | 1767597.2473 | 7659588.0717 | 5891990.8244 | 1767597.2473 | 7659588.0717 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Valve | [6 empty] | 15191076.4 | 2017377.4463 | 17208453.8463 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Pressure Gauges | 1 | 1 | pcs | 1008000 | 49588 | 1057588 | 1008000 | 49588 | 1057588 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | P - 260, KVS/ Turkey
| Flexible DN25 | 4 | 4 | pcs | 568800 | 50880.368 | 619680.368 | 2275200 | 203521.472 | 2478721.472 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KVS - 501 T/KVS/ Turkey
| Float level indicator | 1 | 1 | pcs | 4200000 | 168000 | 4368000 | 4200000 | 168000 | 4368000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Omron/ Aisa
| Float valve DN25 | 1 | 1 | pcs | 770400 | 50880.368 | 821280.368 | 770400 | 50880.368 | 821280.368 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KVS-703T, KVS/ Turkey
| Y-Strainer DN25 | 2 | 2 | pcs | 322800 | 50880.368 | 373680.368 | 645600 | 101760.736 | 747360.736 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KVS 200 - T/ KVS/ Turkey
| Safety valve DN25 | 1 | 1 | pcs | 1376400 | 50880.368 | 1427280.368 | 1376400 | 50880.368 | 1427280.368 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 3110N, KVS/ Turkey
| Check valve DN25 | 3 | 3 | pcs | 480000 | 50880.368 | 530880.368 | 1440000 | 152641.104 | 1592641.104 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KVS - 101/ LVS/ Turkey
| Gate valve DN25 | 5 | 5 | pcs | 322800 | 50880.368 | 373680.368 | 1614000 | 254401.84 | 1868401.84 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 402, KVS/Turkey
| Gate valve DN25 PPR | 8 | 8 | pcs | 85924.8 | 49415.0989 | 135339.8989 | 687398.4 | 395320.791 | 1082719.191 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN
| Gate valve DN20 PPR | 9 | 9 | pcs | 63367.2 | 45472.3119 | 108839.5119 | 570304.8 | 409250.8073 | 979555.6073 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN
| Accessories | 1 | 1 | lot | 603773.2 | 181131.96 | 784905.16 | 603773.2 | 181131.96 | 784905.16 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Cold water pipe | [6 empty] | 7418628 | 14924281.536 | 22342909.536 |  |  | 0 |  |  | 0 | 4616035.2 | 0 | 4616035.2
| PPR pipe D63 - PN10 | 10 | 12 | m | 71884.8 | 34720 | 106604.8 | 862617.6 | 416640 | 1279257.6 | 70% |  | 70% |  |  | 0 | 603832.32 | 0 | 603832.32 | De Nhat, VN, Ø63, 5.8mm, PN10
| PPR pipe D40 - PN10 | 5 | 7 | m | 30841.2 | 25388.1544 | 56229.3544 | 215888.4 | 177717.0808 | 393605.4808 | 70% |  | 70% |  |  | 0 | 151121.88 | 0 | 151121.88 | De Nhat, VN, Ø40, 3.7mm, PN10
| PPR pipe D32 - PN10 | 29 | 32 | m | 22978.8 | 22306.7432 | 45285.5432 | 735321.6 | 713815.7824 | 1449137.3824 | 70% |  | 70% |  |  | 0 | 514725.12 | 0 | 514725.12 | De Nhat, VN, Ø32, 2.9mm, PN10
| PPR pipe D25 - PN10 | 21 | 28 | m | 17737.2 | 18258.8168 | 35996.0168 | 496641.6 | 511246.8704 | 1007888.4704 | 70% |  | 70% |  |  | 0 | 347649.12 | 0 | 347649.12 | De Nhat, VN, Ø25, 2.8mm, PN10
| PPR pipe D20 - PN10 | 130 | 143 | m | 9921.6 | 15682.8168 | 25604.4168 | 1418788.8 | 2242642.8024 | 3661431.6024 | 70% |  | 70% |  |  | 0 | 993152.16 | 0 | 993152.16 | De Nhat, VN, Ø20, 2.3mm, PN10
| PPR Fitting | 1 | 1 | lot | 860598 | 258179.4 | 1118777.4 | 860598 | 258179.4 | 1118777.4 | 70% |  | 70% |  |  | 0 | 602418.6 | 0 | 602418.6 | Viet Nam
| uPVC pipe D34 - PN10 | 104 | 100 | m | 16286.4 | 13440 | 29726.4 | 1628640 | 1344000 | 2972640 | 70% |  | 70% |  |  | 0 | 1140048 | 0 | 1140048 | De Nhat, VN, Ø34 2.1mm, PN12.5
| uPVC Fitting | 1 | 1 | lot | 375840 | 112752 | 488592 | 375840 | 112752 | 488592 | 70% |  | 70% |  |  | 0 | 263088 | 0 | 263088 | Viet Nam
| Connect to existing pipe | 1 | 1 | lot | 0 | 1000000 | 1000000 | 0 | 1000000 | 1000000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Excavation & backfill | 10 | 20 | m3 | 0 | 200000 | 200000 | 0 | 4000000 | 4000000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Cut wall and backfill | 91 | 130 | m | 0 | 30000 | 30000 | 0 | 3900000 | 3900000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Accessories + Support | 1 | 1 | lot | 824292 | 247287.6 | 1071579.6 | 824292 | 247287.6 | 1071579.6 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Hot water pipe | [6 empty] | 128275.2 | 134517.2544 | 262792.4544 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| PPR pipe D20 - PN20 | 7 | 8 | m | 12261.6 | 15682.8168 | 27944.4168 | 98092.8 | 125462.5344 | 223555.3344 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN, Ø20, 3.4mm, PN20
| PPR Fitting | 1 | 1 | lot | 22636.8 | 6791.04 | 29427.84 | 22636.8 | 6791.04 | 29427.84 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
| Accessories + Support | 1 | 1 | lot | 7545.6 | 2263.68 | 9809.28 | 7545.6 | 2263.68 | 9809.28 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
3. 3. 30. | Sanitary Furnishings | 1 | 1 | PSCH |  |  |  | 1589161013.1409 | 79558059.1592 | 1668719072.3001 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| West side | 0 |  | m |  |  |  |  | 50588775.2524 | 1032592350.3478 |  |  | 0 |  |  | 0 |  | 0 | 0
| Santinary | [6 empty] | 982003575.0955 | 50588775.2524 | 1032592350.3478 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Water closet one block, included stop valve | 37 | 37 | pcs | 14750000 | 413200.4464 | 15163200.4464 | 545750000 | 15288416.5168 | 561038416.5168 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CW762#XW TC384CVK#W + WH172A + MB174P#WH, Toto/ VN, China
| Water closet spray | 37 | 37 | pcs | 638000 | 50232 | 688232 | 23606000 | 1858584 | 25464584 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TVCF201/ Toto/ VN
| Paper holder | 37 | 37 | pcs | 653000 | 50232 | 703232 | 24161000 | 1858584 | 26019584 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | YH406RV/ Toto/ China
| Lavatory under-mounted type | 43 | 43 | pcs | 1443000 | 300710.7768 | 1743710.7768 | 62049000 | 12930563.4024 | 74979563.4024 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | L501C#W+TVLF405/ Toto/ VN, China
| Water tap for lavatory (cold) | 43 | 43 | pcs | 953000 | 50232 | 1003232 | 40979000 | 2159976 | 43138976 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TVLC101NSR/ Toto/ VN
| Mirror (H=1m, L according to the lavabo table) | 33 | 33 | m2 | 768883.5 | 123200 | 892083.5 | 25373155.5 | 4065600 | 29438755.5 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | t=5mm, Vietnam
| Hand Dryer | 8 | 8 | pcs | 5018000 | 61600 | 5079600 | 40144000 | 492800 | 40636800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TYC322WF/ Toto/ China
| Uniral included flush valve | 15 | 15 | pcs | 11003000 | 280000 | 11283000 | 165045000 | 4200000 | 169245000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | UT57S#W + DU601N/ Toto/ VN, China
| Floor drain DN80 | 16 | 16 | pcs | 855000 | 88480 | 943480 | 13680000 | 1415680 | 15095680 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TVBA407/ Toto/ Vietnam
| Floor drain W100xL5100 | 1 | 1 | pcs | 5417500 | 476000 | 5893500 | 5417500 | 476000 | 5893500 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Inox 304, ZT758-100(75x1000mm), Zento
| Floor drain W100xL3800 | 1 | 1 | pcs | 4334000 | 380800 | 4714800 | 4334000 | 380800 | 4714800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Inox 304, ZT758-100(75x1000mm), Zento
| Floor drain W100xL3000 | 1 | 1 | pcs | 3250500 | 285600 | 3536100 | 3250500 | 285600 | 3536100 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Inox 304, ZT758-100(75x1000mm), Zento
| Shower | 1 | 1 | pcs | 7305000 | 196000 | 7501000 | 7305000 | 196000 | 7501000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TVSM104NSR DM907CS/ Toto/ China
| Heat Water 5L for kitchen | 2 | 2 | pcs | 1628727.2727 | 168000 | 1796727.2727 | 3257454.5455 | 336000 | 3593454.5455 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | HOT DOG 5L, Ferroli/ Asia
| Heat Water 50L for shower | 1 | 1 | pcs | 3104727.2727 | 280000 | 3384727.2727 | 3104727.2727 | 280000 | 3384727.2727 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Aqua 50L, Ferroli/ Asia
| Waterproof for neck pipe | 114 | 114 | nos | 50000 | 15000 | 65000 | 5700000 | 1710000 | 7410000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| Accessories | 1 | 1 | lot | 8847237.7773 | 2654171.3332 | 11501409.1105 | 8847237.7773 | 2654171.3332 | 11501409.1105 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| East side | [6 empty] | 607157438.0455 | 28969283.9068 | 636126721.9523 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Santinary | [6 empty] | 607157438.0455 | 28969283.9068 | 636126721.9523 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Water closet one block, included stop valve | 24 | 24 | pcs | 14750000 | 413200.4464 | 15163200.4464 | 354000000 | 9916810.7136 | 363916810.7136 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CW762#XW TC384CVK#W + WH172A + MB174P#WH, Toto/ VN, China
| Water closet spray | 24 | 24 | pcs | 638000 | 50232 | 688232 | 15312000 | 1205568 | 16517568 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TVCF201/ Toto/ VN
| Paper holder | 24 | 24 | pcs | 653000 | 50232 | 703232 | 15672000 | 1205568 | 16877568 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | YH406RV/ Toto/ China
| Lavatory under-mounted type | 12 | 24 | pcs | 1443000 | 300710.7768 | 1743710.7768 | 34632000 | 7217058.6432 | 41849058.6432 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | L501C#W+TVLF405/ Toto/ VN, China
| Water tap for lavatory (cold) | 12 | 12 | pcs | 953000 | 50232 | 1003232 | 11436000 | 602784 | 12038784 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TVLC101NSR/ Toto/ VN
| Mirror (H=1m, L according to the lavabo table) | 10 | 10 | m2 | 768883.5 | 123200 | 892083.5 | 7688835 | 1232000 | 8920835 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | t=5mm, Vietnam
| Hand Dryer | 4 | 4 | pcs | 5018000 | 61600 | 5079600 | 20072000 | 246400 | 20318400 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TYC322WF/ Toto/ China
| Uniral included flush valve | 11 | 11 | pcs | 11003000 | 280000 | 11283000 | 121033000 | 3080000 | 124113000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | UT57S#W + DU601N/ Toto/ VN, China
| Floor drain DN80 | 10 | 10 | pcs | 855000 | 88480 | 943480 | 8550000 | 884800 | 9434800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TVBA407/ Toto/ Vietnam
| Floor drain W100xL4400 | 1 | 1 | pcs | 4334000 | 380800 | 4714800 | 4334000 | 380800 | 4714800 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Inox 304, ZT758-100(75x1000mm), Zento
| Floor drain W100xL3200 | 1 | 1 | pcs | 3250500 | 285600 | 3536100 | 3250500 | 285600 | 3536100 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Inox 304, ZT758-100(75x1000mm), Zento
| Heat Water 5L for kitchen | 2 | 2 | pcs | 1628727.2727 | 168000 | 1796727.2727 | 3257454.5455 | 336000 | 3593454.5455 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | HOT DOG 5L, Ferroli/ Asia
| Waterproof for neck pipe | 49 | 49 | nos | 50000 | 15000 | 65000 | 2450000 | 735000 | 3185000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| Accessories | 1 | 1 | lot | 5469648.5 | 1640894.55 | 7110543.05 | 5469648.5 | 1640894.55 | 7110543.05 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
4. | Machine hook-up (Hall 3) | [8 empty] | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
5. | Scooter Garage | [6 empty] | 36457255.9273 | 16528783.2582 | 52986039.1855 |  |  | 0 |  |  | 0 | 12798873.36 | 0 | 12798873.36
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
5. 3. | Mechancial Engineering | [6 empty] | 36457255.9273 | 16528783.2582 | 52986039.1855 |  |  | 0 |  |  | 0 | 12798873.36 | 0 | 12798873.36
5. 3. 10. | Rainwater System | 1 | 1 | PSCH |  |  |  | 36457255.9273 | 16528783.2582 | 52986039.1855 |  |  | 0 |  |  | 0 | 12798873.36 | 0 | 12798873.36
| uPVC pipe D220-PN6 | 12 | 15 | m | 356616 | 71941.408 | 428557.408 | 5349240 | 1079121.12 | 6428361.12 | 70% |  | 0.7 |  |  | 0 | 3744468 | 0 | 3744468 | De Nhat, VN, Ø220 5.9mm, PN6
| uPVC pipe D110-PN6 | 92 | 112 | m | 93225.6 | 42504 | 135729.6 | 10441267.2 | 4760448 | 15201715.2 | 70% |  | 0.7 |  |  | 0 | 7308887.04 | 0 | 7308887.04 | De Nhat, VN, Ø114 3.2mm, PN6
| uPVC pipe D60-PN6 | 59 | 55 | m | 29858.4 | 24884.16 | 54742.56 | 1642212 | 1368628.8 | 3010840.8 | 70% |  | 0.7 |  |  | 0 | 1149548.4 | 0 | 1149548.4 | De Nhat, VN, Ø60 2.0mm, PN6
| uPVC Cleanout DN100 | 8 | 8 | pcs | 106423.2 | 28000 | 134423.2 | 851385.6 | 224000 | 1075385.6 | 70% |  | 0.7 |  |  | 0 | 595969.92 | 0 | 595969.92 | De Nhat, VN
| Leaf gaurd DN100 | 8 | 8 | pcs | 231000 | 50400 | 281400 | 1848000 | 403200 | 2251200 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Ngoc Thao, VN
| Floor Drain DN50 | 8 | 8 | pcs | 855000 | 88480 | 943480 | 6840000 | 707840 | 7547840 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TVBA407/ Toto/ Vietnam
| Fitting for uPVC piping | 8 | 1 | lot | 6588863.3455 | 1976659.0036 | 8565522.3491 | 6588863.3455 | 1976659.0036 | 8565522.3491 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Excavation and backfill | 15 | 18 | m3 | 0 | 200000 | 200000 | 0 | 3600000 | 3600000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Hanger/ support and Accessories | 1 | 1 | lot | 2196287.7818 | 658886.3345 | 2855174.1164 | 2196287.7818 | 658886.3345 | 2855174.1164 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Conection existing drain stormwater | 1 | 1 | lot | 700000 | 1750000 | 2450000 | 700000 | 1750000 | 2450000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
6. | Canteen | [6 empty] | 420920023.6422 | 58959472.3741 | 479879496.0162 |  |  | 0 |  |  | 0 | 9151168.32 | 0 | 9151168.32
[13 empty] | 0 |  |  | 0
6. 3. | Mechancial Engineering | [6 empty] | 420920023.6422 | 58959472.3741 | 479879496.0162 |  |  | 0 |  |  | 0 | 9151168.32 | 0 | 9151168.32
6. 3. 10. | Rainwater System | 1 | 1 | PSCH |  |  |  | 16378977.6 | 11954799.36 | 28333776.96 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| uPVC pipe D110-PN6 | 93 | 112 | m | 93225.6 | 42504 | 135729.6 | 10441267.2 | 4760448 | 15201715.2 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN, Ø114 3.2mm, PN6
| Leaf gaurd DN100 | 6 | 6 | pcs | 231000 | 50400 | 281400 | 1386000 | 302400 | 1688400 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Ngoc Thao, VN
| uPVC Cleanout DN100 | 6 | 6 | pcs | 106423.2 | 28000 | 134423.2 | 638539.2 | 168000 | 806539.2 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN
| Fitting for uPVC piping | 1 | 1 | lot | 2934878.4 | 880463.52 | 3815341.92 | 2934878.4 | 880463.52 | 3815341.92 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Excavation and backfill | 13 | 19 | m3 | 0 | 200000 | 200000 | 0 | 3800000 | 3800000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Hanger/ support and Accessories | 1 | 1 | lot | 978292.8 | 293487.84 | 1271780.64 | 978292.8 | 293487.84 | 1271780.64 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Conection existing drain stormwater | 1 | 1 | lot | 0 | 1750000 | 1750000 | 0 | 1750000 | 1750000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
6. 3. 20. | Waste Water System | 1 | 1 | PSCH |  |  |  | 20651731.2 | 14688997.44 | 35340728.64 |  |  | 0 |  |  | 0 | 6678977.76 | 0 | 6678977.76
| Piping for Bain maries | [11 empty] | 0 |  |  | 0 | 0 | 0 | 0
| uPVC pipe DN80 | 43 | 50 | m | 65145.6 | 36064 | 101209.6 | 3257280 | 1803200 | 5060480 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN, Ø90 2.7mm, PN6
| Water pipe heating system | 1 | 1 | lot |  |  |  |  | 0 | 0 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Not included
| Fitting for uPVC piping | 1 | 1 | lot | 751680 | 225504 | 977184 | 751680 | 225504 | 977184 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Hanger/ support and Accessories | 1 | 1 | lot | 250560 | 75168 | 325728 | 250560 | 75168 | 325728 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Piping | [6 empty] | 16392211.2 | 12585125.44 | 28977336.64 |  |  | 0 |  |  | 0 | 6678977.76 | 0 | 6678977.76
| uPVC pipe DN100 - PN6 | 7 | 9 | m | 93225.6 | 42504 | 135729.6 | 839030.4 | 382536 | 1221566.4 | 70% |  | 0.7 |  |  | 0 | 587321.28 | 0 | 587321.28 | De Nhat, VN, Ø114 3.2mm, PN6
| uPVC pipe DN80 - PN6 | 89 | 96 | m | 65145.6 | 36064 | 101209.6 | 6253977.6 | 3462144 | 9716121.6 | 70% |  | 0.7 |  |  | 0 | 4377784.32 | 0 | 4377784.32 | De Nhat, VN, Ø90 2.7mm, PN6
| uPVC pipe DN50 - PN6 | 75 | 82 | m | 29858.4 | 24884.16 | 54742.56 | 2448388.8 | 2040501.12 | 4488889.92 | 70% |  | 0.7 |  |  | 0 | 1713872.16 | 0 | 1713872.16 | De Nhat, VN, Ø60 2.0mm, PN6
| Clean Out DN50 | 1 | 1 | m | 297000 | 84000 | 381000 | 297000 | 84000 | 381000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Model O2,Ngoc Thao, VN
| Clean Out DN80 | 7 | 7 | m | 319000 | 84000 | 403000 | 2233000 | 588000 | 2821000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Model O2,Ngoc Thao, VN
| Clean Out DN100 | 1 | 1 | m | 341000 | 84000 | 425000 | 341000 | 84000 | 425000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Model O2,Ngoc Thao, VN
| Fitting for uPVC piping | 1 | 1 | lot | 2984860.8 | 895458.24 | 3880319.04 | 2984860.8 | 895458.24 | 3880319.04 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Connect pipes to existing manhole | 1 | 1 | lot | 0 | 1750000 | 1750000 | 0 | 1750000 | 1750000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Excavation and backfill | 8 | 15 | m3 | 0 | 200000 | 200000 | 0 | 3000000 | 3000000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Hanger/ support and Accessories | 1 | 1 | lot | 994953.6 | 298486.08 | 1293439.68 | 994953.6 | 298486.08 | 1293439.68 |  |  | 0 |  |  | 0 | 0 | 0 | 0
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
6. 3. 30. | Service Water System | 1 | 1 | PSCH |  |  |  | 10371428 | 9116560.5373 | 19487988.5373 |  |  | 0 |  |  | 0 | 2472190.56 | 0 | 2472190.56
| Valve | [6 empty] | 2328612.8 | 1693755.9317 | 4022368.7317 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Gate valve DN25 | 1 | 1 | pcs | 322800 | 50880.368 | 373680.368 | 322800 | 50880.368 | 373680.368 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 402, KVS/Turkey
| Gate valve DN25 PPR | 7 | 7 | pcs | 85924.8 | 49415.0989 | 135339.8989 | 601473.6 | 345905.6922 | 947379.2922 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN
| Gate valve DN20 PPR | 6 | 6 | pcs | 63367.2 | 45472.3119 | 108839.5119 | 380203.2 | 272833.8715 | 653037.0715 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN
| Accessories | 1 | 1 | lot | 1024136 | 1024136 | 2048272 | 1024136 | 1024136 | 2048272 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Cold water pipe | [6 empty] | 4239540 | 3735787.3512 | 7975327.3512 |  |  | 0 |  |  | 0 | 2472190.56 | 0 | 2472190.56
| PPR pipe DN40 - PN10 | 12 | 8 | m | 45208.8 | 28000 | 73208.8 | 361670.4 | 224000 | 585670.4 | 70% |  | 0.7 |  |  | 0 | 253169.28 | 0 | 253169.28 | De Nhat, VN, Ø40, 3.7mm, PN10
| PPR pipe DN32 - PN10 | 5 | 6 | m | 30841.2 | 25388.1544 | 56229.3544 | 185047.2 | 152328.9264 | 337376.1264 | 70% |  | 0.7 |  |  | 0 | 129533.04 | 0 | 129533.04 | De Nhat, VN, Ø32, 2.9mm, PN10
| PPR pipe DN25 - PN10 | 7 | 10 | m | 22978.8 | 22306.7432 | 45285.5432 | 229788 | 223067.432 | 452855.432 | 70% |  | 0.7 |  |  | 0 | 160851.6 | 0 | 160851.6 | De Nhat, VN, Ø25, 2.8mm, PN10
| PPR pipe DN20 - PN10 | 61 | 71 | m | 17737.2 | 18258.8168 | 35996.0168 | 1259341.2 | 1296375.9928 | 2555717.1928 | 70% |  | 0.7 |  |  | 0 | 881538.84 | 0 | 881538.84 | De Nhat, VN, Ø20, 2.3mm, PN10
| PPR Fitting | 1 | 1 | lot | 469810.8 | 140943.24 | 610754.04 | 469810.8 | 140943.24 | 610754.04 | 70% |  | 0.7 |  |  | 0 | 328867.56 | 0 | 328867.56 | Viet Nam
| uPVC pipe D34 - PN10 | 60 | 63 | m | 16286.4 | 13440 | 29726.4 | 1026043.2 | 846720 | 1872763.2 | 70% |  | 0.7 |  |  | 0 | 718230.24 | 0 | 718230.24 | De Nhat, VN, Ø34 2.1mm, PN12.5
| Fitting for uPVC piping | 1 | 1 | lot | 236779.2 | 71033.76 | 307812.96 | 236779.2 | 71033.76 | 307812.96 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Excavation and backfill | 2 | 3.2 | m3 | 0 | 200000 | 200000 | 0 | 640000 | 640000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
| Accessories + Support | 1 | 1 | lot | 471060 | 141318 | 612378 | 471060 | 141318 | 612378 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| hot water pipe | [6 empty] | 3803275.2 | 3687017.2544 | 7490292.4544 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| PPR pipe DN15 - PN20 | 10 | 8 | m | 12261.6 | 15682.8168 | 27944.4168 | 98092.8 | 125462.5344 | 223555.3344 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN, Ø20, 3.4mm, PN20
| PPR Fitting | 1 | 1 | lot | 22636.8 | 6791.04 | 29427.84 | 22636.8 | 6791.04 | 29427.84 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Fire stop | 1 | 1 | lot | 3500000 | 3500000 | 7000000 | 3500000 | 3500000 | 7000000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
| Accessories + Support | 1 | 1 | lot | 182545.6 | 54763.68 | 237309.28 | 182545.6 | 54763.68 | 237309.28 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
6. 3. 40. | Sanitary Furnishings | 1 | 1 | PSCH |  |  |  | 240793394.3675 | 15204292.8421 | 255997687.2095 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Lavatory under-mounted type | 2 | 2 | pcs | 1443000 | 300710.7768 | 1743710.7768 | 2886000 | 601421.5536 | 3487421.5536 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | L501C#W+TVLF405/ Toto/ VN, China
| Lavatory wall mounted type | 1 | 1 | pcs | 1253000 | 300710.7768 | 1553710.7768 | 1253000 | 300710.7768 | 1553710.7768 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | LT300C#W+TVLF405/ Toto/ VN, China
| Water tap for lavatory (hot and cold) | 2 | 2 | pcs | 1320000 | 50232 | 1370232 | 2640000 | 100464 | 2740464 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TVLM102NSR/ Toto/ VN
| Water tap for lavatory (cold) | 1 | 1 | pcs | 953000 | 50232 | 1003232 | 953000 | 50232 | 1003232 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TVLC101NSR/ Toto/ VN
| Mirror 700x500x6mm | 3 | 3 | pcs | 2896300 | 61600 | 2957900 | 8688900 | 184800 | 8873700 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | YM6075FA/ Toto/ Japan
| Water closet one block, included stop valve | 2 | 2 | set | 14750000 | 413200.4464 | 15163200.4464 | 29500000 | 826400.8928 | 30326400.8928 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CW762#XW TC384CVK#W + WH172A + MB174P#WH, Toto/ VN, China
| Water closet spray | 2 | 2 | pcs | 638000 | 50232 | 688232 | 1276000 | 100464 | 1376464 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TVCF201/ Toto/ VN
| Paper holder | 2 | 2 | pcs | 653000 | 50232 | 703232 | 1306000 | 100464 | 1406464 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | YH406RV/ Toto/ China
| Hand Dryer | 1 | 1 | pcs | 5018000 | 61600 | 5079600 | 5018000 | 61600 | 5079600 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TYC322WF/ Toto/ China
| Floor Drain DN50 | 1 | 1 | m | 855000 | 88480 | 943480 | 855000 | 88480 | 943480 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TVBA407/ Toto/ Vietnam
| Floor Drain DN80 | 12 | 12 | m | 855000 | 88480 | 943480 | 10260000 | 1061760 | 11321760 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TVBA407/ Toto/ Vietnam
| Stainless steel hand washing channel: L10000xH170xD500 | 1 | 1 | pcs | 44000000 | 2240000 | 46240000 | 44000000 | 2240000 | 46240000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Inox304, 3mm/ Vietnam
| Taps for hand washing (Cold) | 14 | 14 | pcs | 7755000 | 50400 | 7805400 | 108570000 | 705600 | 109275600 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | TLE29002A+TLE01502A1+TLN01102A/ Toto/ China
| Heat Water 5l | 2 | 2 | pcs | 1628727.2727 | 168000 | 1796727.2727 | 3257454.5455 | 336000 | 3593454.5455 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | HOT DOG 5L, Ferroli/ Asia
| Double Socket 16A/230V | 3 | 3 | pcs | 150480 | 54500 | 204980 | 451440 | 163500 | 614940 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KB426UES2_WE_G19/ Schneider/ VN, Plastic type
| Single Socket 16A/230V | 14 | 14 | pcs | 124560 | 54500 | 179060 | 1743840 | 763000 | 2506840 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KB426UEST_G19 / Schneider/ VN, Plastic type
| 3C-2.5mm2 Cu/XLPE/PVC | 105 | 112 | m | 32518.74 | 7485.665 | 40004.405 | 3642098.88 | 838394.48 | 4480493.36 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
| 3C-1.5mm2 Cu/XLPE/PVC | 84 | 95 | m | 22980.09 | 5743.9305 | 28724.0205 | 2183108.55 | 545673.3975 | 2728781.9475 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
| PVC conduit D20 | 105 | 110 | m | 8773.9726 | 14594.0164 | 23367.989 | 965136.9863 | 1605341.8053 | 2570478.7916 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
| PVC conduit D20 | 8 | 10 | m | 8773.9726 | 14594.0164 | 23367.989 | 87739.726 | 145940.1641 | 233679.8901 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
| PVC conduit D16 | 84 | 90 | m | 6646.8692 | 13183.4282 | 19830.2974 | 598218.226 | 1186508.5359 | 1784726.7619 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC16, Nano/ VN
| Waterproof for neck pipe | 5 | 5 | nos | 50000 | 15000 | 65000 | 250000 | 75000 | 325000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| Accessories | 1 | 1 | lot | 10408457.4536 | 3122537.2361 | 13530994.6897 | 10408457.4536 | 3122537.2361 | 13530994.6897 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
6. 3. 90. | Booster pump assembly | 1 |  | PSCH |  |  |  | 132724492.4747 | 7994822.1947 | 140719314.6694 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| PUMP ROOM | [6 empty] | 119059072.0747 | 5427258.3947 | 125718330.4694 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Booster pump Q=11.7 m3, H=30m | 2 | 2 | set | 17380000 | 616000 | 17996000 | 34760000 | 1232000 | 35992000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | CM 10-3, Grundfos/ Taiwan
| Electrical control panel for booster pump | 1 | 1 | set | 44440000 | 1400000 | 45840000 | 44440000 | 1400000 | 45840000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Encloser: VN Circuit breaker: LS/ Korea
| Pressure tank 100l | 1 | 1 | pcs | 7915200 | 168000 | 8083200 | 7915200 | 168000 | 8083200 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Varem/ Italia
| Storage tank 3m3 | 1 | 1 | pcs | 9970909.0909 | 322000 | 10292909.0909 | 9970909.0909 | 322000 | 10292909.0909 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | SHN3000 (Φ1380)/ Son Ha/ VN
| Filter | 1 | 1 | set | 10800000 | 225400 | 11025400 | 10800000 | 225400 | 11025400 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | VN
| Water metter DN25 | 1 | 1 | pcs | 1014000 | 50880.368 | 1064880.368 | 1014000 | 50880.368 | 1064880.368 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | MTM-55, KVS / Turkey
| Cable Cu/PVC/PVC 2Cx1.5mm2 | 20 | 25 | m | 15443.88 | 5031.18 | 20475.06 | 386097 | 125779.5 | 511876.5 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
| Cable Cu/XLPE/PVC 3Cx2.5mm2+E2.5mm2 | 20 | 25 | m | 40467 | 9350 | 49817 | 1011675 | 233750 | 1245425 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Cadivi/ Vietnam
| PVC conduit D20 | 40 | 50 | m | 8773.9726 | 14594.0164 | 23367.989 | 438698.6301 | 729700.8206 | 1168399.4507 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | FPC20, Nano/ VN
| Concrete base for pump | 1 | 1 | lot | 2500000 | 450000 | 2950000 | 2500000 | 450000 | 2950000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| Cover for pump | 1 | 1 | lot | 750000 | 200000 | 950000 | 750000 | 200000 | 950000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| Hanger + Support | 1 | 1 | lot | 3043495.4122 | 913048.6237 | 3956544.0359 | 3043495.4122 | 913048.6237 | 3956544.0359 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Accessories | 1 | 1 | lot | 2028996.9415 | 608699.0824 | 2637696.0239 | 2028996.9415 | 608699.0824 | 2637696.0239 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Valve | [6 empty] | 13303750 | 1140438.52 | 14444188.52 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Pressure Gauges | 1 | 1 | pcs | 1008000 | 49588 | 1057588 | 1008000 | 49588 | 1057588 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | P - 260, KVS/ Turkey
| Flexible DN25 | 4 | 4 | pcs | 568800 | 50880.368 | 619680.368 | 2275200 | 203521.472 | 2478721.472 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KVS - 501 T/KVS/ Turkey
| Float level indicator | 1 | 1 | pcs | 4200000 | 168000 | 4368000 | 4200000 | 168000 | 4368000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Omron/ Aisa
| Float valve DN25 | 1 | 1 | pcs | 770400 | 50880.368 | 821280.368 | 770400 | 50880.368 | 821280.368 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KVS-703T, KVS/ Turkey
| Y-Strainer DN25 | 2 | 2 | pcs | 322800 | 50880.368 | 373680.368 | 645600 | 101760.736 | 747360.736 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KVS 200 - T/ KVS/ Turkey
| Safety valve DN25 | 1 | 1 | pcs | 1376400 | 50880.368 | 1427280.368 | 1376400 | 50880.368 | 1427280.368 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 3110N, KVS/ Turkey
| Check valve DN25 | 3 | 3 | pcs | 480000 | 50880.368 | 530880.368 | 1440000 | 152641.104 | 1592641.104 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | KVS - 101/ LVS/ Turkey
| Gate valve DN25 | 4 | 4 | pcs | 264000 | 50880.368 | 314880.368 | 1056000 | 203521.472 | 1259521.472 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 402, KVS/Turkey
| Accessories | 1 | 1 | lot | 532150 | 159645 | 691795 | 532150 | 159645 | 691795 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Cold water pipe | [6 empty] | 361670.4 | 195125.28 | 556795.68 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| PPR pipe DN50 - PN10 | 5 | 6 | m | 45208.8 | 28000 | 73208.8 | 271252.8 | 168000 | 439252.8 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | De Nhat, VN, Ø50, 4.6mm, PN10
| PPR Fitting | 1 | 1 | lot | 52164 | 15649.2 | 67813.2 | 52164 | 15649.2 | 67813.2 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| Accessories + Support | 1 | 1 | lot | 38253.6 | 11476.08 | 49729.68 | 38253.6 | 11476.08 | 49729.68 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
| TOTAL AMOUNT (Not included VAT) | [6 empty] | 2592489399.0247 | 285926135.5267 | 2878415534.5514 | [6 empty] | 114633635.2767 | 0 | 114633635.2767
-3148920
NHÀ THẦU PHỤ: CÔNG TY CỔ PHẦN HMEP | [11 empty] | NHÀ THẦU CHÍNH: CÔNG TY CỔ PHẦN KỸ THUẬT XÂY DỰNG DINCO | [8 empty] | -2049800
ĐẠI DIỆN NHÀ THẦU HMEP | [20 empty] | -240000
[14 empty] | GIÁM SÁT THI CÔNG | CHỈ HUY TRƯỞNG | [5 empty] | 0
-16649183.5127

## 8. CIVIL (hidden)
Project: VN-RENTAL BUILDING HALL 3 ELECTRIC
Location: Lô D1, Khu công nghiệp Tam Thăng, Huyện Tam Thăng, thành Phố Tam Kỳ, Tỉnh quản Nam, Việt Nam
Client: Draexlmaier Automotive Vietnam Company Limited
Package: Cơ - Điện
Item: Work related in the Civil work
Date: 27/02/2022
Contractor name: HMEP
Position | Headline | Quantity | Quantity By contractor | Unit | Material Unit | Labor Unit | Unit rate | Material Amount | Labor Amount | Amount (VND) | % Công việc hoàn thành vật tư |  |  | % Công việc hoàn thành nhân công |  |  | Giá trị thanh toán đợt 1 |  |  | Remark
[11 empty] | Đợt 1 | đợt 2 | % KL hoàn thành lũy kế | Đợt 1 | đợt 2 | % KL hoàn thành lũy kế | Vật tư | Nhân công | Tổng
7. | Exterior Area | [6 empty] | 187529525 | 150438500 | 337968025
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
7. 1. | Civil Engineering | [6 empty] | 187529525 | 150438500 | 337968025 |  |  | 0 |  |  | 0 | 76910400 | 33266800 | 110177200
7. 1. 50. | Excavation | 1 | 1 | PSCH |  |  |  | 86750000 | 108855000 | 195605000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| LV | [6 empty] | 58500000 | 54800000 | 115800000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Manhole 1000x1000x1000 | 5 | 5 | m | 4500000 | 2000000 | 6500000 | 22500000 | 10000000 | 32500000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Excavation and backfilling | 164 | 164 | m3 | 0 | 200000 | 200000 | 0 | 32800000 | 32800000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Concrete crossroads protection | 190 | 120 | m | 300000 | 100000 | 400000 | 36000000 | 12000000 | 48000000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Labor (Remove old cable) | 1 | 1 | m | 0 | 2500000 | 2500000 | 0 | 2500000 | 2500000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| AIR COMPRESSOR | [6 empty] | 1250000 | 4515000 | 5765000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Excavation and backfill | 31 | 20.7 | m3 | 0 | 200000 | 200000 | 0 | 4140000 | 4140000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| The cost of cutting and refinishing the concrete path for the undergruond pipe | 15 | 10 | m | 125000 | 37500 | 162500 | 1250000 | 375000 | 1625000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
| ELV |  | 11 |  |  |  |  | 27000000 | 47040000 | 74040000 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Khoan đường đi ống | 52 | 52 | m | 0 | 300000 | 300000 | 0 | 15600000 | 15600000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | VN
| Manhole 1200x1200x1200 | 4 | 6 | pcs | 4500000 | 2000000 | 6500000 | 27000000 | 12000000 | 39000000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Included labour
| Spare fee for Move and reinstall lighting pole if can't excavation pavement | 6 | 6 | pcs | 0 | 1200000 | 1200000 | 0 | 7200000 | 7200000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | VN
| Excavation and backfill | 100 | 61.2 | m3 | 0 | 200000 | 200000 | 0 | 12240000 | 12240000 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Viet Nam
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
7. 1. 60. | Laying conduits, pipes, etc. | 1 |  | PSCH |  |  |  | 100779525 | 41583500 | 142363025 |  |  | 0 |  |  | 0 | 76910400 | 33266800 | 110177200
| LV | [6 empty] | 41773725 | 16061150 | 57834875 |  |  | 0 |  |  | 0 | 29705760 | 12848920 | 42554680
| HDPE pipe D160/125 | 340 | 421 | m | 88200 | 38150 | 126350 | 37132200 | 16061150 | 53193350 | 80% |  | 80% | 80% |  | 0.8 | 29705760 | 12848920 | 42554680 | Vietnam
| Accessories | 1 | 1 | lot | 4641525 | 0 | 4641525 | 4641525 | 0 | 4641525 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| ELV | [6 empty] | 59005800 | 25522350 | 84528150 |  |  | 0 |  |  | 0 | 47204640 | 20417880 | 67622520
| HDPE pipe D160/125 | 848 | 669 | m | 88200 | 38150 | 126350 | 59005800 | 25522350 | 84528150 | 80% |  | 0.8 | 80% |  | 0.8 | 47204640 | 20417880 | 67622520 | Vietnam
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
| TOTAL AMOUNT (Not included VAT) | [6 empty] | 187529525 | 150438500 | 337968025 | [6 empty] | 76910400 | 33266800 | 110177200
0
NHÀ THẦU PHỤ: CÔNG TY CỔ PHẦN HMEP | [11 empty] | NHÀ THẦU CHÍNH: CÔNG TY CỔ PHẦN KỸ THUẬT XÂY DỰNG DINCO | [8 empty] | 0
ĐẠI DIỆN NHÀ THẦU HMEP | [20 empty] | 0
[14 empty] | GIÁM SÁT THI CÔNG | CHỈ HUY TRƯỞNG | [5 empty] | 0
0
TVLC101NSR/ Toto/ VN
DM345S/DM906CFS/ Toto/ China

## 9. Equipment kitchen (hidden)
Project: VN-RENTAL BUILDING HALL 3 ELECTRIC
Location: Lô D1, Khu công nghiệp Tam Thăng, Huyện Tam Thăng, thành Phố Tam Kỳ, Tỉnh quản Nam, Việt Nam
Client: Draexlmaier Automotive Vietnam Company Limited
Package: Cơ - Điện
Item: Kitchen equipments
Date: 27/02/2022
Contractor name: HMEP
Position | Headline | Quantity | Quantity By contractor | Unit | Material Unit | Labor Unit | Unit rate | Material Amount | Labor Amount | Amount (VND) | % Công việc hoàn thành vật tư |  |  | % Công việc hoàn thành nhân công |  |  | Giá trị thanh toán đợt 1 |  |  | Remark
[11 empty] | Đợt 1 | đợt 2 | % KL hoàn thành lũy kế | Đợt 1 | đợt 2 | % KL hoàn thành lũy kế | Vật tư | Nhân công | Tổng
3. | Office, Social and Technical Areas (Hall 3) | [6 empty] | 225500372.3178 | 4188800 | 229689172.3178 | [6 empty] | 0 | 0 | 0
[13 empty] | 0 |  |  | 0
3. 3. | Mechanical Engineering | [6 empty] | 225500372.3178 | 4188800 | 229689172.3178 |  |  | 0 |  |  | 0 | 0 | 0 | 0
3. 3. 30. | Sanitary Furnishings | 1 | 1 | PSCH |  |  |  | 225500372.3178 | 4188800 | 229689172.3178 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| West side | 0 | 0 | m |  |  | 0 | 107848004.152 | 2094400 | 109942404.152 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Equiment kitchen | [6 empty] | 107848004.152 | 2094400 | 109942404.152 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Hafele refrigerator (1-wing refrigerator) | 2 | 2 | pcs | 20093299.732 | 224000 | 20317299.732 | 40186599.464 | 448000 | 40634599.464 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | HF-SBSID.562L/ Hafele/ China
| Single sink for kitchen included faucet waster pop up, flexiable, stop valve | 2 | 2 | pcs | 3486000.21 | 280000 | 3766000.21 | 6972000.42 | 560000 | 7532000.42 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | HS19-SSD1R60+HT19-CH1F220/ Hafele/ China
| Hafele semi-sonic dishwasher | 2 | 2 | pcs | 15336300.067 | 168000 | 15504300.067 | 30672600.134 | 336000 | 31008600.134 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | HDW-HI60B/ Hafele/ China
| Hafele standalone microwave oven | 2 | 2 | pcs | 2807300.067 | 95200 | 2902500.067 | 5614600.134 | 190400 | 5805000.134 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | HW-F23B/ Hafele/ China
| Domino's Induction Cooker | 4 | 4 | pcs | 6100551 | 140000 | 6240551 | 24402204 | 560000 | 24962204 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | HC-I302D/ Hafele/ China
| Accessories | 1 | 1 | lot | 4902182.0069 | 0 | 4902182.0069 | 4902182.0069 | 0 | 4902182.0069 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
| East side | [6 empty] | 112750186.1589 | 2094400 | 114844586.1589 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Equiment kitchen | [6 empty] | 107848004.152 | 2094400 | 109942404.152 |  |  | 0 |  |  | 0 | 0 | 0 | 0
| Hafele refrigerator (1-wing refrigerator) | 2 | 2 | pcs | 20093299.732 | 224000 | 20317299.732 | 40186599.464 | 448000 | 40634599.464 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | HF-SBSID.562L/ Hafele/ China
| Single sink for kitchen included faucet waster pop up, flexiable, stop valve | 2 | 2 | pcs | 3486000.21 | 280000 | 3766000.21 | 6972000.42 | 560000 | 7532000.42 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | HS19-SSD1R60+HT19-CH1F220/ Hafele/ China
| Hafele semi-sonic dishwasher | 2 | 2 | pcs | 15336300.067 | 168000 | 15504300.067 | 30672600.134 | 336000 | 31008600.134 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | HDW-HI60B/ Hafele/ China
| Hafele standalone microwave oven | 2 | 2 | pcs | 2807300.067 | 95200 | 2902500.067 | 5614600.134 | 190400 | 5805000.134 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | HW-F23B/ Hafele/ China
| Domino's Induction Cooker | 4 | 4 | pcs | 6100551 | 140000 | 6240551 | 24402204 | 560000 | 24962204 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | HC-I302D/ Hafele/ China
| Accessories | 1 | 1 | lot | 4902182.0069 | 0 | 4902182.0069 | 4902182.0069 | 0 | 4902182.0069 |  |  | 0 |  |  | 0 | 0 | 0 | 0 | Vietnam
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0
| TOTAL AMOUNT (Not included VAT) | [6 empty] | 225500372.3178 | 4188800 | 229689172.3178 | [6 empty] | 0 | 0 | 0
0
NHÀ THẦU PHỤ: CÔNG TY CỔ PHẦN HMEP | [11 empty] | NHÀ THẦU CHÍNH: CÔNG TY CỔ PHẦN KỸ THUẬT XÂY DỰNG DINCO | [8 empty] | 0
ĐẠI DIỆN NHÀ THẦU HMEP | [20 empty] | 0
[14 empty] | GIÁM SÁT THI CÔNG | CHỈ HUY TRƯỞNG | [5 empty] | 0
0
TVLC101NSR/ Toto/ VN
DM345S/DM906CFS/ Toto/ China

## 10.ELEVATOR (hidden)
Project: VN-RENTAL BUILDING HALL 3 ELECTRIC
Location: Lô D1, Khu công nghiệp Tam Thăng, Huyện Tam Thăng, thành Phố Tam Kỳ, Tỉnh quản Nam, Việt Nam
Client: Draexlmaier Automotive Vietnam Company Limited
Package: Cơ - Điện
Item: Elevator
Date: 27/02/2022
Contractor name: HMEP
Position | Headline | Quantity | Quantity By contractor | Unit | Material Unit | Labor Unit | Unit rate | Material Amount | Labor Amount | Total amount (VND) | % Công việc hoàn thành vật tư |  |  | % Công việc hoàn thành nhân công |  |  | Giá trị thanh toán đợt 1 |  |  | Remark
[11 empty] | Đợt 1 | đợt 2 | % KL hoàn thành lũy kế | Đợt 1 | đợt 2 | % KL hoàn thành lũy kế | Vật tư | Nhân công | Tổng
6. | Canteen | [6 empty] | 280000000 | 0 | 280000000
6. 1. | Civil Engineering | [6 empty] | 280000000 | 0 | 280000000
6. 1. 260. | Elevator for goods | [6 empty] | 280000000 | 0 | 280000000 |  |  | 0 |  |  | 0 | 0 |  | 0
| Food elevator without person, no loading machine room weight 200kg/02stop/30m/min | 1 | 1 | lot | 280000000 | 0 | 280000000 | 280000000 | 0 | 280000000 |  |  | 0 |  |  | 0 | 0 |  | 0 | DNWW 200-02S-30m/P/DAINAM ELEVATOR Engine with gearbox: Mitsubishi/ Thailand
| TOTAL AMOUNT (Not included VAT) | [8 empty] | 280000000 | [8 empty] | 0
0
NHÀ THẦU PHỤ: CÔNG TY CỔ PHẦN HMEP | [11 empty] | NHÀ THẦU CHÍNH: CÔNG TY CỔ PHẦN KỸ THUẬT XÂY DỰNG DINCO | [8 empty] | 0
ĐẠI DIỆN NHÀ THẦU HMEP | [20 empty] | 0
[14 empty] | GIÁM SÁT THI CÔNG | CHỈ HUY TRƯỞNG | [5 empty] | 0
0